AH2-184 | PA- Shadeland 13 kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 |  |  | Energy | Generation Interconnection | Storage; Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 2/20/2024 |  | 6/21/2024 |  |  | Y | No
AH2-185 | PA-Beaver 13.2 kV |  | PA | Franklin | Withdrawn | PENELEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 1/3/2024 |  | 6/21/2024 |  |  | Y | No
AH2-186 | Enfield 12kV |  | VA | King William | Withdrawn | Dominion | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 5/17/2022 |  | 5/29/2026 |  |  | N | No
AH2-187 | Burma – Seminole Road Junction 25 kV |  | PA | Clarion | Active | APS | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AH2-188 | Youst Solar |  | PA | Tioga | Withdrawn | PENELEC | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 6/3/2022 |  | 12/31/2025 |  |  | N | No
AH2-189 | Fearnley Solar 34.5 kV |  | PA | Susquehanna | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-190 | Higgins Run Solar |  | PA | Somerset | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-191 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-192 | Wharton 138 kV |  | WV | N/A | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-193 | Pax Branch 138 kV |  | WV | N/A | Active | AEP | 70 | 70 | 46 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-194 | Bergen 138kV |  | NJ | Bergen | Active | PSEG | 736 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 4/30/2026 |  |  | N | No
AH2-195 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 10/29/2027 |  |  | N | No
AH2-196 |  |  | NJ | Monmouth | Withdrawn | JCPL | 1600 | 1600 | 281.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 4/7/2022 |  | 12/31/2031 |  |  | N | No
AH2-197 | North Huntley - Pleasant Valley 138 kV |  | IL | McHenry | Active | ComEd | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-198 | Mt. Hermon 69 kV |  | MD | Wicomico | Active | DPL | 74.715 | 74.715 | 53.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH2-199 | Shorewood 138 kV |  | IL | Will | Active | ComEd | 51.7 | 51.7 | 36.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH2-200 | TBD 12kV |  | NJ | N/A | Withdrawn | AEC | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/8/2024 |  | 1/1/2025 |  |  | N | No
AH2-201 | TBD 12kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/3/2024 |  | 1/1/2025 |  |  | N | No
AH2-202 | Hunterdon 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/3/2024 |  | 1/1/2025 |  |  | N | No
AH2-204 | Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-205 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AH2-206 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AH2-207 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 85 | 85 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-208 |  |  | VA | Lee | Withdrawn | Dominion | 45 | 45 | 31 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 3/17/2022 |  | 3/10/2024 |  |  | N | No
AH2-209 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-210 | Stillwell - Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 78 | 78 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 6/26/2025 |  | 12/31/2025 |  |  | N | No
AH2-211 | Olive - Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 6/26/2025 |  | 12/31/2025 |  |  | N | No
AH2-212 | Cardington 138 kV |  | OH | Madison | Withdrawn | ATSI | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 2/4/2025 |  | 12/31/2026 |  |  | N | No
AH2-213 | London 138 kV |  | IN | Randolph | Withdrawn | ATSI | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 2/4/2025 |  | 12/31/2026 |  |  | N | No
AH2-214 |  |  | OH | Pickaway | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/1/2022 |  | 12/31/2026 |  |  | N | No
AH2-215 | Midway 138 kV |  | OH | Henry | Withdrawn | ATSI | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 2/4/2025 |  | 12/31/2026 |  |  | N | No
AH2-216 |  |  | OH | Miami | Withdrawn | Dayton | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/1/2022 |  | 12/31/2026 |  |  | N | No
AH2-217 | Cardington 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-218 | London 138 kV II |  | OH | Morrow | Withdrawn | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 2/4/2025 |  | 12/31/2026 |  |  | N | No
AH2-219 |  |  | OH | Pickaway | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/1/2022 |  | 12/31/2026 |  |  | N | No
AH2-220 | Midway 138 kV |  | OH | Henry | Withdrawn | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 2/4/2025 |  | 12/31/2026 |  |  | N | No
AH2-221 |  |  | OH | Miami | Withdrawn | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/1/2022 |  | 12/31/2026 |  |  | N | No
AH2-222 | Millersburg 69 kV |  | KY | N/A | Withdrawn | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/14/2025 |  | 12/31/2026 |  |  | N | No
AH2-223 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-224 | Millersburg 69 kV |  | KY | N/A | Withdrawn | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/14/2025 |  | 12/31/2026 |  |  | N | No
AH2-225 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 10/13/2022 |  | 12/31/2027 |  |  | N | No
AH2-226 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 175 | 175 | 175 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2027 |  |  | N | No
AH2-227 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/27/2026 |  |  | N | No
AH2-228 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-229 | Bedforth North 115 kV |  | PA | Bedford | Active | PENELEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-230 | Gardners 115 kV |  | PA | Adams | Active | ME | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-232 |  |  | VA | Rockingham | Withdrawn | Dominion | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/15/2022 |  | 12/31/2027 |  |  | N | No
AH2-233 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-234 | W Dekalb 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-235 | Orrtana 115 kV |  | PA | Adams | Active | ME | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-236 | McDowell 138 kV |  | PA | Mercer | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-237 | Adams 138 kV |  | IN | Wells | Withdrawn | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/17/2025 |  | 12/31/2026 |  |  | N | No
AH2-238 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-239 | Trumbull138 kV |  | OH | Trumbull | Active | ATSI | 49 | 49 | 46.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2027 |  |  | N | No
AH2-240 | Oceanview 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1493 | 1493 | 424.872 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/1/2022 |  | 11/1/2027 |  |  | N | No
AH2-241 | Loudoun 115kV |  | VA | City of Chesapeake | Active | Dominion | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AH2-242 | Crown - New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 45 | 45 | 40.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/8/2027 |  |  | N | No
AH2-243 | South Summitville 69 kV |  | IN | Madison | Withdrawn | AEP | 43 | 43 | 25.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 8/30/2024 |  | 10/27/2028 |  |  | N | No
AH2-244 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/29/2023 |  |  | N | No
AH2-245 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/29/2023 |  |  | N | No
AH2-246 | Polyester S/S 230kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-247 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 158.2836 | 83.2836 | 14.6579 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-248 | Carrolltown 46 kV |  | PA | Cambria | Active | PENELEC | 113.2592 | 83.2592 | 14.6536 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-249 | Busseyville 138 kV |  | KY | Lawrence | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 7/17/2025 |  | 12/22/2027 |  |  | N | No
AH2-250 | TBD 13.2 kV |  | PA | Bucks | Withdrawn | PECO | 9.25 | 9.25 | 3.885 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 7/23/2024 |  | 2/28/2024 |  |  | N | No
AH2-251 | PA- Shorb Mill 13 kV |  | VA | Rockingham | Withdrawn | ME | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 1/3/2024 |  | 6/21/2024 |  |  | Y | No
AH2-252 | Middleburg 12 kV |  | N/A | N/A | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/21/2024 |  |  | Y | No
AH2-253 | Beaver Valley - Crescent 138 kV |  | PA | Beaver | Active | DL | 70 | 70 | 65 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 11/25/2025 |  |  | N | No
AH2-254 |  |  | NJ | Mercer | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/1/2022 |  | 1/1/2025 |  |  | N | No
AH2-255 |  |  | WV | Preston | Withdrawn | APS | 70 | 70 | 65 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 4/13/2022 |  | 11/25/2025 |  |  | N | No
AH2-256 | Wheelabrator Frackville-Gilberton 69 kV II |  | PA | Schuylkill | Active | PPL | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-257 | Dequine - Eugene 345 kV |  | IN | Vermillion | Active | AEP | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/29/2024 |  |  | N | No
AH2-258 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | 172 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/27/2024 |  |  | N | No
AH2-259 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | 172 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/27/2024 |  |  | N | No
AH2-260 | Garrett - Albright 138 kV |  | WV | Preston | Withdrawn | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 3/7/2025 |  | 6/30/2026 |  |  | N | No
AH2-261 | Garrett - Albright 138 kV |  | WV | Preston | Withdrawn | APS | 98 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 3/7/2025 |  | 6/30/2026 |  |  | N | No
AH2-262 | Catoctin-Carroll 138 kV |  | MD | Frederick | Active | APS | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-263 | Marion Co - Marion Co industrial 161 kV |  | KY | Marion | Active | EKPC | 63.6 | 25.8 | 15.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-264 | Logtown - North Delphos 138 kV |  | OH | Van Wert | Active | AEP | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-265 | Oak Grove - Hawkins Gate 230kV |  | MD | Charles | Active | PEPCO | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-266 | Hughesville-Cedarville 69kV |  | MD | Charles | Active | SMECO | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-267 | Modera - BioEnergy Tap 115 kV |  | PA | Clearfield | Active | PENELEC | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH2-268 | Sapony 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 37 | 37 | 33.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH2-269 | Lakewood 230 kV |  | NJ | Ocean | Active | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH2-269A | Burches Hill-Chalk Point 500kV |  | MD | Prince George's | Active | PEPCO | 845 | 45 | 45 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 11/2/2026 |  |  | N | No
AH2-270 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 300 | 300 | 51 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-271 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2026 |  |  | N | No
AH2-272 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2027 |  |  | N | No
AH2-273 | Eagle Road 138 kV |  | OH | Union | Withdrawn | Dayton | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 1/14/2025 |  | 12/31/2026 |  |  | N | No
AH2-274 | Eagle Road 138 kV |  | OH | Union | Withdrawn | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 1/14/2025 |  | 12/31/2026 |  |  | N | No
AH2-275 | Carrollton Solar 138 kV |  | OH | Carroll | Withdrawn | ATSI | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 1/21/2025 |  | 3/3/2023 |  |  | N | No
AH2-276 | Second Fork 69 kV |  | KY | Pike | Active | AEP | 40 | 40 | 28 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-277 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-278 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-279 | Whiteley 138 kV |  | PA | Greene | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-280 | Noblesville - Fall Creek 345 kV |  | IN | Hamilton | Withdrawn | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 6/1/2022 |  | 5/31/2025 |  |  | N | No
AH2-281 | Trego 34.5 kV |  | VA | Greensville | Withdrawn | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 3/26/2025 |  | 12/30/2024 |  |  | N | No
AH2-282 | Burnworth 138 kV |  | IN | Noble | Withdrawn | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 11/3/2023 |  | 12/1/2026 |  |  | N | No
AH2-283 |  |  | OH | Morgan | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/12/2022 |  | 12/1/2026 |  |  | N | No
AH2-284 | Adams 138 kV |  | OH | Adams | Withdrawn | AEP | 49.9 | 49.9 | 49.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 12/13/2024 |  | 12/1/2026 |  |  | N | No
AH2-285 |  |  | NJ | Middlesex | Withdrawn | JCPL | 1400 | 1400 | 378 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 4/8/2022 |  | 12/31/2029 |  |  | N | No
AH2-287 |  |  | NJ | Monmouth | Withdrawn | JCPL | 600 | 600 | 162 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/8/2022 |  | 12/31/2029 |  |  | N | No
AH2-288 | Napoleon Muni 138 kV |  | OH | Henry | Active | AMPT | 206 | 0 | 82.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-289 | East Fayette 138 kV II |  | OH | Fulton | Active | ATSI | 199 | 0 | 79.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-290 | Sandwich 138 kV |  | IL | DeKalb | Active | ComEd | 86 | 0 | 34.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-291 | Rawlings-Clover 500kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH2-292 | Bear Rock 230 kV |  | PA | Cambria | Active | PENELEC | 76.95 | 76.95 | 13.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-293 | Gilbert - Morris Park 115 kV |  | NJ | Warren | Withdrawn | JCPL | 50 | 50 | 34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 4/12/2023 |  | 6/30/2025 |  |  | N | No
AH2-294 | Mazon Blue - Lasalle 138 kV |  | IL | Grundy | Withdrawn | ComEd | 150 | 40 | 29.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 12/13/2024 |  | 6/1/2026 |  |  | N | No
AH2-295 | Emerald 25 kV |  | PA | Greene | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 9/15/2025 |  |  | N | No
AH2-296 |  |  | IL | Cook | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-297 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-298 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-299 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-300 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-301 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-302 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-303 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-304 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-305 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-306 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-307 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-308 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-309 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-310 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-311 |  |  | IL | Cook | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-312 |  |  | IL | Cook | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-313 |  |  | IL | Cook | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-314 |  |  | IL | Cook | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-315 |  |  | IL | Cook | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/6/2022 |  | 12/1/2023 |  |  | Y | No
AH2-316 | Somerset 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 8/7/2024 |  | 3/29/2024 |  |  | N | No
AH2-317 | Fredericksburg - North Lebanon 13.2 kV |  | PA | Lebanon | Withdrawn | ME | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 8/7/2024 |  | 3/29/2024 |  |  | N | No
AH2-318 | Corry East 34.5 kV |  | PA | Warren | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-319 | Milan 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 7.5 | 7.5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 8/7/2024 |  | 3/29/2024 |  |  | N | No
AH2-320 | Revloc 34.5 kV |  | PA | Cambria | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-321 | Cooper 34.5 kV |  | PA | York | Withdrawn | ME | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 8/7/2024 |  | 3/29/2024 |  |  | N | No
AH2-322 | East Danville-Smith Mountain 138 kV |  | VA | Pittsylvania | Active | AEP | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-330 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AH2-331 | North Delphos - Logtown 138 kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 6/24/2025 |  | 3/31/2027 |  |  | N | No
AH2-332 | Talbert 230kV |  | MD | Prince George's | Active | PEPCO | 115 | 115 | 115 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-333 | Orchard 230kV |  | NJ | Salem | Active | AEC | 415 | 415 | 415 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-334 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-335 | Roundtop 115 kV |  | PA | York | Active | ME | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-336 | Kenney - Mt Olive 69 kV |  | MD | Worcester | Withdrawn | DPL | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/15/2022 |  | 2/27/2026 |  |  | N | No
AH2-337 | Talbot 69 kV |  | MD | Worcester | Active | DPL | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 2/27/2026 |  |  | N | No
AH2-338 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-339 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 0 | 64 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-340 | Toulon 138kV |  | IL | Stark | Active | ComEd | 350 | 350 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-341 | Toulon 138 kV |  | IL | Stark | Active | ComEd | 350 | 0 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-342 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 280 | 168 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-343 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 0 | 112 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-344 | La Rue 138 kV |  | OH | Marion | Active | AEP | 94.5 | 45 | 30.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-345 | Wellington 138 kV |  | OH | Lorain | Active | ATSI | 120 | 120 | 80.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-346 | East Arlington 69 kV |  | OH | Hancock | Active | AEP | 47.5 | 47.5 | 31.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-347 | Northern St. Joseph 138 kV |  | IN | St. Joseph | Active | AEP | 200 | 200 | 164 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-348 | Jefferson - Rockport 765 kV |  | IN | Washington | Active | AEP | 700 | 700 | 420 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-349 | Sedge Hill- Person 230kV |  | VA | Halifax | Active | Dominion | 142 | 142 | 85.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-350 | Cartersville 230kV |  | VA | Cumberland | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-351 | Jefferson - Hanging Rock 765 kV |  | KY | N/A | Active | AEP | 1000 | 1000 | 600 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-352 | Fall Creek 345 kV |  | IN | N/A | Active | AEP | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-353 | Jefferson - Hanging Rock 765 kV |  | KY | N/A | Active | AEP | 1000 | 1000 | 600 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-354 | Bishopville - Worcester 138 kV |  | MD | Worcester | Withdrawn | DPL | 30 | 30 | 18.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 7/29/2022 |  | 9/2/2024 |  |  | N | No
AH2-355 | Emlenton - Clark Summit 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-356 | Brookeville 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-357 | Crown - Piney 34.5 kV |  | PA | Clarion | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-359 | Rockwood 23kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-360 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-361 | Scottdale - Iron Bridge 13.2 kV |  | PA | Westmoreland | Withdrawn | APS | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-362 | Guilford - Upton 13 kV |  | PA | Franklin | Withdrawn | APS | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 9/7/2023 |  | 12/31/2024 |  |  | N | No
AH2-363 | Davis Creek - Bloom 345 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/31/2027 |  |  | N | No
AH2-364 |  |  | PA | York | Withdrawn | ME | 75 | 0 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/15/2022 |  | 11/1/2024 |  |  | N | No
AH2-365 | Easton - Steele 138 kV IV |  | MD | Talbot | Withdrawn | DPL | 79 | 0 | 10.787 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 7/7/2025 |  | 6/1/2024 |  |  | N | No
AH2-366 | Carville 138 kV V |  | MD | Queen Anne's | Withdrawn | DPL | 89 | 0 | 18.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/8/2022 |  | 6/3/2024 |  |  | N | No
AH2-367 |  |  | PA | Lebanon | Withdrawn | ME | 70 | 0 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/13/2022 |  | 6/1/2024 |  |  | N | No
AH2-369 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 200 | 0 | 16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH2-370 | Church - Oil City 138 kV III |  | MD | Caroline | Active | DPL | 112 | 0 | 17.816 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 11/15/2023 |  |  | N | No
AH2-371 | Jay 138 kV |  | IN | Jay | Active | AEP | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-372 | Corbin – Cresent Ridge 138kV |  | IL | Stephenson | Active | ComEd | 302 | 52 | 52 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AH2-373 | Blossom Trail 138 kV |  | MI | Berrien | Active | AEP | 180 | 180 | 132 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AH2-374 | Milliron - Brookside 138 kV II |  | OH | Richland | Active | ATSI | 252.31 | 84 | 84 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2027 |  |  | N | No
AH2-375 | Lena- Landcaster 138kV |  | IL | Stephenson | Active | ComEd | 318 | 106 | 106 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-376 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 365.1 | 153 | 153 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AH2-377 | Pontiac Midpoint – Dresden 345 kV |  | IL | Grundy | Active | ComEd | 450 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AH2-378 | Appomattox ESC |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-378A | Monroe 138kV |  | NJ | Gloucester | Active | AEC | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-379 | Sign Post - Stockton 69 kV |  | MD | Worcester | Active | DPL | 28.3 | 28.3 | 16.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-380 | Matteson - East Frankfort 138 kV |  | IL | Cook | Withdrawn | ComEd | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 3/3/2025 |  | 3/1/2026 |  |  | N | No
AH2-381 | North Lebanon - Annville 69 kV |  | PA | Lebanon | Withdrawn | ME | 15.3 | 15.3 | 9.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 3/29/2023 |  | 3/1/2026 |  |  | N | No
AH2-382 | Wythe – Mount Airy 138 kV |  | VA | Wythe | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-383 | Goddard - Flemingsburg 138 kV |  | KY | Fleming | Active | EKPC | 70 | 70 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/10/2027 |  |  | N | No
AH2-384 | Everetts 34.5kV |  | NC | Martin | Active | Dominion | 25 | 10 | 7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-385 | Chinquapin-Everetts 230kV |  | NC | Pitt | Active | Dominion | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-386 | North Franklin 138 kV |  | WV | Pendleton | Active | APS | 191.5 | 191.5 | 28.15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-387 | Long Carolyn PV 34.5 kV |  | PA | Indiana | Withdrawn | PENELEC | 9.99 | 9.99 | 5.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 5/8/2025 |  | 12/29/2023 |  |  | N | No
AH2-388 | Long Carolyn 34.5 kV |  | PA | Indiana | Withdrawn | PENELEC | 9.99 | 0 | 3.85 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 5/8/2025 |  | 12/29/2023 |  |  | N | No
AH2-389 | Devlin 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-390 | Devlin Storage 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 0 | 2.31 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-391 | Pomerico 69 kV |  | PA | Lawrence | Withdrawn | ATSI | 7 | 7 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 5/8/2025 |  | 12/29/2023 |  |  | N | No
AH2-392 | Pomerico 69 kV II |  | PA | Lawrence | Withdrawn | ATSI | 7 | 0 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 5/8/2025 |  | 12/29/2023 |  |  | N | No
AH2-393 | Nowacoski 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 8 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 5/8/2025 |  | 12/29/2023 |  |  | N | No
AH2-394 | Walters Karl 69 kV |  | PA | Lawrence | Active | ATSI | 6.3 | 6.3 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-395 | Walters Karl 69 kV II |  | PA | Lawrence | Active | ATSI | 6.3 | 0 | 2.31 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-396 | Nowacoski 34.5 kV II |  | PA | Bradford | Withdrawn | PENELEC | 8 | 0 | 3.08 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 5/8/2025 |  | 12/29/2023 |  |  | N | No
AH2-397 | Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-398 | Four Rivers- St. Johns 230kV |  | VA | Caroline | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 7/9/2025 |  | 10/1/2026 |  |  | N | No
AH2-399 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-400 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-401 | Dubois 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/12/2024 |  |  | N | No
AH2-402 | Philipsburg 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 9/13/2024 |  |  | N | No
AH2-403 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 148.2836 | 83.2836 | 14.6579 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-404 | East Danville - Banister 138kV |  | VA | Pittsylvania | Active | AEP | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-405 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-406 | Mt. Pleasant-Lums Pond 138 kV II |  | DE | New Castle | Withdrawn | DPL | 34.5 | 34.5 | 34.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/11/2022 |  | 9/24/2027 |  |  | N | No
AH2-407 |  |  | DE | New Castle | Withdrawn | DPL | 34.5 | 34.5 | 20.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  | 4/11/2022 |  | 9/24/2027 |  |  | N | No
AH2-408 | Fostoria - Lemoyne 138 kV |  | OH | Wood | Active | ATSI | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-409 | Fostoria - Lemoyne 138 kV II |  | OH | Wood | Active | ATSI | 80 | 30.1 | 18.06 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-410 | New Castle 69 kV |  | KY | N/A | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-411 | New Castle 69 kV |  | KY | N/A | Active | EKPC | 50 | 30 | 18 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-412 | TBD 69kV |  | NJ | Cumberland | Active | AEC | 7.35 | 7.35 | 3.09 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH2-413 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 365 | 365 | 339 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-414 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 689 | 350 | 350 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-415 | Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-416 | Pontiac Midpoint 345 |  | IL | Livingston | Active | ComEd | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-418 | Riverside - Pokagon 138 kV |  | MI | Berrien | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-419 | Reynolds - Olive 345 kV |  | IN | LaPorte | Active | AEP | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-420 | Morgan Street 115 kV |  | PA | Crawford | Active | PENELEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-421 | Dresden 138kV |  | IL | Grundy | Active | ComEd | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-422 | Yukon 138 kV |  | PA | Westmoreland | Active | APS | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-423 | Sollers 230kV |  | MD | Calvert | Active | SMECO | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-424 | Durbin-Pickens 138 kV |  | WV | Randolph | Withdrawn | APS | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  | 3/21/2022 |  | 6/30/2025 |  |  | N | No
AI1-001 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2100 | 2100 | 369.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2022 | N/A | N/A |  |  |  | 10/10/2029 |  |  | N | No
AI1-003 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 170 | 170 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-006 | Monterville - Pickens 138 kV |  | WV | Randolph | Active | APS | 103 | 103 | 18.128 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-009 | Pendleton - Tanners Creek 138 kV |  | IN | Rush | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-010 | Ladysmith CT 230 kV |  | VA | Caroline | Withdrawn | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  | 5/9/2022 |  | 12/31/2026 |  |  | N | No
AI1-011 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 131 | 46 | 27.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-012 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 131 | 0 | 18.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-013 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-014 | Bismark-Doubs 500 kV |  | WV | Berkeley | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  | 5/24/2022 |  | 12/31/2026 |  |  | N | No
AI1-015 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 320 | 320 | 320 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  | 5/24/2022 |  | 12/31/2026 |  |  | N | No
AI1-016 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 260 | 0 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-017 | Septa 500 kV |  | VA | Surry | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-018 | Spotslvania 500 kV |  | VA | Spotsylvania | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-019 | Laurel - Cooper 161 kV |  | KY | N/A | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-020 | TBD |  | N/A | N/A | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2022 | N/A | N/A |  |  |  | 3/31/2023 |  |  | Y | No
AI1-021 | Hillandale 115kV |  | VA | Pittsylvania | Active | Dominion | 105 | 105 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI1-022 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI1-023 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI1-024 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI1-026 | Ringtown 12 kV |  | N/A | N/A | Active | PPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2022 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AI1-029 |  |  | PA | Delaware | Withdrawn | PECO | 19.8 | 19.8 | 13.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  | 5/4/2022 |  | 6/30/2024 |  |  | N | No
AI1-030 | Corry East - Garland Jct 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/13/2024 |  |  | N | No
AI1-031 | Westmoreland - Oak Grove 230kV |  | VA | Richmond | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  | 6/27/2024 |  | 12/31/2025 |  |  | N | No
AI1-032 | Bristers 115kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  | 6/27/2024 |  | 12/31/2025 |  |  | N | No
AI1-033 | Somerville 26 kV |  | NJ | Somerset | Active | PSEG | 8 | 8 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/5/2022 | N/A | N/A |  |  |  | 12/22/2026 |  |  | N | No
AI1-034 5180926 | PJM-CPLE |  | N/A | N/A | Active |  |  | 1000 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/30/2022 | 6/1/2027 | 6/1/2032 | [6 empty] | PP | No
AI1-036 | Rockwood - Somerset 12.47 kV |  | PA | Somerset | Withdrawn | PENELEC | 13 | 13 | 7.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/8/2022 | N/A | N/A |  | 9/18/2023 |  | 9/30/2028 |  |  | N | No
AI1-037 5178816 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 314 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/8/2022 | 6/1/2023 | 6/1/2027 |  | 6/3/2022 |  |  |  |  | PP | No
AI1-038 | Harwood-Siegfried 230kV II |  | PA | Carbon | Active | PPL | 95.76 | 95.76 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/12/2022 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AI1-039 | Moshannon-Milesburg 230 kV VIII |  | PA | Clearfield | Active | PENELEC | 200 | 200 | 160 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2022 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI1-040 | Ridgway - Elko 138 kV |  | PA | Elk | Active | APS | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2022 | N/A | N/A |  |  |  | 3/31/2025 |  |  | N | No
AI1-044 | Breezewood 12.47 kV |  | PA | Bedford | Withdrawn | PENELEC | 7.5 | 7.5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2022 | N/A | N/A |  | 9/18/2023 |  | 5/1/2026 |  |  | N | No
AI1-046 | Smithburg 500 kV |  | NJ | Monmouth | Active | JCPL | 1600 | 1600 | 281.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2022 | N/A | N/A |  |  |  | 12/31/2031 |  |  | N | No
AI1-047 5189719 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 314 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2022 | 6/1/2023 | 6/1/2024 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-048 5189716 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 518 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2022 | 6/1/2024 | 6/1/2027 |  | 6/3/2022 |  |  |  |  | PP | No
AI1-049 5189731 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 832 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2022 | 6/1/2024 | 6/1/2025 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-050 5189732 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 832 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2022 | 6/1/2025 | 6/1/2026 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-051 5189733 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 832 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2022 | 6/1/2026 | 6/1/2027 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-052 5192320 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 832 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2022 | 6/1/2027 | 6/1/2032 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-053 | McDowell - Campbell 69 kV |  | PA | Mercer | Active | ATSI | 6.6 | 6.6 | 0 |  | Energy | Generation Interconnection | Diesel; Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2022 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AI1-054 5200922 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 134 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2023 | 6/1/2024 |  | 6/21/2022 |  |  |  |  | PP | No
AI1-055 5200930 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 134 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2024 | 6/1/2025 |  | 6/21/2022 |  |  |  |  | PP | No
AI1-056 5200938 | PJM-NIPS |  | N/A | N/A | Withdrawn |  |  | 1404 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2025 | 6/1/2026 |  | 7/6/2022 |  |  |  |  | PP | No
AI1-057 5200939 | PJM-NIPS |  | N/A | N/A | Withdrawn |  |  | 1404 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2026 | 6/1/2027 |  | 7/6/2022 |  |  |  |  | PP | No
AI1-058 5200932 | PJM-NIPS |  | N/A | N/A | Withdrawn |  |  | 1404 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2024 | 6/1/2025 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-059 5200941 | PJM-CIN |  | N/A | N/A | Withdrawn |  |  | 1100 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2025 | 6/1/2026 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-060 5200940 | PJM-NIPS |  | N/A | N/A | Withdrawn |  |  | 1404 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2027 | 6/1/1932 |  | 7/6/2022 |  |  |  |  | PP | No
AI1-061 5200942 | PJM-CIN |  | N/A | N/A | Withdrawn |  |  | 1100 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2026 | 6/1/2027 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-062 5200943 | PJM-CIN |  | N/A | N/A | Withdrawn |  |  | 1100 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2022 | 6/1/2027 | 6/1/1932 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-063 | Bear Peak East St. Clair 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/21/2022 | N/A | N/A |  | 9/18/2023 |  | 6/1/2027 |  |  | N | No
AI1-064 5201681 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 85 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/21/2022 | 6/1/2023 | 6/1/2024 |  | 6/22/2022 |  |  |  |  | PP | No
AI1-065 5201682 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 85 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/21/2022 | 6/1/2024 | 6/1/2025 |  | 6/22/2022 |  |  |  |  | PP | No
AI1-066 | Bear Peak Rostraver 12.47 kV |  | PA | Westmoreland | Withdrawn | APS | 7.5 | 7.5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2022 | N/A | N/A |  | 9/18/2023 |  | 6/1/2026 |  |  | N | No
AI1-067 | Bear Peak Rostraver II 12.47 kV |  | PA | Westmoreland | Withdrawn | APS | 7.5 | 7.5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2022 | N/A | N/A |  | 9/18/2023 |  | 6/1/2027 |  |  | N | No
AI1-068 5201755 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 134 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/22/2022 | 6/1/2023 | 6/1/2024 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-069 5201756 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 60 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/22/2022 | 6/1/2024 | 6/1/2025 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-070 5201757 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 60 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/22/2022 | 6/1/2025 | 6/1/2026 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-071 5201758 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 60 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/22/2022 | 6/1/2026 | 6/1/2027 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-072 5201760 | PJM-WEC |  | N/A | N/A | Withdrawn |  |  | 60 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/22/2022 | 6/1/2027 | 6/1/1932 |  | 9/14/2022 |  |  |  |  | PP | No
AI1-073 | Bear Peak Antrim 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2022 | N/A | N/A |  | 9/18/2023 |  | 6/1/2027 |  |  | N | No
AI1-074 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 120 | 120 | 96 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/5/2022 | N/A | N/A |  |  |  | 12/15/2027 |  |  | N | No
AI1-075 | Lee Co. EC 345kV |  | IL | Lee | Active | ComEd | 239.8 | 0 | 11.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/6/2022 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AI1-076 | TBD 13.2 kV |  | PA | Delaware | Active | PECO | 19.8 | 19.8 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-077 | Marengo 34.5 kV Line |  | IL | McHenry | Active | ComEd | 15.75 | 15.75 | 6.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/15/2022 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AI1-078 | New Carlisle - Bosserman 138 kV |  | IN | LaPorte | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-079 | Summer Shade - West Columbia 69 kV |  | KY | Adair | Active | EKPC | 64.8 | 64.8 | 64.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-080 | Albion - Kendallville - 138 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-081 | Jay - DeSoto 138 kV |  | IN | Jay | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-082 | Laurel 25 kV |  | PA | Westmoreland | Active | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI1-084 | Fawkes - West Berea 138kV |  | KY | Madison | Withdrawn | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  | 4/3/2025 |  | 12/1/2026 |  |  | N | No
AI1-085 | Tanners Creek - DeSoto 345 kV |  | IN | Wayne | Active | AEP | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/15/2030 |  |  | N | No
AI1-086 | Trego - Emporia 115 kV |  | VA | Greensville | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-087 | Disputanta - Bakers Pond 115 kV |  | VA | Prince George | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-088 | Poe- New Bohemia 115kV |  | VA | Prince George | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-089 | Myrtle - Oak Ridge 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-091 | Bascom 69 kV |  | OH | Seneca | Active | AEP | 49.9 | 49.9 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI1-092 | Collinsville - Springfield Road 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 49.9 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI1-093 | Westmoreland 34.5 kV |  | PA | Westmoreland | Withdrawn | APS | 24 | 24 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2022 | N/A | N/A |  | 9/5/2025 |  | 7/1/2026 |  |  | N | No
AI1-094 | Westmoreland 34.5 kV |  | PA | Westmoreland | Withdrawn | APS | 24 | 24 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/16/2022 | N/A | N/A |  | 9/5/2025 |  | 7/1/2026 |  |  | N | No
AI1-095 | Branchron - Keisters 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/19/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI1-096 | Pemberton 138 kV |  | WV | N/A | Active | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2022 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI1-097 | Newcomerstown 12.47 kV |  | OH | Tuscarawas | Withdrawn | AEP | 7 | 7 | 6.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2022 | N/A | N/A |  | 8/30/2024 |  | 12/1/2025 |  |  | N | No
AI1-098 | Circleville 138 kV |  | OH | Pickaway | Withdrawn | AEP | 40 | 40 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  | 8/30/2024 |  | 10/1/2026 |  |  | N | No
AI1-099 | Doubs - Brighton 500 kV |  | N/A | N/A | Withdrawn | APS |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  | 10/23/2023 |  | 6/1/2023 |  |  | EE | No
AI1-100 | Somerton - Norton 138 kV |  | OH | Belmont | Active | AEP | 150 | 150 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-101 | Pocono-Acahela 230 kV |  | PA | Lackawanna | Active | PPL | 100 | 100 | 63.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI1-102 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI1-103 | Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 200 | 200 | 127.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-104 | Timber Road 138 kV |  | OH | Paulding | Withdrawn | AEP | 135 | 135 | 86.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  | 8/19/2025 |  | 9/1/2029 |  |  | N | No
AI1-105 | White Haven 2 Tap-White Haven DC 69 kV |  | PA | Luzerne | Active | PPL | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 12/19/2026 |  |  | N | No
AI1-106 | Sinai 13.2 kV |  | VA | Halifax | Active | Dominion | 9.9 | 9.9 | 9.15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI1-107 | Midlothian - North Pole 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  | 6/27/2024 |  | 12/29/2028 |  |  | N | No
AI1-108 | Endless Caverns - Timberville 115 kV |  | VA | Rockingham | Withdrawn | Dominion | 38.5 | 38.5 | 33.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  | 4/14/2025 |  | 1/1/2026 |  |  | N | No
AI1-109 | Deans 500 kV |  | NJ | Middlesex | Active | PSEG | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-110 | Larrabee 230 kV V |  | NJ | Monmouth | Active | JCPL | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-111 | Werner 230 kV |  | NJ | Middlesex | Active | JCPL | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-112 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-113 | New Halifax - Dawson 115 kV |  | NC | Halifax | Withdrawn | Dominion | 74.9 | 74.9 | 74.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2022 | N/A | N/A |  | 1/17/2024 |  | 6/1/2026 |  |  | N | No
AI1-114 | Revloc 46 kV |  | PA | Cambria | Active | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-115 | Glory 34.5 kV |  | PA | Clearfield | Active | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-116 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AI1-117 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AI1-118 | Pequest river - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 37.6 | 37.6 | 15.792 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-119 | Shorewood 138kV |  | IL | Kendall | Active | ComEd | 28.8 | 28.8 | 18.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AI1-120 | Pequest River - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 51.6 | 51.6 | 21.672 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-121 | North Muskingum 69 KV |  | OH | Morgan | Withdrawn | AEP | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2022 | N/A | N/A |  | 1/30/2024 |  | 12/31/2025 |  |  | N | No
AI1-122 | Sparta LF Solar 34.5 kV |  | NJ | Sussex | Active | JCPL | 5.85 | 5.85 | 2.457 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-123 | Nutbush-Victoria DP 115kV |  | VA | Lunenburg | Active | Dominion | 59 | 59 | 35.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-124 | Nutbush - Victoria DP 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-125 | Mount Eagle 34.5 kV |  | VA | Albemarle | Withdrawn | Dominion | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  | 4/14/2025 |  | 9/30/2024 |  |  | N | No
AI1-126 | Farmville 12.47kV |  | VA | Cumberland | Active | Dominion | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI1-127 | Dauphin 12 kV |  | PA | Dauphin | Active | PPL | 4.5 | 4.5 | 2.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/9/2024 |  |  | N | No
AI1-128 | Milesburg 12.47 kV |  | PA | Centre | Active | APS | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/9/2024 |  |  | N | No
AI1-129 | Muncy 12 kV II |  | PA | Lycoming | Active | PPL | 4.5 | 4.5 | 2.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/9/2024 |  |  | N | No
AI1-130 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/7/2026 |  |  | N | No
AI1-131 | TBD 115 kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/7/2026 |  |  | N | No
AI1-132 | Fredricksburg 69 kV |  | KY | Washington | Active | EKPC | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 4/30/2029 |  |  | N | No
AI1-133 | Hillsboro 69 kV |  | KY | Fleming | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 4/30/2029 |  |  | N | No
AI1-134 | Greentown - Hummel Creek 138 kV |  | IN | Grant | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 4/30/2029 |  |  | N | No
AI1-135 | Perquimans 230 kV |  | NC | Chowan | Withdrawn | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  | 12/4/2024 |  | 6/30/2026 |  |  | N | No
AI1-136 | Brodnax 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  | 1/17/2024 |  | 6/30/2026 |  |  | N | No
AI1-137 | Greystone - Portland 230 kV |  | NJ | Warren | Active | JCPL | 155 | 155 | 65.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-139 | Henrietta Township - New Russia Township 69 kV |  | OH | Lorain | Active | ATSI | 14.8 | 14.8 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AI1-140 | Selma Parker - Richmond 138 kV |  | IN | Wayne | Withdrawn | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 6/26/2025 |  | 6/1/2025 |  |  | N | No
AI1-141 | Blossom - Dowagi TSS 34.5 kV |  | MI | Cass | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 6/26/2025 |  | 6/1/2025 |  |  | N | No
AI1-142 | Warren-National Forge 34.5 kV |  | PA | Warren | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 9/7/2023 |  | 6/30/2026 |  |  | N | No
AI1-143 | Bell Township - Vandergrift 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AI1-144 | Gardners 13.2 kV III |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-145 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-146 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-147 | Sandwich 34kV |  | IL | DeKalb | Active | ComEd | 150 | 64 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-148 | Davis Creek 138kV |  | IL | Kankakee | Active | ComEd | 164 | 164 | 98.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-149 | Pleasant Valley 345 kV |  | IL | McHenry | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI1-150 | Locust - Todd 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-151 | Kyger Creek - Pierce 345 kV |  | OH | Adams | Active | AEP | 231.7 | 53.2 | 31.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-152 | Siegfried - Nazareth 69 kV |  | PA | Northampton | Active | ME | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-153 | North Hershey - Grantville 69 kV |  | PA | Dauphin | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-154 | Goodings Grove 138 kV |  | IL | Will | Active | ComEd | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-155 | Chicago Heights 138kV |  | IL | Cook | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-156 | West Rutland 138 kV |  | IL | Kane | Active | ComEd | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-157 | Pleasant Valley – Crystal Lake 138 kV |  | IL | McHenry | Withdrawn | ComEd | 54.4 | 54.4 | 32.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 8/19/2025 |  | 1/4/2027 |  |  | N | No
AI1-158 | Pleasant Valley - Crystal Lake 138 kV |  | IL | McHenry | Withdrawn | ComEd | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 8/19/2025 |  | 1/4/2027 |  |  | N | No
AI1-159 | Mount Sterling - Sideview 69 kV |  | KY | Montgomery | Active | EKPC | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI1-160 | Crawford Solar 2 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI1-161 | Crawford Solar 3 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI1-162 | Saltsburg-Vandergrift 138 kV |  | PA | Armstrong | Withdrawn | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 3/11/2025 |  | 9/15/2026 |  |  | N | No
AI1-163 | Gates Hill - Luzerne 25 kV |  | PA | Fayette | Withdrawn | APS | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 9/7/2023 |  | 6/30/2026 |  |  | N | No
AI1-164 | Clark Summit - Tionesta Junction 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 9/7/2023 |  | 6/30/2026 |  |  | N | No
AI1-165 | Magnolia - Summersville 69 kV |  | KY | Green | Active | EKPC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-166 | Granger - Ontwa 138 kV |  | MI | Cass | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI1-167 | Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI1-168 | Conesville 345 kV |  | OH | Coshocton | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 8/31/2027 |  |  | N | No
AI1-169 | Moyock 230 kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Storage; Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 4/14/2025 |  | 10/15/2026 |  |  | N | No
AI1-170 | Glidden - Sugar Grove 138kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AI1-171 | Garden Plain - Rock Falls 138 kV |  | IL | Whiteside | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 4/30/2028 |  |  | N | No
AI1-172 | Katydid Road - Goodings Grove 345 kV |  | IL | Grundy | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 4/30/2028 |  |  | N | No
AI1-173 | Lena - Freeport 34.5 kV |  | IL | Stephenson | Active | ComEd | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 4/30/2027 |  |  | N | No
AI1-174 | Garden Plain - Rock Falls 138 kV |  | IL | Stephenson | Active | ComEd | 118 | 118 | 94.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 4/30/2028 |  |  | N | No
AI1-175 | Waldo - North Waldo 69 kV |  | OH | Marion | Active | AEP | 19.5 | 19.5 | 16.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-176 | Cheswick 138 kV |  | PA | Allegheny | Withdrawn | DL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 3/19/2024 |  | 12/31/2025 |  |  | N | No
AI1-177 | Avon 345 kV II |  | OH | Lorain | Withdrawn | ATSI | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 12/3/2024 |  | 12/31/2025 |  |  | N | No
AI1-178 | Red House DP - Sugar Hill 115 kV |  | VA | Campbell | Active | Dominion | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-179 | Colver Power Project 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-180 | Windsor 69 kV |  | KY | N/A | Active | EKPC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-181 | Grandview 115 kV |  | PA | Venango | Active | PENELEC | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-182 | Des Plaines 138 kV |  | IL | Cook | Withdrawn | ComEd | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  | 1/3/2024 |  | 12/31/2027 |  |  | N | No
AI1-183 | DuPont - Marlboro 115 kV |  | VA | Richmond | Active | Dominion | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-184 | Greenwood 138 kV |  | VA | Frederick | Active | APS | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-185 | Valley 230 kV |  | VA | Augusta | Active | Dominion | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-186 | Strasburg 138 kV |  | VA | Shenandoah | Active | APS | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-187 | Glen Gardner 230 kV |  | NJ | Hunterdon | Active | JCPL | 280 | 280 | 280 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-188 | Buffalo 115 kV |  | PA | Erie | Active | PENELEC | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-189 | Northeast - Windy Edge 115 kV |  | MD | Baltimore County | Active | BGE | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-190 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-191 | Landcaster - Pecatonica 138 kV |  | IL | Stephenson | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI1-192 | Price Hill - Pruntytown 138 kV |  | WV | Marion | Active | APS | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI1-193 | Lincoln 13.2 kV II |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-194 | Orrtanna 13.2 kV III |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-195 | Orrtanna 13.2 kV IV |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-196 | Gates Hill 25 kV |  | PA | Fayette | Active | ME | 9.8 | 9.8 | 7.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-197 | Gardners 13.2 kV |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-198 | Gardners 13.2 kV II |  | PA | Adams | Active | ME | 7.1 | 7.1 | 5.76 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-199 | South Union 25 kV |  | PA | Fayette | Active | ME | 8.3 | 8.3 | 6.98 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-200 | Campbell 8.32 kV |  | PA | Lawrence | Active | ME | 5 | 5 | 4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-202 | Greenland Gap 500 kV |  | WV | Grant | Withdrawn | APS | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Solar; Storage; Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  | 4/11/2025 |  | 10/15/2026 |  |  | N | No
AI1-203 | Clover - Rawling 500 kV |  | VA | Lunenburg | Active | Dominion | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 12/30/2027 |  |  | N | No
AI1-204 | Brokaw 345 kV |  | IL | N/A | Withdrawn | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2022 | N/A | N/A |  | 11/22/2022 |  | 12/30/2027 |  |  | N | No
AI1-205 | Brokaw 345 kV |  | IL | N/A | Withdrawn | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  | 11/22/2022 |  | 12/30/2028 |  |  | N | No
AI1-206 | Brokaw 345 kV |  | IL | N/A | Withdrawn | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  | 11/22/2022 |  | 12/31/2029 |  |  | N | No
AI1-211 | Brandonville - Necessity 138 kV |  | WV | Preston | Active | APS | 68 | 68 | 68 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-212 | Homer City - Stolle Road 345 kV |  | PA | Jefferson | Active | PENELEC | 182 | 182 | 182 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-213 | Farmers Valley - Ridgeway 115 kV VI |  | PA | Elk | Active | APS | 174 | 174 | 174 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-214 | Philipsburg 115 kV IV |  | PA | Centre | Active | PENELEC | 160 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-215 | Philipsburg 115 kV V |  | PA | Centre | Active | PENELEC | 180 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-216 | Philipsburg 115 kV VI |  | PA | Centre | Active | PENELEC | 200 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-217 | Philipsburg 115 kV VII |  | PA | Centre | Active | PENELEC | 217 | 17 | 17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-218 5225320 | PJM-TVA |  | N/A | N/A | Confirmed |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-sis/ai1218_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/16/2022 | 6/2/2023 | 6/1/2024 | [6 empty] | PP | No
AI1-219 5225323 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/17/2022 | 6/1/2024 | 6/1/2025 |  | 5/15/2024 |  |  |  |  | PP | No
AI1-220 5227906 | PJM-AMIL |  | N/A | N/A | Withdrawn |  |  | 100 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/25/2022 | 6/1/2023 | 6/1/2024 |  | 9/26/2023 |  |  |  |  | PP | No
AI1-221 5227908 | PJM-AMIL |  | N/A | N/A | Withdrawn |  |  | 175 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/25/2022 | 6/1/2023 | 6/1/2024 |  | 9/26/2023 |  |  |  |  | PP | No
AI1-222 5227909 | PJM-AMIL |  | N/A | N/A | Withdrawn |  |  | 750 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/25/2022 | 6/1/2023 | 6/1/2024 |  | 9/26/2023 |  |  |  |  | PP | No
AI2-001 | Remington 115 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2022 | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AI2-002 | Vanceville 138 kV |  | VA | Washington | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2022 | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AI2-004 | Danieltown – Brunswick 115 kV |  | VA | Brunswick | Active | Dominion | 80 | 80 | 71.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/14/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI2-005 | Bremo 115 kV |  | VA | Fluvanna | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2022 | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AI2-006 | Elgin 138kV |  | IL | Kane | Active | ComEd | 484 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/10/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-007 | Rocky Road 138kV |  | IL | Kane | Active | ComEd | 450.8 | 40 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/10/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-010 | Elmont 34.5 kV |  | VA | Hanover | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/23/2022 | N/A | N/A |  |  |  | 12/30/2025 |  |  | N | No
AI2-011 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 100 | 0 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-012 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-013 | Grundy - Goose Lake 138 kV |  | IL | Grundy | Active | ComEd | 24.1 | 24.1 | 17.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AI2-014 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 37.9 | 37.9 | 20.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AI2-015 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2022 | N/A | N/A |  |  |  | 11/30/2025 |  |  | N | No
AI2-017 | PA Centre Borealis 34.5 kV |  | PA | Centre | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-018 | TBD 23 kV |  | PA | Somerset | Active | PENELEC | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-019 | TBD 12.47 kV |  | PA | Franklin | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-020 | Warren County 500 kV |  | VA | Warren | Active | Dominion | 1518 | 19 | 11 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2022 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-022 | East Towanda 230 kV |  | PA | Bradford | Active | PENELEC | 937.5 | 30 | 60 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2022 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-023 | Lake - 270888 345kV |  | IN | Lake | Withdrawn | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2028 |  |  | N | No
AI2-024 | Racine - Ravenswood 69kV |  | OH | Meigs | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-025 |  |  | DE | New Castle | Active | DPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2022 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-026 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2022 | N/A | N/A |  | 9/18/2024 |  | 12/31/2028 |  |  | N | No
AI2-027 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-028 | Beatty - Biers Run 345 kV |  | OH | Union | Active | AEP | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/29/2022 | N/A | N/A |  |  |  | 12/20/2026 |  |  | N | No
AI2-029 | Clarksburg - Biers Run 69 kV |  | OH | Union | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2022 | N/A | N/A |  |  |  | 12/20/2026 |  |  | N | No
AI2-030 | Poplar Flat Switch - Brown Hill 69 kV |  | OH | Adams | Active | AEP | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2023 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AI2-031 | Sapnony 34.5kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-032 | Distribution Circuit#324 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-033 | Sapony 34.5kV |  | VA | Sussex | Active | Dominion | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-034 | Distribution circuit#332 35kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-035 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-036 | Craigsville-Staunton 115kV |  | VA | Augusta | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-037 | Lauraville-Dunbrooke 115kV |  | VA | King and Queen | Active | Dominion | 142 | 142 | 85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-038 | St. Johns 115kV |  | VA | Spotsylvania | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-039 | Poolesville 230kV |  | VA | Surry | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-040 | Orange 115kV |  | VA | Orange | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-041 | South Boston 115kV |  | VA | Halifax | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-042 | Paytes 115kV |  | VA | Louisa | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-043 | Pamplin 34.5kV |  | VA | Northumberland | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2023 | N/A | N/A |  |  |  | 4/26/2024 |  |  | N | No
AI2-044 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI2-045 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI2-046 5260341 |  |  | N/A | N/A | Withdrawn |  |  | 20 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/14/2023 | 6/1/2026 | 6/1/2031 |  | 3/6/2023 |  |  |  |  | PP | No
AI2-047 5260343 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 157 |  |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/14/2023 | 6/1/2026 | 6/1/2031 |  | 6/11/2025 |  |  |  |  | PP | No
AI2-048 5260618 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 157 |  |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/14/2023 | 6/1/2024 | 6/1/2026 |  | 11/3/2023 |  |  |  |  | PP | No
AI2-049 5260620 |  |  | N/A | N/A | Withdrawn |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/13/2023 | 6/1/2024 | 6/1/2026 |  | 3/6/2023 |  |  |  |  | PP | No
AI2-050 5263047 | PJM-MECS |  | N/A | N/A | Active |  |  | 300 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/15/2023 | 6/1/2025 | 6/1/2030 | [6 empty] | PP | No
AI2-051 5263048 | PJM-AMIL |  | N/A | N/A | Active |  |  | 200 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/15/2023 | 6/1/2025 | 6/1/2030 | [6 empty] | PP | No
AI2-052 | Lakewood 230 kV II |  | NJ | Ocean | Active | JCPL | 170 | 70 | 70 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-053 | New Holland 69 kV |  | OH | Fayette | Withdrawn | Dayton | 100 | 100 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  | 2/18/2025 |  | 12/31/2026 |  |  | N | No
AI2-054 | Rock Springs 500 kV |  | MD | Cecil | Active | DPL | 784 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 6/1/2028 |  |  | N | No
AI2-055 | Summit-West Fall 115kV II |  | PA | Blair | Active | PENELEC | 38 | 0 | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 12/10/2010 |  |  | N | No
AI2-056 | Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 2/6/2024 |  |  | N | No
AI2-057 | Venango 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 0 | 6.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 2/20/2024 |  |  | N | No
AI2-058 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 1/14/2025 |  |  | N | No
AI2-059 | Wolfs Corners 34.5 kV |  | PA | Clarion | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 1/14/2024 |  |  | N | No
AI2-060 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Active | ComEd | 70 | 0 | 40.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AI2-061 | Bedford North-Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 60 | 0 | 17.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI2-062 | Jack Frost - Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 60 | 0 | 18.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 5/15/2027 |  |  | N | No
AI2-063 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 280 | 0 | 82.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 5/15/2027 |  |  | N | No
AI2-064 | Desoto - Keystone 345 kV |  | IN | Blackford | Active | AEP | 245 | 0 | 35.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI2-065 | Varner - Sours 138 kV |  | IN | DeKalb | Active | AEP | 180 | 0 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AI2-066 | Marion County 161 kV |  | KY | Marion | Active | EKPC | 96 | 0 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-067 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI2-068 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-069 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 10/21/2026 |  |  | N | No
AI2-070 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI2-071 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI2-072 | Steubenville 69 kV |  | OH | Jefferson | Active | AEP | 49.5 | 0 | 27.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 5/15/2024 |  |  | N | No
AI2-073 | Columbia-Sunbury 69 kV |  | PA | Snyder | Withdrawn | PPL | 19.8 | 0 | 9.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  | 6/24/2025 |  | 6/30/2024 |  |  | N | No
AI2-074 | Beatty - Greene 345 kV |  | OH | Madison | Active | AEP | 577 | 0 | 87.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AI2-075 | Face Rock-Kinzer #13 69 kV |  | PA | Lancaster | Withdrawn | PPL | 19.8 | 0 | 9.86 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  | 7/17/2025 |  | 7/1/2023 |  |  | N | No
AI2-076 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 175 | 0 | 56 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 3/15/2023 |  |  | N | No
AI2-077 | Kanakee 138 kV |  | IL | Kankakee | Active | ComEd | 175 | 0 | 56 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 3/16/2023 |  |  | N | No
AI2-078 | Myrtle-Windsor 115 kV |  | VA | Isle of Wight | Active | Dominion | 91 | 0 | 52.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-079 | Harmony Village-Shackleford 115 kV |  | VA | Fauquier | Active | Dominion | 70 | 0 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-080 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 134 | 0 | 73.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-081 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 500 | 0 | 271 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-082 | Cardington-Liberty 69 kV IV |  | OH | Morrow | Active | ATSI | 101 | 0 | 34.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-083 | National-Tangy 138kV V |  | OH | Madison | Withdrawn | ATSI | 177 | 0 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  | 12/1/2023 |  | 12/31/2025 |  |  | N | No
AI2-084 | Galion 138 kV VI |  | OH | Morrow | Active | ATSI | 244 | 0 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-085 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Withdrawn | OVEC | 120 | 0 | 65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  | 12/13/2024 |  | 12/31/2025 |  |  | N | No
AI2-086 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 80 | 0 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-087 | Gold-Sabinsville 115kV III |  | PA | Potter | Active | PENELEC | 90 | 0 | 42.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 3/3/2023 |  |  | N | No
AI2-088 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 412.5 | 0 | 229.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-089 | Cedar Creek 138 kV |  | DE | New Castle | Active | DPL | 114.3 | 0 | 71 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AI2-090 | Harrington 69 kV |  | DE | N/A | Active | DPL | 50 | 0 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2025 |  |  | N | No
AI2-091 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 49.2 | 0 | 22.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-092 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 75.9 | 0 | 40.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-093 | Olive-DeQuine 345kV |  | IN | White | Active | AEP | 202 | 0 | 106.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-094 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 104 | 0 | 53.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-095 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 50.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-096 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 54 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-097 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 45.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-098 | Meadow Lake 345kV |  | IN | White | Active | AEP | 200 | 0 | 107 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-099 | Powerton-Goodings Grove 345kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 102 | 0 | 49.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-100 | Powerton - Dresden 345kv (CIR Increase) |  | IL | Livingston | Active | ComEd | 198 | 0 | 96 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-101 | Haviland - Milan 138kV |  | OH | Paulding | Active | AEP | 99 | 0 | 42.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-102 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 101 | 0 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-103 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-104 | Blue Mound I |  | IL | McLean | Active | ComEd | 198 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-105 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-106 | Pontiac MidPoint-Brokaw 345kV |  | IL | Livingston | Active | ComEd | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-107 | Ada-Dunkirk 69kV |  | OH | Hardin | Active | AEP | 66 | 0 | 31.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-109 | Madoc - Delaware 138 kV |  | IN | Randolph | Active | AEP | 150 | 0 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-110 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 100 | 0 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AI2-111 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AI2-112 | Bluff Point-Randolph 138 kV |  | IN | Randolph | Active | AEP | 100 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-113 | Old Church 230 kV |  | VA | Hanover | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 9/18/2029 |  |  | N | No
AI2-114 | Verona - Weyers Cave 115 kV |  | VA | Augusta | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI2-115 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-116 | Allen 345kV |  | IN | Allen | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-117 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 0 | 11.976 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/28/2023 |  |  | N | No
AI2-118 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 0 | 11.976 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/28/2023 |  |  | N | No
AI2-119 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/28/2021 |  |  | N | No
AI2-120 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 125 | 0 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AI2-121 | Hector 115 kV |  | PA | Potter | Withdrawn | PENELEC | 50 | 0 | 19.95 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  | 2/21/2025 |  | 12/31/2024 |  |  | N | No
AI2-122 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 130 | 0 | 66.95 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  | 2/21/2025 |  | 12/31/2024 |  |  | N | No
AI2-123 | Goddard - Plumville 138 kV |  | KY | Fleming | Active | EKPC | 120 | 0 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-124 | Goddard 138 kV |  | KY | Fleming | Active | EKPC | 200 | 0 | 23.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-125 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 96 | 0 | 32.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-126 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 54 | 0 | 16.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-127 | Cynthiana Tie - Headquarters 69 kV |  | KY | Harrison | Active | EKPC | 70 | 0 | 20.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI2-128 | Cardiff 230 kV |  | NJ | Atlantic | Active | AEC | 1509.6 | 0 | 1204.52 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/30/2027 |  |  | N | No
AI2-129 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2250 | 0 | 1675.59 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-130 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 1300 | 0 | 1037.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-131 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 882 | 0 | 703.75 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-132 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 445.2 | 0 | 355.02 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-133 | Kincaid-Pana 345kV |  | IL | Christian | Active | ComEd | 260 | 0 | 84.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-134 | Pontiac Midpoint 345 kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-135 | McLean 345 kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-136 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 0 | 47.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-137 | Stockton 138 kV |  | VA | Henry | Active | AEP | 90 | 0 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-138 | Marysville 345kV |  | OH | Union | Active | AEP | 175 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/26/2023 |  |  | N | No
AI2-139 | Marysville 345kV |  | OH | Union | Active | AEP | 225 | 0 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-141 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 0 | 18.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AI2-143 | Clubhouse-Sappony 230 kV |  | VA | Sussex | Active | Dominion | 149 | 0 | 37.65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-144 | Mottville 138 kV |  | MI | St. Joseph | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-145 | Claytor Lake - Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 126.65 | 0 | 30.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-146 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 0 | 67.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-147 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 200 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-148 | Mississinewa- Gaston 138 kV |  | IN | Grant | Active | AEP | 160 | 0 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-149 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 280 | 0 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/24/2023 |  |  | N | No
AI2-150 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 185 | 0 | 44.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-151 | AC1-053 Tap 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 600 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-152 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 120 | 0 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-153 | Louisa-South Anna 230 kV |  | VA | Louisa | Active | Dominion | 127 | 0 | 31.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-154 | Moshannon-Milesburg 230 kV IX |  | PA | Centre | Active | APS | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-155 | Baker 138 kV II |  | WV | Hardy | Active | APS | 80 | 0 | 29.84 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-156 | East Springfield-London 138 kV III |  | OH | Clark | Active | ATSI | 234 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-157 | Elk 138 kV |  | OH | Vinton | Active | AEP | 125 | 0 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-158 | Fentress - Sligo 230kV (CIR Increase) |  | VA | City of Chesapeake | Withdrawn | Dominion | 192 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  | 9/12/2023 |  | 12/31/2024 |  |  | N | No
AI2-159 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 232 | 0 | 43.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI2-160 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AI2-161 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-162 | Meridian - Twin Branch 345 kV |  | IN | Whitley | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-163 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 200 | 0 | 68.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-164 | Fostoria Central - Lemoyn 345 kV |  | OH | Wood | Active | AEP | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-165 | Clinton - Stuart 345 kV |  | OH | Clinton | Active | Dayton | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-166 | Lanesville-Brokaw |  | IL | Logan | Active | ComEd | 200 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AI2-167 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 400 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-168 | Magley 138 kV |  | IN | Adams | Active | AEP | 135 | 0 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-169 | Brody 138 kV |  | MI | Cass | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-170 | Delaware - Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 0 | 39.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-171 | Cole Road 345 kV |  | OH | Franklin | Active | AEP | 310 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-172 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 205 | 0 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-173 | West Newton-Lynn 138 kV |  | OH | Hardin | Active | AEP | 110 | 0 | 26.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-174 | Kenzie Creek - Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-175 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-176 | Todd 69 kV |  | MD | Dorchester | Active | DPL | 50 | 0 | 14.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-177 | Todd 25 kV |  | MD | Dorchester | Active | DPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 7/31/2021 |  |  | N | No
AI2-178 | LaSalle 138 kV |  | IL | Lasalle | Active | ComEd | 105.6 | 0 | 36.51 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 3/17/2023 |  |  | N | No
AI2-179 | Brokaw-Pontiac 345kV |  | IL | McLean | Active | ComEd | 250 | 0 | 97.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 3/17/2023 |  |  | N | No
AI2-180 | LaSalle 138kV |  | IL | Lasalle | Active | ComEd | 191 | 0 | 6.16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AI2-181 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 170 | 0 | 27.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AI2-182 | Jennings-Hazelton 138kV II |  | WV | Preston | Active | APS | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-183 | Spotsylvania 500kV |  | VA | Spotsylvania | Active | Dominion | 485 | 0 | 123.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-184 | Whitely 138 kV |  | PA | Greene | Active | APS | 30 | 0 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AI2-185 | Franklin 138 kV |  | PA | Greene | Active | APS | 150 | 0 | 41 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AI2-186 | Franklin 138 kV |  | PA | Greene | Active | APS | 74 | 0 | 20.25 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AI2-187 | Mt. Storm 500kV |  | WV | Grant | Active | Dominion | 800 | 0 | 445 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI2-188 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 425 | 0 | 246.25 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2028 |  |  | N | No
AI2-189 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 125 | 0 | 66.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2028 |  |  | N | No
AI2-190 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 0 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2028 |  |  | N | No
AI2-191 | Lyons - Moselem Springs 69 kV |  | PA | Berks | Active | ME | 20 | 0 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AI2-192 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 40 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/15/2025 |  |  | N | No
AI2-193 | East Hartford - Murch 69 kV |  | MI | Van Buren | Active | AEP | 85 | 0 | 28.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI2-194 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 49.9 | 0 | 15.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-195 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 194.11 | 0 | 69.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 4/30/2025 |  |  | N | No
AI2-196 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 143.11 | 0 | 51.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/30/2025 |  |  | N | No
AI2-197 | Reynolds - Olive 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-198 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-199 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-200 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 400 | 0 | 144 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-201 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-202 | Bennett - Farmingdale 34.5 kV |  | NJ | Monmouth | Active | JCPL | 2 | 0 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/11/2023 |  |  | N | No
AI2-203 | Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 2 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AI2-204 | Brokaw 345kV (CIR Increase) |  | NJ | Gloucester | Active | PSEG | 3 | 0 | 1.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AI2-205 | Branchville - Sussex 34.5 kV |  | NJ | Sussex | Active | JCPL | 10 | 0 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-206 | Cardiff 12 kV |  | NJ | Atlantic | Active | AEC | 2.6 | 0 | 1.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AI2-207 | Rockawalkin 69 kV |  | MD | Wicomico | Active | DPL | 15 | 0 | 5.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AI2-208 | Hawks 12.5 kV |  | NJ | Hunterdon | Active | JCPL | 3 | 0 | 1.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-209 | Burlington 26kV (CIR Increase) |  | NJ | Burlington | Active | PSEG | 7 | 0 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-210 | Ringoes-US Bronze 34kV |  | NJ | Hunterdon | Active | JCPL | 10 | 0 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-211 | Price 25 kV |  | MD | Queen Anne's | Active | DPL | 6 | 0 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/3/2023 |  |  | N | No
AI2-212 | Manitou-Pleasant Plains 34.5 kV |  | NJ | Ocean | Active | JCPL | 20 | 0 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AI2-213 | Allenwood-Larrabee 2 34.5 kV |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-214 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Active | AEP | 149.5 | 0 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/12/2025 |  |  | N | No
AI2-215 | Pokagon - Corey 69 kV |  | MI | Cass | Active | AEP | 50 | 0 | 18.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AI2-216 | Wurno - Claytor lake 138 kV |  | VA | Pulaski | Active | AEP | 180 | 0 | 77 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/13/2028 |  |  | N | No
AI2-217 | Greene - Beatty 345 kV |  | OH | Madison | Active | AEP | 155 | 0 | 56.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AI2-218 | Galion - South Berwick 345 kV |  | OH | Wyandot | Active | AEP | 120 | 0 | 43.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AI2-219 | Groton 138 kV II |  | OH | Erie | Active | ATSI | 125 | 0 | 45.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/30/2024 |  |  | N | No
AI2-220 | Beaver-Davis Besse 345 kV II |  | OH | Erie | Active | ATSI | 297.66 | 0 | 103.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AI2-221 | Snyder 69 kV II |  | OH | Williams | Active | ATSI | 49 | 0 | 17.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AI2-222 | Chase City-Lunenburg 115kV |  | VA | Lunenburg | Active | Dominion | 130 | 0 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-223 | WinFall-Chowan 230kV |  | NC | Chowan | Active | Dominion | 189 | 0 | 56.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/28/2024 |  |  | N | No
AI2-224 | Central-Chase City 115kV |  | VA | Charlotte | Active | Dominion | 149.5 | 0 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AI2-225 | Lexington-Low Moor 230kV |  | VA | Botetourt | Active | Dominion | 78.2 | 0 | 32 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/3/2025 |  |  | N | No
AI2-226 | Jug Street 138 kV |  | OH | Licking | Active | AEP | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 8/22/2022 |  |  | N | No
AI2-227 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AI2-228 | Silver Lake 345 |  | IL | McHenry | Active | ComEd | 400 | 0 | 240 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AI2-229 | Silver Lake 138 |  | IL | McHenry | Active | ComEd | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AI2-230 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AI2-231 | Gainesville-Loudoun 230 kV |  | VA | Prince William | Active | Dominion | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/22/2023 |  |  | N | No
AI2-231A | Cloverdale-Burlington Height 138 kV |  | VA | Botetourt | Active | AEP | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/22/2023 |  |  | N | No
AI2-232 | Shady Oaks Road 138 kV |  | IL | Lee | Active | ComEd | 215.4 | 0 | 99.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AI2-233 | Eagle Valley 115kV II |  | PA | Centre | Active | PENELEC | 137.6 | 0 | 49.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AI2-234 | Mole Creek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 200 | 0 | 92.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AI2-235 | King's Creek 138 kV |  | MD | Somerset | Active | DPL | 118 | 0 | 62.652 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/2/2023 |  |  | N | No
AI2-236 | Smith Mountain - Candler Mountain 138 kV |  | VA | Campbell | Active | AEP | 80 | 0 | 22.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AI2-237 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 0 | 69.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI2-238 | College Corner 138 kV |  | OH | Preble | Active | AEP | 98 | 0 | 39.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-239 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 150 | 0 | 50.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI2-240 | Camden - Crystal 69 kV |  | OH | Preble | Active | Dayton | 69.9 | 0 | 25.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-241 | Congress-Toronto 138 kV II |  | OH | Columbiana | Active | ATSI | 145 | 0 | 55.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-242 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 144 | 0 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI2-243 | Ecogrove 138 kV (CIR Increase) |  | IL | Stephenson | Active | ComEd | 199 | 0 | 80.3 |  | Capacity | Generation Interconnection | Solar; Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-244 | Victoria DP-Martin DP 115 kV |  | VA | Nottoway | Active | Dominion | 150 | 0 | 50.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2028 |  |  | N | No
AI2-245 | TSS 968 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 200 | 0 | 55.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2028 |  |  | N | No
AI2-246 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/30/2024 |  |  | N | No
AI2-248 | Schauff Road 138 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/25/2019 |  |  | N | No
AI2-249 | Biers Run-Circleville 138 kV |  | OH | Ross | Active | AEP | 274 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/14/2023 |  |  | N | No
AI2-250 | Greenfield 69 kV |  | OH | Fayette | Active | Dayton | 48 | 0 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AI2-251 | Buckskin 69kV |  | OH | Ross | Active | AEP | 120 | 0 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 7/31/2024 |  |  | N | No
AI2-252 | Hillsboro-Clinton 138kV |  | OH | Ross | Active | AEP | 117 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI2-253 | Chatfield-Howard 138kV |  | OH | Crawford | Active | AEP | 117 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI2-254 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 60 | 0 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 1/15/2025 |  | 10/1/2028 |  |  | N | No
AI2-255 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 11/21/2024 |  | 10/1/2028 |  |  | N | No
AI2-256 | Gary 115kV |  | VA | Lunenburg | Withdrawn | Dominion | 80 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 6/28/2023 |  | 10/1/2028 |  |  | N | No
AI2-257 | Cordova 345kV (CIR Increase) |  | IL | Lee | Withdrawn | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 11/21/2024 |  | 10/1/2028 |  |  | N | No
AI2-259 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 11/23/2024 |  | 10/1/2028 |  |  | N | No
AI2-260 | Keeney - Steele 230 kV |  | MD | Caroline | Withdrawn | DPL | 189 | 0 | 82.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 1/31/2025 |  | 12/30/2025 |  |  | N | No
AI2-261 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 1/15/2025 |  | 10/1/2028 |  |  | N | No
AI2-263 | Nelson 345kV (CIR Increase) |  | IL | Lee | Withdrawn | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 11/21/2024 |  | 10/1/2028 |  |  | N | No
AI2-264 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AI2-265 | Kincaid 345kV (CIR Increase) |  | IL | Christian | Withdrawn | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 11/21/2024 |  | 10/1/2028 |  |  | N | No
AI2-266 | R.P.Mone 345 kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 11/23/2024 |  | 10/1/2028 |  |  | N | No
AI2-267 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 1/15/2025 |  | 10/1/2028 |  |  | N | No
AI2-269 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 70 | 0 | 32.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-270 | East Lima-Marysville 345kV |  | OH | Hardin | Active | AEP | 150 | 0 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/25/2023 |  |  | N | No
AI2-271 | Smith Mountain-Bearskin 138 kV |  | VA | Pittsylvania | Active | AEP | 120 | 0 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-272 | Pantago-Five Points 115kV |  | NC | Beaufort | Active | Dominion | 74 | 0 | 32.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/23/2023 |  |  | N | No
AI2-273 | Boykins-Handsome 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/25/2023 |  |  | N | No
AI2-274 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 17 | 0 | 6.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AI2-275 | Garner-Northern Neck 115 kV |  | VA | Pittsylvania | Active | Dominion | 42 | 0 | 5.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/24/2023 |  |  | N | No
AI2-277 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 75 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-278 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI2-279 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 75 | 0 | 43 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-280 | Carson-Wake 500kV |  | VA | Brunswick | Active | Dominion | 1525.5 | 0 | 34 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/24/2023 |  |  | N | No
AI2-281 | Heritage-Carson |  | VA | Greensville | Active | Dominion | 1756 | 0 | 44.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-282 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 11.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-283 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 12.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-284 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 10.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AI2-285 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-286 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 9.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-287 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 18.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-288 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-289 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 16.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-290 | Brookside-Cloverdale 138 kV II |  | OH | Wayne | Active | ATSI | 130 | 0 | 9.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-291 | Edison-Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 10.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-292 | Hunterstown-Texas Eastern Tap 115 kV III |  | PA | Adams | Active | ME | 70 | 0 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-293 | Edinboro South-Venango Junction 115 kV IV |  | PA | Crawford | Active | PENELEC | 116.5 | 0 | 8.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-294 | Laurel Mountain 138 kV |  | WV | Randolph | Active | APS | 125 | 0 | 52.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-295 | Cox-Whitakers 115kV |  | NC | Halifax | Active | Dominion | 80 | 0 | 20.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-296 | Chickahominy 230kV |  | VA | Charles City | Active | Dominion | 320 | 0 | 83.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/25/2025 |  |  | N | No
AI2-297 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 0 | 18.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-298 | McConnellsburg-Texas Eastern 138 kV |  | PA | Franklin | Active | APS | 150 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-299 | Benson-Dunbar 115 kV |  | NC | Edgecombe | Active | Dominion | 100 | 0 | 30.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/11/2020 |  |  | N | No
AI2-300 | Elizabeth City 34.5 kV |  | NC | Pasquotank | Active | Dominion | 20 | 0 | 6.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 10/18/2021 |  |  | N | No
AI2-301 | Dawson-South Justice 115kV |  | NC | Halifax | Active | Dominion | 140 | 0 | 45.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-302 | Jacksonville Tap - Renaker 138 kV |  | KY | Harrison | Active | EKPC | 100 | 0 | 26.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 8/30/2024 |  |  | N | No
AI2-303 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 0 | 18.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-304 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 0 | 36.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-305 | Ebersole #2-Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 120 | 0 | 33.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-306 | Osterburg - Bedford North 23 kV II |  | PA | Bedford | Withdrawn | PENELEC | 12 | 0 | 4.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 7/22/2025 |  | 7/18/2025 |  |  | N | No
AI2-307 | Colora 230 kV |  | MD | Cecil | Active | DPL | 100.8 | 0 | 60.48 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/10/2026 |  |  | N | No
AI2-308 | Snake Spring-Bedford Area 23 kV |  | PA | Bedford | Active | PENELEC | 12 | 0 | 4.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/27/2024 |  |  | N | No
AI2-309 | Marysville-Gunn Road 345 kV |  | OH | Hardin | Withdrawn | AEP | 250 | 0 | 90.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 2/18/2025 |  | 4/15/2025 |  |  | N | No
AI2-310 | Emlenton 34.5 kV II |  | PA | Venango | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/3/2025 |  |  | N | No
AI2-311 | Ringgold 138 kV II |  | MD | Washington | Active | APS | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 1/11/2025 |  |  | N | No
AI2-312 | Clark Summit 34.5 kV II |  | PA | Venango | Active | PENELEC | 15 | 0 | 5.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AI2-313 | Ravenswood-Hemlock 69kV |  | OH | Meigs | Active | AEP | 48 | 0 | 17.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI2-314 | Molecreek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 100 | 0 | 27 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-315 | Mole Creek 345 kV |  | IL | Woodford | Active | ComEd | 300 | 0 | 90 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-316 | Powerton 345 kV (CIR increase) |  | IL | Woodford | Active | ComEd | 50 | 0 | 19 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-317 | Powertn - Goodings Grove 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 350 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-318 | White Marsh 34.5 kV |  | VA | Gloucester | Active | Dominion | 19 | 0 | 12.84 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-320 | Edinboro South - Erie South 25 kV |  | PA | Erie | Withdrawn | PENELEC | 19.9 | 0 | 5.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 7/7/2025 |  | 6/1/2025 |  |  | N | No
AI2-321 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 0 | 8.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-322 | Findlay - Midfield 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 0 | 1.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-323 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Withdrawn | APS | 30 | 0 | 7.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 6/30/2025 |  | 6/1/2025 |  |  | N | No
AI2-324 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 14.7 | 0 | 3.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-325 | Oyster Creek 230 kV |  | NJ | Ocean | Active | JCPL | 816 | 0 | 178.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-326 | BL England 138 kV |  | NJ | Cape May | Active | AEC | 432 | 0 | 94.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-327 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 55 | 0 | 19.91 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/15/2023 |  |  | N | No
AI2-328 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-329 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-330 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 83.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-331 | Hopkins 138 kV |  | WV | N/A | Withdrawn | AEP | 180 | 0 | 42.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 3/4/2025 |  | 5/1/2025 |  |  | N | No
AI2-332 | Gilboa-Jones Branch 138 kV VI |  | WV | Nicholas | Active | APS | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/1/2030 |  |  | N | No
AI2-333 | Johns Creek-Excel 138kV I |  | KY | Pike | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-334 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 0 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-335 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 0 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-336 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 400 | 0 | 34.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/10/2026 |  |  | N | No
AI2-337 | Broadview-Tangy 138 kV IV |  | OH | Madison | Active | ATSI | 180 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AI2-338 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 0 | 29.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-339 | Gilboa-Jones Branch 138 kV VII |  | WV | Nicholas | Active | APS | 100 | 0 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-340 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 100 | 0 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-341 | Galion-Roberts South 138 kV III |  | OH | Marion | Active | ATSI | 99.96 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-342 | Excel-Johns Creek 138 kV |  | KY | Pike | Active | AEP | 75 | 0 | 15.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/31/2027 |  |  | N | No
AI2-343 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 0 | 15.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/3/2025 |  |  | N | No
AI2-344 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 100 | 0 | 17 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-345 | Amherst-Riverville138 kV |  | VA | Amherst | Active | AEP | 75 | 0 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-346 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 400 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/10/2025 |  |  | N | No
AI2-347 | Van Arsdell-Mercer Industrial 69kV |  | KY | Mercer | Withdrawn | EKPC | 95 | 0 | 17 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  | 3/5/2025 |  | 9/1/2026 |  |  | N | No
AI2-348 | Ford - Ceddarville 138 kV |  | OH | Clermont | Active | DEOK | 152.2 | 0 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-349 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/28/2029 |  |  | N | No
AI2-350 | Hillsboro - Wye Mills 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 0 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-351 | Lappans 34.5kV II |  | MD | Washington | Withdrawn | APS | 20 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  | 9/11/2023 |  | 6/1/2025 |  |  | N | No
AI2-352 | Martins Creek–Cherry Hill 69 kV |  | PA | Northampton | Withdrawn | PPL | 60.25 | 22 | 22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 6/26/2024 |  | 12/31/2025 |  |  | N | No
AI2-353 | Carlos Jct. – Ridgeley 138 kV |  | MD | Allegany | Active | APS | 54.9 | 0 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 4/1/2024 |  |  | N | No
AI2-354 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 0 | 58.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI2-355 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 300 | 0 | 103.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-356 | Greenland Gap 500 kV II |  | WV | Grant | Active | APS | 471.6 | 0 | 57.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 7/31/2027 |  |  | N | No
AI2-357 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 260 | 0 | 18.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-358 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 300 | 0 | 70 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2023 | N/A | N/A |  |  |  | 5/1/2028 |  |  | N | No
AI2-359 | Cross School 138 kV |  | WV | Mineral | Active | APS | 53.7 | 0 | 13.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-360 | Elk Garden - Parr Run 138 kV |  | WV | Mineral | Active | APS | 110 | 0 | 45.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-361 | Hooversville - Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 29.4 | 0 | 10.17 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 3/2/2023 |  |  | N | No
AI2-362 | Rockwood - Meyersdale North 115 kV |  | PA | Somerset | Active | PENELEC | 37.8 | 0 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-363 5267408 | PJM-CIN |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/8/2023 | 6/1/2025 | 6/1/2026 |  | 6/19/2024 |  |  |  |  | PP | No
AI2-364 | Brokaw - Lanesville 345 kV (CIR Increase) |  | IL | Fulton | Active | ComEd | 200 | 0 | 79.91 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/20/2023 |  |  | N | No
AI2-365 | Lake Lynn-Hazelton 138 kV II |  | WV | Preston | Active | APS | 99.6 | 0 | 32.06 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AI2-366 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 300 | 0 | 93.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AI2-367 | Sleepy Hollow 138 kV II |  | WV | Jefferson | Withdrawn | APS | 125 | 0 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 6/30/2025 |  | 6/30/2023 |  |  | N | No
AI2-368 | TSS 994 345 kV (CIR Increase) |  | IL | Logan | Active | ComEd | 187.5 | 0 | 77.87 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/17/2023 |  |  | N | No
AI2-369 | Apple Grove 138 kV |  | WV | Mason | Withdrawn | AEP | 99 | 0 | 29.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 5/23/2025 |  | 6/30/2023 |  |  | N | No
AI2-370 | Twombley Road 138kV (CIR Increase) |  | IL | Ogle | Active | ComEd | 60 | 0 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/1/2026 |  |  | N | No
AI2-371 | Walnut Grove - Asahi Tap 69 kV |  | KY | McLean | Active | EKPC | 57 | 0 | 17.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AI2-372 | Hill Topper 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 65 | 0 | 23.56 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/30/2020 |  |  | N | No
AI2-373 | Easton - Steele 138 kV |  | MD | Talbot | Withdrawn | DPL | 79 | 0 | 23.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 7/7/2025 |  | 3/31/2026 |  |  | N | No
AI2-374 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 0 | 20.59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/31/2025 |  |  | N | No
AI2-375 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 80 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-376 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 70 | 0 | 21.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  | 10/23/2024 |  | 3/31/2025 |  |  | N | No
AI2-377 | Maysville 69 kV VI |  | PA | Mercer | Active | ATSI | 50 | 0 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-378 | Merrill Creek 115 kV II |  | NJ | Warren | Active | JCPL | 70 | 0 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-379 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 78.38 | 0 | 24.51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-380 | Altoona-Raystown 230 kV III |  | PA | Blair | Withdrawn | PENELEC | 80 | 0 | 30.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 8/7/2024 |  | 12/1/2024 |  |  | N | No
AI2-381 | Layland 69 kV |  | WV | Fayette | Withdrawn | AEP | 75 | 0 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 1/16/2025 |  | 12/1/2024 |  |  | N | No
AI2-383 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 83.6 | 0 | 26.29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-384 | Nelson 138kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 89.44 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-385 | South Millville - Newport 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 59.7 | 0 | 23.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 4/4/2025 |  | 3/31/2025 |  |  | N | No
AI2-386 | PG - Juniata 69 kV |  | PA | Dauphin | Withdrawn | PPL | 55 | 0 | 20.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 6/26/2025 |  | 12/31/2026 |  |  | N | No
AI2-387 | Carlls Corner - Sherman Ave 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 49.7 | 0 | 19.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 5/7/2025 |  | 12/31/2024 |  |  | N | No
AI2-388 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 70 | 0 | 20.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-389 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Withdrawn | ComEd | 300 | 0 | 134.16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  | 1/16/2025 |  | 12/31/2027 |  |  | N | No
AI2-390 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 134.16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-391 | Emporia-Trego 115kV |  | VA | Greensville | Active | Dominion | 80 | 0 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 2/25/2023 |  |  | N | No
AI2-392 | Beatty-London 138 kV |  | OH | Madison | Active | AEP | 196 | 0 | 31.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-393 | Hickory-Moyock 230 kV |  | NC | Currituck | Active | Dominion | 100 | 0 | 17.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-394 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-395 | Reynolds–Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 0 | 59.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-396 | Jay-Desoto 138kV |  | IN | Blackford | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-397 | West Manchester-Crown 69kV |  | OH | Preble | Active | AEP | 80 | 0 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-398 | West Manchester 69 kV |  | OH | Preble | Active | AEP | 40 | 0 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-399 | Jay 138 kV |  | IN | Jay | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-400 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 72.6 | 0 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-401 | Olive-Reynolds #1 345 kV |  | IN | White | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-402 | Kirk - Newark Center 138 kV |  | OH | Licking | Active | AEP | 107.7 | 0 | 25.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-403 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 81.4 | 0 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-404 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-405 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 94.9 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-407 | Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 205 | 0 | 31.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-408 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-409 | Wayne-Byron 345 kV |  | IL | DeKalb | Active | ComEd | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-410 | Glidden - Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 118.6 | 0 | 28.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-411 | Glidden - Waterman 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 95.1 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-412 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-413 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-414 | Lynnville-South Hamburg 69 kV |  | PA | Berks | Active | ME | 50 | 0 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-415 | Campbell-Kiesters 138 kV |  | PA | Butler | Active | APS | 70 | 0 | 20.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-416 | Lexington-Dooms 230 kV |  | VA | Augusta | Active | Dominion | 200 | 0 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-417 | Wayne 345kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-418 | Sowers 138 kV |  | IN | Allen | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-419 | Oak Grove – Saunders DP 230 kV |  | VA | Westmoreland | Withdrawn | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  | 3/28/2023 |  | 12/31/2027 |  |  | N | No
AI2-420 | Crego Road 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 100 | 0 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-421 | Varner 345 kV |  | IN | DeKalb | Active | AEP | 180 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-422 | Jay 138 kV |  | IN | Jay | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-423 | Jay 69 kV |  | IN | Jay | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-424 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 111.8 | 0 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-425 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 160 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-426 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 180 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-427 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 110 | 0 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-428 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 88.7 | 0 | 20.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-429 | Mendota Hills 138 kV |  | IL | Lee | Active | ComEd | 76.1 | 0 | 22.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-430 | Auburn 69 kV |  | IN | DeKalb | Active | AEP | 11 | 11 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AI2-431 | Larrabee Collector Station 230 kV |  | NJ | Atlantic | Active | JCPL | 2138.85 | 2138.85 | 2083 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-432 | Philipsburg-Clarence 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/27/2022 |  |  | N | No
AI2-433 | Dubois-Curwensville 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AI2-434 |  |  | PA | Lycoming | Active | PPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-435 | South Hamburg – St. Peters Village 69 kV |  | PA | Berks | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-436 | Luthersburg - Curwensville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-437 | Glen Gardner - Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-438 | Apple Valley 138kV |  | OH | Knox | Withdrawn | AEP | 150 | 150 | 148 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  | 7/3/2025 |  | 7/10/2027 |  |  | N | No
AI2-439 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 237 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-440 | Phillipsburg 115 kV |  | PA | Centre | Active | PENELEC | 257 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-441 | Salem - Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 100 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-442 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-443 | North Longview 500 kV |  | PA | Greene | Active | APS | 300 | 300 | 295 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 7/10/2027 |  |  | N | No
AI2-444 | Rum Creek 138kV |  | WV | N/A | Active | AEP | 59.5 | 59.5 | 52.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 3/8/2026 |  |  | N | No
AI2-445 | Parsons - William 138 kV |  | WV | Tucker | Active | APS | 148 | 148 | 128.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 3/8/2026 |  |  | N | No
AI2-446 | Medera - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-447 | Hillsboro-Wildcat 138kV |  | OH | Highland | Active | AEP | 150 | 0 | 87.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AI2-448 | Curdsville-Willis Mtn 115 kV |  | VA | Buckingham | Active | Dominion | 100 | 0 | 36.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-449 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 100 | 0 | 36.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-450 | DeSoto-Keystone 345 kV |  | IN | Blackford | Active | AEP | 100 | 0 | 48.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-451 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 38.5 | 0 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-452 | Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 130 | 0 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-453 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 0 | 28.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-454 | Mazon-Oglesby 138kV (CIR Increase) |  | IL | Grundy | Active | ComEd | 116 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-455 | W4-005 345kV (CIR Increase) |  | PA | Union | Active | ComEd | 306 | 0 | 162.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AI2-456 | Birchwood - Fines Corner 230 kV |  | VA | King George | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 9/15/2027 |  |  | N | No
AI2-457 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 1122 | 1122 | 1122 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 10/1/2027 |  |  | N | No
AI2-458 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-459 | Bernville 34.5 kV 2 |  | PA | Berks | Active | ME | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-460 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-461 | Wilton Center - Loretto 345 kV(CIR Increase) |  | IL | Kankakee | Active | ComEd | 850 | 0 | 173 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-462 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 150 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-463 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-464 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-465 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-466 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-467 | Maysville 138 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-468 | Summit Road 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-469 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-470 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-471 | Montour 230 kV |  | PA | Montour | Active | PPL | 101.6 | 0 | 29.464 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-472 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 0 | 14.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-473 | Montour 230 kV |  | PA | Montour | Active | PPL | 100 | 0 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-474 | Montour 230 kV |  | PA | Montour | Active | PPL | 120 | 0 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-475 | Montour 230 kV |  | PA | Montour | Active | PPL | 140 | 0 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-476 | Snake Spring 115 kV |  | PA | Bedford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-477 | Snake Spring 115 kV II |  | PA | Bedford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-478 | Snake Spring 115 kV III |  | PA | Bedford | Withdrawn | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  | 10/24/2023 |  | 5/1/2027 |  |  | N | No
AI2-479 | Snake Spring 115 kV |  | PA | Bedford | Withdrawn | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  | 10/24/2023 |  | 5/1/2027 |  |  | N | No
AI2-480 | Crawford 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-481 | Union City - French Road 12.5kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-482 | Copperstone-North Lebanon 230 kV IV |  | PA | Lebanon | Withdrawn | ME | 100 | 0 | 58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2023 | N/A | N/A |  | 7/1/2025 |  | 12/1/2023 |  |  | N | No
AI2-483 | Heath 69 kV |  | OH | Licking | Active | AEP | 22.4 | 0 | 13.44 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2023 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI2-484 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-485 | Bruin Junction - Petrol Junction 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AI2-486 | Bethelboro - Connellsville 25 kV |  | PA | Fayette | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AI2-487 | Kewanee-Hennepin Tap 138kV |  | IL | Bureau | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-488 | Electric Junction - Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-489 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-490 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 0 | 31.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AI2-491 | East Lima-Marysville 345kV |  | OH | Champaign | Active | AEP | 250 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-492 | Deer Creek-Fisher Body-Mullin 138kV |  | IN | Grant | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/26/2012 |  |  | N | No
AI2-493 | New Baltimore 115kV (Stony Creek) |  | PA | Somerset | Active | PENELEC | 52.5 | 0 | 18.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AI2-494 5271400 | PJM-TVA |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/24/2023 | 6/1/2025 | 6/1/2026 |  | 6/19/2024 |  |  |  |  | PP | No
AJ1-001 | Boydton DP 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-002 | North River Delivery Point 115 kV |  | VA | Rockingham | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-003 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-004 5279789 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/1/2023 | 6/1/2025 | 6/1/2026 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-005 5279793 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/1/2023 | 6/1/2025 | 6/1/2026 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-006 5279794 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/2/2023 | 6/1/2025 | 6/1/2026 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-007 5279795 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/2/2023 | 6/1/2025 | 6/1/2026 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-008 | Zimmer 345 kV |  | OH | Clermont | Active | DEOK | 800 | 800 | 692.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AJ1-009 |  |  | NJ | Essex | Active | PSEG | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AJ1-010 | Racine - Sarah Lane 69 kV |  | WV | Mason | Active | AEP | 35 | 35 | 7.098 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/22/2023 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AJ1-011 | Waukegan Unit 7 CIR Transfer |  | IL | Lake | Active | ComEd | 328 | 328 | 328 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-012 | Waukegan Unit 8 CIR Transfer |  | IL | Lake | Active | ComEd | 354.4 | 354.4 | 354.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-013 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-014 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 260 | 260 | 260 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-015 | Larrabee Collector 230 kV |  | NJ | Monmouth | Active | JCPL | 1342 | 1342 | 403 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/2/2023 | N/A | N/A |  |  |  | 5/1/2030 |  |  | N | No
AJ1-016 | Cambria Slope 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/7/2023 | N/A | N/A |  |  |  | 11/9/2028 |  |  | N | No
AJ1-018 | Bishopville – Worcester 138 kV |  | MD | Worcester | Active | DPL | 39 | 39 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2023 | N/A | N/A |  |  |  | 12/29/2028 |  |  | N | No
AJ1-019 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-020 | St. Johns – Woodpecker 115 kV |  | VA | Caroline | Active | Dominion | 86.38 | 86.38 | 51.828 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/15/2029 |  |  | N | No
AJ1-021 | Woodpecker – Slabtown 115 kV |  | VA | Caroline | Active | Dominion | 16.2 | 16.2 | 10.0584 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/15/2029 |  |  | N | No
AJ1-022 | Kerr Dam - Henderson NC 115 kV |  | VA | Mecklenburg | Active | Dominion | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 6/30/2027 |  |  | N | No
AJ1-023 | Trumbull 345 kV |  | OH | Trumbull | Active | ATSI | 1010 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AJ1-024 5294080 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2024 | 6/1/2025 |  | 11/6/2023 |  |  |  |  | PP | No
AJ1-025 5294081 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2024 | 6/1/2025 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-026 5294082 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2024 | 6/1/2025 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-027 5294084 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2026 | 6/1/2027 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-028 5294085 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2026 | 6/1/2027 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-029 5294090 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2026 | 6/1/2027 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-030 5294092 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2026 | 6/1/2027 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-031 5294093 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2027 | 6/1/2028 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-032 5294095 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2027 | 6/1/2028 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-033 5294096 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2027 | 6/1/2028 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-034 5294097 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2027 | 6/1/2028 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-035 5294098 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2024 | 6/1/2025 |  | 5/15/2024 |  |  |  |  | PP | No
AJ1-037 | Northeast - CP Crane 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 500 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/8/2023 | N/A | N/A |  | 5/7/2025 |  | 10/1/2028 |  |  | N | No
AJ1-038 | Penniman 34.5 kV |  | VA | York | Active | Dominion | 33 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2023 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
1003606 | FE-PJM |  | N/A | N/A | Withdrawn |  | 208 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/11/2008 | 11/1/2008 | 6/1/2009 | [6 empty] | FF | No
1041672 | PJM-TVA |  | N/A | N/A | Confirmed |  | 106 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
1041677 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
1041678 | PJM-TVA |  | N/A | N/A | Confirmed |  | 52 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2011 | [6 empty] | FF | No
1070958 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/6/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1070959 | PJM-FE |  | N/A | N/A | Confirmed |  | 42 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/6/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1070962 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/6/2009 | 7/1/2009 | 7/1/2014 | [6 empty] | FF | No
1070966 | PJM-FE |  | N/A | N/A | Confirmed |  | 142 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/6/2009 | 7/1/2009 | 7/1/2014 | [6 empty] | FF | No
1070967 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/6/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1091513 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 68 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/29/2009 | 2/1/2009 | 3/13/2026 | [6 empty] | FF | No
1091532 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 11 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/29/2009 | 2/1/2009 | 3/13/2026 | [6 empty] | FF | No
1091549 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 203 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/29/2009 | 5/1/2009 | 3/13/2026 | [6 empty] | FF | No
1115220 | PJM-AMIL |  | N/A | N/A | Confirmed |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/3/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1119633 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 142 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/10/2009 | 5/1/2009 | 5/1/2014 | [6 empty] | FF | No
1119653 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 118 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/10/2009 | 5/1/2009 | 5/1/2014 | [6 empty] | FF | No
1121578 | PJM-WEC |  | N/A | N/A | Confirmed |  | 10 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/12/2009 | 6/1/2009 | 6/1/2017 | [6 empty] | FF | No
1129395 | PJM-MECS |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2011 | [6 empty] | FF | No
1132597 | PJM-MECS |  | N/A | N/A | Confirmed |  | 25 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2010 | [6 empty] | FF | No
1132611 | PJM-FE |  | N/A | N/A | Confirmed |  | 38 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2012 | [6 empty] | FF | No
1134215 | FE-PJM |  | N/A | N/A | Annulled |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134216 | FE-PJM |  | N/A | N/A | Annulled |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134217 | FE-PJM |  | N/A | N/A | Annulled |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134219 | FE-PJM |  | N/A | N/A | Annulled |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1180629 | DUK-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/16/2009 | 10/1/2009 | 10/1/2014 | [6 empty] | FF | No
1251680 | PJM-TVA |  | N/A | N/A | Confirmed |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252025 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
1252026 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
1252090 | PJM-ALTW |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252092 | PJM-ALTW |  | N/A | N/A | Confirmed |  | 65 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252093 | PJM-ALTW |  | N/A | N/A | Confirmed |  | 149 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252097 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252098 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252099 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
4183678 | DUK-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/19/2012 | 10/1/2013 | 10/1/2018 | [6 empty] | FF | No
4244941 | PJM-TVA |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
500310 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 10/1/2006 | 4/1/2007 | [6 empty] | FF | No
500311 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 10/1/2006 | 1/1/2007 | [6 empty] | FF | No
501061 | PJM-NYIS |  | N/A | N/A | Withdrawn |  | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/501061_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/31/2006 | 6/1/2009 | 6/1/2019 | [6 empty] | FF | No
502025 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
502029 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
506017 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2007 | 2/1/2007 | [6 empty] | FF | No
507525 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
510924 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
510926 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
510942 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/510942_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/16/2006 | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510945 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510946 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510947 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510948 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520594 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520595 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520948 | PJM-NYIS |  | N/A | N/A | Confirmed |  | 26 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/520948_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
520949 | PJM-NYIS |  | N/A | N/A | Confirmed |  | 26 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2012 | [6 empty] | FF | No
520950 | PJM-NYIS |  | N/A | N/A | Confirmed |  | 26 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2012 | [6 empty] | FF | No
527594 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
527597 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
528018 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528020 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528021 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528022 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528023 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528024 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528028 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 2/1/2007 | 6/1/2007 | [6 empty] | FF | No
529891 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/529891_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/8/2007 | 7/1/2009 | 7/1/2010 | [6 empty] | FF | No
530761 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
530778 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
530783 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
531601 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 253 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/531601_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/531601_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/6/2007 | 10/1/2008 | 10/1/2013 | [6 empty] | FF | No
531604 | OVEC_PJM |  | N/A | N/A | Confirmed |  | 210 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/531604_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/531604_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
531616 | FE-PJM |  | N/A | N/A | Withdrawn |  | 2510 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
531617 | FE-PJM |  | N/A | N/A | Withdrawn |  | 1940 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
532696 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/532696_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/532696_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2007 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
533213 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
533260 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
539601 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/539601_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/20/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
539610 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
547020 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
547022 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
549214 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 12/1/2007 | [6 empty] | FF | No
549854 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 12/1/2007 | [6 empty] | FF | No
554476 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
554497 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
554504 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
554507 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
554509 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
554950 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 63 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/554950_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2007 | 6/1/2008 | 6/1/2010 | [6 empty] | FF | No
555079 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555085 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555092 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555096 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
560490 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
560494 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
564527 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
564533 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
564538 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
564539 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
564543 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
564544 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
564878 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564884 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564895 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564938 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564940 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
565380 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/31/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
568552 | PJM.AP-PJM.DPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568554 | PJM.AP-PJM.PSEG |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568555 | PJM.AP-PJM.PSEG |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568556 | PJM.AP-PJM.PPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568557 | PJM.AP-PJM.PPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
708103 | PJM-CPLE |  | N/A | N/A | Confirmed |  | 89 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/15/2007 | 11/1/2007 | 11/1/2008 | [6 empty] | FF | No
811046 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811048 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811061 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811067 | PJM_MECS |  | N/A | N/A | Confirmed |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811071 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811073 | PJM_MECS |  | N/A | N/A | Confirmed |  | 27 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811074 | PJM_MECS |  | N/A | N/A | Confirmed |  | 27 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811075 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811080 | PJM_MECS |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 2/1/2008 | 6/1/2009 | [6 empty] | FF | No
811082 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811086 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811089 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811092 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811095 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811097 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811101 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811105 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 4/1/2008 | 6/1/2009 | [6 empty] | FF | No
816850 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 15 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/4/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
818965 | PJM-TVA |  | N/A | N/A | Confirmed |  | 180 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/10/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
818967 | PJM-TVA |  | N/A | N/A | Confirmed |  | 138 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/10/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
818976 | PJM-TVA |  | N/A | N/A | Confirmed |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/10/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
825955 | PJM-AMIL |  | N/A | N/A | Confirmed |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/30/2007 | 4/1/2008 | 6/1/2009 | [6 empty] | FF | No
847949 | PJM-MEC |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/27/2007 | 6/1/2008 | 6/1/2010 | [6 empty] | FF | No
863796 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 | [6 empty] | FF | No
863799 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 | [6 empty] | FF | No
866859 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 468 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
869320 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2008 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
869642 | PJM-FE |  | N/A | N/A | Confirmed |  | 42 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2008 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
869659 | PJM-FE |  | N/A | N/A | Confirmed |  | 142 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 7/1/2008 | 7/1/2009 | [6 empty] | FF | No
869681 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
869803 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2008 | 7/1/2008 | 7/1/2009 | [6 empty] | FF | No
893173 | OVEC-PJM-FE |  | N/A | N/A | Confirmed |  | 462 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/31/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893692 | FE-PJM |  | N/A | N/A | Confirmed |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893694 | FE-PJM |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893702 | FE-PJM |  | N/A | N/A | Confirmed |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893704 | FE-PJM |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
894765 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/3/2008 | 7/1/2008 | 7/1/2010 | [6 empty] | FF | No
894769 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/3/2008 | 7/1/2008 | 7/1/2010 | [6 empty] | FF | No
894770 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/3/2008 | 12/1/2008 | 12/1/2010 | [6 empty] | FF | No
894774 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/3/2008 | 12/1/2008 | 12/1/2010 | [6 empty] | FF | No
903384 | PJM-WEC |  | N/A | N/A | Confirmed |  | 320 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/25/2008 | 5/15/2010 | 5/31/2011 | [6 empty] | FF | No
988887 | PJM-CIN |  | N/A | N/A | Confirmed |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/10/2008 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
994856 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 138 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
994857 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
994858 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No

## Definitions-Mapping
Column Names from Data Tab
Project ID | Project/OASIS ID
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection request process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Generation Interconnection Agreement | After the project’s required study work is completed, PJM will tender a Generation Interconnection Agreement (“GIA”) to be executed by the Project Developer, the Transmission Owner, and PJM.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Submitted Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Project
Sliding Project