## Data
Project ID | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim/Interconnection Service/Generation Interconnection Agreement | Interim/Interconnection Service/Generation Interconnection Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Submitted Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Commercial Operation Milestone | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Project | Sliding Project
A01 | South Lebanon 230 KV | Ironwood | PA | Lebanon | In Service | ME | 720 | 720 | 673 | 673 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a01_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 4/1/2002 | 4/1/2002 | 4/1/2002 | N | No
A02 | Oak Hall 138 kV (Oil CT) | Chesapeake | VA | Unknown | In Service | DPL | 315 | 315 | 315 | 311.8 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 8/22/2001 |  | 8/22/2001 | N | No
A03 | Linden 230 kV or 138 kV | Linden 5 & 6 | NJ | Union | In Service | PSEG | 120 | 120 | 120 | 114 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 6/1/2000 |  | 6/1/2000 | N | No
A04 | Linden 230 kV or 138 kV | Linden 1, 2 & 3 | NJ | Union | In Service | PPL | 1186 | 750 | 750 | 750 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a04_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a04_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/10/2004 | 4/1/1997 | N/A | N/A | 3/11/2005 |  |  | 5/1/2006 |  | 5/1/2006 | N | No
A05 | Bergen | Bergen | NJ | Bergen | In Service | PSEG | 500 | 500 | 500 | 500 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a05_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a05_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
A06 | Kearny |  | NJ | Gloucester | Withdrawn | PSEG | 800 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a06_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/1997 | N/A | N/A |  | 8/28/2000 |  |  |  |  | N | No
A07 | Dickerson 120 MW |  | MD | Montgomery | Withdrawn | PEPCO | 120 | 25 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a07_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a07_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/1/1997 | N/A | N/A |  | 7/22/2002 | Customer Initiated Withdrawal |  |  |  | N | No
A08 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 1140 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a08_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/1/1997 | N/A | N/A |  |  |  | 7/1/2002 |  | 7/1/2002 | N | No
A09 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 1140 | 35 | 35 | 35 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/1/1997 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
A10 | Glory 115 kV | Colver Power | PA | Cambria | In Service | PENELEC | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a10_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 6/2/1997 | N/A | N/A |  |  |  | 1/8/2000 |  | 1/8/2000 | N | No
A11 | Harwood 230 kV | Hazelton | PA | Luzerne | In Service | PPL | 356 | 201 | 201 | 31.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/1997 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
A12 | Martins Creek 230 kV | Lower Mt Bethel | PA | Northampton | In Service | PPL | 600 | 600 | 600 | 582 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/13/2003 | 8/20/1997 | N/A | N/A | 12/15/2003 |  |  | 5/14/2004 |  | 5/14/2004 | N | No
A13 | Mickleton 230 kV | Mantua Creek Generating Station | NJ | Gloucester | Withdrawn | AEC | 803 | 803 | 803 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a13_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/26/1997 | N/A | N/A |  |  |  | 6/1/2004 |  |  | N | No
A14 | Sewaren |  | NJ | Middlesex | Withdrawn | PSEG | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a14_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1998 | N/A | N/A |  | 6/18/2002 |  |  |  |  | N | No
A15 | Sayreville 230 kV | Red Oak CC1, CT1 - CT4 | NJ | Middlesex | In Service | JCPL | 765 | 765 | 765 | 765 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a15_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a15_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/1998 | N/A | N/A |  |  |  | 2/1/2002 |  | 2/1/2002 | N | No
A16 | Eagle Point 230 kV |  | NJ | Gloucester | Withdrawn | PECO | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a16_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/1998 | N/A | N/A |  | 4/19/2000 |  |  |  |  | N | No
A17 | Linden 230 kV |  | NJ | Union | Withdrawn | PSEG | 1100 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a17_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a17_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/8/1998 | N/A | N/A |  | 10/10/2003 |  | 5/1/2006 |  |  | N | No
A18 | North Temple 230 kV |  | PA | Berks | In Service | ME | 557 | 557 | 557 | 557 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a18_imp2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/a18_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/11/1998 | N/A | N/A |  |  |  | 12/1/2002 | 12/1/2002 | 12/1/2002 | N | No
A19 | Eddystone 230 kV | Liberty (Eddy) | PA | Delaware | In Service | PECO | 521 | 521 | 521 | 521 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a19_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a19_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/15/1998 | N/A | N/A |  |  |  | 1/1/2002 |  | 1/1/2002 | N | No
A20 | Juniata 500 kV |  | PA | Dauphin | Withdrawn | PPL | 485 | 12 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a20_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/9/1998 | N/A | N/A |  | 7/18/1999 | Customer Milestone Not Met |  |  |  | N | No
A21 | Chichester 230 kV | Phillips Island | PA | Philadelphia | In Service | PECO | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a21_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a21_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a21_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/a21_csa.pdf | Document Posted | N/A | N/A | 6/2/2003 | 8/17/1998 | N/A | N/A | 6/4/2004 |  |  | 12/31/2004 |  | 12/31/2004 | N | No
A22 | Hudson 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/1998 | N/A | N/A |  | 8/28/2000 |  |  |  |  | N | No
A23 | New Castle 138 kV |  | DE | New Castle | Withdrawn | DPL | 257 | 257 | 257 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/1998 | N/A | N/A |  | 7/23/1999 |  |  |  |  | N | No
A24 | South River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 725 | 725 | 725 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/1998 | N/A | N/A |  | 6/26/1999 |  |  |  |  | N | No
A25 | Hosensack 500 kV |  | PA | Northampton | Withdrawn | PPL | 1000 | 1000 | 1000 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a25_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a25_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/30/1998 | N/A | N/A |  | 1/24/2002 |  |  |  |  | N | No
A26 | Linden | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 180 |  | 157.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a26_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a26_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/1998 | N/A | N/A |  |  |  | 1/25/2002 |  | 1/25/2002 | N | No
A27 | Passyunk 230 kV |  | PA | Philadelphia | Withdrawn | PECO | 615 | 615 | 515 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a27_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a27_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/4/1998 | N/A | N/A |  | 4/30/2002 |  |  |  |  | N | No
A28 | Dover | Kent | DE | Kent | In Service | DPL | 100 | 100 | 98 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/4/1998 | N/A | N/A |  |  |  | 6/14/2001 |  | 6/14/2001 | N | No
A29 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | 465 | 465 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a29_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a29_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a29_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/18/1998 | N/A | N/A |  |  |  | 6/13/2003 |  | 6/13/2003 | N | No
A30 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | 465 | 465 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a30_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a30_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/2/2002 | 12/3/1998 | N/A | N/A |  |  |  | 12/1/2005 |  | 12/1/2005 | N | No
A31 | Peckville/Varden 69 kV | Archbald | PA | Lackawanna | In Service | PPL | 46 | 44 | 44 | 43.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a31_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a31_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a31_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/22/1998 | N/A | N/A |  |  |  | 10/27/2001 |  | 10/27/2001 | N | No
A32 | Montour #1 | Montour #1 | PA | Montour | In Service | PPL | 759 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 6/19/2001 |  | 6/19/2001 | N | No
A33 | Montour #2 | Montour #2 | PA | Montour | In Service | PPL | 14 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a33_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a33_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 11/1/2000 |  | 11/1/2000 | N | No
A34 | Brunner 230 kV |  | PA | York | In Service | PPL | 749 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a34_imp2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a34_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 4/27/2002 |  | 4/27/2002 | N | No
A35 | North Bangor 34.5 kV | Grand Central Sanitary LF | PA | Northampton | In Service | ME | 10 | 10 | 10 | 8.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a35_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a35_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a35_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/13/1999 | N/A | N/A |  |  |  | 4/18/2001 |  | 4/18/2001 | N | No
A36 | Hunterstown 500 kV | Hunterstown | PA | Adams | In Service | ME | 830 | 830 | 830 | 830 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a36_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/1999 | N/A | N/A | 4/23/2003 |  |  | 7/31/2003 | 7/31/2003 | 7/31/2003 | N | No
A37 | Sayreville 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 749 | 749 | 749 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 9/8/1999 |  |  |  |  | N | No
A38 | Erie West 345 kV |  | PA | Crawford | Withdrawn | PENELEC | 765 | 765 | 765 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a38_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/6/2001 |  |  |  |  | N | No
A39 | Pequest River 115 kV |  | NJ | Warren | Withdrawn | JCPL | 73 | 73 | 73 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a39_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/6/2001 |  |  |  |  | N | No
A40 | TMI 500 kV |  | PA | Dauphin | Withdrawn | ME | 1271 | 1271 | 1271 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a40_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 10/12/1999 |  |  |  |  | N | No
A41 | TMI 500 kV |  | PA | Dauphin | Withdrawn | ME | 765 | 765 | 765 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a41_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A | [6 empty] | N | No
A42 | Atlantic 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 449 | 449 | 449 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a42_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/6/2001 |  |  |  |  | N | No
A43 | Portland 230 kV |  | PA | Northampton | Withdrawn | ME | 472 | 472 | 472 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a43_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 7/20/2003 |  |  |  |  | N | No
A44 | Shelocta 230 kV |  | PA | Indiana | Withdrawn | PENELEC | 402 | 402 | 402 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a44_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 10/22/1999 |  |  |  |  | N | No
A45 | Oyster Creek 230 kV |  | NJ | Ocean | Withdrawn | JCPL | 752 | 752 | 752 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a45_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 12/6/1999 |  |  |  |  | N | No
A46 | Gilbert 115 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a46_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/30/1999 |  |  |  |  | N | No
A47 | Perryman 230kV or 115kV |  | MD | Harford | Withdrawn | BGE | 740 | 740 | 740 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/1999 | N/A | N/A |  | 8/30/1999 |  |  |  |  | N | No
A48 | East Towanda 230kV |  | NJ | Union | Withdrawn | PENELEC | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a48_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 10/3/2001 |  |  |  |  | N | No
A49 | West Hempfield 230kV |  | NJ | Bergen | Withdrawn | PPL | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a49_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 9/10/1999 |  |  |  |  | N | No
A50 | Bayonne |  | NJ | Hudson | Withdrawn | PSEG | 60 | 60 |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a50_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  |  | Customer Initiated Withdrawal | 12/1/2005 |  |  | N | No
A51 | Camden |  | NJ | Camden | Withdrawn | PSEG | 258 | 258 | 258 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a51_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 11/26/2001 |  |  |  |  | N | No
A52 | Linden |  | NJ | Union | Withdrawn | PSEG | 180 | 180 |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a52_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 3/17/2004 |  | 6/1/2005 | 6/1/2005 |  | N | No
A53 | Titusville |  | PA | Crawford | Withdrawn | PENELEC | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a53_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a53_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 1/15/2002 |  |  |  |  | N | No
A54 | TMI 230 kV |  | PA | Dauphin | Withdrawn | ME | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a54_imp2.pdf | Interim Study |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/9/1999 | N/A | N/A |  |  | Customer Milestone Not Met | 6/1/2002 |  |  | N | No
A55 | Lakewood 230kV | Lakewood NUG | NJ | Ocean | In Service | JCPL | 500 | 500 | 500 | 301 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a55_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a55_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 1/7/2003 | 2/22/1999 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | N | No
A56 | Pedricktown 230kV |  | NJ | Salem | Withdrawn | AEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a56_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/1999 | N/A | N/A |  | 8/17/1999 |  |  |  |  | N | No
A57 | Edgemoor | Unit 1 | PA | Dauphin | Withdrawn | AEC | 500 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a57_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a57_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/1999 | N/A | N/A |  | 7/27/2000 |  | 10/31/2001 |  |  | N | No
A58 | Hawkins Gate / Oak Grove 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a58_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/1999 | N/A | N/A |  | 8/28/1999 |  |  |  |  | N | No
A59 | Emilie | Ford Mill | PA | Bucks | In Service | PECO | 1145 | 540 | 540 | 540 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a59_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a59_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a59_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/1/2003 | 4/1/1999 | N/A | N/A | 1/21/2004 |  |  | 5/27/2004 |  | 5/27/2004 | N | No
A59_W00 | Springdale 138 kV | Springdale 1 & 2 | PA | Allegheny | In Service | APS | 96 | 96 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a59_w00_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a59_w00_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 12/1/2000 |  | 12/1/2000 | N | No
A60 | Hunterstown 500 kV |  | PA | Adams | Withdrawn | ME | 679 | 679 | 679 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a60_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/8/1999 | N/A | N/A | [6 empty] | N | No
A61 | Hawkins Gate / Oak Grove 230kV |  | DE | New Castle | Withdrawn | PEPCO | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a61_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/1999 | N/A | N/A | [6 empty] | N | No
B01 | Dickerson |  | MD | Montgomery | Withdrawn | PEPCO | 398 | 398 | 398 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b01_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/29/1999 | N/A | N/A |  | 7/22/2002 |  |  |  |  | N | No
B02 | Morgantown | Morgantown Units 1 & 2 | MD | Charles | In Service | PEPCO | 80 | 80 | 80 | 80 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
B03 | Hosensack 500kV | Bethlehem | PA | Northampton | In Service | PPL | 750 | 750 | 750 | 788 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b03_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 1/28/2003 |  | 1/28/2003 | N | No
B04 | Oyster Creek |  | NJ | Ocean | Withdrawn | JCPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/1999 | N/A | N/A | [6 empty] | N | No
B05 | Wayne-Homer City 345kV |  | PA | Indiana | In Service | PENELEC | 265 | 265 | 250 | 265 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b05_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 1/1/2002 |  | 1/1/2002 | N | No
B06 | Wayne-Homer City 345kV |  | PA | Indiana | Withdrawn | PENELEC | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/1999 | N/A | N/A | [6 empty] | N | No
B07 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b07_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/1999 | N/A | N/A | [6 empty] | N | No
B08 | Friedensburg 69kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b08_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/1999 | N/A | N/A | [6 empty] | N | No
B09A | Burlington 138kV | Burlington | NJ | Burlington | In Service | PSEG | 168 | 168 | 168 | 168 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b09a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b09a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b09a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b09a_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/10/1999 | N/A | N/A |  |  |  | 7/22/2000 |  | 7/22/2000 | N | No
B09b | Burlington 138kV |  | NJ | Burlington | Withdrawn | PSEG | 336 | 336 | 336 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b09b_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b09b_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/1999 | N/A | N/A | [6 empty] | N | No
B10 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b10_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/1999 | N/A | N/A | [6 empty] | N | No
B12 | Limerick 230kV |  | PA | Montgomery | Withdrawn | PECO | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b12_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/14/1999 | N/A | N/A |  | 6/13/2002 |  |  |  |  | N | No
B12_W01 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b12_w01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b12_w01_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 3/1/2002 |  | 3/1/2002 | N | No
B12_W02 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 300 | 300 | 300 | 300 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b12_w01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b12_w02_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 10/1/2002 |  | 10/1/2002 | N | No
B13 | Lakewood 230kV |  | NJ | Ocean | Withdrawn | JCPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/1999 | N/A | N/A | [6 empty] | N | No
B14 | Arnold 115kV | Arnold (Green Mountain) WF | PA | Somerset | Deactivated | PENELEC | 10.4 | 10.4 | 2.08 | 10.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b14_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/6/1999 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
B15 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b15_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b15_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b15_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/12/1999 | N/A | N/A |  | 10/2/2002 |  | 6/1/2003 |  |  | N | No
B16 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b16_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b16_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b16_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/12/1999 | N/A | N/A |  | 10/2/2002 |  | 6/1/2004 |  |  | N | No
B17 | Jerseyville 34.5kV | Statoil | NJ | Monmouth | Withdrawn | JCPL | 2.1 | 2.1 |  | 0 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/17/1999 | N/A | N/A |  | 1/26/2021 |  | 1/1/1999 |  |  | N | No
B18 | Limerick-Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/1999 | N/A | N/A | [6 empty] | N | No
B18_W03 | Springdale 138 kV | Springdale CT3, CT4, ST5 | PA | Allegheny | In Service | APS | 525 | 525 | 525 | 509 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b18_w03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b18_w03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 8/1/2003 |  | 8/1/2003 | N | No
B19 | Melrose 34.5kV | Middlesex Sewer | NJ | Middlesex | In Service | JCPL | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/1999 | N/A | N/A |  |  |  | 4/6/2001 |  | 4/6/2001 | N | No
B20 | Elm St. 115kV |  | PA | Warren | Withdrawn | PENELEC | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b20_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/1999 | N/A | N/A |  | 10/23/2000 |  |  |  |  | N | No
B21 | South Reading 500kV |  | PA | Berks | Withdrawn | ME | 925 | 925 | 925 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/1999 | N/A | N/A |  | 9/15/2000 |  |  |  |  | N | No
B22 | Gould St. 34.5 kV |  | MD | Baltimore City | Withdrawn | BGE | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/11/1999 | N/A | N/A | [6 empty] | N | No
B23 | Siegfried/Allentown 138kV | Northampton | PA | Northampton | In Service | PPL | 115 | 5 | 5 | 2 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/21/1999 | N/A | N/A |  |  |  | 6/10/2001 |  | 6/10/2001 | N | No
B23_W04 | Gans 138 kV | Gans 8 & 9 | PA | Fayette | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b23_w04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b23_w04_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/1999 | N/A | N/A |  |  |  | 12/1/2001 |  | 12/1/2001 | N | No
B24 | Oak Grove 13.8kV |  | MD | Prince George's | Withdrawn | PEPCO | 6.8 | 6.8 | 6.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/1999 | N/A | N/A | [6 empty] | N | No
B25 | Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 870 | 870 | 870 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b25_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b25_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/20/1999 | N/A | N/A |  | 5/3/2002 |  |  |  |  | N | No
B26 | Hunlock Creek 66kV | Hunlock Creek 66kV | PA | Luzerne | In Service | UGI | 50 | 50 | 50 | 44.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b26_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/1999 | N/A | N/A |  |  |  | 5/26/2002 |  | 5/26/2002 | N | No
B27 | Portland 230kV |  | PA | Northampton | Withdrawn | ME | 920.5 | 362 | 362 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/1999 | N/A | N/A |  | 11/6/2000 |  |  |  |  | N | No
B28 | Muddy Run 230kV | Muddy Run | PA | York | In Service | PECO | 160 | 160 | 160 | 160 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 8/27/2003 |  | 8/27/2003 | N | No
B28_W07 | Backbone Mountain 138 kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 90 | 18 | 66 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b28_w07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b28_w07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b28_w07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
B28_W08 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 | 15 |  | 15 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b28_w08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b28_w08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b28_w08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
B29 | Perryman 230kV/115kV |  | MD | Harford | Withdrawn | BGE | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b29_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/1999 | N/A | N/A |  | 4/17/2001 |  |  |  |  | N | No
B30 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 605 | 605 | 605 | 528 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b30_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b30_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/26/2003 | 11/22/1999 | N/A | N/A | 4/1/2004 |  |  | 6/29/2004 |  | 6/29/2004 | N | No
B31 | Brunner-West Hempfield 230kV |  | PA | Lancaster | Withdrawn | PPL | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b31_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/1999 | N/A | N/A |  | 10/9/2000 |  |  |  |  | N | No
B32 | TMI 230kV |  | PA | Dauphin | Withdrawn | ME | 650 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b32_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/23/1999 | N/A | N/A |  | 12/5/2000 |  |  |  |  | N | No
B33 | Steelton 230kV |  | PA | Dauphin | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b33_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/23/1999 | N/A | N/A |  | 12/3/2002 |  | 5/1/2005 |  |  | N | No
B34 | Seward 230kV | Seward 1 (Hay Road 5,6,7,8) | PA | Westmoreland | In Service | PENELEC | 525 | 525 | 304 | 325 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b34_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b34_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/1/2003 | 11/23/1999 | N/A | N/A | 3/10/2004 |  |  | 6/9/2006 |  | 6/9/2006 | N | No
B35 | South Akron 230kV | West Earl | PA | Lancaster | Withdrawn | PPL | 313 | 313 | 313 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b35_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b35_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b35_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 3/10/2003 |  |  |  |  | N | No
B36 | South Akron 230kV | West Earl | PA | Lancaster | Withdrawn | PPL | 78 | 78 | 78 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b36imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b35_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b36_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 3/10/2003 |  | 6/30/2004 |  |  | N | No
B37 | East Greenville 69kV |  | PA | Montgomery | Withdrawn | PPL | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b37_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 4/9/2002 |  |  |  |  | N | No
B38 | Elroy 138kV |  | PA | Montgomery | Withdrawn | PPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b38_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b38_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B39 | Quarryville 69kV |  | PA | Lancaster | Withdrawn | PPL | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B40 | West Hempfield 69kV |  | PA | Lancaster | Withdrawn | PPL | 100 | 100 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b40_fea.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b40_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B41 | West Hempfield 138kV |  | PA | Lancaster | Withdrawn | PPL | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b41_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b41_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B42 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b42_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A |  | 11/8/2000 |  |  |  |  | N | No
B43 | Homer City-Wayne 345kV |  | PA | Venango | Withdrawn | PENELEC | 284 | 284 | 284 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b43_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A |  | 11/8/2000 |  |  |  |  | N | No
B44 | Elko-Forrest 230kV |  | PA | Elk | Withdrawn | PENELEC | 240 | 240 | 240 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b44_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A | [6 empty] | N | No
B45 | Lackawanna 230kV |  | PA | Lackawanna | Withdrawn | PPL | 555 | 555 | 555 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b45_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A |  | 7/23/2002 |  | 6/1/2004 |  |  | N | No
B46 | Conowingo 230kV | Conowingo | MD | Harford | In Service | PECO | 548 | 36 | 36 | 36 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b46_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/1999 | N/A | N/A |  |  |  | 11/21/2003 |  | 11/21/2003 | N | No
B47 | Red Lion 500kV | Hay Road 5, 6, 7 | DE | New Castle | In Service | DPL | 545 |  | 545 | 545 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b47_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b47_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b47_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/1999 | N/A | N/A |  |  |  | 7/22/2002 |  | 7/22/2002 | N | No
B48 | Graceton 230kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b48_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b48_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 10/17/2003 |  | 6/1/2005 |  |  | N | No
B49 | Erie South-Warren 230kV |  | PA | Warren | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b49_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 7/31/2001 |  |  |  |  | N | No
B50 | Morgantown 69kV |  | PA | Erie | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b50_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A | [6 empty] | N | No
B51 | Wayne 345 |  | PA | Indiana | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b51_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 11/19/2001 |  |  |  |  | N | No
B52 | Woodbridge 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b52_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 12/5/2000 |  |  |  |  | N | No
C01 | Linden 138kV | Linden 1, 2 & 3 | NJ | Union | In Service | PSEG | 1186 | 436 | 436 | 436 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c01_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/10/2004 | 12/17/1999 | N/A | N/A | 4/22/2005 |  |  | 5/1/2006 |  | 5/1/2006 | N | No
C02 | South Lebanon 230kV | Ironwood | PA | Lebanon | Withdrawn | ME | 720 | 47 | 47 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c02_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2000 | N/A | N/A |  |  |  | 1/1/2007 |  |  | N | No
C03 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c03_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/11/2000 | N/A | N/A |  | 9/16/2002 |  | 12/1/2003 |  |  | N | No
C04 | Burches Hill 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c04_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2000 | N/A | N/A |  | 1/25/2002 |  |  |  |  | N | No
C05 | Somerset 34.5kV |  | NJ | Somerset | Withdrawn | JCPL | 3.75 | 3.75 | 3.75 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c05_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2000 | N/A | N/A | [6 empty] | N | No
C06 | Susquehanna 230kV** |  | PA | Luzerne | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c06_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2000 | N/A | N/A |  | 7/6/2001 |  |  |  |  | N | No
C07 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 1119 | 26 | 26 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c07_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c07_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2000 | N/A | N/A |  |  |  | 7/19/2001 |  | 7/19/2001 | N | No
C08 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1100 | 69 | 69 | 18 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c08_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2000 | N/A | N/A |  |  |  | 8/1/2001 |  | 8/1/2001 | N | No
C09 | Fairlawn 26.4kV |  | NJ | Bergen | Withdrawn | PSEG | 37 | 37 | 37 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2000 | N/A | N/A |  | 1/25/2001 |  |  |  |  | N | No
C10 | Erie East 230kV | Northeast Cogen | PA | Erie | Withdrawn | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c10_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c10_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/8/2000 | N/A | N/A |  | 6/23/2005 | Customer Milestone Not Met | 6/1/2006 |  |  | N | No
C11 | Mifflintown 69kV |  | PA | Juniata | Withdrawn | PPL | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c11_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2000 | N/A | N/A |  | 7/6/2001 |  |  |  |  | N | No
C11_W11 | Hunker 138 kV |  | PA | Westmoreland | Withdrawn | APS | 88 | 88 | 88 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2000 | N/A | N/A | [6 empty] | N | No
C12 | Conastone - Peach Bottom 500kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c12_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/15/2000 | N/A | N/A |  | 6/22/2004 |  | 12/1/2004 |  |  | N | No
C13 | Conastone - Peach Bottom 500kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c13_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/15/2000 | N/A | N/A |  | 6/22/2004 |  | 12/1/2004 |  |  | N | No
C14 | Keystone - Conemaugh 550 |  | PA | Indiana | Withdrawn | PENELEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c14_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2000 | N/A | N/A |  | 3/1/2002 |  |  |  |  | N | No
C15 | Friedensburg 69kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c15_fea.pdf | Document Posted |  | Withdrawn |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/28/2000 | N/A | N/A |  |  |  | 12/1/2002 |  |  | N | No
C16 | Westover South 34.5kV |  | PA | Clearfield | Withdrawn | PENELEC | 13.5 | 13.15 | 13.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2000 | N/A | N/A | [6 empty] | N | No
C17 | Somerset 23kV |  | PA | Somerset | Withdrawn | PENELEC | 4.5 | 4.5 | 4.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2000 | N/A | N/A | [6 empty] | N | No
D01 | Engleside 69kV | Sight and Sound Theater | PA | Lancaster | In Service | PPL | 1.6 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/6/2000 | N/A | N/A |  |  |  | 5/31/2000 |  | 5/31/2000 | N | No
D02 | Edgemoor | Hay Road 1-4 | DE | New Castle | In Service | DPL | 521 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2000 | N/A | N/A |  |  |  | 4/12/2000 |  | 4/12/2000 | N | No
D03 | Harwood 69kV | Haxelton Units 2-4 | PA | Luzerne | In Service | PPL | 99 | 99 | 99 | 60.8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d03_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2000 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
D03_W15 | Horse Shoe Run 69 kV |  | WV | Preston | Withdrawn | APS | 10.6 | 12 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d03_w15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d03_w15_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2000 | N/A | N/A |  |  |  | 6/1/2003 |  |  | N | No
D04 | Peckville 69kV | Archbald | PA | Wayne | In Service | PPL | 20 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/26/2000 | N/A | N/A |  |  |  | 6/9/2000 |  | 6/9/2000 | N | No
D05 | East Carbondale 69kV | Waymart WF | PA | Wayne | In Service | PPL | 70 | 70 |  | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d05_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d05_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d05_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/d05_csa.pdf | Document Posted | N/A | N/A |  | 6/15/2000 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 | 12/1/2003 | N | No
D05_W17 | Friendsville 500 kV |  | MD | Garrett | Withdrawn | APS | 432 | 432 | 432 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d05_w17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d05_w17_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2000 | N/A | N/A |  | 9/20/2002 |  | 6/1/2004 |  |  | N | No
D06 | Eclipse 115kV | Scrubgrass NUG | PA | Unknown | In Service | PENELEC | 85 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/19/2000 | N/A | N/A |  |  |  | 7/15/2000 |  | 7/15/2000 | N | No
D07 | Blueball 69kV | Sunoil Gen Unit | PA | Delaware | Deactivated | PECO | 53 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2000 | N/A | N/A |  |  |  | 7/25/2000 |  | 7/25/2000 | N | No
D08 | Kearny 230kV | Kearny #12 | NJ | Hudson | In Service | PSEG | 168 | 168 | 168 | 168 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d08_fac2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/3/2000 | N/A | N/A |  |  |  | 8/4/2001 |  | 8/4/2001 | N | No
D08_W18 | Terra Alta 138 kV |  | WV | Preston | Withdrawn | APS | 88 | 88 | 88 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2000 | N/A | N/A | [6 empty] | N | No
D08_W19 | Bald Eagle 46 kV |  | PA | Centre | Withdrawn | APS | 88 | 88 | 88 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2000 | N/A | N/A | [6 empty] | N | No
D09 | 9th St (sub 117) 13kV | Central Heating & Refrigeriation Facility 1 & 2 | DC | N/A | In Service | PEPCO | 11 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d09_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/15/2003 | 7/24/2000 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
D10 | NIH 13kV | NIH Unit 1 | MD | Montgomery | In Service | PEPCO | 25 | 25 |  | 25 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d10_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d10_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/30/2003 | 7/26/2000 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
D11 | Clayton 138kV | DEMEC/Smyrna 1 &2 | DE | Kent | In Service | DPL | 100 | 100 | 100 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/26/2000 | N/A | N/A |  |  |  | 5/1/2002 |  | 5/1/2002 | N | No
D13 | Deep Run 34.5kV |  | NJ | Middlesex | Withdrawn | JCPL | 12 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2000 | N/A | N/A |  | 3/21/2002 |  |  |  |  | N | No
D14 | Red Lion 500kV |  | DE | New Castle | Withdrawn | DPL | 711 | 190 | 190 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 3/1/2002 |  |  |  |  | N | No
D15 | Red Lion 500kV |  | DE | New Castle | Withdrawn | DPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A | [6 empty] | N | No
D16 | Hummelstown 230kV |  | PA | Dauphin | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 1/15/2002 |  |  |  |  | N | No
D17 | Hummelstown 230kV |  | PA | Dauphin | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 1/15/2002 |  |  |  |  | N | No
D18 | Hosensack 230kV | Conectiv Bethlem CT 6, ST2 | PA | Northampton | In Service | PPL | 350 | 350 | 350 | 304 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d18_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/d18_csa.pdf | Document Posted | N/A | N/A | 5/31/2003 | 7/28/2000 | N/A | N/A |  |  |  | 5/1/2004 |  | 5/1/2004 | N | No
D19 | Brunner-West Hempfield 230kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d19_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 12/1/2004 |  |  | N | No
D20 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d20_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 5/1/2005 |  |  | N | No
D21 | Hunterstown-Conemaugh 500kV |  | PA | Cambria | Withdrawn | PENELEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d21_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 12/1/2005 |  |  | N | No
D22 | Hunterstown-Conemaugh 500kV |  | PA | Cambria | Withdrawn | PENELEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 12/1/2005 |  |  | N | No
D23 | Keystone 500kV |  | PA | Indiana | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 3/27/2002 |  |  |  |  | N | No
D24 | Mansfield 115kV |  | PA | Tioga | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 3/27/2002 |  |  |  |  | N | No
D25 | Hay Road 69kV & 138kV |  | DE | New Castle | Withdrawn | DPL | 39 | 39 | 39 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d25_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d25_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 9/17/2003 |  |  |  |  | N | No
D26 | Mercer 230kV |  | NJ | Mercer | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A | [6 empty] | N | No
D27 | Salem - East Windsor 500kV |  | NJ | Burlington | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d27_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 12/3/2002 |  | 12/1/2004 |  |  | N | No
D28 | Passyunk 230kV |  | PA | Philadelphia | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d28_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2000 | N/A | N/A |  | 11/12/2002 |  |  |  |  | N | No
D29 | Derwood 13kV |  | MD | Montgomery | In Service | PEPCO | 3 | 3 | 3 | 2.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d29_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d29_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2000 | N/A | N/A |  |  |  | 6/29/2001 |  | 6/29/2001 | N | No
E01 | Kearny 230kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2000 | N/A | N/A |  | 11/1/2001 |  |  |  |  | N | No
E02 | N. Lebanon 69kV |  | PA | Lebanon | In Service | ME | 1.2 | 1.2 | 1.2 | 1.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e02_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2000 | N/A | N/A |  |  |  | 11/17/2000 |  | 11/17/2000 | N | No
E03 | Somerville 13.8kV |  | NJ | Middlesex | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e03_imp2.pdf | Interim Study |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/17/2000 | N/A | N/A |  | 10/25/2002 |  | 1/31/2001 |  |  | N | No
E04 | Atlantic 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 598 | 24 | 24 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2000 | N/A | N/A | [6 empty] | N | No
E04_W20 | Guilford 138 kV |  | PA | Franklin | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e04_w20_fea.pdf | Document Posted |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 9/6/2000 | N/A | N/A |  |  |  | 12/1/2002 |  | 12/1/2002 | N | No
E05 | Bethlehem Steel 33kV | Sparrow Point | MD | Baltimore County | In Service | BGE | 152.5 | 2.5 | 2.5 | 2.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/14/2000 | N/A | N/A |  |  |  | 1/1/2001 |  | 1/1/2001 | N | No
E05_W25 | Doubs 500 kV or 230 kV |  | MD | Frederick | Withdrawn | APS | 620 | 620 | 620 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e05_w25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e05_w25_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2000 | N/A | N/A |  | 11/26/2002 |  | 5/1/2004 |  |  | N | No
E06 | Bear Creek 69kV (Wind) | Bear Creek | PA | Luzerne | Withdrawn | PPL | 15.6 | 15.6 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e06_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/e06_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e06_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/5/2000 | N/A | N/A |  | 10/25/2002 |  | 12/1/2002 |  |  | N | No
E07 | Montour 230kV | Montour #2 | PA | Montour | In Service | PPL | 766 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/6/2000 | N/A | N/A |  |  |  | 1/1/1999 |  | 5/6/2002 | N | No
E08 | Hunlock Creek |  | PA | Luzerne | Withdrawn | UGI | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2000 | N/A | N/A | [6 empty] | N | No
E09 | Kiamensi 34kV |  | DE | New Castle | Withdrawn | DPL | 8.4 | 8.4 | 8.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e09_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/19/2000 | N/A | N/A | [6 empty] | N | No
E10 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 500 | 162 | 162 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e10_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2000 | N/A | N/A | [6 empty] | N | No
E11 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2000 | N/A | N/A | [6 empty] | N | No
E12 | Larrabee 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 661 | 661 | 661 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e12_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2000 | N/A | N/A | [6 empty] | N | No
E13 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 10 | 10 |  | 10 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/e13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/3/2000 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
E14 | Elm St. 115 kV |  | PA | Erie | Withdrawn | PENELEC | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2000 | N/A | N/A | [6 empty] | N | No
E15 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2000 | N/A | N/A | [6 empty] | N | No
E16 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 776 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2000 | N/A | N/A | [6 empty] | N | No
E17 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e17_fea.pdf | Document Posted |  | Withdrawn |  |  |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/9/2000 | N/A | N/A |  | 6/25/2002 |  | 12/1/2003 |  |  | N | No
E17_W26 | Taylorstown 500 kV |  | PA | Unknown | Withdrawn | APS | 1595 | 1595 | 1595 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e17_w26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e17_w26_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/14/2000 | N/A | N/A |  |  |  | 7/1/2005 |  |  | N | No
E17_W27 | Ronco | Ronco CT1, CT2, STG | PA | Fayette | In Service | APS | 661 | 620 | 620 | 620 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e17_w27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e17_w27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e17_w27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2000 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
E17_W29 | Yukon 500 kV |  | PA | Westmoreland | Withdrawn | APS | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e17_w29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e17_w29_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/e17_w29_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/15/2000 | N/A | N/A |  | 6/2/2004 |  | 12/31/2005 |  |  | N | No
E18 | Essex / Foundry St 138kV |  | NJ | Essex | Withdrawn | PSEG | 275 | 275 | 275 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2000 | N/A | N/A | [6 empty] | N | No
E19 | Delco Tap 230kV |  | PA | Delaware | Withdrawn | PECO | 330 | 330 | 330 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e19_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2000 | N/A | N/A | [6 empty] | N | No
E20 | Croydon 230kV | Croydon #11,12,21,22,31,32,41,42 | PA | Bucks | In Service | PECO | 386.5 | 6.5 | 6.5 | 6.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/28/2000 | N/A | N/A |  |  |  | 12/20/2002 |  | 12/20/2002 | N | No
E21 | Camden-Richmond 230kV |  | NJ | Camden | Withdrawn | PSEG | 727 | 727 | 727 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e21_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/e21_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/28/2000 | N/A | N/A |  | 11/11/2004 | Customer Initiated Withdrawal | 12/1/2004 |  |  | N | No
E22 | Burches Hill 500kV |  | VA | Prince William | Withdrawn | PEPCO | 960 | 960 | 960 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2000 | N/A | N/A |  | 8/8/2002 |  | 1/1/2005 |  |  | N | No
E23 | Lakehurst 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e23_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2000 | N/A | N/A |  | 9/17/2002 |  | 12/1/2003 |  |  | N | No
E24 | Parlin 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2000 | N/A | N/A |  | 5/22/2002 |  |  |  |  | N | No
E27 | Hosensack 500kV |  | PA | Northampton | Withdrawn | PPL | 1100 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2000 | N/A | N/A | [6 empty] | N | No
E28 | Motiva | Delaware City/Motiva Unit G6 | DE | New Castle | In Service | DPL | 75 | 60 | 60 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/30/2000 | N/A | N/A |  |  |  | 10/1/2003 |  | 10/1/2003 | N | No
F01 | TMI |  | PA | Dauphin | Withdrawn | ME | 650 | 551 | 551 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2000 | N/A | N/A |  | 4/2/2002 |  | 12/1/2004 |  |  | N | No
F02 | Hudson |  | NJ | Hudson | Withdrawn | PSEG | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/7/2000 | N/A | N/A |  | 12/1/2001 |  |  |  |  | N | No
F03 | Martins Creek 230kV | Martins Creek #3 | PA | Northampton | In Service | PPL | 850 | 30 | 30 | 30 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/f03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/13/2000 | N/A | N/A |  |  |  | 4/1/2001 |  | 4/1/2001 | N | No
F04 | Somerset 115kV | Keystone | PA | Somerset | Withdrawn | PENELEC | 30 | 30 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f04_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/f04_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A | 11/1/2005 | 1/18/2001 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
F05 | Keystone-Conemaugh 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 646 | 646 | 646 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2001 | N/A | N/A | [6 empty] | N | No
F05_W38 | White Oak 500 kV |  | PA | Unknown | Withdrawn | APS | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f05_w38_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2001 | N/A | N/A |  |  |  | 3/1/2004 |  |  | N | No
F06 | Birdsboro 13.2kV |  | PA | Berks | Withdrawn | ME | 6.5 | 6.5 | 6.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2001 | N/A | N/A | [6 empty] | N | No
F07 | Dickerson 230kV | Dickerson | MD | Montgomery | In Service | PEPCO | 20 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/f07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2001 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
F08 | Chalk Point 230kV | Chalk Point | MD | Prince George's | In Service | PEPCO | 20 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/f08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2001 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
F09 | Central City West 23kV |  | PA | Somerset | Withdrawn | PENELEC | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f09_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2001 | N/A | N/A |  | 10/15/2002 |  | 12/1/2003 |  |  | N | No
G00_MTX2B | Keeney-Steele 230kV |  | DC | Unknown | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR/FTR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g00_mtx2b_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2001 | N/A | N/A |  |  |  | 1/1/2005 |  |  | S | No
G00_MTX2C | Vienna-Piney Grove 230kV |  | MD | Dorchester | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR/FTR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g00_mtx2c_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2001 | N/A | N/A |  |  |  | 1/1/2005 |  |  | S | No
G00_MTX3 | Erie West 345kV |  | PA | Erie | Withdrawn | Unknown | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | C/TIR/1000 F/TW | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g00_mtx3_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/g00_mtx3_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2001 | N/A | N/A |  | 7/10/2003 |  | 6/30/2004 |  |  | S | No
G00_W39 | Doubs 500 kV or 230 kV |  | MD | Frederick | Withdrawn | APS | 668 | 668 | 668 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g00_w39_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2001 | N/A | N/A |  | 10/25/2002 |  | 4/1/2004 |  |  | N | No
G00_W40 | Warren 138 kV |  | VA | Warren | Withdrawn | APS | 264 | 264 | 264 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g00_w40_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2001 | N/A | N/A |  | 11/4/2002 |  | 5/1/2005 |  |  | N | No
G02 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 234 | 234 | 234 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g02_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 2/14/2001 | N/A | N/A |  | 10/23/2003 |  | 5/1/2006 |  |  | N | No
G02_W43 | Tallmansville 138 kV |  | WV | Upshur | Withdrawn | APS | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g02_w43_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2001 | N/A | N/A |  | 1/31/2003 |  | 7/1/2005 |  |  | N | No
G03 | Todd 69kV |  | MD | Dorchester | Withdrawn | DPL | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g03_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/22/2001 | N/A | N/A |  | 4/22/2002 |  | 12/1/2002 | 12/1/2002 |  | N | No
G04 | Brunner Island #2 | Brunner Island #2 | PA | York | Withdrawn | PPL | 749 | 14 | 14 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g04_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 1/1/2002 |  |  | N | No
G05 | Brunner Island #1 | Brunner Island #1 | PA | York | Withdrawn | PPL | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g05_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 1/1/2002 |  |  | N | No
G06 | Martins Creek #4 | Martins Creek #4 | PA | Northampton | In Service | PPL | 850 | 30 | 30 | 30 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 3/1/2012 | 3/1/2012 | 3/1/2012 | N | No
G06_W44 | Fort Martin 500 kV |  | WV | Monongalia | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g06_w44_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G06_W45 | Harrison 500 kV |  | WV | Harrison | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g06_w45_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G06_W47 | Black Oak 500 kV |  | PA | Allegheny | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g06_w47_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G07 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g07_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2001 | N/A | N/A |  | 12/4/2001 |  |  |  |  | N | No
G07_MTX1 | Sayreville 230kV | Neptune | NJ | Middlesex | In Service | JCPL | 790 | 790 |  |  | Energy | Merchant Transmission |  | DC | F/TWR 685; NF/TWR 105 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g07_mtx1_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/g07_mtx1_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/g07_mtx1_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/g07_mtx1_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/g07_mtx1_csa.pdf | Document Posted | N/A | N/A |  | 3/8/2001 | N/A | N/A | 1/4/2007 |  |  | 6/30/2007 |  | 6/30/2007 | S | No
G08 | Kearny | Kearny #12 | NJ | Hudson | In Service | PSEG | 215 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g08_fac2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/13/2001 | N/A | N/A |  |  |  | 6/30/2001 |  | 6/30/2001 | N | No
G09 | Homer City |  | PA | Indiana | Withdrawn | PENELEC | 547 | 547 | 547.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2001 | N/A | N/A |  |  |  | 12/1/2004 |  |  | N | No
G10 | Bergen | Bergen #2 | NJ | Bergen | In Service | PSEG | 550 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2001 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
G11 | Burlington 138kV |  | NJ | Burlington | Withdrawn | PSEG | 622 | 622 | 622 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2001 | N/A | N/A |  | 1/8/2002 |  |  |  |  | N | No
G12 | Burlington 230kV |  | NJ | Burlington | Withdrawn | PSEG | 316 | 316 | 316 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g12_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2001 | N/A | N/A |  | 1/4/2002 |  |  |  |  | N | No
G13 | Woodbourne |  | PA | Bucks | Withdrawn | PECO | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g13_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2001 | N/A | N/A |  | 6/3/2003 |  | 12/1/2005 |  |  | N | No
G14 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 610 | 610 | 610 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2001 | N/A | N/A |  |  |  | 12/1/2004 |  |  | N | No
G15 | Sewaren |  | NJ | Middlesex | Withdrawn | PSEG | 800 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2001 | N/A | N/A |  |  |  | 6/1/2004 |  |  | N | No
G16 | Bayview 26kV (Wind) |  | VA | Northampton | Withdrawn | DPL | 8 | 8 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g16_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g16_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/2/2001 | N/A | N/A |  |  |  | 12/1/2002 | 12/1/2002 |  | N | No
G17 | Burlington | Burlington #10 | NJ | Burlington | In Service | PSEG | 261 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 7/19/2002 |  | 7/19/2002 | N | No
G18 | Linden | Linden 5 & 6 | NJ | Union | In Service | PSEG | 172 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 5/4/2004 |  | 5/4/2004 | N | No
G19 | Linden | Linden 7 & 8 | NJ | Union | In Service | PSEG | 168 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 5/4/2004 |  | 5/4/2004 | N | No
G20 | Essex | Essex 9 | NJ | Essex | In Service | PSEG | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G21 | Meyersdale North 115 kV | Meyersdale WF | PA | Somerset | In Service | PENELEC | 30 | 30 |  | 30 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g21_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g21_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g21_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g21_csa.pdf | Document Posted | N/A | N/A |  | 4/6/2001 | N/A | N/A |  |  |  | 12/3/2003 | 12/3/2003 | 12/3/2003 | N | No
G22 | North Wales 34.5 kV | Merck | PA | Montgomery | In Service | PECO | 38 | 38 | 38 | 38 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g22_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/6/2001 | N/A | N/A |  |  |  | 9/30/2002 |  | 9/30/2002 | N | No
G22_MTX5 | Linden 230kV | Linden VFT | NJ | Union | In Service | PSEG | 330 | 330 | 330 |  | Capacity | Merchant Transmission |  | AC | TWR 330 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g22_mtx5_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/g22_mtx5_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/g22_mtx5_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/g22_mtx5_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/g22_mtx5_csa.pdf | Document Posted | N/A | N/A | 6/1/2009 | 6/2/2001 | N/A | N/A | 9/16/2009 |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | S | No
G24 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 1.9 | 1.9 | 1.9 | 1.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g24_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g24_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/1/2001 | N/A | N/A |  |  |  | 6/8/2002 |  | 6/8/2002 | N | No
G25 | Marion 26.4kV | Baler LF | NJ | Bergen | In Service | PSEG | 3.8 | 3.8 | 3.8 | 3.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/1/2001 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
G26 | England 138kV |  | NJ | Cape May | Withdrawn | AEC | 350 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  | 1/10/2002 |  |  |  |  | N | No
G27 | Churchtown 230kV |  | NJ | Salem | Withdrawn | AEC | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  | 1/10/2002 |  |  |  |  | N | No
G28 | Vienna 230kV |  | MD | Dorchester | Withdrawn | DPL | 750 | 390 | 390 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  |  |  | 12/1/2004 |  |  | N | No
G29 | Indian River 138kV |  | DE | Sussex | Withdrawn | DPL | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g29_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  | 1/10/2002 |  |  |  |  | N | No
G30 | Perryman 115kV | Perryman 51 | MD | Harford | In Service | BGE | 152 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2001 | N/A | N/A |  |  |  | 6/1/2001 |  | 6/1/2001 | N | No
G30_W51 | Fort Martin 500 kV | Longview ST1 | WV | Monongalia | In Service | APS | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_w51_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g30_w51_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_w51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g30_w51_csa.pdf | Document Posted | N/A | N/A | 4/5/2009 | 5/21/2001 | N/A | N/A | 5/6/2011 |  |  | 4/22/2011 | 4/22/2011 | 6/1/2008 | N | No
G30_W52 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 354 | 54 | 54 | 15.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_w52_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_w52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g30_w52_csa.pdf | Document Posted | N/A | N/A |  | 5/23/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G30_W53 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 704 | 104 | 104 | 25.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_w53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_w53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/23/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G30_W55 | Kempton 500 kV |  | MD | Unknown | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w55_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2001 | N/A | N/A |  | 11/19/2002 |  | 1/1/2006 |  |  | N | No
G31 | Johnstown 230kV |  | PA | Indiana | Withdrawn | PENELEC | 610 | 610 | 610 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g31_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/30/2001 | N/A | N/A |  | 4/11/2003 |  | 12/1/2005 |  |  | N | No
G32 | TMI - Juniata 500kV |  | PA | York | Withdrawn | ME | 675 | 675 | 675 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g32_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G32_MTX6 | Linden 230kV, 138kV |  | NJ | Union | Withdrawn | PSEG | 365 | 365 | 365 |  | Capacity | Merchant Transmission |  | DC | R/TIR/365 F/TWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g32_mtx6_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/g32_mtx6_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/3/2001 | N/A | N/A |  | 8/12/2004 |  | 12/31/2005 |  |  | S | No
G33 | Brunner Island 230kV |  | PA | York | Withdrawn | PPL | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g33_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2001 | N/A | N/A | [6 empty] | N | No
G34 | Frackville 69kV |  | PA | Schuylkill | Withdrawn | PPL | 51.6 | 51.6 | 51.6 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g34_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/2001 | N/A | N/A | [6 empty] | N | No
G35 | Chalk Point |  | MD | St. Mary's | Withdrawn | PEPCO | 340 | 340 | 340 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g35_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2001 | N/A | N/A |  | 9/25/2003 |  | 12/1/2004 |  |  | N | No
G36 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 107 | 107 | 107 | 5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g36_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g36_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/16/2001 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
G36_W58 | Horse Shoe Run 69 kV |  | WV | Preston | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g36_w58_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A | [6 empty] | N | No
G37 | Atlantic |  | NJ | Monmouth | Withdrawn | JCPL | 471 | 471 | 471 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A |  | 4/10/2002 |  |  |  |  | N | No
G38 | Portland |  | PA | Northampton | Withdrawn | ME | 558 | 86 | 86 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A |  | 4/10/2002 |  | 12/1/2004 |  |  | N | No
G39 | Joppatowne 13kV |  | MD | Baltimore County | Withdrawn | BGE | 4.2 | 4.2 | 4.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g39_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A |  | 6/13/2002 |  | 6/1/2002 |  |  | N | No
G40 | Warren 230kV |  | PA | Warren | Withdrawn | PENELEC | 260 | 260 | 260 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g40_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2001 | N/A | N/A |  | 3/15/2002 |  |  |  |  | N | No
G41 | Croydon |  | PA | Bucks | Withdrawn | PECO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g41_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2001 | N/A | N/A |  | 3/18/2002 |  |  |  |  | N | No
G42 | Keystone/Conemaugh 500kV |  | PA | Indiana | Withdrawn | PENELEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g42_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2001 | N/A | N/A |  | 4/10/2002 |  | 12/1/2004 |  |  | N | No
G43 | Homer City |  | PA | Indiana | Withdrawn | PENELEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g43_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2001 | N/A | N/A |  | 4/9/2002 |  |  |  |  | N | No
G44 | Dupont Seaford 69kV | DuPont Seaford | DE | Sussex | Deactivated | DPL | 30 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g44_fea2.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g44_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g44_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2001 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
G45 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 575 | 575 | 575 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g45_fea2.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2001 | N/A | N/A |  | 6/18/2003 |  | 12/1/2005 |  |  | N | No
G46 | Peach Bottom 500kV | Peach Bottom 2 & 3 | PA | York | In Service | PECO | 2256 | 70 | 70 | 38 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g46_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2001 | N/A | N/A |  |  |  | 12/31/2001 | 12/31/2001 | 12/31/2001 | N | No
G47 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 32 | 32 | 32 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g47_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 4/10/2002 |  |  |  |  | N | No
G48 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g48_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 6/11/2003 |  | 12/1/2003 |  |  | N | No
G49 | Clinton 69kV |  | PA | Lycoming | Withdrawn | PPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g49_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 3/13/2002 |  |  |  |  | N | No
G50 | Dickerson 230kV |  | MD | Frederick | Withdrawn | PEPCO | 910 | 910 | 910 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g50_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 5/25/2002 |  | 12/1/2005 |  |  | N | No
G51 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g51_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 3/25/2002 |  |  |  |  | N | No
G51_W60 | Hatfield Ferry 500 kV | Greene Energy Resource Recovery Project | PA | Greene | Withdrawn | APS | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g51_w60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g51_w60_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g51_w60_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g51_w60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g51_w60_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 3/19/2013 | Customer Initiated Withdrawal | 8/1/2015 | 8/1/2015 |  | N | No
G51_W61 | Gates Hill 138 kV |  | PA | Fayette | Withdrawn | APS | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g51_w61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 7/1/2002 |  | 1/1/2006 |  |  | N | No
G51_W62 | Eastalco 230 kV | Catoctin CC | MD | Frederick | Withdrawn | APS | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g51_w62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g51_w62_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g51_w62_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g51_w62_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g51_w62_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 4/21/2010 | Customer Milestone Not Met | 3/1/2013 | 3/1/2013 |  | N | No
G51_W63 | Upton 34.5 kV | Upton | PA | Franklin | In Service | APS | 9.9 | 9.9 | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g51_w63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g51_w63_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g51_w63_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g51_w63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2001 | N/A | N/A |  |  |  | 4/1/2003 |  | 4/1/2003 | N | No
H01 | Susquehanna 500kV |  | PA | Columbia | Withdrawn | PPL | 52 | 2 | 2 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2001 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 |  | N | No
H02 | Susquehanna 230kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 9 | 9 | 9 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/20/2001 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
H03 | Susquehanna 500kV | Susquehanna #2 | PA | Columbia | In Service | PPL | 1153 | 9 | 9 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/21/2001 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 | 12/1/2003 | N | No
H04 | Wright 69kV (Wind) |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h04_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2001 | N/A | N/A |  |  |  | 12/1/2002 |  |  | N | No
H04_W64 | Henry 138 kV |  | WV | Grant | Withdrawn | APS | 150 | 150 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h04_w64_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h04_w64_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h04_w64_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/17/2001 | N/A | N/A |  | 6/29/2004 |  | 12/31/2005 |  |  | N | No
H05 | Riverside 230/115kV |  | MD | Baltimore County | Withdrawn | BGE | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2001 | N/A | N/A |  | 8/6/2002 |  | 12/1/2007 |  |  | N | No
H05_MTX9 |  |  | MD | Calvert | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2001 | N/A | N/A | [6 empty] | S | No
H05_W65 | Tallmansville 138 kV |  | WV | Upshur | Withdrawn | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h05_w65_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2001 | N/A | N/A |  |  |  | 7/1/2005 |  |  | N | No
H06 | Chichester 230kV | Phillips Island | PA | Philadelphia | In Service | PECO | 750 | 25 | 25 | 25 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/h06_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2001 | N/A | N/A |  |  |  | 12/31/2004 |  | 12/31/2004 | N | No
H07 | Salem - East Windsor 500kV |  | NJ | Burlington | Withdrawn | AEC | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h07_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2001 | N/A | N/A |  | 6/11/2002 |  | 6/1/2004 |  |  | N | No
H08 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 560 | 560 | 560 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2001 | N/A | N/A |  | 6/18/2002 |  | 12/1/2005 |  |  | N | No
H08_W66 | Windsor 138 kV |  | WV | Unknown | Withdrawn | APS | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h08_w66_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/14/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
H09 | Hooversville & Johns-Alt 230kV |  | PA | Somerset | Withdrawn | PENELEC | 635 | 635 | 635 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2001 | N/A | N/A |  | 11/4/2002 |  | 12/1/2006 |  |  | N | No
H10 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 560 | 560 | 560 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h10_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2001 | N/A | N/A |  |  |  | 12/1/2005 |  |  | N | No
H11 | New Freedom - Cardiff 230kV |  | NJ | Gloucester | Withdrawn | AEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2001 | N/A | N/A |  | 7/22/2002 |  | 12/1/2005 |  |  | N | No
H12 | Edgemoor 230kV | Hay Road 4 | DE | New Castle | In Service | DPL | 189 | 10 | 10 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/20/2001 | N/A | N/A |  |  |  | 12/1/2005 |  | 12/1/2005 | N | No
H13 | Dolfield | Owings Mills | MD | Baltimore County | In Service | BGE | 9 | 9 | 0 | 9 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/27/2001 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
H14 | TMI-Peach Bottom 500kV |  | PA | York | Withdrawn | ME | 1060 | 1060 | 1060 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2001 | N/A | N/A |  | 10/29/2002 |  | 12/1/2005 |  |  | N | No
H14_W67 | Enon 138 kV |  | PA | Unknown | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h14_w67_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2001 | N/A | N/A |  | 7/8/2002 |  | 1/1/2007 |  |  | N | No
H15 | Chapman-Moshannon 230kV |  | PA | Clearfield | Withdrawn | PENELEC | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2001 | N/A | N/A |  | 11/4/2002 |  | 12/1/2006 |  |  | N | No
H16 | Edgemoor |  | DE | New Castle | Withdrawn | DPL | 565 | 565 | 565 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2001 | N/A | N/A |  | 9/25/2002 |  | 12/1/2005 |  |  | N | No
H17 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 2336 | 115 | 115 | 83 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h17_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h17_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 6/18/2008 | 6/18/2008 | 6/1/2008 | N | No
H18 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1221 | 78 | 78 | 12 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h18_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 8/26/2008 | 8/26/2008 | 12/1/2007 | N | No
H19 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1221 | 43 | 43 | 43 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h19_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h19_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 8/26/2008 | 8/26/2008 | 12/1/2007 | N | No
H20 | Oak Grove 13.8kV |  | MD | Prince George's | In Service | PEPCO | 3.5 | 3.5 | 3.5 | 3.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/31/2003 | 1/21/2002 | N/A | N/A |  |  |  | 12/31/2003 | 12/31/2003 | 5/31/2003 | N | No
H20_CE12 |  |  | IL | Adams | Withdrawn | ComEd | 700 |  |  |  | Energy | Generation Interconnection | Coal |  |  | N/A | [5 empty] | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2002 | N/A | N/A |  |  |  | 6/6/2001 |  |  | N | No
H21 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2002 | N/A | N/A |  |  |  | 12/1/2005 |  |  | N | No
H21_W68 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 | 300 | 0 | 264 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h21_w68_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h21_w68_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h21_w68_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h21_w68_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/h21_w68_csa.pdf | Document Posted | N/A | N/A |  | 1/29/2002 | N/A | N/A |  |  |  | 9/25/2007 | 9/25/2007 | 9/30/2007 | N | No
H22 | Erie South |  | PA | Erie | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2002 | N/A | N/A |  | 3/17/2003 |  | 6/1/2006 |  |  | N | No
H23 | Bear Creek |  | PA | Luzerne | Withdrawn | PPL | 10 | 10 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2002 | N/A | N/A |  | 10/25/2002 |  | 12/1/2002 |  |  | N | No
H23_W69 | Bluestone Dam 46 kV |  | WV | Summers | Withdrawn | APS | 41 | 41 | 41 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h23_w69_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h23_w69_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2002 | N/A | N/A |  |  |  | 6/1/2006 |  |  | N | No
H23_W70 | Kelso Gap 138 kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 | 100 |  | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h23_w70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h23_w70_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h23_w70_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h23_w70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/h23_w70_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2002 | N/A | N/A | 10/26/2010 |  |  | 10/26/2010 | 10/26/2010 | 11/6/2006 | N | No
H24 | Forest 230kV |  | PA | Elk | Withdrawn | PENELEC | 575 | 575 | 575 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  | 11/13/2002 |  | 6/1/2006 |  |  | N | No
H25 | Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h25_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 6/1/2007 |  |  | N | No
H26 | Eagle Point 230kV |  | NJ | Gloucester | Withdrawn | PSEG | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h26_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  | 7/3/2003 |  | 12/1/2003 |  |  | N | No
H27 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 2.85 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 12/1/2002 |  | 12/1/2002 | N | No
H27_W71 | McConnellsburg-Guilford 138 kV |  | PA | Fulton | Withdrawn | APS | 252 | 252 | 252 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h27_w71_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  | 4/10/2003 |  | 5/1/2004 |  |  | N | No
H27_W72 | McConnellsburg-Cherry Run 138 kV |  | PA | Fulton | Withdrawn | APS | 350 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h27_w72_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 5/1/2004 |  |  | N | No
I01 | Ontario 23kV | Jersey Atlantic WF | NJ | Atlantic | In Service | AEC | 7.5 | 7.5 |  | 7.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i01_csa.pdf | Document Posted | N/A | N/A | 7/1/2005 | 2/13/2002 | N/A | N/A | 12/20/2005 |  |  | 12/30/2005 |  | 12/30/2005 | N | No
I02 | Erie West-Ashtabula 345kV |  | OH | Ashtabula | Withdrawn | PENELEC | 1998 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2002 | N/A | N/A |  | 5/7/2003 |  | 12/1/2007 |  |  | N | No
I02_W73 | Harrison 500 kV | Harrison 1, 2, 3 | WV | Harrison | In Service | APS | 35 | 35 | 35 | 21 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i02_w73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i02_w73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i02_w73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/7/2002 | N/A | N/A |  |  |  | 9/22/2004 |  | 9/22/2004 | N | No
I03 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i03_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2002 | N/A | N/A |  | 4/28/2003 | Customer Milestone Not Met | 6/1/2005 |  |  | N | No
I03_W74 | Savage 138kV | Savage Mtn WF | PA | Allegheny | Withdrawn | APS | 40 | 40 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i03_w74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i03_w74_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/i03_w74_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i03_w74_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i03_w74_csa.pdf | Document Posted | N/A | N/A |  | 3/27/2002 | N/A | N/A |  | 11/18/2009 | Customer Initiated Withdrawal | 9/30/2011 | 9/30/2011 |  | N | No
I04 | Somerset-Allegheny 115kV | Stonycreek | PA | Somerset | Withdrawn | PENELEC | 45 | 45 | 9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i04_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/i04_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A | 11/1/2005 | 3/29/2002 | N/A | N/A | 12/1/2005 | 4/14/2005 |  | 12/31/2005 |  |  | N | No
I05 | Whiteoak (sub153) 13kV |  | MD | Calvert | Withdrawn | PEPCO | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2002 | N/A | N/A |  | 5/21/2003 |  | 12/1/2003 |  |  | N | No
I06 | Greenwich Pumphousse 2.4kV | Repauno Unit 1 | NJ | Unknown | In Service | AEC | 1.7 | 1.7 |  | 1.7 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/8/2002 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
I07 | W. H. Sammis 345kV |  | OH | Jefferson | Withdrawn | PENELEC | 1860 | 1860 | 1860 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i07_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 4/11/2002 | N/A | N/A |  | 12/10/2002 |  | 5/1/2005 |  |  | N | No
I07_MTX8 |  |  | NJ | Middlesex | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2001 | N/A | N/A | [6 empty] | S | No
I08 | Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 870 | 870 | 870 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2002 | N/A | N/A |  |  |  | 5/1/2005 |  |  | N | No
I09 | Bath County 500kV |  | VA | Bath | Withdrawn | APS | 252 | 252 | 252 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i09_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2002 | N/A | N/A |  | 1/15/2004 |  | 6/1/2009 |  |  | N | No
I10 | Bethesda (Sub 6) |  | MD | Montgomery | In Service | PEPCO | 2 | 2 |  | 2 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i10_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i10_csa.pdf | Document Posted | N/A | N/A | 7/1/2004 | 6/11/2002 | N/A | N/A | 9/20/2004 |  |  | 10/1/2004 |  | 10/1/2004 | N | No
I11 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i11_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2002 | N/A | N/A |  | 2/23/2004 |  | 5/1/2006 |  |  | N | No
I12 | Grand Point 69kV | Orchard Park Generating Station | PA | Franklin | In Service | APS | 30.5 | 23.3 | 23.3 | 23.3 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i12_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2002 | N/A | N/A |  |  |  | 1/1/2004 |  | 1/1/2004 | N | No
I13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 29.4 | 0 | 29.4 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/i13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i13_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2002 | N/A | N/A |  |  |  | 3/6/2008 | 3/6/2008 | 3/6/2008 | N | No
I14 | Upton 34.5kV | Upton | PA | Franklin | In Service | APS | 14 | 4.1 | 4.1 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i14_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2002 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
I15 | Scalp Level 115kV |  | PA | Somerset | Withdrawn | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 1/7/2003 |  | 5/1/2003 |  |  | N | No
I16 | Atwell 25kV |  | PA | Butler | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I17 | Pine Grove 69kV |  | PA | Berks | Withdrawn | PPL | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I18 | South Park 25kV |  | PA | Allegheny | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  |  |  | 5/1/2003 |  |  | N | No
I19 | Level Green 25kV |  | PA | Westmoreland | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i19_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I20 | Wycoff 25kV |  | PA | Allegheny | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i20_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I22 | Hinton 46kV |  | WV | Summers | Withdrawn | APS | 41 | 41 | 41 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 11/4/2003 |  | 9/1/2004 |  |  | N | No
J01 | Monterey 69kV |  | VA | Highland | Withdrawn | APS | 41 | 41 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2002 | N/A | N/A |  | 1/20/2004 |  | 12/31/2004 |  |  | N | No
J01_MTX | Hope Creek 500kV Cedar Creek 230kV |  | DC | Unknown | Withdrawn | PSEG | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/j01_mtx_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2002 | N/A | N/A |  | 12/5/2003 |  |  |  |  | S | No
J02 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2002 | N/A | N/A |  |  |  | 12/1/2005 |  |  | N | No
J02_MTX11 | Vienna 230kV - Chalk Point 230kV |  | MD | Dorchester | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2003 | N/A | N/A |  | 4/28/2005 |  | 1/1/2006 |  |  | S | No
J02_MTX13 | Keeney XFMR 230/138kV | Keeney Autotransformer AT20 | DE | New Castle | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/j02_mtx13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/j02_mtx13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/j02_mtx13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/16/2002 | N/A | N/A |  | 12/8/2003 |  | 5/31/2003 |  | 5/31/2003 | S | No
J03 | Edgemoor |  | DE | New Castle | Withdrawn | DPL | 565 | 565 | 565 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j03_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2002 | N/A | N/A |  | 2/12/2004 |  | 12/1/2005 |  |  | N | No
J03_CE14 | Sublette Wind Farm |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j03_ce14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/15/2002 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
J04 | Bustleton 138kV |  | NJ | Burlington | Withdrawn | PSEG | 7 | 7 | 7 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j04_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/18/2002 | N/A | N/A |  | 8/4/2004 |  | 11/1/2004 |  |  | N | No
J04_CE15 | West Brooklyn Wind Farm |  | IL | Lasalle | Withdrawn | ComEd | 25 | 25 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j04_ce15_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/20/2002 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
J05 | Huron 69kV | Borgata D1 / D2 | NJ | Atlantic | In Service | AEC | 8 | 8 | 8 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/25/2002 | N/A | N/A |  |  |  | 7/30/2003 |  | 7/30/2003 | N | No
J06 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 34 | 34 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j06_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/j06_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j06_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 10/25/2002 | N/A | N/A |  | 5/14/2003 |  | 12/1/2003 |  |  | N | No
J06_CE16 |  |  | IL | Adams | Withdrawn | ComEd | 100 |  |  |  | Energy | Generation Interconnection | Hydro |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2002 | N/A | N/A |  |  |  | 8/1/2005 |  |  | N | No
J07 | North Franklin 138kV | Liberty Gap WF | WV | Pendleton | Withdrawn | APS | 155 | 155 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j07_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/j07_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j07_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/j07_csa.pdf | Document Posted | N/A | N/A |  | 11/1/2002 | N/A | N/A |  | 6/28/2010 | Customer Initiated Withdrawal | 11/30/2011 | 11/30/2011 |  | N | No
J07_MTX12 | Cheswold XFMR 138/69kV |  | DE | Kent | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/j07_mtx12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/j07_mtx12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/j07_mtx12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2002 | N/A | N/A |  |  |  | 12/31/2003 |  | 12/31/2003 | S | No
J08 | Whiteoak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 6 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j08_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/j08_csa.pdf | Document Posted | N/A | N/A | 4/1/2004 | 12/12/2002 | N/A | N/A | 4/30/2004 |  |  | 8/15/2004 |  | 8/15/2004 | N | No
J08_MTX14 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | Unknown | 80 | 80 | 80 |  | Capacity | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2003 | N/A | N/A |  | 4/22/2003 |  | 6/30/2005 |  |  | S | No
J08_MTX15 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | Unknown | 790 |  |  |  | Energy | Merchant Transmission |  | DC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2003 | N/A | N/A |  | 9/26/2003 |  | 6/30/2006 |  |  | S | No
J09 | Harrisburg Authority | Harrisburg Municipal Solid Waste Authority | PA | Dauphin | In Service | PPL | 26 | 26 | 26 | 11 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/j09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j09_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/j09_csa.pdf | Document Posted | N/A | N/A | 6/30/2005 | 1/31/2003 | N/A | N/A | 2/1/2006 |  |  | 4/24/2006 |  | 4/24/2006 | N | No
K01 | Salem 69kV | Mannington Mills Units 1,2,3 | NJ | Salem | Deactivated | AEC | 8 | 8 | 8 | 8 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/10/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K02 | East Towanda-Moshannon 230kV | Laurel Hill | PA | Lycoming | In Service | PENELEC | 70 | 70 | 0 | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k02_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k02_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k02_csa.pdf | Document Posted | N/A | N/A | 9/17/2012 | 2/25/2003 | N/A | N/A | 9/19/2012 |  |  | 10/29/2012 | 10/29/2012 | 9/25/2012 | N | No
K02_CE18 | Baileyville Wind Farm | Baileyville Wind Farm | IL | Stephenson | Withdrawn | ComEd | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k02_ce18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k02_ce18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k02_ce18_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2003 | N/A | N/A |  | 8/26/2013 | Customer Milestone Not Met | 12/31/2011 | 12/31/2011 |  | N | No
K03 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 39.6 | 39.6 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k03_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2003 | N/A | N/A |  | 6/5/2003 |  |  |  |  | N | No
K04 | Camden 26kV | Pennsauken Sanitary Landfill / Aluminum Shapes | NJ | Camden | In Service | PSEG | 5.1 | 5.1 | 0 | 5.1 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k04_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k04_csa.pdf | Document Posted | N/A | N/A | 9/15/2004 | 4/15/2003 | N/A | N/A | 10/15/2004 |  |  | 6/30/2005 |  | 6/30/2005 | N | No
K04_CE17 | Lena Wind Farm |  | IL | Stephenson | Withdrawn | ComEd | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k04_ce17_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/15/2003 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
K04_CE19 | Freeport Wind Farm | Freeport Wind Farm | IL | Stephenson | Withdrawn | ComEd | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k04_ce19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k04_ce19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k04_ce19_csa.pdf | Document Posted | N/A | N/A |  | 4/15/2003 | N/A | N/A |  | 9/26/2011 | Customer Milestone Not Met | 10/15/2011 | 10/15/2011 |  | N | No
K05 | Cedar 69kV |  | NJ | Ocean | Withdrawn | AEC | 0.12 | 0.12 |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/23/2003 | N/A | N/A |  |  |  | 6/1/2003 |  |  | N | No
K06 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 10 | 5 | 5 | 4.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2003 | N/A | N/A | 11/1/2004 |  |  | 11/1/2004 |  | 11/1/2004 | N | No
K07 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 10 | 5 | 5 | 4.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2003 | N/A | N/A | 11/1/2004 |  |  | 11/1/2004 |  | 11/1/2004 | N | No
K07_CE20 | Benson Wind Farm | Benson Wind Farm | IL | Woodford | Withdrawn | ComEd | 158 | 158 | 31.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k07_ce20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k07_ce20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k07_ce20_csa.pdf | Document Posted | N/A | N/A |  | 5/16/2003 | N/A | N/A |  | 9/18/2009 | Customer Initiated Withdrawal | 12/31/2010 | 12/31/2010 |  | N | No
K08 | Morgantown / Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 |  | 1800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/21/2003 | N/A | N/A |  | 8/13/2003 |  |  |  |  | N | No
K09 | Bear Creek |  | PA | Luzerne | Withdrawn | PPL | 34 | 34 | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/5/2003 | N/A | N/A |  | 1/9/2004 |  | 6/1/2004 |  |  | N | No
K10 | Somerset 115kV |  | PA | Somerset | Withdrawn | PENELEC | 6 |  | 6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k10_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k10_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/16/2003 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
K11 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 |  | 60 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k11_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2003 | N/A | N/A |  |  |  | 10/1/2007 | 10/1/2007 | 9/30/2007 | N | No
K12 | Somerset-Allegheny 115kV |  | PA | Somerset | Withdrawn | PENELEC | 13 | 13.6 | 2.72 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k12_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A | 11/1/2005 | 7/28/2003 | N/A | N/A | 12/1/2005 | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
K13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 0 | 5.88 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k13_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2003 | N/A | N/A |  |  |  | 3/6/2008 | 3/6/2008 | 9/1/2007 | N | No
K14 | Monterey 69kV |  | VA | Highland | Withdrawn | APS | 7 |  | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 1/20/2004 |  |  |  |  | N | No
K15 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 6.8 |  | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 1/9/2004 |  |  |  |  | N | No
K16 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9.9 |  | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 2/19/2004 |  | 8/1/2004 |  |  | N | No
K17 | Emerald 6 25kV |  | PA | Greene | Withdrawn | APS | 5 |  | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 2/12/2004 |  | 6/1/2004 |  |  | N | No
K18 | Arnold (Green Mountain) 115kV | Green Mountain | PA | Somerset | Deactivated | PENELEC | 10.4 |  | 2.08 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 8/13/2004 |  | 8/13/2004 | N | No
K19 | Backbone Mountain 138kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 0 | 18 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 6/1/2001 |  | 11/12/2006 | N | No
K20 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 |  | 3 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 4/1/2002 |  | 7/28/2005 | N | No
K21 | East Carbondale 69kV | Waymart | PA | Wayne | In Service | PPL | 69 |  | 13 | 64.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k21_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k21_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K22 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 9 |  | 1.8 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k22_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
K23 | Meyersdale North 115 kV | Meyersdale WF | PA | Somerset | In Service | PENELEC | 30 | 0 | 5.1 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K24 | Henry 138kV |  | WV | Grant | Withdrawn | APS | 150 |  | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k24_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 7/21/2004 |  | 12/1/2005 |  |  | N | No
K25 | Savage 138kV | Savage Mtn WF | PA | Allegheny | Withdrawn | APS | 40 |  | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k25_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k25_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k25_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 11/12/2009 | Customer Initiated Withdrawal | 9/30/2011 | 9/30/2011 |  | N | No
K26 | North Franklin 138kV | Liberty Gap WF | WV | Pendleton | Withdrawn | APS | 155 |  | 31 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k26_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k26_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 6/28/2010 | Customer Initiated Withdrawal | 11/30/2011 | 11/30/2011 |  | N | No
K27 | Calvert Cliffs 500kV |  | MD | Calvert | Withdrawn | BGE | 1740 |  | 35 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k27_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k27_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 8/20/2005 |  | 6/1/2004 |  |  | N | No
K28 | Kelso Gap 138kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 |  | 20 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k28_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2003 | N/A | N/A | 10/26/2010 |  |  | 10/26/2010 | 10/26/2010 | 11/6/2006 | N | No
K29 | Ontario |  | NJ | Atlantic | Withdrawn | AEC | 7.5 |  | 1.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k29_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2003 | N/A | N/A |  | 9/28/2004 |  |  |  |  | N | No
L01 | Morgantown / Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 | 1800 | 1800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2003 | N/A | N/A |  | 4/8/2004 |  | 1/6/2008 |  |  | N | No
L01_AEP137 | Bellefonte-N. Proctorville 138kV |  | OH | Lawrence | Withdrawn | AEP | 165 | 165 | 165 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l01_aep137_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l01_aep137_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l01_aep137_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2003 | N/A | N/A |  | 3/21/2012 | Customer Milestone Not Met | 12/31/2012 | 12/31/2012 |  | N | No
L01_CE21 | Pearl City Wind Farm |  | IL | Stephenson | Withdrawn | ComEd | 15 | 15 | 3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l01_ce21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l01_ce21_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/5/2003 | N/A | N/A |  | 11/1/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
L02 | Pleasantville 12 kV | Pleasantville / AC LF Unit 1 | NJ | Atlantic | In Service | AEC | 1.5 | 1.5 | 1.4 | 0.07 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l02_csa.pdf | Document Posted | N/A | N/A |  | 9/10/2003 | N/A | N/A |  |  |  | 1/30/2005 |  | 1/30/2005 | N | No
L03 | Morgantown | Morgantown LF | PA | Berks | Withdrawn | PPL | 0.8 | 0.8 |  |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l03_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l03_csa.pdf | Document Posted | N/A | N/A | 2/6/2006 | 9/10/2003 | N/A | N/A | 5/1/2006 | 6/3/2008 | Customer Initiated Withdrawal | 5/31/2009 |  |  | N | No
L04 | Chestnut Ridge 138 kV |  | PA | Westmoreland | Withdrawn | APS | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2003 | N/A | N/A |  | 7/7/2004 |  | 12/31/2005 |  |  | N | No
L05 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2003 | N/A | N/A |  | 4/30/2004 |  | 6/30/2005 |  |  | N | No
L05_CE22 | Camp Grove | Camp Grove Wind Farm | IL | Stark | In Service | ComEd | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l05_ce22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l05_ce22_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l05_ce22_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l05_ce22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l05_ce22_csa.pdf | Document Posted | N/A | N/A |  | 10/15/2003 | N/A | N/A |  |  |  | 12/14/2007 | 12/14/2007 | 9/1/2006 | N | No
L06 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2003 | N/A | N/A |  | 6/22/2004 |  | 6/1/2006 |  |  | N | No
L07 | Jenkins-Harwood #2 69kV | Mountain Top | PA | Luzerne | Withdrawn | PPL | 42.9 | 42.9 | 8.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l07_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l07_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/23/2003 | N/A | N/A |  | 5/18/2005 |  | 12/31/2005 |  |  | N | No
L08 | Holtwood 69kV | Holtwood | PA | Lancaster | In Service | PPL | 109 | 2 | 2 | 2 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/7/2003 | N/A | N/A |  |  |  | 10/1/2003 |  | 8/16/2004 | N | No
L09 | Montour #1 230kV | Montour #1 | PA | Montour | In Service | PPL | 761 | 2 | 2 | 2 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l09_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/7/2003 | N/A | N/A |  |  |  | 10/1/2003 |  | 8/16/2004 | N | No
L10 | Hatfield 500 kV |  | PA | Greene | Withdrawn | APS | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l10_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2003 | N/A | N/A |  | 7/12/2004 |  | 12/1/2006 |  |  | N | No
L11 | Rockwood 25 kV |  | PA | Somerset | Withdrawn | APS | 9.9 | 9.9 | 2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l11_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2003 | N/A | N/A |  | 4/15/2005 | Customer Initiated Withdrawal | 12/1/2005 |  |  | N | No
L12 | Essex |  | NJ | Essex | Withdrawn | PSEG | 6 | 6.2 | 6.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l12_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/4/2003 | N/A | N/A |  | 8/31/2004 |  | 9/30/2004 |  |  | N | No
L12_CE23 | West Brooklyn II | West Brooklyn WF | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l12_ce23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l12_ce23_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/8/2003 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
L12_CE24 | Willow Creek Wind Farm |  | IL | Lee | Withdrawn | ComEd | 79 | 79 | 15.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l12_ce24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2003 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 12/1/2005 |  |  | N | No
L13 | Rockwood | Casselman WF1 | PA | Somerset | In Service | PENELEC | 40 | 40 | 8 | 40 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l13_csa.pdf | Document Posted | N/A | N/A |  | 12/19/2003 | N/A | N/A |  |  |  | 1/11/2008 | 1/11/2008 | 12/31/2007 | N | No
L13_CE25 | Geneva | City of Geneva Units 1-5 | IL | Kane | In Service | ComEd | 29 | 29 | 29 | 29 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l13_ce25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l13_ce25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l13_ce25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/26/2003 | N/A | N/A |  |  |  | 6/1/2005 |  | 6/1/2005 | N | No
L13_CE26 | Heartland Grand Ridge |  | IL | Lasalle | Withdrawn | ComEd | 175 | 175 | 35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l13_ce26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l13_ce26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l13_ce26_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2004 | N/A | N/A |  | 8/9/2006 | Customer Initiated Withdrawal | 10/30/2006 |  |  | N | No
L13_CE27 | Heartland Wind Livingston |  | IL | Livingston | Withdrawn | ComEd | 225 | 225 | 45 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l13_ce27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l13_ce27_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2004 | N/A | N/A |  | 10/3/2005 | Customer Initiated Withdrawal | 10/30/2006 |  |  | N | No
L14 | Berlin 69kV Tap 5 MW |  | MD | Worcester | Withdrawn | AEC | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2004 | N/A | N/A |  | 8/19/2004 | Customer Milestone Not Met | 7/1/2005 |  |  | N | No
L15 | Buffalo Road-Carry East to NY |  | NY | Chautauqua | Withdrawn | PENELEC | 34 | 34 | 34 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/l15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2004 | N/A | N/A |  | 10/18/2004 | Customer Milestone Not Met | 11/1/2005 |  |  | S | No
L16 | Monterey 69KV |  | VA | Highland | Withdrawn | APS | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2004 | N/A | N/A |  | 9/20/2004 |  | 12/1/2005 |  |  | N | No
L17 | Rolling Hills | Rolling Hills | PA | Berks | Deactivated | ME | 6 | 6 |  | 6 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l17_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l17_csa.pdf | Document Posted | N/A | N/A | 2/7/2005 | 1/22/2004 | N/A | N/A | 3/20/2005 |  |  | 4/1/2005 |  | 4/1/2005 | N | No
L18 | Bear Creek | Bear Creek WF | PA | Luzerne | In Service | PPL | 26 | 26 | 5.2 | 24 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l18_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l18_csa.pdf | Document Posted | N/A | N/A | 11/15/2005 | 1/28/2004 | N/A | N/A | 12/31/2005 |  |  | 2/26/2006 |  | 2/26/2006 | N | No
L19 | Karthaus 230kV | Karthaus | PA | Clearfield | Withdrawn | APS | 290 | 290 | 290 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l19_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l19_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l19_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2004 | N/A | N/A |  | 3/24/2010 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
L20 | Birdsboro 13.2kV |  | PA | Berks | Withdrawn | ME | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l20_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2004 | N/A | N/A |  | 8/4/2004 |  | 3/31/2005 |  |  | N | No
L21 | Hudson #2 |  | NJ | Hudson | Withdrawn | PSEG | 0 |  | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2004 | N/A | N/A |  | 9/2/2004 |  | 1/1/2006 |  |  | N | No
M01 | Morgantown-Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 | 1800 | 1800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2004 | N/A | N/A |  | 3/18/2005 | Customer Milestone Not Met | 1/1/2008 |  |  | N | No
M02 | Jenkins-Harwood #2 | Mountain Top | PA | Luzerne | Withdrawn | PPL | 51 | 8.1 | 8.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m02_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m02_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/23/2004 | N/A | N/A |  | 5/18/2005 |  | 12/31/2005 |  |  | N | No
M03 | Cardiff |  | NJ | Atlantic | Withdrawn | AEC | 450 | 150 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m03_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2004 | N/A | N/A |  | 4/5/2005 | Customer Milestone Not Met | 6/1/2005 |  |  | N | No
M04 | Calvert Cliffs | Clavert Cliffs 1 and 2 | MD | Calvert | In Service | BGE | 1740 | 63 |  | 63 | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/25/2004 | N/A | N/A |  |  |  | 6/30/2005 |  | 6/30/2005 | N | No
M05 | Black Oak - Bedington | Black Oak - Bedington Wave Traps 500kV | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/m05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/m05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/m05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/5/2004 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | S | No
M06 | Grand Point |  | PA | Franklin | Withdrawn | APS | 30.5 | 30.5 | 30.5 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m06_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2004 | N/A | N/A |  | 10/20/2005 |  | 6/1/2006 |  |  | N | No
M07 | Peckville (Archbald) | Archbald | PA | Lackawanna | In Service | PPL | 50 | 6.3 | 6.3 | 6.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/12/2004 | N/A | N/A |  |  |  | 3/15/2004 |  | 3/15/2004 | N | No
M08 | Somerset-Allegheny | Stonycreek | PA | Somerset | Withdrawn | PENELEC | 65 | 65 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m08_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/29/2004 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
M09 | Island Road |  | PA | Philadelphia | Withdrawn | PECO | 50 | 50 |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/m09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/m09_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2004 | N/A | N/A |  |  | Customer Initiated Withdrawal | 8/31/2007 |  |  | S | No
M09_CE28 | Wempletown 345kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m09_ce28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2004 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 11/30/2006 |  |  | N | No
M10 | Vienna/Chalk Point |  | MD | Prince George's | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2004 | N/A | N/A |  | 10/28/2004 | Customer Initiated Withdrawal | 1/1/2008 |  |  | S | No
M11 | Susquehanna #1 | Susquehanna #1 | PA | Luzerne | In Service | PPL | 2520 | 111 | 111 | 111 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m11_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2004 | N/A | N/A |  |  |  | 7/24/2010 | 7/24/2010 | 7/24/2010 | N | No
M12 | Susquehanna #2 | Susquehanna #2 | PA | Luzerne | In Service | PPL | 2520 | 107 | 107 | 107 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m12_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2004 | N/A | N/A |  |  |  | 8/18/2011 | 8/18/2011 | 8/18/2011 | N | No
M13 | Amboy |  | IL | Lee | Withdrawn | ComEd | 3.3 | 3.3 | 3.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m13_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/27/2004 | N/A | N/A |  | 1/4/2005 | Customer Initiated Withdrawal | 6/1/2005 |  |  | N | No
M14 | Churchtown-Cumberland 230kV |  | NJ | Atlantic | Withdrawn | AEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2004 | N/A | N/A |  | 12/13/2004 | Customer Initiated Withdrawal | 6/15/2006 |  |  | N | No
M15 | Union City 230kV |  | PA | Erie | Withdrawn | PENELEC | 302 | 302 | 301.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m15_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2004 | N/A | N/A |  | 10/17/2005 | Customer Initiated Withdrawal | 6/1/2007 |  |  | N | No
M16 | Peach Bottom T1 |  | PA | York | Withdrawn | PECO | 0 |  |  |  | Energy | Merchant Transmission | Nuclear | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2004 | N/A | N/A |  | 12/7/2004 | Customer Initiated Withdrawal | 11/1/2005 |  |  | S | No
M17 | Mount Zion 13.8 kV |  | MD | Montgomery | Withdrawn | PEPCO | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2004 | N/A | N/A |  | 9/30/2004 |  | 5/1/2005 |  |  | N | No
M18 | Dixon-Mendota 34kV |  | IL | Lee | Withdrawn | ComEd | 1.65 | 1.65 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m18_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/17/2004 | N/A | N/A |  | 1/3/2006 |  | 12/31/2005 |  |  | N | No
M19 | Otter Point | Otter Point LF-1 | MD | Baltimore County | In Service | BGE | 4.5 | 4.5 |  | 4.5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m19_csa.pdf | Document Posted | N/A | N/A |  | 6/25/2004 | N/A | N/A |  |  |  | 9/1/2006 |  | 9/1/2006 | N | No
M20 | Chestnut Valley 25kV |  | PA | Fayette | Withdrawn | APS | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m20_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/13/2004 | N/A | N/A |  | 7/7/2006 | Customer Initiated Withdrawal | 5/30/2006 |  |  | N | No
M21 | Rochelle | City of Rochelle, IL | IL | Ogle | In Service | ComEd | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m21_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m21_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/23/2004 | N/A | N/A |  |  |  | 12/31/2006 | 12/31/2006 | 11/11/2005 | N | No
M22 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2004 | N/A | N/A |  | 10/23/2006 | Customer Milestone Not Met | 2/1/2008 |  |  | N | No
M23 | Henry 138kV | Mt Storm WF | WV | Grant | Withdrawn | APS | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m23_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m23_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m23_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m23_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2004 | N/A | N/A |  | 2/4/2016 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
M24 | Grassy Falls | Beech Ridge / Field Mtn WF | WV | Greenbrier | In Service | APS | 186 | 186 | 37.2 | 132.5 | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m24_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m24_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m24_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m24_csa.pdf | Document Posted | N/A | N/A | 12/17/2009 | 7/27/2004 | N/A | N/A | 1/15/2010 |  |  | 12/1/2014 | 12/1/2014 | 11/1/2007 | N | No
M25 | South Reading (United Corrstack) 69kV | United Corrstack | PA | Berks | Withdrawn | ME | 12 | 11 | 2 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m25_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/29/2004 | N/A | N/A |  | 11/18/2005 | Customer Milestone Not Met | 12/1/2006 |  |  | N | No
M26 | Champion | Beech Hollow | PA | Washington | Withdrawn | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m26_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m26_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2004 | N/A | N/A |  | 7/8/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
M27 | Eddystone 138kV | Eddystone | PA | Delaware | In Service | PECO | 1408 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2004 | N/A | N/A |  |  |  | 6/17/2004 |  | 12/1/2006 | N | No
M28 | Elwood-Dresden 345kV | Indeck-Elwood Energy Center | IL | Will | Withdrawn | ComEd | 700 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m28_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/30/2004 | N/A | N/A |  | 11/30/2006 | Customer Milestone Not Met | 12/31/2011 | 12/31/2011 |  | N | No
1267313 | PJM-FE |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2010 | 6/1/2011 | [6 empty] | FF | No
1302456 | PJM-TVA |  | N/A | N/A | Confirmed |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 5/1/2010 | 1/1/2015 | [6 empty] | FF | No
1363850 | CIN-PJM |  | N/A | N/A | Confirmed |  | 82 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2014 | 1/1/2019 | [6 empty] | FF | No
1363870 | CIN-PJM |  | N/A | N/A | Confirmed |  | 87 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2014 | 1/1/2014 | [6 empty] | FF | No
845542 | PJM-TVA |  | N/A | N/A | Confirmed |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/20/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
845546 | PJM-TVA |  | N/A | N/A | Confirmed |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/20/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
852544 | PJM-WEC |  | N/A | N/A | Confirmed |  | 10 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/8/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
930679 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 43 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/19/2008 | 1/1/2009 | 9/30/2035 | [6 empty] | FF | No
931128 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 25 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/19/2008 | 1/1/2009 | 9/30/2035 | [6 empty] | FF | No
931224 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 63 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/19/2008 | 6/1/2010 | 9/30/2035 | [6 empty] | FF | No
931229 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 62 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/19/2008 | 6/1/2012 | 9/30/2035 | [6 empty] | FF | No
931258 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 240 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/19/2008 | 1/1/2014 | 9/30/2035 | [6 empty] | FF | No
945095 | CIN-PJM |  | N/A | N/A | Confirmed |  | 368 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/15/2008 | 8/1/2008 | 8/1/2020 | [6 empty] | FF | No
963385 | PJM-CPLE |  | N/A | N/A | Confirmed |  | 89 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/11/2008 | 11/1/2008 | 11/1/2013 | [6 empty] | FF | No
999367 | FE-PJM |  | N/A | N/A | Withdrawn |  | 108 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/26/2008 | 10/1/2008 | 6/1/2009 | [6 empty] | FF | No
N01 | Graceton-Nottingham 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2004 | N/A | N/A |  | 8/30/2005 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
N02 | Peach Bottom |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2004 | N/A | N/A |  | 8/30/2005 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
N02_AEP139 | McClung 138kV |  | WV | Greenbrier | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n02_aep139_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2004 | N/A | N/A |  | 6/23/2005 | Customer Milestone Not Met | 9/1/2006 |  |  | N | No
N03 | Edgemoor 69kV | Hay Road 2 | DE | New Castle | In Service | DPL | 121 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/25/2004 | N/A | N/A |  |  |  | 8/9/2004 |  | 6/1/2006 | N | No
N04 | Edgemoor 230kV |  | DE | New Castle | Withdrawn | DPL | 189 | 8 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2004 | N/A | N/A |  | 10/12/2004 |  | 8/9/2004 |  |  | N | No
N05 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 242 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/25/2004 | N/A | N/A |  |  |  | 8/9/2004 |  | 6/1/2006 | N | No
N06 | Hamilton 12kV | Pine Hurst Acres | PA | Northumberland | In Service | PPL | 0.047 | 0.047 |  | 0.047 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n06_csa.pdf | Document Posted | N/A | N/A |  | 9/16/2004 | N/A | N/A |  |  |  | 3/1/2005 |  | 3/1/2005 | N | No
N07 | Monterey 69kV | Highland New Wind | VA | Highland | Withdrawn | APS | 39 | 39 | 7.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n07_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n07_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/n07_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/28/2004 | N/A | N/A | 4/29/2021 | 3/10/2020 |  | 4/29/2021 | 4/29/2021 |  | N | No
N08 | Dans Mountain |  | PA | Allegheny | Withdrawn | APS | 125 | 125 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2004 | N/A | N/A |  | 9/1/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N09 | Grassy Falls 138kV | West Greenbrier | WV | Greenbrier | Withdrawn | APS | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n09_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/4/2004 | N/A | N/A |  | 8/26/2008 |  | 3/31/2009 | 3/31/2009 |  | N | No
N10 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 300 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/11/2004 | N/A | N/A |  |  |  | 6/1/2005 | 6/1/2005 | 6/1/2005 | N | No
N11 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 275 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/11/2004 | N/A | N/A |  |  |  | 6/1/2005 | 6/1/2005 | 6/1/2005 | N | No
N12 | North Haverhill 69 kV | North Haverhill | OH | Scioto | In Service | AEP | 75 | 75 | 75 | 75 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n12_csa.pdf | Document Posted | N/A | N/A |  | 10/13/2004 | N/A | N/A |  |  |  | 6/1/2009 | 6/1/2009 | 6/1/2009 | N | No
N13 | Beaver Valley |  | PA | Beaver | In Service | DL | 1652 | 1630 | 1630 | 1630 | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2004 | N/A | N/A |  |  |  | 1/1/2005 |  | 1/1/2005 | N | No
N14 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 24 | 5.4 | 24 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n14_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n14_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n14_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2004 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
N15 | LaSalle 138 kV | Grand Ridge Energy LLC | IL | Lasalle | In Service | ComEd | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n15_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n15_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n15_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n15_csa.pdf | Document Posted | N/A | N/A |  | 12/2/2004 | N/A | N/A |  |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | N | No
N16 | Kent-Harrington 69kV | Central Landfill Units 1-4 | DE | New Castle | In Service | DPL | 4 | 4 |  | 4 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n16_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/9/2004 | N/A | N/A |  |  |  | 12/7/2006 | 12/7/2006 | 12/7/2006 | N | No
N17 | Laurel-Sussex 69kV | Southern Landfill Units 1-4 | DE | New Castle | In Service | DPL | 3 | 3 |  | 3 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/9/2004 | N/A | N/A |  |  |  | 10/24/2006 |  | 10/24/2006 | N | No
N18 | Clinton-Collier 345kV |  | PA | Allegheny | Withdrawn | DL | 19.2 | 19.2 | 19.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2004 | N/A | N/A |  | 2/16/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N19 | Paw Paw 12 kV |  | IL | Lee | Withdrawn | ComEd | 1.65 | 1.65 | 1.65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n19_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/28/2004 | N/A | N/A |  | 9/6/2005 | Customer Milestone Not Met | 3/31/2006 |  |  | N | No
N20 | Poplar Grove 34kV |  | IL | Boone | Withdrawn | ComEd | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2005 | N/A | N/A |  | 2/17/2005 | Customer Initiated Withdrawal | 12/29/2005 |  |  | N | No
N21 | Sublette Wind II | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 30 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n21_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N22 | Sublette Wind 3 | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 30 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n22_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N23 | West Brooklyn Wind 3 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 53 | 53 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n23_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N24 | West Brooklyn 4 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 53 | 53 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n24_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N25 | West Brooklyn 5 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 11 | 11 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n25_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N26 | Daleville | SECCRA LF | PA | Chester | In Service | PECO | 1.74 | 1.74 | 1.7 | 1.7 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n26_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2005 | N/A | N/A |  |  |  | 12/31/2009 | 12/31/2009 | 12/31/2009 | N | No
N27 | Pequest River 34.5 kV | Warren County LF | NJ | Warren | In Service | JCPL | 3.6 | 3.6 | 3.6 | 3.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n27_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n27_csa.pdf | Document Posted | N/A | N/A |  | 1/27/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
N28 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 165 | 40 | 40 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2005 | N/A | N/A |  | 6/24/2005 | Customer Milestone Not Met | 2/1/2007 |  |  | N | No
N29 | Roth Rock 138kV |  | MD | Garrett | Withdrawn | APS | 40 | 40 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n29_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n29_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 9/5/2007 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
N30 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 5 | 5 |  |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n30_fea.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 4/3/2007 | Customer Initiated Withdrawal | 12/31/2007 | 12/31/2007 |  | N | No
N31 | Freemansburg 69kV | Bethlehem LF | PA | Northampton | Deactivated | PPL | 5 | 5 |  | 5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n31_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/n31_wmpa.pdf |  | Not Required | N/A | N/A | 5/1/2007 | 1/28/2005 | N/A | N/A | 7/1/2007 |  |  | 5/1/2008 | 5/1/2008 | 5/1/2008 | N | No
N32 | Gans 138kV | South Chestnut WF | PA | Fayette | In Service | APS | 50.4 | 50.4 | 10.1 | 50.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n32_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n32_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n32_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 12/24/2011 | N | No
N33 | Afton 138kV | North Briery WF | WV | Preston | Withdrawn | APS | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n33_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n33_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n33_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n33_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 2/16/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
N34 | Motiva | Delaware City | DE | New Castle | In Service | DPL | 250 | 250 | 142 | 250 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n34_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 12/31/2005 | 12/31/2005 | 12/31/2005 | N | No
N35 | South Reading-Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n35_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 12/14/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N36 | Gold-Sabinsville 115kV | Gold Sabinsville | PA | Potter | Withdrawn | PENELEC | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n36_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 1/15/2014 | Customer Initiated Withdrawal | 12/15/2014 | 12/15/2014 |  | N | No
N37 | Windsor 138kV |  | PA | Washington | Withdrawn | APS | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 11/1/2005 | Customer Initiated Withdrawal | 11/1/2006 |  |  | N | No
N38 | W. Newton-Lynn 138kV |  | OH | Hardin | Withdrawn | AEP | 120 | 120 | 24 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 8/2/2005 | Customer Initiated Withdrawal | 11/1/2006 |  |  | N | No
N39 | Johnstown-Altoona 230kV | Allegheny Ridge WF1 | PA | Cambria | In Service | PENELEC | 80 | 80 | 16 | 80 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n39_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n39_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n39_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n39_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 3/15/2007 | 3/15/2007 | 11/1/2006 | N | No
N40 | Champion 345kV |  | PA | Washington | Withdrawn | DL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n40_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 9/6/2005 | Customer Initiated Withdrawal | 5/31/2009 |  |  | N | No
N41 | Mountaineer 765kV |  | WV | Mason | Withdrawn | AEP | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n41_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 10/21/2008 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
N42 | Mountaineer-Belmont 765kV |  | OH | Meigs | Withdrawn | AEP | 1200 | 1200 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n42_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 12/1/2011 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
N43 | Hanging Rock-Jefferson 765kV |  | KY | Lewis | Withdrawn | AEP | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n43_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/28/2006 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
N44 | Dover |  | DE | Kent | Withdrawn | DPL | 103 | 1 | 1 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n44_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n44_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 10/11/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
N45 | Ft. Martin 500kV |  | WV | Monongalia | Withdrawn | APS | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n45_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 12/14/2005 | Customer Initiated Withdrawal | 1/31/2010 |  |  | N | No
N46 | Cook 345kV |  | MI | Berrien | Withdrawn | AEP | 1120 | 1120 | 1120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 10/18/2005 | Customer Initiated Withdrawal | 6/1/2009 |  |  | N | No
N47 | Beryl 138kV | Pinnacle WF | WV | Mineral | In Service | APS | 85 | 85 | 17 | 55.2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n47_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n47_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n47_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n47_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2005 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 11/16/2011 | N | No
N48 | Lancaster-Maryland 138kV |  | IL | Ogle | Withdrawn | ComEd | 84 | 84 | 84 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/11/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N49 | Salix-Claysburg 115kV |  | PA | Cambria | Withdrawn | PENELEC | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
N50 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 90 | 90 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n50_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
N51 | Harwood 230kV |  | PA | Carbon | Withdrawn | PPL | 100.5 | 100.5 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n51_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
O01 | Letort 12kV | Frey Farms LF | PA | Lancaster | Withdrawn | PPL | 3.2 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o01_csa.pdf | Document Posted | N/A | N/A | 12/1/2005 | 2/8/2005 | N/A | N/A | 1/3/2006 | 5/26/2011 | Customer Initiated Withdrawal | 1/12/2006 | 1/12/2006 | 1/12/2006 | N | No
O02 | Glendon 34.5kV |  | PA | Northampton | Withdrawn | PPL | 3 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o02_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/8/2005 | N/A | N/A |  | 8/16/2006 | Customer Milestone Not Met | 12/31/2006 | 12/31/2006 |  | N | No
O03 | Sublette | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 11 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o03_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/11/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
O04 | Camden-Richmond |  | NJ | Camden | Withdrawn | PSEG | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2005 | N/A | N/A |  | 2/1/2006 | Customer Initiated Withdrawal | 6/1/2008 |  |  | N | No
O05 | Rochelle | City of Rochelle | IL | Ogle | In Service | ComEd | 22 | 22 | 2 | 22 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/22/2005 | N/A | N/A |  |  |  | 12/31/2006 | 12/31/2006 | 6/30/2005 | N | No
O06 | Ft. Martin Pruntytown |  | WV | Taylor | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o06_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2005 | N/A | N/A |  | 6/13/2006 |  | 6/1/2008 |  |  | S | No
O06_DP01 | Altavista 115kV | Pittsylvania | VA | Pittsylvania | In Service | Dominion | 83.6 | 4 | 4 | 3.4 | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o06_dp01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o06_dp01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o06_dp01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/24/2005 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
O07 | Poplar Grove 34.5kV | Boone Heritage WF | IL | Boone | Withdrawn | ComEd | 25 | 25 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o07_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/1/2005 | N/A | N/A |  | 3/22/2007 | Customer Initiated Withdrawal | 6/30/2007 |  |  | N | No
O08 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2005 | N/A | N/A | [6 empty] | S | No
O09 | Normandy | Walnut Ridge Wind, LLC | IL | Lee | In Service | ComEd | 212 | 212 | 42.4 | 212 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o09_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o09_csa.pdf | Document Posted | N/A | N/A |  | 3/7/2005 | N/A | N/A |  |  |  | 10/15/2018 | 10/15/2018 | 10/31/2018 | N | No
O10 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 242 | 7 | 7 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/14/2005 | N/A | N/A |  |  |  | 6/1/2005 |  | 6/1/2005 | N | No
O11 | Bustelton 13kV | Burlington Co LF | NJ | Burlington | Deactivated | PSEG | 7.2 | 7 | 7 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o11_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2005 | N/A | N/A |  |  |  | 8/28/2007 | 8/28/2007 | 6/1/2007 | N | No
O12 | Chicago Heights 138kV | Geneva Energy LLC | IL | Adams | Deactivated | ComEd | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2005 | N/A | N/A | 11/17/2005 |  |  | 12/31/2006 | 12/31/2006 | 12/1/2005 | N | No
O13 | Linden - Harbor Cable II |  | NJ | Union | Withdrawn | PSEG | 520 |  |  |  | Energy | Merchant Transmission |  | DC | F/TWR/520 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 2/1/2008 |  |  | S | No
O14 | Black Oak - Bedinton RTU |  | MD | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/5/2005 | N/A | N/A |  | 8/14/2006 | Customer Milestone Not Met |  |  |  | S | No
O15 | Black Oak - Hatfield Wave Trap |  | PA | Greene | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o15_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/6/2005 | N/A | N/A |  | 10/3/2006 | Customer Initiated Withdrawal |  |  |  | S | No
O16 | Chichester-Linwood 230kV | FPL Energy Markus Hook | PA | Delaware | In Service | PECO | 230 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/o16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/o16_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2005 | N/A | N/A |  |  |  | 6/19/2005 |  | 6/19/2005 | S | No
O17 | Somerset-Allegheny 115kV | Stoney Creek WF | PA | Somerset | Withdrawn | PENELEC | 65 | 65 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o17_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o17_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/14/2005 | N/A | N/A |  | 1/6/2009 | Customer Milestone Not Met | 12/1/2009 | 12/1/2009 |  | N | No
O18 | Salix-Claysburg (Krayn) 115kV | Highland WF | PA | Somerset | In Service | PENELEC | 65 | 65 | 13 | 62.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o18_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2005 | N/A | N/A | 1/14/2009 |  |  | 12/18/2008 | 12/18/2008 | 12/18/2008 | N | No
O19 | Somerset 115kV | Somerset (Kimberly Run) WF | PA | Somerset | Withdrawn | PENELEC | 33 | 33 | 6.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o19_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o19_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o19_csa.pdf | Document Posted | N/A | N/A |  | 5/4/2005 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 5/31/2013 | 5/31/2013 |  | N | No
O20 | Lakehurst 34.5kV | Ocean Energy LF | NJ | Ocean | Deactivated | JCPL | 9.4 | 9.4 | 9.4 | 9.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o20_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/o20_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/4/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
O21 | Liberty 69kV |  | OH | Logan | Withdrawn | Dayton | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o21_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2005 | N/A | N/A |  | 10/6/2009 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
O22 | Powerton-Goodings Grove 345kV | Top Crop Generating Facility | IL | Livingston | In Service | ComEd | 300 | 300 | 60 | 300 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o22_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o22_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o22_csa.pdf | Document Posted | N/A | N/A | 10/17/2009 | 5/11/2005 | N/A | N/A | 10/23/2009 |  |  | 10/25/2010 | 10/25/2010 | 10/25/2010 | N | No
O23 | Powerton-Dresden 345kV | Top Crop Wind Farm | IL | Livingston | Withdrawn | ComEd | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o23_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o23_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o23_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 5/11/2005 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
O24 | Pontiac Midpoint-Dresden 345kV | Bright Stalk WF | IL | Livingston | Withdrawn | ComEd | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o24_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o24_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o24_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 5/11/2005 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
O25 | N. Salisbury 25kV | Newland Park LF | MD | Wicomico | In Service | DPL | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o25_csa.pdf | Document Posted | N/A | N/A |  | 5/12/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
O26 | Pine Grove 69kV | Guilford Mills LF | PA | Schuylkill | In Service | PPL | 8 | 8 | 8 | 6 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o26_csa.pdf | Document Posted | N/A | N/A |  | 5/12/2005 | N/A | N/A |  |  |  | 6/30/2008 | 6/30/2008 | 6/30/2008 | N | No
O27 | Powerton-Goodings Grove 345kV |  | IL | Livingston | Withdrawn | ComEd | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o27_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o27_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/13/2005 | N/A | N/A |  | 5/15/2012 | Customer Initiated Withdrawal | 5/31/2015 | 5/31/2015 |  | N | No
O28 | Jenkins-Harwood #2 69kV | Penobscot Mountain WF | PA | Luzerne | Withdrawn | PPL | 51 | 51 | 10.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o28_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 5/13/2005 | N/A | N/A |  | 4/15/2010 | Customer Initiated Withdrawal | 11/30/2011 | 11/30/2011 |  | N | No
O29 | Normandy 138kV | Green River Wind Farm Phase 2 | IL | Lee | In Service | ComEd | 225 | 225 | 45 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o29_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o29_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o29_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o29_csa.pdf | Document Posted | N/A | N/A |  | 5/16/2005 | N/A | N/A | 10/1/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/25/2019 | N | No
O30 | Nora |  | IL | JoDaviess | Withdrawn | ComEd | 9 | 9 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/16/2005 | N/A | N/A |  | 7/25/2005 | Customer Initiated Withdrawal | 10/1/2006 |  |  | N | No
O31 | Fries 12kV | Fries Hydorelectric Plant | VA | Grayson | In Service | AEP | 5.21 | 5.21 | 5.21 | 5.21 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o31_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o31_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o31_csa.pdf | Document Posted | N/A | N/A |  | 5/18/2005 | N/A | N/A |  |  |  | 12/31/2006 |  | 12/31/2006 | N | No
O32 | Mountaineer 765kV | Mountaineer #1 | WV | Mason | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/31/2005 | N/A | N/A |  |  |  | 5/31/2005 | 5/31/2005 | 5/31/2005 | N | No
O33 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 20 | 20 | 4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o33_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o33_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/o33_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/2/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
O34 | Frederick 12kV |  | MD | Frederick | Withdrawn | APS | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/3/2005 | N/A | N/A |  | 10/6/2005 | Customer Initiated Withdrawal | 5/1/2006 |  |  | N | No
O35 | Providence Heights #1 138kV | Providence Heights WF | IL | Bureau | In Service | ComEd | 74 | 74 | 14.8 | 74 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o35_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o35_csa.pdf | Document Posted | N/A | N/A | 6/2/2008 | 6/6/2005 | N/A | N/A | 6/2/2008 |  |  | 6/26/2008 | 6/26/2008 | 6/30/2007 | N | No
O36 | Honey Brook 12kV | Honeybrook | PA | Chester | In Service | PPL | 1.6 | 1.6 | 0 | 1.6 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o36_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/o36_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/6/2005 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
O37 | Belle 46kV |  | WV | Kanawha | Withdrawn | AEP | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o37_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2005 | N/A | N/A |  | 4/12/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
O38 | Johnstown-Altoona 230kV | North Alleghney WF | PA | Cambria | In Service | PENELEC | 50 | 50 | 10 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o38_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o38_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  |  |  | 9/1/2009 | 9/1/2009 | 12/15/2007 | N | No
O39 | Sunbury - Dauphin 69kV | Mahantango WF | PA | Dauphin | Withdrawn | PPL | 56 | 56 | 11.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o39_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o39_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o39_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o39_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  | 5/18/2010 | Customer Initiated Withdrawal | 6/1/2010 | 6/1/2010 |  | N | No
O40 | Pine Grove - Frailey 69kV | Pine Grove WF | PA | Schuylkill | Withdrawn | PPL | 28 | 28 | 5.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o40_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o40_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o40_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  | 4/1/2011 | Customer Initiated Withdrawal | 7/1/2012 | 7/1/2012 |  | N | No
O42 | Cook 345 kV | Cook #1 | MI | Berrien | In Service | AEP | 1100 | 84 | 84 | 84 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o42_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/6/2005 | N/A | N/A |  |  |  | 1/19/2007 | 1/19/2007 | 12/31/2006 | N | No
O43 | University Park | University Park North Energy Center | IL | Will | In Service | ComEd | 504 | 54 | 54 | 54 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o43_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o43_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/7/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 12/19/2011 | N | No
O44 | West Lima 138kV |  | OH | Allen | Withdrawn | AEP | 540 | 540 | 540 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2005 | N/A | N/A |  | 1/23/2006 |  | 6/1/2007 | 6/1/2007 |  | N | No
O45 | Grassy Falls | University Park | WV | Greenbrier | Withdrawn | APS | 143 | 143 | 143 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o45_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o45_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/o45_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2005 | N/A | N/A |  | 1/6/2009 | Customer Initiated Withdrawal | 11/1/2007 |  |  | S | No
O46 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 2 | 0.4 | 2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o46_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o46_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o46_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o46_csa.pdf | Document Posted | N/A | N/A |  | 7/22/2005 | N/A | N/A |  |  |  | 12/1/2007 |  | 12/1/2007 | N | No
O47 | Nora |  | IL | JoDaviess | Withdrawn | ComEd | 10 | 10 | 2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o47_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/25/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
O48 | Hays Mill - Lookout 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 36 | 36 | 7.2 | 36 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o48_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o48_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2005 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
O49 | Wempletown-Byron 345kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o49_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o49_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/26/2005 | N/A | N/A |  | 8/2/2012 | Customer Milestone Not Met | 12/31/2012 | 12/31/2012 |  | N | No
O50 | Powerton-Dresden 345kV | Minonk Wind Farm | IL | Woodford | In Service | ComEd | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o50_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o50_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o50_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o50_csa.pdf | Document Posted | N/A | N/A | 10/16/2012 | 7/26/2005 | N/A | N/A | 10/31/2012 |  |  | 12/31/2012 | 12/31/2012 | 10/31/2012 | N | No
O51 | Pontiac Midpoint-Wilton Center 345kV | Cayuga Ridge South WF | IL | Livingston | In Service | ComEd | 300 | 300 | 60 | 300 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o51_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o51_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o51_csa.pdf | Document Posted | N/A | N/A | 9/29/2009 | 7/27/2005 | N/A | N/A | 10/26/2009 |  |  | 5/6/2010 | 5/6/2010 | 12/31/2007 | N | No
O52 | Gold-Potter Co 115kV | Potter WF | PA | Potter | Withdrawn | PENELEC | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o52_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o52_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o52_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2005 | N/A | N/A |  | 5/8/2013 | Customer Initiated Withdrawal | 12/25/2014 | 12/25/2014 |  | N | No
O53 | Beaver Valley #1 | Beaver Valley 1 | PA | Beaver | In Service | DL | 902 | 81 | 81 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/27/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 9/15/2006 | N | No
O54 | Beaver Valley #2 | Beaver Valley 2 | PA | Beaver | In Service | DL | 908 | 77 | 77 | 54 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o54_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o54_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/27/2005 | N/A | N/A |  |  |  | 7/1/2008 | 7/1/2008 | 10/23/2006 | N | No
O55 | Peckville 69kV |  | PA | Lackawanna | Withdrawn | PPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o55_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/27/2005 | N/A | N/A |  | 7/17/2006 | Customer Milestone Not Met | 1/1/2007 |  |  | N | No
O56 | Osterburg East 115kV | Dunning Mountain WF | PA | Bedford | Withdrawn | PENELEC | 76 | 76 | 15.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o56_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o56_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o56_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o56_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o56_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2005 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 3/1/2013 | 3/1/2013 |  | N | No
O57 | Kanawha 138kV |  | WV | Fayette | Withdrawn | AEP | 142 | 142 |  |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2005 | N/A | N/A |  | 4/18/2006 | Customer Milestone Not Met | 6/1/2006 |  |  | N | No
O58 | Tenn Eastman 138kV |  | TN | Sullivan | Withdrawn | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o58_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o58_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o58_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/28/2005 | N/A | N/A |  | 8/14/2008 | Customer Milestone Not Met | 6/1/2007 |  |  | N | No
O59 | Gold 115kV | Gold | PA | Potter | Withdrawn | PENELEC | 99 | 99 | 19.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o59_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 12/21/2009 | Customer Initiated Withdrawal | 12/1/2009 | 12/1/2009 |  | N | No
O60 | Berlin 23 kV | AMP Berlin WF | PA | Somerset | Withdrawn | PENELEC | 5.4 | 5.4 | 1.08 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o60_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o60_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o60_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 4/9/2014 | Customer Initiated Withdrawal | 1/31/2012 | 1/31/2012 |  | N | No
O61 | Lawrenceville 34.5kV |  | VA | Brunswick | Withdrawn | Dominion | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 3/9/2007 | Customer Initiated Withdrawal | 1/31/2007 |  |  | N | No
O62 | Shackleford 34.5kV |  | VA | King and Queen | Withdrawn | Dominion | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o62_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 4/27/2006 | Customer Milestone Not Met | 10/31/2006 |  |  | N | No
O63 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o63_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 6/1/2009 |  |  | N | No
O64 | Grays Ferry - Island Road |  | PA | Philadelphia | Withdrawn | PECO | 201 | 201 | 201 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o64_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 2/11/2006 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
O65 | Olive-Dumont 345kV |  | IN | St. Joseph | Withdrawn | AEP | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 10/17/2005 | Customer Initiated Withdrawal | 7/1/2010 |  |  | N | No
O66 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | JCPL | 670 | 670 | 320 |  | Capacity | Merchant Transmission |  | DC | NF/TWR 320/NFTWR 673 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o66_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/o66_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/o66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/o66_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2005 | N/A | N/A | 4/4/2013 |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
O67 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A | [6 empty] | S | No
O68 | Dixon-Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o68_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o68_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 11/15/2011 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
O69 | Beaver Creek-Hazard 138kV |  | KY | Perry | Withdrawn | AEP | 535 | 535 | 535 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o69_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 6/30/2006 | Customer Milestone Not Met | 7/1/2009 |  |  | N | No
O70 | Susquehanna - Harwood 230kV | Nescopeck WF | PA | Luzerne | Withdrawn | PPL | 124 | 124 | 24.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o70_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o70_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o70_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 5/9/2011 | Customer Initiated Withdrawal | 12/1/2011 | 12/1/2011 |  | N | No
O71 | Hooversville 115kV |  | PA | Somerset | Withdrawn | PENELEC | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o71_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 4/12/2006 | Customer Initiated Withdrawal | 11/30/2007 |  |  | N | No
O72 | Hooversville-Central City | Shaffer Mountain WF | PA | Somerset | Withdrawn | PENELEC | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o72_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o72_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o72_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o72_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 6/12/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
O73 | Benson 345kV |  | IL | Woodford | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o73_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 11/15/2011 | Customer Initiated Withdrawal | 12/31/2010 | 12/31/2010 |  | N | No
P01 | Westover-Madera 115kV | Rock Run Wind Park | PA | Cambria | Withdrawn | PENELEC | 65 | 65 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p01_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p01_csa.pdf | Document Posted | N/A | N/A |  | 8/23/2005 | N/A | N/A |  | 1/4/2013 | Customer Initiated Withdrawal | 12/31/2011 | 12/31/2011 |  | N | No
P02 | Ohio Central 138kV |  | OH | Muskingum | Withdrawn | AEP | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2005 | N/A | N/A |  | 8/14/2006 | Customer Initiated Withdrawal | 6/1/2007 |  |  | N | No
P03 | Frackville-Hauto #3 | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 1.3 | 1.3 | 1.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p03_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p03_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p03_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2005 | N/A | N/A |  |  |  | 12/31/2007 |  | 12/31/2007 | N | No
P04 | Peach Bottom 500kV | Delta | PA | York | In Service | PECO | 557 | 550 | 550 | 550 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p04_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p04_csa.pdf | Document Posted | N/A | N/A |  | 9/8/2005 | N/A | N/A | 12/21/2010 |  |  | 3/1/2011 | 3/1/2011 | 3/1/2011 | N | No
P05 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2005 | N/A | N/A |  | 6/12/2006 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
P06 | Cumberland 230 kV | Cumberland 2 | NJ | Cumberland | In Service | AEC | 225 | 225 | 225 | 100 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p06_csa.pdf | Document Posted | N/A | N/A | 2/6/2009 | 9/9/2005 | N/A | N/A | 5/4/2009 |  |  | 6/1/2016 | 6/1/2016 | 12/31/2008 | N | No
P07 | Middle 138kV |  | NJ | Cape May | Withdrawn | AEC | 122 | 122 | 122 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p07_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2005 | N/A | N/A |  | 6/16/2006 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
P08 | Possum Point |  | VA | Prince William | Withdrawn | Dominion | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p08_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/14/2005 | N/A | N/A |  | 4/24/2009 | Customer Milestone Not Met | 6/1/2014 | 6/1/2014 |  | N | No
P09 | Kerr Dam 115kV | John H. Kerr Dam Hydro Units 1(15MW), 2-7(42MW) | VA | Mecklenburg | In Service | Dominion | 267 | 27 | 27 | 27 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/14/2005 | N/A | N/A |  |  |  | 1/19/2011 | 1/19/2011 | 1/19/2011 | N | No
P10 | LaSalle 138kV | Grand Ridge WF | IL | Lasalle | In Service | ComEd | 190.5 | 190.5 | 37.2 | 135 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p10_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p10_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p10_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p10_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2005 | N/A | N/A |  |  |  | 12/1/2013 | 12/1/2013 | 6/1/2010 | N | No
P11 | Kewanee 138kV | Bishop Hill WF | IL | Mercer | In Service | ComEd | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p11_csa.pdf | Document Posted | N/A | N/A | 2/1/2012 | 9/26/2005 | N/A | N/A | 2/16/2012 |  |  | 10/1/2011 | 10/1/2011 | 2/24/2012 | N | No
P12 | Cheswick - Springdale 138kV |  | PA | Allegheny | Withdrawn | DL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2005 | N/A | N/A |  | 4/28/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P13 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/5/2005 | N/A | N/A |  | 6/27/2006 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
P14 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 80 | 80 | 16 | 80 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p14_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p14_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p14_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/12/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
P15 | McGirr - Mendota 138kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2005 | N/A | N/A |  | 2/2/2006 | Customer Initiated Withdrawal | 12/1/2006 |  |  | N | No
P16 | Bath County | Bath County | VA | Bath | In Service | Dominion | 3030 | 340 | 340 | 340 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p16_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p16_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p16_csa.pdf | Document Posted | N/A | N/A |  | 10/19/2005 | N/A | N/A |  |  |  | 12/1/2009 | 12/1/2009 | 12/1/2009 | N | No
P17 | Dixon-Mendota 34kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2005 | N/A | N/A |  | 2/2/2006 | Customer Initiated Withdrawal | 9/30/2006 |  |  | N | No
P18 | Dixon-Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 2.5 | 2.5 | 0.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p18_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/20/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
P19 | McGirr Road - Mendota 138kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2005 | N/A | N/A |  | 2/2/2006 | Customer Initiated Withdrawal | 12/31/2006 |  |  | N | No
P20 | Nelson-Electric Junction 345kV | Walnut Ridge Wind Farm | IL | Bureau | Withdrawn | ComEd | 210 | 210 | 42 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p20_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p20_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p20_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2005 | N/A | N/A |  | 12/14/2016 |  | 12/31/2017 | 12/31/2017 |  | N | No
P21 | McGirr Road - Dixon 138kV |  | IL | Bureau | Withdrawn | ComEd | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2005 | N/A | N/A |  | 10/24/2006 | Customer Milestone Not Met | 9/15/2007 |  |  | N | No
P22 | Johnstown Altoona 230kV | North Allegheny WF | PA | Cambria | In Service | PENELEC | 20 | 20 | 4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p22_csa.pdf | Document Posted | N/A | N/A |  | 10/28/2005 | N/A | N/A |  |  |  | 9/1/2009 | 9/1/2009 | 9/1/2009 | N | No
P23 | Bayonne 138kV |  | NJ | Hudson | Withdrawn | PSEG | 46 | 46 | 45.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p23_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p23_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/28/2005 | N/A | N/A |  | 2/18/2009 | Customer Milestone Not Met | 1/1/2009 | 1/1/2009 |  | N | No
P24 | Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p24_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/1/2008 | 12/1/2008 |  | N | No
P25 | Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p25_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/1/2008 | 12/1/2008 |  | N | No
P26 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 9.5 | 9.5 | 1.9 | 9.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p26_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p26_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
P27 | Winchester 34.5 kV | Bethel LF | VA | Unknown | In Service | Dominion | 13 | 13 | 13 | 13 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p27_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p27_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p27_csa.pdf | Document Posted | N/A | N/A |  | 11/18/2005 | N/A | N/A |  |  |  | 1/25/2008 | 1/25/2008 | 1/25/2008 | N | No
P28 | Mehoopany 115kV | Mehoopany WF | PA | Wyoming | In Service | PENELEC | 150 | 150 | 30 | 148 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p28_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2005 | N/A | N/A |  |  |  | 1/21/2013 | 1/21/2013 | 1/9/2013 | N | No
P29 | Hunterstown 500/230kV |  | PA | Adams | Withdrawn | ME | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/p29_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/2005 | N/A | N/A |  | 5/17/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P30 | Bellefonte - N. Proctorville 138kV | South Point | OH | Lawrence | Withdrawn | AEP | 185 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p30_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p30_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/30/2005 | N/A | N/A |  | 3/21/2012 | Customer Milestone Not Met | 12/31/2012 | 12/31/2012 |  | N | No
P31 | Bath County |  | VA | Highland | In Service | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/p31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/p31_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/p31_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/p31_csa.pdf | Document Posted | N/A | N/A |  | 12/5/2005 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | S | No
P32 | White Oak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 19.5 | 19.5 |  | 19.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/7/2005 | N/A | N/A |  |  |  | 12/31/2007 |  | 12/31/2007 | N | No
P33 | Laurel - Sussex 69kV | Southern Landfill Units 1-4 | DE | Sussex | In Service | DPL | 4.25 | 1 |  | 1 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p33_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p33_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/8/2005 | N/A | N/A |  |  |  | 10/24/2006 |  | 10/24/2006 | N | No
P34 | Washington Landfill |  | PA | Washington | In Service | APS | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p34_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p34_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/20/2005 | N/A | N/A |  |  |  | 3/17/2009 | 3/17/2009 | 12/31/2006 | N | No
P35 | Pleasantville | Pleasantville /AC LF Unit 2 | NJ | Atlantic | Deactivated | AEC | 4 | 2 | 2 | 1.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p35_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p35_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2005 | N/A | N/A |  |  |  | 7/31/2006 |  | 7/31/2006 | N | No
P36 | Nelson - Lee Co. EC 345kV | Big Sky | IL | Bureau | In Service | ComEd | 240 | 240 | 48 | 240 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p36_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p36_csa.pdf | Document Posted | N/A | N/A |  | 12/22/2005 | N/A | N/A |  |  |  | 8/31/2010 | 8/31/2010 | 8/31/2010 | N | No
P37 | Normandy 138kV |  | IL | Bureau | Withdrawn | ComEd | 140 | 140 | 28 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p37_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p37_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/22/2005 | N/A | N/A |  | 7/17/2013 | Customer Initiated Withdrawal | 5/31/2013 | 5/31/2013 |  | N | No
P38 | Bremo 230kV | Bremo | VA | Buckingham | In Service | Dominion | 675 | 675 | 625 | 675 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p38_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p38_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p38_csa.pdf | Document Posted | N/A | N/A | 7/21/2010 | 12/22/2005 | N/A | N/A |  |  |  | 3/30/2011 | 3/30/2011 | 3/30/2011 | N | No
P39 | Kewanee-Powerton 138kV |  | IL | Stark | Withdrawn | ComEd | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2005 | N/A | N/A |  | 3/2/2011 | Customer Milestone Not Met | 12/1/2008 | 12/1/2008 |  | N | No
P40 | Crescent Ridge 138kV | Providence Heights WF | IL | Bureau | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p40_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2005 | N/A | N/A |  | 2/21/2013 | Customer Initiated Withdrawal | 11/12/2010 | 11/12/2010 |  | N | No
P41 | South Reading - Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p41_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/3/2006 | N/A | N/A |  | 6/28/2006 | Customer Milestone Not Met | 9/30/2006 |  |  | N | No
P42 | West Kingsport 138kV | West Kingsport | TN | Sullivan | Deactivated | AEP | 50 | 50 | 45 | 45 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p42_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/2006 | N/A | N/A |  |  |  | 1/8/2007 | 1/8/2007 | 1/8/2007 | N | No
P43 | Weyerhaeuser 115kV | Domtar Paper Company Generating Units 7-10 | NC | Martin | In Service | Dominion | 62.5 | 62.5 | 50 | 62.5 | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p43_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p43_csa.pdf | Document Posted | N/A | N/A |  | 1/13/2006 | N/A | N/A |  |  |  | 10/1/2021 | 10/1/2021 | 1/1/2010 | N | No
P44 | City of Columbus | Columbus Floodwall | OH | Franklin | In Service | AEP | 7.47 | 7.47 | 7 | 7 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p44_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p44_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p44_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/16/2006 | N/A | N/A |  |  |  | 12/31/2006 |  | 12/31/2006 | N | No
P45A | Thompson 115kV |  | PA | Wayne | Withdrawn | PPL | 120 | 120 | 24 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p45a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p45a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p45a_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/17/2006 | N/A | N/A |  | 9/1/2009 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
P45B | Mt. Storm 500kV |  | WV | Unknown | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2006 | N/A | N/A |  | 10/3/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P46 | Lena 138kV | EcoGrove WF (67 WT) | IL | JoDaviess | In Service | ComEd | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p46_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p46_csa.pdf | Document Posted | N/A | N/A | 2/11/2009 | 1/23/2006 | N/A | N/A | 2/11/2009 |  |  | 3/11/2009 | 3/11/2009 | 10/1/2007 | N | No
P47 | Mansfield-S. Troy 115kV | Armenia Mountain WF | PA | Bradford | In Service | PENELEC | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p47_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p47_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p47_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p47_csa.pdf | Document Posted | N/A | N/A | 10/23/2009 | 1/25/2006 | N/A | N/A | 11/4/2009 |  |  | 12/16/2009 | 12/16/2009 | 12/16/2009 | N | No
P48 | Bedford North - Allegheny 115kV |  | PA | Somerset | Withdrawn | PENELEC | 120 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p48_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2006 | N/A | N/A |  | 2/12/2007 | Customer Initiated Withdrawal | 12/15/2007 |  |  | N | No
P49 | Adkins 345kV | Darby Generating Station | OH | Pickaway | In Service | Dayton | 564 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P50 | Greenville 69kV | Greenville Electric Generating Station | OH | Darke | In Service | Dayton | 236 | 14 | 14 | 14 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P51 | Stuart 345kV | Stuart Electric Generating Station | OH | Adams | In Service | Dayton | 2362 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p51_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P52 | Albright 138kV |  | WV | Preston | Withdrawn | APS | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p52_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2006 | N/A | N/A |  | 12/30/2010 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
P53 | Bent Mtn. 138kV |  | VA | Roanoke | Withdrawn | AEP | 81 | 81 | 16.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p53_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2006 | N/A | N/A |  | 8/21/2006 | Customer Initiated Withdrawal | 12/31/2008 |  |  | N | No
P54 | Sporn - Waterford 345kV | Racine | OH | Meigs | Withdrawn | AEP | 1035 | 1035 | 1035 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p54_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p54_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p54_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p54_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2006 | N/A | N/A |  | 1/26/2010 | Customer Milestone Not Met | 8/30/2014 | 8/30/2014 |  | N | No
P55 | West Lima 138kV |  | OH | Allen | Withdrawn | AEP | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p55_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 3/20/2009 | Customer Milestone Not Met | 10/1/2010 | 10/1/2010 |  | N | No
P56 | Elrama-Mitchell 138kV |  | PA | Allegheny | Withdrawn | DL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/p56_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/p56_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 8/21/2007 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
P57 | Charleroi - Mitchell 138kV |  | PA | Allegheny | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/p57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 8/28/2006 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
P58 | Canaan - Seneca 138kV |  | WV | Randolph | Withdrawn | APS | 150 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p58_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p58_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 2/17/2010 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
P59 | Belington 138kV | Laurel Mountain WF | WV | Barbour | In Service | APS | 97.6 | 97.6 | 19.52 | 97.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p59_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p59_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A | 5/23/2011 |  |  | 6/15/2011 | 6/15/2011 | 12/31/2008 | N | No
P60 | New Baltimore 115kV (Stony Creek) | Stony Creek WF | PA | Somerset | In Service | PENELEC | 52.5 | 52.5 | 10.5 | 52.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p60_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p60_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p60_csa.pdf | Document Posted | N/A | N/A | 10/22/2009 | 1/31/2006 | N/A | N/A | 10/23/2009 |  |  | 3/1/2010 | 3/1/2010 | 3/1/2010 | N | No
P61 | Gavin #1 765kV | Gavin 1 | OH | Adams | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p61_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p61_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p61_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p61_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A |  |  |  | 1/1/2010 | 1/1/2010 | 5/1/2007 | N | No
P62 | Gavin #2 765kV | Gavin 2 | OH | Adams | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p62_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p62_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p62_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A |  |  |  | 5/1/2009 | 5/1/2009 | 5/1/2009 | N | No
Q01 | Olive-Dequine 345kv | Fowler Ridge WF | IN | Benton | In Service | AEP | 500 | 500 | 100 | 500 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q01_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2006 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 12/1/2008 | N | No
Q02 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2006 | N/A | N/A |  | 7/17/2006 | Customer Initiated Withdrawal | 12/31/2008 |  |  | N | No
Q03 | Olive-Dequine 345kV | Fowler Ridge 4 WF | IN | Benton | In Service | AEP | 250 | 250 | 50 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/13/2006 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 12/3/2015 | N | No
Q04 | Snake Spring 115kV |  | PA | Bedford | Withdrawn | PENELEC | 140 | 140 | 28 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q05 | Emmaville Mountain |  | PA | Fulton | Withdrawn | APS | 18 | 18 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q05_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q06 | Breezewood |  | PA | Fulton | Withdrawn | APS | 18 | 18 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q06_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q07 | DuVall South |  | PA | Fulton | Withdrawn | PENELEC | 18 | 18 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 6/14/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q08 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q08_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/21/2006 | N/A | N/A |  | 8/18/2009 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
Q09 | Emporia | Emporia Hydro | VA | Greensville | In Service | Dominion | 2.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q09_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q09_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/21/2006 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
Q10 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 238 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/23/2006 | N/A | N/A |  |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
Q11 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q11_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/23/2006 | N/A | N/A |  | 3/31/2010 | Customer Milestone Not Met | 12/1/2011 | 12/1/2011 |  | N | No
Q12 | Fox River Heights 12kV |  | IL | Kane | Withdrawn | ComEd | 1.6 | 1.6 | 1.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q12_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q13 | Kankakee 12kV |  | IL | Kankakee | Withdrawn | ComEd | 1.6 | 1.6 | 1.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q13_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q14 | Hegewisch 12kV |  | IL | Cook | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q15 | Woodridge 12kV |  | IL | Du Page | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q15_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q16 | Western Ave 12kV |  | IL | Kane | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q16_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/23/2010 | Customer Milestone Not Met | 9/1/2007 | 9/1/2007 |  | N | No
Q17 | Northbrook 12kV |  | IL | Cook | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q17_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/23/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q18 | Moser 34.5kV | Pottstown LF Units 1 & 2 | PA | Montgomery | In Service | PECO | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/8/2006 | N/A | N/A |  |  |  | 11/6/2007 | 11/6/2007 | 11/6/2007 | N | No
Q19 | Atlantic 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1 | 1 | 1 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q19_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/13/2006 | N/A | N/A |  | 12/6/2006 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
Q20 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 249 | 140 | 140 | 140 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q20_csa.pdf | Document Posted | N/A | N/A |  | 3/17/2006 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 10/30/2010 | N | No
Q21 | Lewistown-Juniata 230kV |  | PA | Cambria | Withdrawn | PENELEC | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2006 | N/A | N/A |  | 5/4/2006 | Customer Initiated Withdrawal | 12/15/2006 |  |  | S | No
Q22 | Columbia 34.5kV | Great Bear Hydro | NJ | Warren | In Service | JCPL | 0.5 | 0.5 | 0.5 | 0.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q22_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q22_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/20/2006 | N/A | N/A |  |  |  | 5/5/2009 | 5/5/2009 | 12/26/2006 | N | No
Q23 | Bayard |  | WV | Grant | Withdrawn | APS | 19 | 19 | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2006 | N/A | N/A |  | 11/27/2006 | Customer Milestone Not Met | 3/31/2007 |  |  | N | No
Q24 | Gold-Sabinsville 115kV |  | PA | Potter | Withdrawn | PENELEC | 101 | 101 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q24_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2006 | N/A | N/A |  | 2/2/2009 | Customer Milestone Not Met | 12/30/2010 | 12/30/2010 |  | N | No
Q25 | Donegal-Iron City 138kV | Harmony WF | PA | Fayette | Withdrawn | APS | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q25_csa.pdf | Document Posted | N/A | N/A |  | 3/24/2006 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 3/1/2014 | 3/1/2014 |  | N | No
Q26 | Churchtown 230kV |  | NJ | Salem | Withdrawn | AEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2006 | N/A | N/A |  | 10/12/2006 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
Q27 | Frackville-Shennandoah 69kV | Locust Ridge II WF | PA | Schuylkill | In Service | PPL | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q27_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q27_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2006 | N/A | N/A | 10/23/2008 |  |  | 4/29/2009 | 4/29/2009 | 4/29/2009 | N | No
Q28 | Eldred-Frackville 230kV | Rausch Creek WF (68 WT) | PA | Schuylkill | Withdrawn | PPL | 170 | 170 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q28_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2006 | N/A | N/A |  | 8/2/2013 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
Q29 | Zion 12kV |  | IL | Lake | Withdrawn | ComEd | 6 | 5.4 | 5.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q29_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 4/11/2006 | N/A | N/A |  | 10/29/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q30 | City of Columbus |  | OH | Franklin | Withdrawn | AEP | 3 | 3 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/11/2006 | N/A | N/A |  | 9/20/2006 | Customer Initiated Withdrawal | 12/31/2006 |  |  | N | No
Q31 | Wagner 34kV | Hawkins Point | MD | Baltimore City | In Service | BGE | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q31_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q31_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/11/2006 | N/A | N/A |  |  |  | 4/24/2007 | 4/24/2007 | 6/1/2006 | N | No
Q32 | Gosport 115kV | Gosport | VA | City of Portsmouth | Withdrawn | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q32_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2006 | N/A | N/A |  | 8/22/2007 | Customer Initiated Withdrawal | 7/1/2007 | 7/1/2007 |  | N | No
Q33 | Homer-Watercure 345kV |  | PA | Tioga | Withdrawn | PENELEC | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2006 | N/A | N/A |  | 6/6/2006 | Customer Initiated Withdrawal | 12/15/2008 |  |  | N | No
Q34 | Garrett 115kV |  | PA | Somerset | Withdrawn | PENELEC | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q34_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q34_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q34_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q34_csa.pdf | Document Posted | N/A | N/A |  | 4/24/2006 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 4/1/2011 | 4/1/2011 |  | N | No
Q35 | N. Coshocton 69kV |  | OH | Coshocton | Withdrawn | AEP | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q35_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/26/2006 | N/A | N/A |  | 11/28/2006 | Customer Milestone Not Met | 6/1/2007 |  |  | N | No
Q36 | Philipsburg - Tyrone North 115kV | Sandy Ridge WF | PA | Centre | In Service | PENELEC | 50 | 50 | 10 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q36_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2006 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 4/17/2012 | N | No
Q37 | Loganton 12kV | Schrack Farms | PA | Clinton | Withdrawn | PPL | 0.02 | 0.02 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q37_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q37_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/2/2006 | N/A | N/A |  | 1/12/2007 | Customer Initiated Withdrawal | 6/16/2006 |  |  | N | No
Q38 | C2 Tap - Mt. Union 46kV |  | PA | Cambria | Withdrawn | PENELEC | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/q38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/q38_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/4/2006 | N/A | N/A |  | 12/5/2007 | Customer Milestone Not Met | 12/15/2007 | 12/15/2007 |  | S | No
Q39 | Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 105 | 105 | 21 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q39_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q39_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/8/2006 | N/A | N/A |  | 10/22/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
Q40 | Renovo Lock Haven |  | PA | Clinton | Withdrawn | PPL | 40 | 40 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q40_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/15/2006 | N/A | N/A |  | 8/29/2008 | Customer Initiated Withdrawal | 6/1/2009 | 6/1/2009 |  | N | No
Q41 | Mt. Hope Mine 34.5kV | Mt Hope Waterpower Project | NJ | Morris | Withdrawn | JCPL | 30 | 30 |  |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q41_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q41_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/5/2006 | N/A | N/A |  | 11/11/2013 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
Q42 | Indian River |  | DE | Sussex | Withdrawn | DPL | 630 | 630 | 630 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q42_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/5/2006 | N/A | N/A |  | 7/30/2008 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
Q43 | Clinch River 138kV | Virginia City Hybrid Energy Center - 1 Unit | VA | Wise | In Service | AEP | 534 | 534 | 534 | 534 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q43_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q43_csa.pdf | Document Posted | N/A | N/A | 11/12/2010 | 6/7/2006 | N/A | N/A |  |  |  | 3/1/2012 |  | 3/22/2012 | N | No
Q44 | Elizabethtown | Elizabethtown | PA | Lancaster | In Service | PPL | 0.3 | 0.3 | 0 | 0.3 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q44_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q44_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q44_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/9/2006 | N/A | N/A |  |  |  | 7/1/2006 |  | 7/1/2006 | N | No
Q45 | North Lebanon 13.2kV | GLRA LF | PA | Lebanon | In Service | ME | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q45_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q45_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q45_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q45_csa.pdf | Document Posted | N/A | N/A |  | 6/14/2006 | N/A | N/A |  |  |  | 9/25/2007 | 9/25/2007 | 9/25/2007 | N | No
Q46 | Curwensville 34.5 kV | Sunnyside Ethonol | PA | Clearfield | Withdrawn | PENELEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q46_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q46_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/16/2006 | N/A | N/A |  | 3/14/2013 | Customer Milestone Not Met | 3/1/2009 |  |  | N | No
Q47 | Peach Bottom | Peach Bottom - Units 2 & 3 | PA | York | In Service | PECO | 2532 | 140 | 140 | 140 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q47_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q47_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 4/1/2013 | 4/1/2013 | 11/12/2012 | N | No
Q48 | Calvert Cliffs | Calvert Cliffs Nuclear Power Plant Unit 3 | MD | Calvert | Withdrawn | BGE | 1640 | 1640 | 1640 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q48_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q48_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q48_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2006 | N/A | N/A |  | 11/16/2009 | Customer Initiated Withdrawal | 1/1/2016 | 1/1/2016 |  | N | No
Q49 | Dresden 345kV | Dresden Nuclear Generating Station U2 | IL | Grundy | In Service | ComEd | 957 | 70 | 70 | 70 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 11/14/2011 | N | No
Q50 | Dresden 345kV | Dresden Nuclear Station Unit 3 | IL | Grundy | In Service | ComEd | 957 | 70 | 70 | 70 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 12/12/2012 | N | No
Q51 | Quad City 345kV | Quad Cities - Units 1 & 2 | IL | Rock Island | In Service | ComEd | 1914 | 140 | 140 | 140 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q51_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 9/25/2011 | N | No
Q52 | Hunlock Creek |  | PA | Luzerne | Withdrawn | UGI | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q52_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/21/2006 | N/A | N/A |  | 12/11/2007 | Customer Initiated Withdrawal | 6/15/2011 |  |  | N | No
Q53 | Summit-West Fall 115kV | Chestnut Flats WF | PA | Blair | In Service | PENELEC | 38 | 38 | 7.6 | 38 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q53_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q53_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q53_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q53_csa.pdf | Document Posted | N/A | N/A |  | 6/23/2006 | N/A | N/A |  |  |  | 5/20/2011 | 5/20/2011 | 5/20/2011 | N | No
Q54 | Haviland-Tillman 138kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q54_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2006 | N/A | N/A |  | 10/27/2006 | Customer Milestone Not Met | 12/15/2009 |  |  | N | No
Q55 | Snowy Creek |  | WV | Preston | Withdrawn | APS | 62.5 | 62.5 | 12.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q55_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q55_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/28/2006 | N/A | N/A |  | 7/31/2012 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
Q56 | Claysburg 115kV |  | PA | Blair | Withdrawn | PENELEC | 180 | 180 | 36 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q56_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/5/2006 | N/A | N/A |  | 11/17/2006 | Customer Milestone Not Met | 6/30/2008 |  |  | N | No
Q57 | Steward-Waterman 138kV | Lee - DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 240 | 240 | 48 | 237.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q57_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q57_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q57_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q57_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q57_csa.pdf | Document Posted | N/A | N/A |  | 7/6/2006 | N/A | N/A |  |  |  | 6/1/2010 | 6/1/2010 | 11/14/2014 | N | No
Q58 | Sunbury-Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q58_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q58_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/6/2006 | N/A | N/A |  | 8/18/2008 | Customer Initiated Withdrawal | 12/31/2009 | 12/31/2009 |  | N | No
Q59 | S. Reading-Birdsboro 64kV | Pioneer Crossing LF | PA | Berks | In Service | ME | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q59_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q59_csa.pdf | Document Posted | N/A | N/A |  | 7/7/2006 | N/A | N/A |  |  |  | 5/30/2008 | 5/30/2008 | 5/30/2008 | N | No
Q60 | Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 201 | 201 | 40.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q60_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2006 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 3/1/2009 | 3/1/2009 |  | N | No
Q61 | Grassy Falls 138kV |  | WV | Greenbrier | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2006 | N/A | N/A |  | 8/26/2008 |  | 1/1/2010 |  |  | N | No
Q62 | Sayton -Snake Spring 115kV |  | PA | Bedford | Withdrawn | PENELEC | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q62_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2006 | N/A | N/A |  | 3/27/2009 | Customer Initiated Withdrawal | 12/1/2009 | 12/1/2009 |  | N | No
Q63 | Seneca 230kV | Seneca Pumped Storage Generating Station Unit 1 | PA | Warren | In Service | PENELEC | 468 | 16 | 16 | 16 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/11/2006 | N/A | N/A |  |  |  | 8/11/2010 | 8/11/2010 | 8/11/2010 | N | No
Q64 | Gosport 115kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q64_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2006 | N/A | N/A |  | 5/31/2007 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
Q65 | North Anna 500kV | North Anna Power Station Unit 3 | VA | Louisa | Withdrawn | Dominion | 1594 | 1594 | 1570 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q65_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q65_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q65_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q65_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q65_csa.pdf | Document Posted | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 4/28/2016 | Customer Initiated Withdrawal | 1/1/2024 | 1/1/2024 |  | N | No
Q66 | Beecher Energy - Distribution Cener #36 |  | IL | Will | Withdrawn | ComEd | 2 | 2.1 | 2.1 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q66_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q67 | LaGrange Park - West Chester Sexton Energy |  | IL | Cook | Withdrawn | ComEd | 4 | 3.5 | 3.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q67_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q67_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q67B | Mt. Prospect - Des Plaines Sexton Energy |  | IL | Cook | Withdrawn | ComEd | 4 | 3.5 | 3.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q67b_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q67b_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q68 | Kincaid 345kV |  | IL | Christian | Withdrawn | ComEd | 726 | 726 | 641 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q68_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q68_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2006 | N/A | N/A |  | 6/5/2012 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | No
Q69 | Shackleford 34.5kV | King - Queen | VA | Brunswick | In Service | Dominion | 10 | 10 | 10 | 10 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q69_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q69_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q69_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q69_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2006 | N/A | N/A |  |  |  | 2/7/2008 | 2/7/2008 | 2/7/2008 | N | No
Q70 | Lawrenceville 34.5kV | Brunswick | VA | King and Queen | In Service | Dominion | 11 | 11 | 11 | 11 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q70_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q70_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2006 | N/A | N/A |  |  |  | 11/1/2007 | 11/1/2007 | 11/1/2007 | N | No
Q71 | Cranes Corner 13.2kV | Strafford Regional LF | VA | Stafford | In Service | Dominion | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q71_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q71_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q71_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q71_csa.pdf | Document Posted | N/A | N/A | 2/3/2009 | 7/26/2006 | N/A | N/A | 2/6/2009 |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
Q72 | Mansfield - S. Troy 115kV |  | PA | Bradford | Withdrawn | PENELEC | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q72_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q72_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2006 | N/A | N/A |  | 12/23/2009 | Customer Initiated Withdrawal | 12/1/2010 | 12/1/2010 |  | N | No
Q73 | South Reading 69kV | Evergreen Community Power | PA | Berks | Deactivated | ME | 30 | 30 | 16 | 19 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q73_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q73_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2006 | N/A | N/A | 8/17/2009 |  |  | 4/6/2010 | 4/6/2010 | 4/6/2010 | N | No
Q74 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q74_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/22/2008 | Customer Initiated Withdrawal | 6/1/2013 | 6/1/2013 |  | N | No
Q75 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 1000 | 1000 | 685 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/q75_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/q75_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 12/2/2008 |  | 6/1/2010 |  |  | S | No
Q76 | Quinton 12kV | Salem County LF Generating Unit I | NJ | Salem | Deactivated | AEC | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q76_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q76_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/31/2006 | N/A | N/A |  |  |  | 12/19/2008 | 12/19/2008 | 12/19/2008 | N | No
Q77 | Calvert Cliffs |  | MD | Calvert | Withdrawn | PEPCO | 1640 | 1640 | 1640 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q77_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 3/21/2007 | Customer Initiated Withdrawal | 12/30/2016 |  |  | N | No
Q78 | Trail Fork 34.5kV |  | WV | McDowell | Withdrawn | AEP | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 1/24/2007 | Customer Milestone Not Met | 4/1/2007 |  |  | N | No
Q79 | Ft. Martin - Kammer 500kV | Longview ST1 | WV | Monongalia | In Service | APS | 700 | 100 | 100 | 100 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q79_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/5/2009 | 7/31/2006 | N/A | N/A | 5/6/2011 |  |  | 4/22/2011 | 4/22/2011 | 9/1/2010 | N | No
Q80 | Ft. Martin - Kammer 500kV |  | WV | Monongalia | Withdrawn | APS | 750 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q80_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q80_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 8/1/2012 |  |  | N | No
Q81 | AMOS 765kV |  | WV | Putnam | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q81_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/24/2006 | Customer Milestone Not Met | 12/30/2007 |  |  | N | No
Q85 | Minonk 34.5kV |  | IL | Marshall | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 12/15/2008 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
Q86 | Hudson - Essex 230kV |  | NJ | Hudson | Withdrawn | PSEG | 455.1 | 455.1 | 455.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q86_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 4/2/2009 | Customer Milestone Not Met | 5/31/2010 | 5/31/2010 |  | N | No
Q87 | Quad Cities 345kV |  | IL | Whiteside | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 1/22/2007 | Customer Milestone Not Met | 1/1/2008 |  |  | S | No
Q88 | Black Oak SVC |  | WV | Berkeley | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/q88_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/31/2006 | Customer Initiated Withdrawal | 6/1/2008 |  |  | S | No
Q89 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q89_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 3/30/2007 | Customer Initiated Withdrawal | 8/1/2012 |  |  | N | No
Q90 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 650 | 650 | 650 | 650 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q90_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q90_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q90_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q90_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q90_csa.pdf | Document Posted | N/A | N/A | 7/1/2014 | 7/31/2006 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 8/11/2014 | N | No
R01 | Susquehanna |  | PA | Montour | Withdrawn | PPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r01_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/25/2006 | N/A | N/A |  | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
R02 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r02_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r02_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/25/2006 | N/A | N/A |  | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
R03 | Adams - Allen 138kV |  | IN | Adams | Withdrawn | AEP | 130 | 130 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r03_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2006 | N/A | N/A |  | 2/5/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
R04 | Sunbury 500kV |  | PA | Snyder | Withdrawn | PPL | 817 | 817 | 817 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r04_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2006 | N/A | N/A |  | 10/13/2008 | Customer Initiated Withdrawal | 12/15/2011 |  |  | N | No
R05 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r05_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2006 | N/A | N/A |  | 8/5/2009 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
R06 | Weissport 69kV |  | PA | Carbon | Withdrawn | PPL | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2006 | N/A | N/A |  | 4/3/2007 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
R07 | Pleasantville | AC Landfill Energy Units 1-3 | NJ | Atlantic | Deactivated | AEC | 6 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/12/2006 | N/A | N/A |  |  |  | 10/1/2007 | 10/1/2007 | 10/1/2007 | N | No
R08 | Central City 115kV, Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2006 | N/A | N/A |  | 2/18/2009 | Customer Initiated Withdrawal | 12/10/2012 |  |  | N | No
R09 | Johnstown-Altoona 230 kV |  | PA | Cambria | Withdrawn | PENELEC | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r09_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2006 | N/A | N/A |  | 9/3/2009 | Customer Milestone Not Met | 12/15/2009 | 12/15/2009 |  | N | No
R11 | South River 230 kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 440 | 440 | 440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r11_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2006 | N/A | N/A |  | 11/27/2019 |  | 5/16/2020 | 5/16/2020 |  | N | No
R12 | Bedington - Nipetown |  | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/r12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/r12_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/r12_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2006 | N/A | N/A |  |  |  | 4/4/2008 | 4/4/2008 | 6/1/2008 | S | No
R13 | Tidd - Canton Central 345kV |  | OH | Columbiana | Withdrawn | AEP | 350 | 350 | 350 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2006 | N/A | N/A |  | 6/18/2008 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
R14 | Tait 69kV | Tait Generating Units 4-7 | OH | Montgomery | In Service | Dayton | 376 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r14_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2006 | N/A | N/A |  |  |  | 5/1/2007 | 5/1/2007 | 5/1/2007 | N | No
R15 | Adkins 345kV | Darby Generation Station Units 1-6 | OH | Pickaway | In Service | Dayton | 564 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r15_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r15_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2006 | N/A | N/A |  |  |  | 5/1/2007 | 5/1/2007 | 5/1/2007 | N | No
R16 | Lena 138kV |  | IL | Stephenson | Withdrawn | ComEd | 126 | 126 | 25.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r16_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2006 | N/A | N/A |  | 11/24/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
R17 | Morgantown - Oak Grove 230kV | CPV St. Charles | MD | Charles | Withdrawn | PEPCO | 645 | 645 | 645 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r17_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r17_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/2/2006 | N/A | N/A |  | 4/1/2010 | Customer Milestone Not Met | 6/1/2013 | 6/1/2013 |  | N | No
R18 | Blackhawk | Winnebago Energy Center | IL | Boone | In Service | ComEd | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r18_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/r18_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/2/2006 | N/A | N/A |  |  |  | 1/3/2008 | 1/3/2008 | 1/3/2008 | N | No
R19 | Ladysmith 230kV | Ladysmith CT Units 3 & 4 | VA | Caroline | In Service | Dominion | 720 | 340 | 340 | 340 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r19_csa.pdf | Document Posted | N/A | N/A |  | 10/3/2006 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
R20 | Rock Springs | Rock Springs Units 3 & 4 | MD | Cecil | In Service | ODEC | 330 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/4/2006 | N/A | N/A |  |  |  | 7/1/2010 | 7/1/2010 | 1/1/2007 | N | No
R21 | Short Mountain |  | WV | Hardy | Withdrawn | APS | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2006 | N/A | N/A |  | 5/18/2007 | Customer Initiated Withdrawal | 11/30/2010 |  |  | N | No
R22 | Elk Garden - Junction 138kV |  | WV | Mineral | Withdrawn | APS | 90 | 90 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2006 | N/A | N/A |  | 1/9/2009 | Customer Initiated Withdrawal | 11/30/2009 |  |  | N | No
R23 | Lakewood 230kV | Ocean Peaking Power (Lakewood CT1, CT2) | NJ | Ocean | In Service | JCPL | 375.6 | 20 | 20 | 19.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/16/2006 | N/A | N/A |  |  |  | 1/1/2007 |  | 1/1/2007 | N | No
R24 | Susquehanna - Alburtis 500kV |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r24_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2006 | N/A | N/A |  | 7/16/2008 | Customer Initiated Withdrawal | 4/1/2011 |  |  | N | No
R25 | Dickerson - Pleasant View 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2006 | N/A | N/A |  | 1/30/2007 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
R26 | Sunbury - Susquehanna 500kV |  | PA | Northumberland | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2006 | N/A | N/A |  | 6/13/2007 | Customer Milestone Not Met | 7/1/2011 |  |  | N | No
R27 | Frackville |  | PA | Schuylkill | Withdrawn | PPL | 52 | 52 | 52 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r27_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 1/20/2009 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
R28 | Susquehanna - Alburtis 500kV |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 7/19/2007 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
R29 | Kawanee 138kV |  | IL | Knox | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r29_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 1/20/2010 | Customer Milestone Not Met | 12/1/2008 |  |  | N | No
R30 | Pontiac Mid-Point 345kV | Pleasant Ridge Wind Farm | IL | Livingston | Withdrawn | ComEd | 500 | 500 | 100 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r30_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r30_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r30_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r30_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 8/19/2019 |  | 12/31/2020 | 12/31/2020 |  | N | No
R31 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 18 | 18 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r31_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2006 | N/A | N/A |  | 4/27/2010 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | N | No
R32 | Salix - Claysburg 115kV | Highland North | PA | Cambria | In Service | PENELEC | 75 | 75 | 15 | 75 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r32_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r32_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r32_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2006 | N/A | N/A | 10/23/2010 |  |  | 3/31/2012 | 3/31/2012 | 3/23/2012 | N | No
R33 | Nelson 345 kV | Nelson Energy Center | IL | Unknown | In Service | ComEd | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r33_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r33_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r33_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r33_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2006 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 5/8/2015 | N | No
R34 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2006 | N/A | N/A | [6 empty] | S | No
R35 | Robbins 138kV | Robbins Community Power | IL | Cook | Withdrawn | ComEd | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r35_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/3/2006 | N/A | N/A |  | 1/25/2013 | Customer Milestone Not Met | 9/30/2011 | 9/30/2011 |  | N | No
R36 | Bethany 138kV | Bluewater Wind - Bethany | DE | Unknown | Withdrawn | DPL | 450 | 450 | 90 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r36_csa.pdf | Document Posted | N/A | N/A |  | 11/8/2006 | N/A | N/A |  | 8/6/2012 | Customer Initiated Withdrawal | 6/1/2018 | 6/1/2018 |  | N | No
R37 | Rehoboth 138kV |  | DE | Sussex | Withdrawn | DPL | 450 | 450 | 90 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r37_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2006 | N/A | N/A |  | 1/12/2009 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
R38 | Milford 230kV |  | DE | Sussex | Withdrawn | DPL | 547 | 547 | 110 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2006 | N/A | N/A |  | 9/7/2007 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
R39 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/10/2006 | N/A | N/A |  | 12/2/2008 |  | 8/1/2009 |  |  | N | No
R40 | Rockwood - Meyersdale 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 1.8 | 1.8 | 0.36 | 1.8 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r40_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r40_csa.pdf | Document Posted | N/A | N/A |  | 11/15/2006 | N/A | N/A |  |  |  | 6/30/2008 | 6/30/2008 | 6/30/2008 | N | No
R41 | Roxbury - Blain 23kV |  | PA | Cumberland | Withdrawn | PENELEC | 6 | 6 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2006 | N/A | N/A |  | 11/27/2007 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R42 | Moselem 69kV | Evansville Biomass | PA | Berks | Withdrawn | ME | 9 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r42_csa.pdf | Document Posted | N/A | N/A |  | 11/21/2006 | N/A | N/A |  | 8/6/2009 | Customer Initiated Withdrawal | 3/1/2009 | 3/1/2009 |  | N | No
R43 | Frackville - Hauto #3 | GCC Realty | PA | Schuylkill | Withdrawn | PPL | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r43_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r43_csa.pdf | Document Posted | N/A | N/A |  | 11/27/2006 | N/A | N/A |  | 6/15/2015 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
R44 | Rockport 765kV |  | KY | Henderson | Withdrawn | AEP | 485 | 485 | 485 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r44_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2006 | N/A | N/A |  | 5/21/2010 | Customer Initiated Withdrawal | 3/31/2011 |  |  | N | No
R45 | Mansfield - Tower Hill 115kV |  | PA | Tioga | Withdrawn | PENELEC | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r45_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2006 | N/A | N/A |  | 2/2/2009 |  | 4/30/2009 | 4/30/2009 |  | N | No
R46 | Providence Heights #1A 138kV |  | IL | Bureau | Withdrawn | ComEd | 9 | 9 | 1.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2006 | N/A | N/A |  | 10/1/2007 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R47 |  |  | PA | Lancaster | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2006 | N/A | N/A | [6 empty] | S | No
R48 | Antwerp - Payne 69kV | Paulding aka Project R48 | OH | Paulding | Withdrawn | AEP | 48.3 | 48.3 | 9.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r48_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r48_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 1/4/2018 |  | 11/30/2020 | 11/30/2020 |  | N | No
R49 | Haviland - Milan 138kV | Timber Road II WF | OH | Paulding | In Service | AEP | 99 | 150 | 30 | 99 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r49_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r49_csa.pdf | Document Posted | N/A | N/A | 6/9/2011 | 12/6/2006 | N/A | N/A | 6/13/2011 |  |  | 12/31/2012 | 12/31/2012 | 7/15/2011 | N | No
R50 | Liberty - Blue Jacket 69kV |  | OH | Logan | Withdrawn | Dayton | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r50_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 9/6/2007 | Customer Milestone Not Met | 2/15/2009 |  |  | N | No
R51 | Kings Creek - Woodstock 69kV |  | OH | Champaign | Withdrawn | Dayton | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r51_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 9/6/2007 | Customer Milestone Not Met | 12/15/2010 |  |  | N | No
R52 | Mechanicsburg - Darby | Buckeye Wind Farm - Phase 1 | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r52_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r52_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r52_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 2/21/2018 |  | 12/31/2019 | 12/31/2019 |  | N | No
R52A | Kings Creek 69kV | Buckeye Wind Farm - Phase 2 | OH | Champaign | Withdrawn | Dayton | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r52a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r52a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r52a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r52a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r52a_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 9/12/2019 |  | 12/31/2019 | 12/31/2019 |  | N | No
R53 | Stanton-Brookside 69kV |  | PA | Lackawanna | Withdrawn | PPL | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r53_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/8/2006 | N/A | N/A |  | 2/19/2009 | Customer Milestone Not Met | 11/11/2009 | 11/11/2009 |  | N | No
R54 | Dixon - Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r54_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2006 | N/A | N/A |  | 6/10/2011 | Customer Initiated Withdrawal | 12/1/2013 | 12/1/2013 |  | N | No
R55 | Dixon - Maryland 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r55_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2006 | N/A | N/A |  | 6/10/2011 | Customer Initiated Withdrawal | 12/1/2014 | 12/1/2014 |  | N | No
R56 | Quemahoning - Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 124 | 124 | 24.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r56_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r56_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2006 | N/A | N/A |  | 12/31/2009 | Customer Milestone Not Met | 11/30/2009 |  |  | N | No
R57 | South Reading 69kV | Evergreen Community Power | PA | Berks | Deactivated | ME | 30 | 30 | 9 | 11 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r57_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r57_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r57_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r57_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2006 | N/A | N/A | 8/17/2009 |  |  | 4/6/2010 | 4/6/2010 | 4/6/2010 | N | No
R58 | Gloucester 230kV | Camden Cogen Tech | NJ | Camden | Withdrawn | PSEG | 204 | 55 | 55 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r58_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r58_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r58_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r58_csa.pdf | Document Posted | N/A | N/A |  | 12/21/2006 | N/A | N/A |  | 12/3/2009 | Customer Initiated Withdrawal | 6/1/2013 | 6/1/2013 |  | N | No
R59 | Nelson-Lee County Energy Ctr 345kV |  | IL | Bureau | Withdrawn | ComEd | 160 | 160 | 32 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r59_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2007 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R60 | Convoy-East Lima 345kV | Blue Creek WF | OH | Van Wert | In Service | AEP | 350 | 350 | 70 | 304 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r60_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r60_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/15/2011 | 1/8/2007 | N/A | N/A | 10/7/2011 |  |  | 4/1/2012 | 4/1/2012 | 4/1/2012 | N | No
R61 | Collingwood-Hiple 345kV |  | IN | LeGrange | Withdrawn | AEP | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r61_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r61_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2007 | N/A | N/A |  | 4/13/2009 | Customer Initiated Withdrawal | 6/30/2010 | 6/30/2010 |  | N | No
R62 | Big Sandy 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r62_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r62_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/8/2007 | N/A | N/A |  |  |  | 6/1/2009 | 6/1/2009 | 5/31/2016 | N | No
R63 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 356 | 19 | 19 | 19 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
R64 | Lancaster 138kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r64_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r64_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/12/2007 | N/A | N/A |  | 1/28/2010 | Customer Initiated Withdrawal | 7/1/2009 |  |  | N | No
R65 | Dixon-Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r65_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r65_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/12/2007 | N/A | N/A |  | 1/28/2010 | Customer Initiated Withdrawal | 2/25/2010 | 2/25/2010 |  | N | No
R66 | Fairlawn 138kV | Marcal Paper | NJ | Bergen | In Service | PSEG | 67 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r66_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r66_csa.pdf | Document Posted | N/A | N/A |  | 1/12/2007 | N/A | N/A |  |  |  | 5/1/2009 | 5/1/2009 | 3/1/2007 | N | No
R67 | Beaver Valley 345kV |  | PA | Beaver | Withdrawn | DL | 2510 | 2510 | 2510 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R68 | Sammis 345kV |  | OH | Jefferson | Withdrawn | AEP | 1940 | 1940 | 1940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R69 | Clifty Creek 345kV |  | IN | Jefferson | Withdrawn | AEP | 251 | 251 | 251 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R70 | Kygov Creek |  | OH | Gallia | Withdrawn | AEP | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R72 | Indian River 230kV | Indian River Units 3-4 | DE | Sussex | Deactivated | DPL | 438 | 18 | 18 | 18 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r72_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r72_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r72_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/18/2007 | N/A | N/A |  |  |  | 12/10/2008 | 12/10/2008 | 12/10/2008 | N | No
R73 | Indian River 138kV | Indian River Units #3 & #4 | DE | Sussex | In Service | DPL | 170 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/18/2007 | N/A | N/A |  |  |  | 12/10/2008 | 12/10/2008 | 12/10/2008 | N | No
R74 | Carlls Corner | Shoreham Energy Units 1-3 | NJ | Atlantic | In Service | AEC | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r74_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/r74_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/19/2007 | N/A | N/A |  |  |  | 11/14/2008 | 11/14/2008 | 11/14/2008 | N | No
R75 | Mitchell - Shepler Hill 138kV |  | PA | Allegheny | Withdrawn | APS | 242 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/r75_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/r75_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2007 | N/A | N/A |  | 5/3/2007 | Customer Milestone Not Met | 1/1/2008 |  |  | S | No
R76 | Kanawha 138kV | Hawks Nest Hydro | WV | Fayette | In Service | AEP | 54.159 | 54.159 | 5.5 | 6.159 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r76_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r76_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/r76_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r76_csa.pdf | Document Posted | N/A | N/A |  | 1/23/2007 | N/A | N/A |  |  |  | 1/23/2017 | 1/23/2017 | 3/1/2009 | N | No
R77 | Morrisville 500kV |  | VA | Warren | Withdrawn | APS | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r77_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r77_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2007 | N/A | N/A |  | 7/20/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
R78 | Dresden-Pontiac 345kV |  | IL | Livingston | Withdrawn | ComEd | 300.3 | 300.3 | 60.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r78_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r78_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2007 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
R79 | Tazewell-Kendall 345kV |  | IL | Livingston | Withdrawn | ComEd | 300.3 | 300.3 | 60.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r79_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2007 | N/A | N/A |  | 5/5/2014 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
R80 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 640 | 0 | 60 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r80_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r80_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r80_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/26/2007 | N/A | N/A |  |  |  | 1/26/2017 | 1/26/2017 | 4/30/2015 | N | No
R81 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 1268 | 101 | 101 | 101 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r81_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r81_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r81_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r81_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r81_csa.pdf | Document Posted | N/A | N/A |  | 1/26/2007 | N/A | N/A |  |  |  | 2/8/2010 | 2/8/2010 | 2/8/2010 | N | No
R82 | Kanawha #1 | Kanawna River #1 | WV | Kanawha | In Service | AEP | 200 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r82_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r82_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r82_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R83 | Kanawha #2 | Kanawna River #2 | WV | Kanawha | In Service | AEP | 200 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r83_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r83_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r83_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R84 | Picway #5 | Pickway #5 | OH | Pickaway | In Service | AEP | 95 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r84_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r84_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r84_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R85 | Tanners Creek #1 | Tanners Creek #1 | IN | Dearborn | In Service | AEP | 145 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r85_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r85_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R86 | Tanners Creek #2 | Tanners Creek #2 | IN | Dearborn | In Service | AEP | 145 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r86_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R87 | Muskingum River #5 | Muskingum River #5 | OH | Washington | In Service | AEP | 585 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r87_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r87_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r87_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R88 | Providence Heights #2 138kV |  | IL | Bureau | Withdrawn | ComEd | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r88_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2007 | N/A | N/A |  | 7/8/2008 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R89 | Conowingo | Conowingo Hydro Station | MD | Harford | In Service | PECO | 572 | 24 | 24 | 12 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r89_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r89_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r89_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/30/2007 | N/A | N/A |  |  |  | 12/1/2010 | 12/1/2010 | 12/1/2010 | N | No
R90 | Dickerson-Pleasant View 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 14 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/r90_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/r90_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 1/30/2007 | N/A | N/A |  | 7/3/2007 | Customer Milestone Not Met | 6/1/2007 |  |  | S | No
R91 | Columbus-NJ |  | NJ | Burlington | In Service | PSEG | 0.37 | 0.37 | 0 | 0.25 | Energy | Generation Interconnection | Methane |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r91_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r91_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2007 | N/A | N/A |  |  |  | 10/15/2008 | 10/15/2008 | 6/1/2007 | N | No
R92 | DuBois 115kV |  | PA | Clearfield | Withdrawn | PENELEC | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r92_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r92_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r92_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 12/19/2013 | Customer Initiated Withdrawal | 6/30/2009 |  |  | N | No
R93 | Kelford 115kV |  | NC | Bertie | Withdrawn | Dominion | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r93_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 5/31/2007 | Customer Milestone Not Met | 3/1/2008 | 3/1/2008 |  | N | No
R94 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 7/23/2007 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
R95 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 7/23/2007 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
R96 | Lancaster-Maryland 138kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r96_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r96_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 8/29/2012 | Customer Initiated Withdrawal | 5/31/2010 | 5/31/2010 |  | N | No
R97 | Rockport 765kV | Rockport Unit 1 | IN | Spencer | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r97_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r97_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r97_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2007 | N/A | N/A |  |  |  | 11/1/2011 | 11/1/2011 | 11/1/2011 | N | No
R98 | Northeast 34.5kV |  | VA | Henrico | Withdrawn | Dominion | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r98_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r98_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 2/27/2008 | Customer Milestone Not Met | 6/30/2008 |  |  | N | No
S01 | Derwood 13kV | Gude LF | MD | Montgomery | Deactivated | PEPCO | 1 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s01_csa.pdf | Document Posted | N/A | N/A |  | 2/5/2007 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 7/1/2008 | N | No
S02 | Mt. Zion 13kV | Oaks LF | MD | Montgomery | Deactivated | PEPCO | 4 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s02_csa.pdf | Document Posted | N/A | N/A |  | 2/5/2007 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 7/1/2008 | N | No
S03 | Edgemoor 230kV | Edgemoor #5 | DE | New Castle | In Service | DPL | 450 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/13/2007 | N/A | N/A |  |  |  | 12/31/2007 | 12/31/2007 | 12/31/2007 | N | No
S04 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 633 | 633 | 633 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2007 | N/A | N/A |  | 11/1/2007 | Customer Milestone Not Met | 7/1/2010 |  |  | N | No
S05 | Seneca #2 230kV | Seneca Pumped Generating Station Unit 2 | PA | Warren | In Service | PENELEC | 468 | 16 | 16 | 16 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2007 | N/A | N/A |  |  |  | 8/11/2010 | 8/11/2010 | 8/11/2010 | N | No
S06 | Olive-DeQuine 345kV | Meadow Lake | IN | White | In Service | AEP | 202 | 202 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s06_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2007 | N/A | N/A |  |  |  | 10/6/2009 | 10/6/2009 | 12/1/2009 | N | No
S07 | Keystone-Branchburg | AC Landfill Energy Units 1, 2, 3 | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/s07_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/s07_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/s07_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S08 | Kammer-Doubs |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/s08_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/s08_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/s08_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S09 | Conemaugh-Conastone |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/s09_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/s09_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/s09_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S10 | Jacksons Ferry-Burches Hill |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/s10_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/s10_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/s10_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S100 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 614 | 80 | 80 | 80 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s100_csa.pdf | Document Posted | N/A | N/A | 11/12/2010 | 7/31/2007 | N/A | N/A |  |  |  | 3/1/2012 |  | 3/22/2012 | N | No
S101 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 580 | 580 | 580 | 580 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s101_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s101_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 10/22/2011 | 10/22/2011 | 10/22/2011 | N | No
S102 | Ladysmith 230kV | Ladysmith Combustion Turbine Unit 5 | VA | Caroline | In Service | Dominion | 950 | 170 | 170 | 170 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s102_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 3/31/2009 | 3/31/2009 | 3/31/2009 | N | No
S103 | Warren 115kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 57 | 57 | 57 | 57 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s103_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A | 4/5/2011 |  |  | 4/5/2011 | 4/5/2011 | 4/5/2011 | N | No
S104 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 5/14/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | S | No
S105 | Croydon-Emilie |  | PA | Bucks | Withdrawn | PECO | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s105_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 3/3/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
S107 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s107_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/16/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
S108 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 1023 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/18/2010 | 5/18/2010 | 5/18/2010 | N | No
S109 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 1030 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/2/2010 | 5/2/2010 | 5/2/2010 | N | No
S11 | Seward-Tower 51 115kV |  | PA | Cambria | Withdrawn | PENELEC | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2007 | N/A | N/A |  | 6/26/2009 | Customer Initiated Withdrawal | 2/1/2009 |  |  | N | No
S110 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 1023 | 65 | 65 | 65 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/2/2010 | 5/2/2010 | 5/2/2010 | N | No
S111 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S112 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 1030 | 65 | 65 | 65 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/18/2010 | 5/18/2010 | 5/18/2010 | N | No
S113 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S114 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 75 | 75 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s114_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 6/13/2012 | N | No
S115 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 75 | 75 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s115_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s115_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 7/1/2011 | 7/1/2011 | 7/1/2011 | N | No
S116 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 912 | 912 | 912 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s116_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 2/24/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
S117 | Haviland 138kV |  | OH | Paulding | Withdrawn | AEP | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 9/17/2007 | Customer Initiated Withdrawal | 10/1/2008 |  |  | N | No
S118 | North Delphos 138kV |  | OH | Paulding | Withdrawn | AEP | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 9/17/2007 | Customer Initiated Withdrawal | 10/1/2008 |  |  | N | No
S119 | Lexington-Dooms 500kV |  | VA | Augusta | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/s119_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 1/16/2008 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
S12 | Killen 345kV |  | OH | Adams | Withdrawn | Dayton | 1300 | 1300 | 1300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s12_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2007 | N/A | N/A |  | 3/12/2008 |  | 1/1/2014 |  |  | N | No
S120 | Bristers-Ox 500kV |  | VA | Fauquier | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/s120_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 1/16/2008 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
S121 | Vineland 69kV | Howard M. Down Power Plant Unit 11 | NJ | Cumberland | In Service | AEC | 63 | 63 | 63 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s121_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s121_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 4/18/2012 | N | No
S122 | Churchtown-Cumberland 230kV |  | NJ | Cumberland | Withdrawn | AEC | 478 | 478 | 478 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s122_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/28/2008 |  | 6/1/2010 | 6/1/2010 |  | N | No
S123 | Tiltonsville 138kV | Pike Island | OH | Jefferson | Withdrawn | AEP | 50 | 50 | 39 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s123_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s123_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
S124 | Aroyo-Wilie Ridge 138kV |  | WV | Hancock | Withdrawn | APS | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s124_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 3/27/2009 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
S13 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 238 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/19/2007 | N/A | N/A |  |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
S14 | Dans Mountain | Dans Mountain | MD | Allegany | In Service | APS | 54.9 | 54.9 | 14 | 54.9 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s14_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s14_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s14_csa.pdf | Document Posted | N/A | N/A | 1/8/2025 | 3/20/2007 | N/A | N/A | 2/6/2025 |  |  | 3/1/2025 | 3/1/2025 | 5/12/2025 | N | No
S15 | Burches Hill 500-230kV |  | MD | Prince George's | Withdrawn | PEPCO | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/s15_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 8/7/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
S16 | Gilbert-Glen Gardner 230kV |  | NJ | Hunterdon | Withdrawn | JCPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/s16_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 12/4/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
S17 | Talbert 230kV |  | MD | Charles | Withdrawn | PEPCO | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s17_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s17_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s17_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s17_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 12/18/2013 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
S18 | Talbert 230kV |  | MD | Charles | Withdrawn | PEPCO | 1250 | 1250 | 1250 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 2/21/2008 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
S19 | Pine Grove-Frailey 69kV |  | PA | Schuylkill | Withdrawn | PPL | 28 | 28 | 5.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s19_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 11/1/2007 | Customer Initiated Withdrawal | 10/1/2009 |  |  | N | No
S20 | Pine Grove-Fishbach 69kV | Pine Grove WF | PA | Schuylkill | Withdrawn | PPL | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s20_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 5/12/2011 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
S21B |  |  | N/A | N/A | Withdrawn |  | 0 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
S22 | Peach Bottom 500kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2007 | N/A | N/A |  | 11/13/2007 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
S23 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s23_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2007 | N/A | N/A |  | 9/9/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
S25 | Parlin 230kV | Calpine Parlin Energy Center | NJ | Middlesex | Deactivated | JCPL | 124 | 114 | 114 | 114 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2007 | N/A | N/A |  |  |  | 5/13/2008 |  | 5/13/2008 | N | No
S26 | Bluff Point-Jay 138kV |  | IN | Jay | Withdrawn | AEP | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/9/2007 | N/A | N/A |  | 5/29/2008 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
S27 | Blue Mound I | Twin Groves I WF | IL | McLean | In Service | ComEd | 198 | 0 | 39.6 | 198 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2007 | N/A | N/A |  |  |  | 6/24/2010 | 6/24/2010 | 6/24/2010 | N | No
S28 | Blue Mound II | Twin Groves II WF | IL | McLean | In Service | ComEd | 198 | 0 | 39.6 | 198 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2007 | N/A | N/A |  |  |  | 6/24/2010 | 6/24/2010 | 6/24/2010 | N | No
S28B |  |  | N/A | N/A | Withdrawn |  | 0 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
S29 | Morgantown-Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 900 | 900 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s29_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2007 | N/A | N/A |  | 2/23/2008 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
S29B | Somerset 23kV | SCI Laurel Highlands | PA | Somerset | Deactivated | PENELEC | 6.75 | 6.75 | 5.7 | 6.75 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s29b_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s29b_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s29b_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s29b_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s29b_csa.pdf | Document Posted | N/A | N/A | 6/20/2011 | 4/27/2007 | N/A | N/A | 9/27/2011 |  |  | 9/1/2011 | 9/1/2011 | 9/29/2011 | N | No
S30 | Gould | Sun Paper | MD | Baltimore City | In Service | BGE | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s30_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/s30_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2007 | N/A | N/A |  |  |  | 8/8/2008 | 8/8/2008 | 12/31/2007 | N | No
S30B 564954 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 640 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/564954_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/1/2007 | 3/1/2012 | 3/1/2041 |  | 8/31/2007 |  |  |  |  | FF | No
S31 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 450 | 450 | 90 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s31_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2007 | N/A | N/A |  | 4/9/2008 | Customer Milestone Not Met | 12/9/2009 |  |  | N | No
S32 | Perryman | Perryman 6 Units 1-4 | MD | Harford | In Service | BGE | 130 | 130 | 130 | 130 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s32_csa.pdf | Document Posted | N/A | N/A | 5/6/2015 | 5/3/2007 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 5/9/2015 | N | No
S33 | Riverside |  | MD | Baltimore County | Withdrawn | BGE | 120 | 120 | 85 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s33_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/3/2007 | N/A | N/A |  | 7/2/2009 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
S34 | Handsome Lake Energy 345kV | Handsome Lake | PA | Venango | In Service | PENELEC | 270 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s34_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/1/2007 |  | 6/1/2007 | N | No
S35 | Beverly 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 620 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s35_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/27/2007 | 6/27/2007 | 6/1/2008 | N | No
S36 | Kankakee 138 kV | Kankakee Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 175 | 35 | 175 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s36_csa.pdf | Document Posted | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/30/2015 | 6/30/2015 | 7/28/2015 | N | No
S37 | Kankakee 138kV | Kelly Creek Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 175 | 35 | 175 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s37_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s37_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s37_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s37_csa.pdf | Document Posted | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 11/9/2016 | N | No
S38 | Westvaco 138kV | Luke Paper | PA | Allegheny | Deactivated | APS | 8 | 8 | 0 | 8 | Energy | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s38_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s38_csa.pdf | Document Posted | N/A | N/A | 1/26/2009 | 5/7/2007 | N/A | N/A | 1/26/2009 |  |  | 1/26/2009 | 1/26/2009 | 4/1/2009 | N | No
S39 |  |  | N/A | N/A | Withdrawn |  | 0 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
S40 | Hegins | Commonwealth LF | PA | Schuylkill | In Service | PPL | 10.5 | 10.5 | 10.5 | 10.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s40_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s40_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s40_csa.pdf | Document Posted | N/A | N/A | 12/23/2008 | 5/10/2007 | N/A | N/A | 1/22/2009 |  |  | 1/21/2009 | 1/21/2009 | 1/21/2009 | N | No
S41 | Eldred-Reed 69kV | IntelliWatt | PA | Northumberland | Withdrawn | PPL | 12.5 | 12.5 | 12.5 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s41_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s41_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s41_csa.pdf | Document Posted | N/A | N/A |  | 5/10/2007 | N/A | N/A |  | 2/16/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
S42 | Eldred-Fairview | Penn Wind | PA | Northumberland | Withdrawn | PPL | 18 | 18 | 3.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s42_csa.pdf | Document Posted | N/A | N/A |  | 5/15/2007 | N/A | N/A |  | 1/8/2014 | Customer Initiated Withdrawal | 5/1/2013 | 5/1/2013 |  | N | No
S43 | Vineland | Vineland Unit #9 | NJ | Cumberland | In Service | AEC | 17 | 17 | 17 | 17 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s43_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s43_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/15/2007 | N/A | N/A |  |  |  | 11/12/2007 | 11/12/2007 | 11/12/2007 | N | No
S44 | Mifflin County |  | PA | Mifflin | Withdrawn | PENELEC | 110 | 110 | 22 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2007 | N/A | N/A |  | 10/28/2008 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
S45 | Mechanicsburg North |  | OH | Champaign | Withdrawn | Dayton | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s45_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2007 | N/A | N/A |  | 3/12/2012 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
S46 | Mechanicsburg South |  | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s46_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2007 | N/A | N/A |  | 5/15/2009 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
S47 |  |  | N/A | N/A | Withdrawn | MISO |  |  |  |  | Energy | Long-Term Firm Transmission | [7 empty] | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 12/14/2007 |  |  |  |  | FF | No
S48 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [7 empty] | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 12/14/2007 |  |  |  |  | FF | No
S49 | Bedford 115kV |  | PA | Bedford | Withdrawn | PENELEC | 202.5 | 90 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s49_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2007 | N/A | N/A |  | 9/22/2010 | Customer Initiated Withdrawal | 10/31/2013 | 10/31/2013 |  | N | No
S50 | Occoquan 230kV | Ogden Martin | VA | Fairfax | In Service | Dominion | 98 | 18 | 18 | 18 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/24/2007 | N/A | N/A |  |  |  | 6/30/2007 |  | 6/30/2007 | N | No
S51 | E. Liberty-Blue Jacket 69kV |  | OH | Logan | Withdrawn | Dayton | 99 | 99 | 19.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s51_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2007 | N/A | N/A |  | 4/7/2010 | Customer Initiated Withdrawal | 6/1/2009 |  |  | N | No
S52 | Morrisville 500kV |  | VA | Warren | Withdrawn | Dominion | 600 | 50 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s52_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s52_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/29/2007 | N/A | N/A |  | 7/2/2009 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
S53 | Lee County E.C. 345kV |  | IL | Bureau | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s53_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2007 | N/A | N/A |  | 8/15/2008 | Customer Milestone Not Met | 9/1/2008 |  |  | N | No
S53B 568550 | PJM.AP-PJM.DPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/568550_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
S53C 565854 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 310 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/565855_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/565855_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/1/2007 | 6/1/2010 | 6/1/2011 |  | 9/12/2008 |  |  |  |  | FF | No
S54 | Tazewell 138kV |  | VA | Tazewell | Withdrawn | AEP | 130 | 130 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s54_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/5/2007 | N/A | N/A |  | 6/25/2009 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
S55 | Zion 345kV | Zion Energy Center | IL | Lake | In Service | ComEd | 585 | 585 | 495 | 585 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s55_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/6/2007 | N/A | N/A |  |  |  | 2/25/2011 | 2/25/2011 | 12/19/2011 | N | No
S56 | Beaver Creek-Hazard 138kV |  | KY | Knott | Withdrawn | AEP | 535 | 535 | 535 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s56_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2007 | N/A | N/A |  | 4/28/2008 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
S57 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1500 |  |  |  | Energy | Merchant Transmission | Wind | DC | F/TIR 300/NF/TIR 1200 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s57_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/s57_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2007 | N/A | N/A |  | 4/10/2017 |  | 12/31/2020 | 12/31/2020 |  | S | No
S58 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1600 | 0 | 0 |  | Energy | Merchant Transmission | Wind | DC | F/TIR 400/NF/TIR 1200 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s58_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/s58_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2007 | N/A | N/A |  | 1/19/2018 |  | 12/31/2020 | 12/31/2020 |  | S | No
S58B 573929 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 240 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/573929_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/19/2007 | 1/1/2012 | 1/1/2014 |  | 6/4/2008 |  |  |  |  | FF | No
S58C 574221 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/574222_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/574222_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2007 | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
S58D 574906 | PJM.AP-PJM.DOM |  | N/A | N/A | Confirmed |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/574906_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/21/2007 | 4/1/2011 | 3/31/2041 | [6 empty] | FF | No
S59 | Sharpsburg 12kV | Wenning Poultry | OH | Mercer | In Service | Dayton | 1.89 | 1.89 | 0 | 1.5 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s59_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/s59_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/25/2007 | N/A | N/A |  |  |  | 11/1/2007 |  | 10/30/2008 | N | No
S59B 577135 | PJM-CIN |  | N/A | N/A | Confirmed |  | 20 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/577135_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/577135_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/26/2007 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
S60 | Essex 26kV | Newark Boxboard | NJ | Essex | Withdrawn | PSEG | 63 | 63 | 63 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s60_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/27/2007 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
S61 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s61_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s61_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s61_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/27/2007 | N/A | N/A |  |  |  | 10/11/2011 | 10/11/2011 | 10/11/2011 | N | No
S62 | LaSalle-Braidwood 345kV |  | IL | Lasalle | Withdrawn | ComEd | 500 | 500 | 100 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s62_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2007 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
S63 | Tait 69kV | Tait Generating Station | OH | Montgomery | In Service | Dayton | 376 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/5/2007 | N/A | N/A |  |  |  | 6/29/2007 |  | 10/5/2007 | N | No
S64 | York Inc. 115kV |  | PA | York | Withdrawn | ME | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s64_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s64_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s64_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/6/2007 | N/A | N/A |  | 5/31/2013 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
S65 | Cambria |  | PA | Cambria | Withdrawn | PENELEC | 85 | 85 | 17 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s65_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2007 | N/A | N/A |  | 12/30/2008 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
S66 | Downing Avenue 115kV |  | PA | Erie | Withdrawn | PENELEC | 96 | 96 | 96 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s66_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2007 | N/A | N/A |  | 8/28/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
S67 | Gould St. | Gould Street | MD | Baltimore City | Deactivated | BGE | 106 | 101 | 101 | 99.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s67_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s67_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s67_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s67_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2007 | N/A | N/A |  |  |  | 5/30/2008 | 5/30/2008 | 6/1/2008 | N | No
S68 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 660 | 660 | 0 |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/s68_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2007 | N/A | N/A |  | 4/23/2008 | Customer Initiated Withdrawal | 12/31/2007 |  |  | S | No
S70 | Eureka 138kV | Willow Island Hydro Generation Project | WV | Wetzel | In Service | APS | 36.4 | 36.4 | 36.4 | 36.4 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s70_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s70_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2007 | N/A | N/A |  |  |  | 7/31/2015 | 7/31/2015 | 11/15/2015 | N | No
S71 | Bluff Point 138kV | Bluff Point | IN | Jay | In Service | AEP | 120 | 120 | 24 | 120 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s71_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s71_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s71_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s71_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s71_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2007 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 9/15/2017 | N | No
S72 | Convoy-East Lima 345kV | Dog Creek Wind Farm | IN | Allen | Withdrawn | AEP | 240 | 240 | 48 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s72_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s72_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s72_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s72_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s72_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2007 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
S73 | Lincoln-North Delphos |  | IN | Allen | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s73_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s73_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2007 | N/A | N/A |  | 1/7/2014 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
S74 | Mount Storm 500kV | Mount Storm Unit 2 | WV | Grant | In Service | Dominion | 585 | 38 | 25 | 38 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s74_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s74_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S75 | Mount Storm 500kV | Mount Storm Unit 3 | WV | Grant | Withdrawn | Dominion | 574 | 29 | 29 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s75_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s75_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s75_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 6/1/2012 | 6/1/2012 |  | N | No
S76 | Mount Storm 500kV | Mount Storm Unit 1 | WV | Grant | In Service | Dominion | 585 | 38 | 25 | 38 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s76_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s76_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/6/2013 | N | No
S77 | Clover 230kV |  | VA | Halifax | Withdrawn | Dominion | 450 | 16 | 16 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s77_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 12/4/2008 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
S78 | Clover 230kV |  | VA | Halifax | Withdrawn | Dominion | 450 | 19 | 19 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s78_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 12/4/2008 | Customer Initiated Withdrawal | 4/1/2012 |  |  | N | No
S79 | Chesterfield 230kV | Chesterfield Unit #6 | VA | Chesterfield | In Service | Dominion | 691 | 27 | 27 | 27 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s79_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 12/1/2010 | 12/1/2010 | 12/1/2010 | N | No
S80 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 356 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s80_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s80_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s80_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S81 | Basin 230kV | Bellemeade | VA | City of Richmond | Deactivated | Dominion | 306 | 22 | 22 | 22 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s81_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s81_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s81_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 4/27/2010 | 4/27/2010 | 4/27/2010 | N | No
S82 | Surry 230kV | Gravel Neck Gas Turbine #3 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s82_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s82_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s82_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s82_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S83 | Surry 230kV | Gravel Neck Gas Turbine #4 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s83_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s83_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s83_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s83_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S84 | Surry 230kV | Gravel Neck Gas Turbine #5 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s84_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s84_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s84_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s84_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S85 | Surry 230kV | Gravel Neck Gas Turbine #6 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s85_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s85_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s85_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S86 | Darbytown 230kV | Darbytown GT1 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s86_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S87 | Darbytown 230kV | Darbytown GT2 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s87_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s87_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s87_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S88 | Darbytown 230kV | Darbytown GT3 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s88_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s88_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s88_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S89 | Darbytown 230kV | Darbytown GT4 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s89_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s89_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s89_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S90 | Elizabeth River 230kV | Elizabeth River GT1 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s90_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s90_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s90_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S91 | Elizabeth River 230kV | Elizabeth River GT2 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s91_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s91_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s91_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S92 | Elizabeth River 230kV | Elizabeth River GT3 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s92_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s92_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s92_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S93 | Remington 230kV | Remington GT1 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s93_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s93_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s93_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S94 | Remington 230kV | Remington GT2 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s94_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s94_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s94_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S95 | Remington 230kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s95_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s95_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s95_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S96 | Remington 230kV | Remington GT4 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s96_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s96_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s96_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S97 | South Anna 230kV | South Anna Unit 1 | VA | Orange | Withdrawn | Dominion | 144 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s97_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s97_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s97_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 6/1/2013 | 6/1/2013 |  | N | No
S98 | South Anna 230kV | South Anna Unit 2 | VA | Orange | Withdrawn | Dominion | 144 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s98_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s98_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s98_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 6/1/2013 | 6/1/2013 |  | N | No
S99 | Possum Point 230kV |  | VA | Prince William | Withdrawn | Dominion | 806 | 20 | 20 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s99_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s99_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 4/3/2009 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
T01 639662 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 75 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2008 | 6/1/2009 |  | 8/30/2007 |  |  |  |  | FF | No
T02 639671 | CPLE-PJM |  | N/A | N/A | Withdrawn |  | 172 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/639671_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2008 | 6/1/2009 |  | 10/30/2007 |  |  |  |  | FF | No
T03 639678 | CPLE-PJM |  | N/A | N/A | Withdrawn |  | 172 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/639678_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2009 | 6/1/2010 |  | 10/30/2007 |  |  |  |  | FF | No
T04 639742 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 171 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/639742_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2009 | 6/1/2010 |  | 10/30/2007 |  |  |  |  | FF | No
T05 639743 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 171 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/639743_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2008 | 6/1/2009 |  | 10/30/2007 |  |  |  |  | FF | No
T06 | Yorktown 230kV | Yorktown 3 | VA | York | Withdrawn | Dominion | 838 | 20 | 20 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t06_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 8/3/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 5/1/2014 |  |  | N | No
T07 664042 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 1000 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/6/2007 | 1/1/2008 | 1/1/2010 |  | 8/30/2007 |  |  |  |  | FF | No
T08 692322 | PJM-NIPS |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/692322_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/10/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T09 692342 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/692342_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/10/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T10 | Cranes Corner 34.5KV | Stafford Regional LF | VA | Stafford | In Service | Dominion | 3 | 3 | 3 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 2/3/2009 | 8/15/2007 | N/A | N/A | 2/6/2009 |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T100 | Grover-East Towanda 230 kV |  | PA | Bradford | Withdrawn | PENELEC | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2007 | N/A | N/A |  | 10/15/2008 | Customer Initiated Withdrawal | 9/30/2009 |  |  | N | No
T101 | Glassrock 69kV |  | OH | Perry | Withdrawn | AEP | 6.4 | 6.4 | 6.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2007 | N/A | N/A |  | 5/21/2008 |  | 11/1/2008 |  |  | N | No
T102 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 160 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t102_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/13/2007 | N/A | N/A |  |  |  | 10/30/2007 |  | 9/2/2008 | N | No
T103 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 160 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/13/2007 | N/A | N/A |  |  |  | 10/30/2007 |  | 9/2/2008 | N | No
T104 | Gosport 115kV | SPSA Navy Power Plant | VA | City of Portsmouth | Deactivated | Dominion | 50 | 20 |  | 20 | Energy | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t104_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t104_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2007 | N/A | N/A |  |  |  | 4/1/2008 |  | 4/1/2008 | N | No
T105 | Pontiac Midpoint-Wilton Center 350 MW |  | IL | Livingston | Withdrawn | ComEd | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t105_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2007 | N/A | N/A |  | 12/20/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
T106 | Lee County |  | IL | Bureau | Withdrawn | ComEd | 140 | 140 | 28 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t106_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/21/2007 | N/A | N/A |  | 4/27/2010 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
T107 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 675 | 625 | 625 | 625 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t107_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 11/21/2007 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
T108 | Archbald 69kV | Archbald Generating Station | PA | Lackawanna | In Service | PPL | 9.2 | 9.2 | 9.2 | 9.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t108_csa.pdf | Document Posted | N/A | N/A |  | 11/29/2007 | N/A | N/A | 11/13/2009 |  |  | 1/25/2010 | 1/25/2010 | 1/25/2010 | N | No
T109 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 918 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/3/2007 | N/A | N/A |  |  |  | 8/23/2010 | 8/23/2010 | 8/23/2010 | N | No
T11 | Laurel-Sussex 69kV | Southern LF Units 1-5 | DE | Sussex | In Service | DPL | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2007 | N/A | N/A |  |  |  | 5/21/2010 | 5/21/2010 | 5/21/2010 | N | No
T110 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 916 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/3/2007 | N/A | N/A |  |  |  | 8/23/2010 | 8/23/2010 | 8/23/2010 | N | No
T111 | Buchanan Hydro-Niles 69kV | Southeast Berrien LF | MI | Berrien | In Service | AEP | 6.4 | 6.4 | 6.4 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t111_csa.pdf | Document Posted | N/A | N/A |  | 12/12/2007 | N/A | N/A |  |  |  | 5/29/2009 | 5/29/2009 | 5/29/2009 | N | No
T112 | Morrisville-Loudoun 500kV |  | VA | Fauquier | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/t112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/t112_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/12/2007 | N/A | N/A |  | 7/28/2009 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | S | No
T113 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 132 | 16 | 16 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t113_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/14/2007 | N/A | N/A |  | 11/10/2008 | Customer Initiated Withdrawal | 5/31/2010 |  |  | N | No
T114 | Croydon 230kV |  | PA | Bucks | Withdrawn | PECO | 600 | 32.5 | 32.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t114_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2007 | N/A | N/A |  | 2/20/2008 | Customer Milestone Not Met | 5/31/2010 |  |  | N | No
T115 | Croydon 230kV |  | PA | Bucks | Withdrawn | PECO | 600 | 32.5 | 32.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t115_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2007 | N/A | N/A |  | 2/20/2008 | Customer Milestone Not Met | 5/31/2010 |  |  | N | No
T116 | LaSalle 1 |  | IL | Lasalle | Withdrawn | ComEd | 1151 | 18 | 18 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t116_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/17/2007 | N/A | N/A |  | 3/19/2010 | Customer Milestone Not Met | 3/1/2008 |  |  | N | No
T117 | Hunlock Creek 69kV | Hunlock Creek | PA | Luzerne | In Service | UGI | 126 | 126 | 126 | 126 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t117_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t117_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t117_csa.pdf | Document Posted | N/A | N/A |  | 12/17/2007 | N/A | N/A |  |  |  | 6/30/2011 | 6/30/2011 | 1/31/2011 | N | No
T118 | Linwood 230kV | Phillips Island CT1, CT2, CT3, CT4 | PA | Delaware | In Service | PECO | 840 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t118_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t118_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/19/2007 | N/A | N/A |  |  |  | 9/30/2009 | 9/30/2009 | 9/30/2009 | N | No
T119 | Metuchen 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t119_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2007 | N/A | N/A |  | 12/21/2009 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
T12 | Kent-Harrington 69kV | Central LF Units 1-4 | DE | Kent | In Service | DPL | 4.25 | 4 | 4 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2007 | N/A | N/A |  |  |  | 8/14/2007 |  | 10/1/2007 | N | No
T120 | Kankakee #3 138kV |  | IL | Iroquois | Withdrawn | ComEd | 250 | 250 | 50 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2007 | N/A | N/A |  | 6/30/2010 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
T121 | Potter-Gold 115kV | Potter Wind Farm | PA | Potter | Withdrawn | PENELEC | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t121_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t121_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t121_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t121_csa.pdf | Document Posted | N/A | N/A |  | 12/28/2007 | N/A | N/A |  | 2/22/2016 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
T122 | Ocean Bay 138kV |  | MD | Worcester | Withdrawn | DPL | 600 | 600 | 120 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t122_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2007 | N/A | N/A |  | 7/30/2009 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
T123 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 440 | 440 | 440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/2/2008 | N/A | N/A |  | 5/29/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
T124 | Latham-Pontiac I 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t124_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/2/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
T125 | Latham-Pontiac II 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t125_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/2/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
T126 | Olive-Dequine 345kV | Meadow Lake WF II, Meadow Lake WF III | IN | Benton | In Service | AEP | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t126_csa.pdf | Document Posted | N/A | N/A |  | 1/2/2008 | N/A | N/A |  |  |  | 10/28/2010 | 10/28/2010 | 10/28/2010 | N | No
T127 | Olive-Dequine 345kV | Meadow Lake WF 4 - 5 | IN | White | In Service | AEP | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/2/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 10/30/2010 | N | No
T128 | Masontown 500kV |  | PA | Fayette | Withdrawn | APS | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t128_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2008 | N/A | N/A |  | 6/2/2008 | Customer Milestone Not Met | 1/1/2012 |  |  | N | No
T129 | Printz 230kV | Liberty | PA | Delaware | In Service | PECO | 541 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t129_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t129_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/8/2008 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | N | No
T13 707849 | PJM-MECS |  | N/A | N/A | Withdrawn |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/707849_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/15/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T130 | Maddox Creek-RP Mone 345 kV |  | OH | Paulding | Withdrawn | AEP | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t130_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/9/2008 | N/A | N/A |  | 1/26/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
T131 | Lincoln-Sterling 138kV | Timber Road III | OH | Paulding | In Service | AEP | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t131_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t131_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t131_csa.pdf | Document Posted | N/A | N/A |  | 1/9/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/23/2016 | N | No
T132 | Cloverdale-Lexington 500kV |  | VA | Botetourt | Withdrawn | AEP | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2008 | N/A | N/A |  | 12/9/2009 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
T133 | Chalk Point-Bowie 230kV | Powell Generation Facility | MD | Prince George's | Withdrawn | PEPCO | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t133_csa.pdf | Document Posted | N/A | N/A |  | 1/10/2008 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 7/31/2018 | 7/31/2018 |  | N | No
T134 | Chalk Point-Bowie 230kV | Powell Generation Facility | MD | Prince George's | Withdrawn | PEPCO | 325 | 325 | 325 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t134_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t134_csa.pdf | Document Posted | N/A | N/A |  | 1/10/2008 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 7/31/2018 | 7/31/2018 |  | N | No
T135 | Chambers 230kV |  | NJ | Salem | Withdrawn | AEC | 240 | 15 | 15 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t135_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 1/10/2008 | N/A | N/A |  | 4/28/2009 | Queue Not Required | 1/7/2008 |  |  | N | No
T136 852816 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 350 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/9/2008 | 6/1/2008 | 6/1/2009 |  | 1/29/2008 |  |  |  |  | FF | No
T137 852819 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 350 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/9/2008 | 6/1/2008 | 6/1/2009 |  | 1/29/2008 |  |  |  |  | FF | No
T138 852821 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/9/2008 | 6/1/2008 | 6/1/2009 |  | 1/29/2008 |  |  |  |  | FF | No
T139 853465 | FE-PJM |  | N/A | N/A | Withdrawn |  | 707 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/853465_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/853465_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/10/2008 | 6/1/2008 | 6/1/2009 |  | 9/18/2009 |  |  |  |  | FF | No
T14 707852 | PJM-WEC |  | N/A | N/A | Withdrawn |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/707852_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/15/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T140 853531 | FE-PJM |  | N/A | N/A | Withdrawn |  | 2510 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/853531_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/853531_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/10/2008 | 6/1/2008 | 6/1/2009 |  | 11/4/2008 |  |  |  |  | FF | No
T141 853853 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/853853_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/11/2008 | 6/1/2008 | 6/1/2013 |  | 4/14/2008 |  |  |  |  | FF | No
T142 | Southwest Lima-Marysville 345kV | Van Wert II | OH | Hardin | Withdrawn | AEP | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t142_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t142_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t142_csa.pdf | Document Posted | N/A | N/A |  | 1/15/2008 | N/A | N/A |  | 9/18/2018 |  | 12/31/2019 | 12/31/2019 |  | N | No
T143 | Hennepin |  | IL | Putnam | Withdrawn | ComEd | 250 | 250 | 50 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2008 | N/A | N/A |  | 11/16/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
T144 | Pocomoke |  | MD | Somerset | Withdrawn | DPL | 19.8 | 19.8 | 10 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t144_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t144_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/17/2008 | N/A | N/A |  | 7/30/2014 | Customer Initiated Withdrawal | 1/1/2010 |  |  | N | No
T145 | AP South 500kV |  | N/A | N/A | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2008 | N/A | N/A |  | 12/29/2009 | Customer Milestone Not Met | 12/31/2008 |  |  | S | No
T146 | England |  | NJ | Cape May | Withdrawn | AEC | 346 | 346 | 69.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t146_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2008 | N/A | N/A |  | 1/28/2014 | Customer Initiated Withdrawal | 12/31/2020 | 12/31/2020 |  | N | No
T147 | Perryman | Perryman Generating Unit 51 | MD | Harford | In Service | BGE | 183 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t147_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t147_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/24/2008 | N/A | N/A |  |  |  | 6/1/2008 |  | 6/1/2008 | N | No
T148 | Wempletown-Belvidere 138kV |  | IL | Boone | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t148_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2008 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
T149 | Birchwood 230kV |  | VA | King George | Withdrawn | Dominion | 580 | 580 | 580 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t149_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2008 | N/A | N/A |  | 5/29/2008 | Customer Milestone Not Met | 1/1/2012 |  |  | N | No
T15 709682 | CPLE-PJM |  | N/A | N/A | Confirmed |  | 47 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/709682_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/709682_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/16/2007 | 1/1/2009 | 1/1/2014 | [6 empty] | FF | No
T152 | North Haverhill 69kV |  | OH | Scioto | Withdrawn | AEP | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t152_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2008 | N/A | N/A |  | 9/28/2009 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
T153 | Milford 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1.12 | 1.12 | 1.12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t153_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2008 | N/A | N/A |  | 12/11/2008 | Customer Initiated Withdrawal | 6/1/2008 |  |  | N | No
T154 | Bellefontaine 69kV | Cherokee Run LF | OH | Logan | Deactivated | Dayton | 10 | 10 | 10 | 10 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t154_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/t154_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/28/2008 | N/A | N/A |  |  |  | 2/27/2009 | 2/27/2009 | 2/27/2009 | N | No
T155 | Belknap 25kV | Mahoning Creek Dam Hydro Project | PA | Armstrong | In Service | APS | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t155_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/t155_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2008 | N/A | N/A |  |  |  | 3/1/2014 | 3/1/2014 | 12/26/2013 | N | No
T156 | Champion |  | PA | Washington | Withdrawn | APS | 292 | 20 | 20 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t156_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 5/28/2013 | Customer Initiated Withdrawal | 2/28/2011 |  |  | N | No
T157 | New Creek Mountain 500kV | New Creek Mountain Wind Farm | WV | Mineral | In Service | Dominion | 102.5 | 102.5 | 20.5 | 102.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t157_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t157_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t157_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2008 | N/A | N/A |  |  |  | 12/18/2016 | 12/18/2016 | 12/26/2016 | N | No
T158 | Elk Garden-Junction 138kV |  | WV | Mineral | Withdrawn | APS | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t158_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 7/24/2008 |  | 11/30/2010 |  |  | N | No
T159 | Bergen 230kV |  | NJ | Hudson | Withdrawn | PSEG | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t159_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 5/7/2008 |  | 6/1/2011 |  |  | N | No
T16 | Kelso Gap 138kV | Fair Wind Project | MD | Garrett | In Service | APS | 30 | 30 | 6 | 30 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t16_csa.pdf | Document Posted | N/A | N/A |  | 8/20/2007 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 11/15/2015 | N | No
T162 | Lock Haven |  | PA | Clinton | Withdrawn | PPL | 90 | 90 | 63 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t162_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 7/16/2009 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
T163 | Carter Fabrics 115kV |  | VA | Halifax | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t163_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 5/29/2008 | Customer Milestone Not Met | 4/1/2012 |  |  | N | No
T164 | Muskingum River | Muskingum River #5 | OH | Washington | In Service | AEP | 600 | 15 | 15 | 15 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t164_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t164_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T165 | Conesville #5 | Conesville #5 | OH | Coshocton | Deactivated | AEP | 395 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t165_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t165_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T166 | Conesville #6 | Conesville #6 | OH | Coshocton | Deactivated | AEP | 395 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t166_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t166_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T167 | Four Rivers 230kV | Four Rivers NUG CC | VA | Hanover | Withdrawn | Dominion | 287.3 | 190 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t167_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t167_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t167_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t167_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 1/10/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
T168 | Four Rivers 500kV |  | VA | Hanover | Withdrawn | Dominion | 1010 | 1010 | 1010 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t168_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 7/21/2009 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
T169 | Corson |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t169_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/3/2008 | Customer Milestone Not Met | 1/1/2009 |  |  | N | No
T17 774202 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 106 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/774202_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/774202_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/28/2007 | 1/1/2009 | 1/1/2014 |  | 10/7/2008 |  |  |  |  | FF | No
T170 | Graceton |  | MD | Harford | Withdrawn | BGE | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 2/29/2008 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
T171 | Morgantown 69kV | Newburg High Efficiency Flywheel | MD | Charles | Withdrawn | PEPCO | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t171_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/t171_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 7/23/2010 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
T172 | Northwest |  | MD | Baltimore County | Withdrawn | BGE | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 2/29/2008 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
T174 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 930 | 930 | 900 | 930 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t174_csa.pdf | Document Posted | N/A | N/A | 3/22/2018 | 1/31/2008 | N/A | N/A | 9/25/2018 |  |  | 3/1/2019 | 3/1/2019 | 11/18/2018 | N | No
T175 | Tiltonsville 69kV |  | OH | Jefferson | Withdrawn | AEP | 50 | 11 | 11 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t175_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
T176 | Juniata-Branchburg |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T177 | Belmont-Brighton |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T178 | Keystone-Juniata |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T179 | Steel City |  | PA | Northampton | Withdrawn | PPL | 873 | 873 | 873 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t179_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 9/19/2008 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
T18 774383 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 106 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/774383_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/774383_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/28/2007 | 1/1/2009 | 1/1/2014 |  | 10/7/2008 |  |  |  |  | FF | No
T180 | Gainesville 230kV |  | VA | Prince William | Withdrawn | Dominion | 690 | 690 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t180_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t180_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 3/10/2010 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
T182 | TMI 230kV | Three Mile Island 1 | PA | Dauphin | Deactivated | ME | 824 | 14 | 16.8 | 14 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t182_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t182_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 4/10/2015 | 4/10/2015 | 10/22/2015 | N | No
T183 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t183_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 1/3/2013 | Customer Initiated Withdrawal | 10/30/2010 |  |  | N | No
T184 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t184_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 1/3/2013 | Customer Initiated Withdrawal | 10/30/2010 |  |  | N | No
T185 | Lewis |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t185_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/19/2008 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
T186 | England |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t186_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/19/2008 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
T187 | Reybold |  | DE | New Castle | Withdrawn | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t187_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 8/24/2009 | Customer Milestone Not Met | 1/1/2009 |  |  | N | No
T188 863799 |  |  | N/A | N/A | Withdrawn |  | 545 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
T189 863796 |  |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
T19 774404 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 106 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/774404_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/774404_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/28/2007 | 1/1/2009 | 1/1/2014 |  | 10/7/2008 |  |  |  |  | FF | No
T190 863792 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 1045 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/863792_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/863792_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 |  | 11/4/2008 |  |  |  |  | FF | No
T192 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 1.8 | 1.8 | 0 |  | Energy | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 4/30/2008 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
T20 | Falls | Exelon Epuron Solar Energy Center | PA | Bucks | In Service | PECO | 3.3 | 3.3 | 1.1 | 3.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t20_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2007 | N/A | N/A |  |  |  | 12/23/2008 | 12/23/2008 | 4/28/2008 | N | No
T21 805563 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 62 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/805563_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2008 | 6/1/2010 |  | 12/14/2007 |  |  |  |  | FF | No
T22 805594 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/805594_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T23 805597 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/805597_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T24 805598 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 120 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/805598_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T25 805599 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 120 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/805599_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T26 805601 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 62 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/805601_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2008 | 6/1/2010 |  | 12/14/2007 |  |  |  |  | FF | No
T27 | Hyndman 34kV |  | PA | Somerset | Withdrawn | APS | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2007 | N/A | N/A |  | 1/9/2009 | Customer Initiated Withdrawal | 1/1/2010 |  |  | N | No
T28 807067 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 218 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/807067_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/10/2007 | 6/1/2008 | 6/1/2009 |  | 10/29/2007 |  |  |  |  | FF | No
T29 807071 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 218 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/807071_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/10/2007 | 6/1/2009 | 6/1/2010 |  | 10/29/2007 |  |  |  |  | FF | No
T31 807646 | WEC-PJM |  | N/A | N/A | Withdrawn |  | 195 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/807646_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/12/2007 | 6/1/2009 | 6/1/2010 |  | 10/30/2007 |  |  |  |  | FF | No
T32 | Collins |  | SD | McPherson | Withdrawn | ComEd | 2500 | 2500 | 925 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t32_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 12/6/2012 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T33 | Collins II |  | SD | McPherson | Withdrawn | ComEd | 1000 | 1000 | 370 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t33_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T34 | Collins III |  | SD | McPherson | Withdrawn | ComEd | 1500 | 1500 | 555 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t34_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T35 | Byron Wind IV |  | ND | LaMoure | Withdrawn | ComEd | 1500 | 1500 | 300 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t35_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 4/22/2010 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T36 808148 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 62 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/808148_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/13/2007 | 6/1/2010 | 6/1/2012 |  | 6/4/2008 |  |  |  |  | FF | No
T37 | Hegins |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 12/17/2008 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
T38 | Delco Tap 230kV |  | PA | Delaware | Withdrawn | PECO | 900 | 900 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 9/8/2008 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
T39 | Coudersport 46kV |  | PA | Potter | Withdrawn | APS | 18 | 18 | 3.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 12/6/2010 | Customer Initiated Withdrawal | 3/31/2011 | 3/31/2011 |  | N | No
T40 | South Harrington |  | DE | Kent | Withdrawn | DPL | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t40_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 7/21/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
T41 | Kearny 138kV | Kearny #13 | NJ | Hudson | In Service | PSEG | 178 | 178 | 178 | 178 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t41_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t41_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t41_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t41_csa.pdf | Document Posted | N/A | N/A |  | 9/19/2007 | N/A | N/A |  |  |  | 8/31/2012 | 8/31/2012 | 5/7/2012 | N | No
T42 | Kearny 138kV | Kearny #14 | NJ | Hudson | In Service | PSEG | 89 | 89 | 89 | 89 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t42_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t42_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t42_csa.pdf | Document Posted | N/A | N/A |  | 9/19/2007 | N/A | N/A |  |  |  | 8/31/2012 | 8/31/2012 | 5/7/2012 | N | No
T43 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 178 | 178 | 178 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t43_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/19/2007 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 6/1/2012 | 6/1/2012 |  | N | No
T44 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 205 | 205 | 205 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t44_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t44_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2007 | N/A | N/A |  | 7/28/2009 | Customer Milestone Not Met | 9/19/2014 | 9/19/2014 |  | N | No
T45 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 205 | 205 | 205 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t45_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2007 | N/A | N/A |  | 4/10/2012 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
T46 810954 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 80 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/811015_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/811015_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/20/2007 | 6/1/2010 | 6/1/2015 |  | 10/3/2008 |  |  |  |  | FF | No
T47 | Mt. Storm-Doubs 500kV |  | VA | Unknown | Withdrawn | Dominion | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/t47_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2007 | N/A | N/A |  | 12/17/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
T48 | Coldwater-Rossburg 69kV |  | OH | Mercer | Withdrawn | Dayton | 40 | 40 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t48_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 5/9/2012 | Customer Initiated Withdrawal | 11/30/2013 |  |  | N | No
T49 | Steel City | Bethlehem Gen Facility Units 1 - 8 | PA | Northampton | In Service | PPL | 1134 | 42 | 42 | 42 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/6/2009 | 5/6/2009 | 5/6/2009 | N | No
T51 | Hay Road | Hay Road Units 1, 2, 3, 4 | DE | New Castle | In Service | DPL | 565 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t51_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/26/2010 | 5/26/2010 | 5/26/2010 | N | No
T52 | Red Lion 500kV | Hay Road Units 5, 6, 7, 8 | DE | New Castle | In Service | DPL | 565 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t52_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t52_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/1/2008 | 5/1/2008 | 5/1/2008 | N | No
T53 | Delaware City | Delaware City Unit #10 | DE | New Castle | In Service | DPL | 23.3 | 7.3 | 7.3 | 7.3 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 6/1/2008 |  | 6/1/2008 | N | No
T54 | Cumberland 138kV | Cumberland Unit 1 | NJ | Cumberland | In Service | AEC | 93.4 | 9.4 | 9.4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t54_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t54_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 8/12/2010 | 8/12/2010 | 8/12/2010 | N | No
T55 | Sherman Ave | Sherman Avenue Unit 1 | NJ | Cumberland | In Service | AEC | 93.4 | 12.4 | 12.4 | 12.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t55_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/3/2010 | 5/3/2010 | 5/3/2010 | N | No
T56 | Christiana | Christiana Units #11 & 14 | DE | New Castle | In Service | DPL | 53.4 | 8.4 | 8.4 | 8.4 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t56_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t56_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t56_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/31/2009 | 5/31/2009 | 5/31/2009 | N | No
T57 | Middle |  | NJ | Cape May | Withdrawn | AEC | 109.2 | 22.2 | 22.2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T59 | Mickleton |  | NJ | Gloucester | In Service | AEC | 73.4 | 14.4 | 14.4 | 7.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t59_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 7/7/2011 | 7/7/2011 | 7/7/2011 | N | No
T60 | Missouri Ave |  | NJ | Atlantic | Withdrawn | AEC | 798 | 10.5 | 10.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t60_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T61 | Cedar |  | NJ | Ocean | Withdrawn | AEC | 68.3 | 8.3 | 8.3 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T63 | Carlls Corner |  | NJ | Cumberland | Withdrawn | AEC | 102.2 | 27.2 | 27.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t63_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T66 | Tasley | Tasley | VA | Accomack | In Service | DPL | 33 | 6.7 | 6.7 | 6.7 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t66_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t66_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 3/26/2009 | 3/26/2009 | 3/26/2009 | N | No
T67 | West | West #1 | DE | New Castle | In Service | DPL | 20.3 | 5.3 | 5.3 | 5.3 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t67_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t67_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t67_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 4/1/2009 | 4/1/2009 | 4/1/2009 | N | No
T68 | Edgemoor | Edgemoor #10 | DE | New Castle | In Service | DPL | 18.2 | 5.2 | 5.2 | 5.2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t68_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t68_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t68_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 4/1/2009 | 4/1/2009 | 4/1/2009 | N | No
T69 811670 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 171 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/811670_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/21/2007 | 6/1/2010 | 6/1/2011 |  | 1/4/2008 |  |  |  |  | FF | No
T70 811671 | CPLE-PJM |  | N/A | N/A | Withdrawn |  | 172 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/21/2007 | 6/1/2010 | 6/1/2011 |  | 9/24/2007 |  |  |  |  | FF | No
T71 811672 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 218 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/811672_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/21/2007 | 6/1/2010 | 6/1/2011 |  | 1/4/2008 |  |  |  |  | FF | No
T72 812613 | NYISJK-PJM-NYISABC |  | N/A | N/A | Confirmed |  | 1000 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/24/2007 | 5/1/2012 | 5/1/2017 | [6 empty] | FF | No
T73 | Hanging Rock 765kV | Hanging Rock CC2 | OH | Lawrence | In Service | AEP | 1240 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T74 | Elgin | Elgin Energy Center | IL | Kane | In Service | ComEd | 484 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t74_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t74_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2007 | N/A | N/A |  |  |  | 9/1/2007 |  | 1/8/2013 | N | No
T75 | South River 230kV | South River | NJ | Middlesex | In Service | JCPL | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t75_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t75_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t75_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t75_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2007 | N/A | N/A |  |  |  | 4/16/2009 | 4/16/2009 | 11/15/2012 | N | No
T76 | South River 230 kV | South River | NJ | Middlesex | In Service | JCPL | 307 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t76_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t76_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t76_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2007 | N/A | N/A |  |  |  | 6/15/2009 |  | 11/15/2012 | N | No
T77 | Linden 230kV | Linden 1 & 2 | NJ | Union | In Service | PSEG | 1570 | 44 | 44 | 44 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t77_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t77_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 6/1/2008 | N | No
T78 | Arnolds Corner 34.5kV | King George Renewable Energy Facility | VA | King George | In Service | Dominion | 9.8 | 9.8 | 8.5 | 9.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t78_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t78_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t78_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t78_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 5/4/2010 | 5/4/2010 | 5/4/2010 | N | No
T79 | Shacklefords 34.5kv | Middle Pennisula Gas to Energy Power Plant | VA | Gloucester | In Service | Dominion | 6.2 | 6.2 | 6.2 | 6.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t79_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t79_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 10/1/2009 | 10/1/2009 | 10/1/2009 | N | No
T80 818375 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 436 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/818375_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/8/2007 | 6/1/2010 | 6/1/2011 |  | 1/4/2008 |  |  |  |  | FF | No
T81 | Cedar 230kV |  | NJ | Ocean | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t81_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 7/18/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
T82 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t82_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t82_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 7/20/2009 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
T83 | Merion 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t83_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 7/9/2008 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
T84 | Corson 138kV |  | NJ | Cape May | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t84_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t84_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 10/15/2012 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
T85 | Roxbury-Blain 23kV | Cumberland County LF | PA | Cumberland | In Service | PENELEC | 6.4 | 6.4 | 6 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t85_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t85_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t85_csa.pdf | Document Posted | N/A | N/A | 1/26/2009 | 10/16/2007 | N/A | N/A | 1/27/2009 |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
T86 | Bradford 34.5kV | North Tier LF | PA | Bradford | In Service | PENELEC | 1.6 | 1.6 | 1.5 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t86_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t86_csa.pdf | Document Posted | N/A | N/A |  | 10/16/2007 | N/A | N/A | 1/9/2009 |  |  | 7/1/2008 | 7/1/2008 | 7/1/2008 | N | No
T87 822067 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 103 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/18/2007 | 1/1/2008 | 1/1/2009 |  | 10/19/2007 |  |  |  |  | FF | No
T88 822068 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 103 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/18/2007 | 1/1/2008 | 1/1/2009 |  | 10/19/2007 |  |  |  |  | FF | No
T90 823424 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 885 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/823424_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/22/2007 | 6/1/2010 | 6/1/2012 |  | 2/5/2008 |  |  |  |  | FF | No
T92 | Paddtown I Wind 1500 MW |  | IA | Pocahontas | Withdrawn | ComEd | 1500 | 1500 | 300 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2007 | N/A | N/A |  | 9/16/2009 | Customer Initiated Withdrawal | 8/1/2010 |  |  | N | No
T93 | Paddtown II Wind 1500 MW |  | IA | Pocahontas | Withdrawn | ComEd | 1500 | 1500 | 300 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2007 | N/A | N/A |  | 9/16/2009 | Customer Initiated Withdrawal | 8/1/2010 |  |  | N | No
T94 | Cook-Palesades 345kV |  | MI | Van Buren | In Service | ITCI | 1035 | 1035 | 1035 | 1035 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t94_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t94_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t94_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t94_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t94_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2007 | N/A | N/A |  |  |  | 6/30/2016 | 6/30/2016 | 6/1/2016 | N | No
T95 824309 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/824309_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/25/2007 | 6/1/2008 | 6/1/2013 |  | 2/5/2008 |  |  |  |  | FF | No
T96 824313 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/824313_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/25/2007 | 6/1/2008 | 6/1/2013 |  | 2/5/2008 |  |  |  |  | FF | No
T97 824314 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/824314_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/25/2007 | 6/1/2008 | 6/1/2013 |  | 2/5/2008 |  |  |  |  | FF | No
T98 | South Mahwah 69kV |  | NJ | Bergen | Withdrawn | RECO | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2007 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 10/29/2007 |  |  | N | No
T99 | Wempletown-Belvidere 138kV |  | IL | Boone | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t99_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t99_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2007 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
U1-001 864402 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 486 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/864402_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/4/2008 | 6/1/2011 | 6/1/2012 |  | 5/2/2008 |  |  |  |  | FF | No
U1-002 864412 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 162 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/4/2008 | 6/1/2011 | 6/1/2012 |  | 2/6/2008 |  |  |  |  | FF | No
U1-003 864415 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 162 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/4/2008 | 6/1/2011 | 6/1/2012 |  | 2/6/2008 |  |  |  |  | FF | No
U1-004 865838 | FE-PJM |  | N/A | N/A | Retracted |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/865838_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-005 865843 | FE-PJM |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/865843_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-006 866341 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2012 |  | 2/7/2008 |  |  |  |  | FF | No
U1-007 866343 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2012 |  | 2/7/2008 |  |  |  |  | FF | No
U1-008 866347 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 |  | 2/7/2008 |  |  |  |  | FF | No
U1-009 866348 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 |  | 2/7/2008 |  |  |  |  | FF | No
U1-010 | Peach Bottom | Delta | PA | York | In Service | PECO | 575 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/7/2008 | N/A | N/A | 12/21/2010 |  |  | 3/1/2011 | 3/1/2011 | 3/1/2011 | N | No
U1-011 | Minonk II 34.5kV |  | IL | Woodford | Withdrawn | ComEd | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 12/15/2008 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
U1-012 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 630 | 630 | 630 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1012_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 9/3/2009 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-013 | Eddystone |  | PA | Delaware | Withdrawn | PECO | 630 | 630 | 630 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 10/14/2009 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-014 | Cromby |  | PA | Montgomery | Withdrawn | PECO | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 8/15/2008 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-015 | Barbados |  | PA | Montgomery | Withdrawn | PECO | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 6/18/2008 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-016 | Muddy Run |  | PA | Lancaster | Withdrawn | PECO | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 6/18/2008 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-017 866822 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-018 866823 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-019 866827 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-020 866830 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-021 866856 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/866856_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2013 |  | 5/2/2008 |  |  |  |  | FF | No
U1-022 866859 |  |  | N/A | N/A | Withdrawn |  | 468 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 3/18/2008 |  |  |  |  | FF | No
U1-023 867311 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 486 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/867311_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/8/2008 | 6/1/2012 | 6/1/2013 |  | 5/2/2008 |  |  |  |  | FF | No
U1-024 | Dequine-Eugene 345kV |  | IN | Warren | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2008 | N/A | N/A |  | 9/8/2008 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U1-025 869760 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2008 | 6/1/2008 | 6/1/2009 |  | 3/5/2008 |  |  |  |  | FF | No
U1-026 869774 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2008 | 6/1/2008 | 6/1/2009 |  | 3/5/2008 |  |  |  |  | FF | No
U1-027 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
U1-028 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
U1-029 | Sherman Ave 138kV |  | NJ | Cumberland | Withdrawn | AEC | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1029_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2008 | N/A | N/A |  | 7/21/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
U1-030 | Missouri Ave |  | NJ | Atlantic | Withdrawn | AEC | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2008 | N/A | N/A |  | 7/21/2009 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
U1-031 | Earleys 230kV |  | NC | Hertford | Withdrawn | Dominion | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u1031_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/19/2008 | N/A | N/A |  | 12/3/2010 | Customer Initiated Withdrawal | 6/30/2012 | 6/30/2012 |  | N | No
U1-032 | Hopewell 230kV |  | VA | City of Hopewell | Deactivated | Dominion | 112.5 | 20 | 0 | 20 | Energy | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_032_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/20/2008 | N/A | N/A |  |  |  | 9/28/2009 | 9/28/2009 | 9/28/2009 | N | No
U1-033 | Miami Fort 345kV |  | OH | Hamilton | Withdrawn | Dayton | 180 | 4 | 4 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2008 | N/A | N/A |  | 7/18/2008 | Customer Initiated Withdrawal | 2/6/2008 |  |  | N | No
U1-034 | Miami Fort 345kV |  | OH | Hamilton | Withdrawn | Dayton | 180 | 4 | 4 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2008 | N/A | N/A |  | 7/18/2008 | Customer Initiated Withdrawal | 2/6/2008 |  |  | N | No
U1-034A 874121 | PJM-CIN |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/874121_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/21/2008 | 6/1/2008 | 6/1/2009 |  | 5/21/2008 |  |  |  |  | FF | No
U1-034B 874123 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/21/2008 | 6/1/2008 | 6/1/2009 |  | 4/15/2008 |  |  |  |  | FF | No
U1-035 875042 | FE-PJM |  | N/A | N/A | Retracted |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/875042_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/22/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-036 | Steel Side 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 220 | 220 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1036_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2008 | N/A | N/A |  | 10/29/2009 | Customer Milestone Not Met | 6/1/2011 | 6/1/2011 |  | N | No
U1-037 | LaSalle-Plano 345kV |  | IL | Lasalle | Withdrawn | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2008 | N/A | N/A |  | 7/12/2010 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
U1-038 | Millheim |  | PA | Centre | Withdrawn | APS | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1038_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2008 | N/A | N/A |  | 1/27/2010 |  | 12/1/2010 |  |  | N | No
U1-039 877998 | NYIS-PJM |  | N/A | N/A | Retracted |  | 774 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/877998_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/28/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-040 878534 | NYIS-PJM-FE |  | N/A | N/A | Withdrawn |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/29/2008 | 4/1/2009 | 4/1/2010 |  | 3/21/2008 |  |  |  |  | FF | No
U1-041 882124 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/7/2008 | 6/1/2011 | 6/1/2012 |  | 3/17/2008 |  |  |  |  | FF | No
U1-042 885633 | PJM-NIPS |  | N/A | N/A | Withdrawn |  | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/885633_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/14/2008 | 6/1/2008 | 6/1/2009 |  | 6/12/2008 |  |  |  |  | FF | No
U1-043 885634 | PJM-NIPS |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/14/2008 | 6/1/2008 | 6/1/2009 |  | 3/19/2008 |  |  |  |  | FF | No
U1-044 | Frederick County VA Regional Landfill | Fredrick County Regional LF | VA | Frederick | In Service | APS | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u1044_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/18/2008 | N/A | N/A |  |  |  | 11/4/2010 | 11/4/2010 | 1/1/2009 | N | No
U1-045 886741 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/886741_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/17/2008 | 6/1/2012 | 6/1/2014 |  | 5/7/2008 |  |  |  |  | FF | No
U1-046 886748 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 150 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/886748_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/17/2008 | 6/1/2012 | 6/1/2015 |  | 5/7/2008 |  |  |  |  | FF | No
U1-047 887539 | PJM-NIPS |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/19/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
U1-048 | Reichs Ford Landfill | Reichs LF | MD | Frederick | Deactivated | APS | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u1048_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/24/2008 | N/A | N/A | 4/22/2010 |  |  | 5/3/2010 | 5/3/2010 | 2/1/2009 | N | No
U1-049 | Kankakee #4 138kV |  | IL | Kankakee | Withdrawn | ComEd | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1049_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2008 | N/A | N/A |  | 12/6/2013 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
U1-050 | Clearfield |  | PA | Clearfield | Withdrawn | PENELEC | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1050_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2008 | N/A | N/A |  | 5/12/2009 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U1-051 | Clearfield |  | PA | Clearfield | Withdrawn | PENELEC | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2008 | N/A | N/A |  | 1/9/2012 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U1-052 889837 | Duquesne-PJM |  | N/A | N/A | Confirmed |  | 1188 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2008 | 9/9/2008 | 9/9/2009 | [6 empty] | FF | No
U1-053 889882 | FE-PJM |  | N/A | N/A | Withdrawn |  | 1188 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2008 | 9/9/2008 | 9/9/2013 | [6 empty] | FF | No
U1-054 | Calumet | River Energy Center | IL | Cook | In Service | ComEd | 327 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/26/2008 | N/A | N/A |  |  |  | 3/28/2008 |  | 1/25/2013 | N | No
U1-055 890480 | PJM-NIPS |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/890480_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/27/2008 | 6/1/2008 | 6/1/2009 |  | 6/12/2008 |  |  |  |  | FF | No
U1-056 | Lewis 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 45.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1056_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u1056_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2008 | N/A | N/A |  | 7/14/2014 | Customer Initiated Withdrawal | 4/1/2014 |  |  | N | No
U1-057 | North Lebanon |  | PA | Lebanon | Withdrawn | ME | 950 | 950 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1057_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2008 | N/A | N/A |  | 1/28/2010 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U1-058 | Olive-Dumont 345kV |  | IN | St. Joseph | Withdrawn | AEP | 586 | 586 | 586 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2008 | N/A | N/A |  | 1/8/2009 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
U1-059 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 48.3 | 48.3 | 9.6 | 48.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u1059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_059_csa.pdf | Document Posted | N/A | N/A |  | 4/2/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/15/2017 | N | No
U1-060 | East Lima-South Kenton 138kV |  | OH | Hardin | Withdrawn | AEP | 151.8 | 151.8 | 19.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1060_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2008 | N/A | N/A |  | 1/23/2013 | Customer Initiated Withdrawal | 4/1/2011 |  |  | N | No
U1-061 893756 | Duquesne-PJM |  | N/A | N/A | Confirmed |  | 141 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/2/2008 | 9/9/2008 | 9/9/2009 | [6 empty] | FF | No
U1-062 893757 | FE-PJM |  | N/A | N/A | Withdrawn |  | 141 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/2/2008 | 9/9/2008 | 9/9/2013 | [6 empty] | FF | No
U1-063 894818 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 29 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/3/2008 | 6/1/2010 | 6/1/2011 |  | 4/15/2008 |  |  |  |  | FF | No
U1-064 894826 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 29 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/894826_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/894826_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/3/2008 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
U1-065 | Middle 69kV |  | NJ | Cape May | Withdrawn | AEC | 97 | 20 | 20 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1065_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/7/2008 | N/A | N/A |  | 7/28/2009 | Customer Initiated Withdrawal | 5/1/2009 |  |  | N | No
U1-066 | Carlls Corner 69kV | Carll's Corner Units 1 & 2 | NJ | Cumberland | Deactivated | AEC | 91 | 18 | 18 | 6 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_066_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2008 | N/A | N/A |  |  |  | 6/24/2011 | 6/24/2011 | 6/24/2011 | N | No
U1-067 | Honey Brook | Granger of Honeybrook | PA | Lancaster | In Service | PPL | 3.2 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_067_csa.pdf | Document Posted | N/A | N/A |  | 4/9/2008 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
U1-068 | York 115kV | York | PA | Lancaster | Deactivated | ME | 51 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_068_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  |  |  | 2/28/2011 | 2/28/2011 | 2/28/2011 | N | No
U1-069 | Emsworth Locks & Dam |  | PA | Allegheny | Withdrawn | DL | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1069_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-070 | Dashields Lock & Dam |  | PA | Allegheny | Withdrawn | DL | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1070_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 9/11/2008 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-071 | CW Bill Young Lock & Dam |  | PA | Allegheny | Withdrawn | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1071_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 10/23/2009 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-072 | Braddock Lock & Dam |  | PA | Allegheny | Withdrawn | DL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1072_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 8/6/2009 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-073 | Allegheny Lock & Dam #7 |  | PA | Allegheny | Withdrawn | APS | 16 | 16 | 16 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1073_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-074 | Point Marion Lock & Dam |  | PA | Fayette | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1074_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-075 | Sutton Dam |  | WV | Braxton | Withdrawn | APS | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u1075_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 7/10/2013 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-076 | Allegheny Lock & Dam #2 |  | PA | Allegheny | Withdrawn | DL | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1076_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-077 | Allegheny Lock & Dam #4 |  | PA | Allegheny | Withdrawn | APS | 16 | 16 | 16 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 7/24/2009 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-078 | Tionesta Dam |  | PA | Forest | Withdrawn | PENELEC | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 11/10/2008 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-079 | Opekiska Lock & Dam |  | WV | Monongalia | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1079_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-080 | Montgomery Lock & Dam |  | PA | Beaver | Withdrawn | DL | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1080_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-081 | Monongahela Lock & Dam #4 |  | PA | Westmoreland | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1081_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-082 | Maxwell Lock & Dam |  | PA | Fayette | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1082_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-083 | Hildebrand Lock & Dam |  | WV | Monongalia | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1083_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 7/24/2009 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-086 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/17/2008 | N/A | N/A |  | 12/19/2009 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
U1-087 | Dequine 345kV |  | IN | Benton | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2008 | N/A | N/A |  | 1/2/2013 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
U1-088 | Dequine 345kV |  | IN | Benton | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2008 | N/A | N/A |  | 1/2/2013 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
U1-089 | Paper Tap 69kV | Kimberly Clark | PA | Delaware | Deactivated | PECO | 20 | 0 | 20 | 0 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1089_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/18/2008 | N/A | N/A |  |  |  | 10/15/2008 |  | 10/15/2008 | N | No
U1-090 | Killen 345kV | Killen Electric Generating Station | OH | Adams | Deactivated | Dayton | 612 | 12 | 12 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1090_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_090_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/22/2008 | N/A | N/A |  |  |  | 5/31/2008 |  |  | N | No
U1-091 902731 | FE-PJM |  | N/A | N/A | Withdrawn |  | 1329 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/22/2008 | 6/1/2011 | 6/1/2012 |  | 5/8/2008 |  |  |  |  | FF | No
U1-093 | Ladysmith 230kV | Ladysmith Unit 3 | VA | Caroline | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1093_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_093_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 4/8/2008 | 4/8/2008 | 10/1/2009 | N | No
U1-094 | Ladysmith 230kV | Ladysmith Unit 4 | VA | Caroline | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1094_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_094_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 4/8/2008 | 4/8/2008 | 10/1/2009 | N | No
U1-095 | Ladysmith 230kV | Ladysmith Unit 5 | VA | Caroline | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1095_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_095_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_095_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 3/31/2009 | 3/31/2009 | 3/31/2009 | N | No
U1-096 | Reybold |  | DE | New Castle | Withdrawn | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2008 | N/A | N/A |  | 8/26/2008 | Customer Milestone Not Met | 1/1/2009 |  |  | N | No
U1-097 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1097_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2008 | N/A | N/A |  | 12/9/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
U1-098 906034 | Duquesne-PJM |  | N/A | N/A | Confirmed |  | 1788 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2008 | 6/1/2011 | 6/1/2012 | [6 empty] | FF | No
U1-099 | Joliet 4 MW |  | IL | Will | Withdrawn | ComEd | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2008 | N/A | N/A |  | 4/21/2010 | Customer Initiated Withdrawal | 3/31/2011 | 3/31/2011 |  | N | No
U2-002 908694 | PJM-FE |  | N/A | N/A | Retracted |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/908694_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/6/2008 | 1/1/2009 | 1/1/2010 |  | 7/31/2008 |  |  |  |  | FF | No
U2-003 | Wempletown |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2008 | N/A | N/A |  | 4/29/2009 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
U2-004 911979 | MEC-PJM |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/911979_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/13/2008 | 4/1/2009 | 4/1/2010 |  | 7/31/2008 |  |  |  |  | FF | No
U2-005 | Branchburg-Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1010 | 1010 | 1010 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
U2-006 | Branchburg-Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1010 | 1010 | 1010 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
U2-007 912864 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 700 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-008 912865 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 500 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-009 912866 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-010 912867 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-011 912869 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 700 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2016 |  | 6/12/2008 |  |  |  |  | FF | No
U2-012 913162 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/16/2008 | 6/1/2011 | 6/1/2016 |  | 6/12/2008 |  |  |  |  | FF | No
U2-013 | Northeast 34.5kV | Richmond Energy Facility | VA | Henrico | In Service | Dominion | 8 | 8 | 8 | 6.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_013_csa.pdf | Document Posted | N/A | N/A | 9/15/2011 | 5/16/2008 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 12/29/2011 | N | No
U2-014 915083 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 1600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/20/2008 | 6/1/2011 | 6/1/2012 |  | 6/12/2008 |  |  |  |  | FF | No
U2-015 | Harwood-E. Palmerton 230kV | Buck Mountain Wind Farm | PA | Columbia | Withdrawn | PPL | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2015_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_015_csa.pdf | Document Posted | N/A | N/A |  | 5/22/2008 | N/A | N/A |  | 11/15/2019 |  | 10/1/2019 | 10/1/2019 |  | N | No
U2-016 | East Towanda-Grover 230kV |  | PA | Bradford | Withdrawn | PENELEC | 85 | 85 | 11.05 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2008 | N/A | N/A |  | 1/13/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
U2-017 | Tazewell-Baileysville 138kV |  | VA | Tazewell | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2008 | N/A | N/A |  | 10/30/2008 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
U2-024 | Tazewell-Baileyville 138kV |  | WV | McDowell | Withdrawn | AEP | 900 | 900 | 825 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2008 | N/A | N/A |  | 1/6/2009 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
U2-025 | Brooke County Landfill |  | WV | Brooke | Withdrawn | APS | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2025_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 2/23/2009 | Customer Milestone Not Met | 7/31/2009 |  |  | N | No
U2-026 | Antwerp 69kV |  | OH | Paulding | Withdrawn | AEP | 30 | 30 | 3.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 12/9/2008 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-027 | Mehoopany 115kV |  | PA | Bradford | Withdrawn | PENELEC | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 12/8/2008 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-028 | Meadow Brook Capacitor |  | VA | Frederick | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IARR 64.5 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/u2028_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/u2_028_csa.pdf | Document Posted | N/A | N/A |  | 5/30/2008 | N/A | N/A |  |  |  | 10/26/2009 | 10/26/2009 | 6/1/2009 | S | No
U2-028A_AT1 | Ironville | FDS Coke Plant | OH | Lucas | Withdrawn | ATSI | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2028a_at1_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2028a_at1_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2028a_at1_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_028a_at1_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_028A_at1_csa.pdf | Document Posted | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 2/5/2015 | Customer Milestone Not Met | 7/1/2017 | 7/1/2017 |  | N | No
U2-029 | Passyunk |  | PA | Philadelphia | Withdrawn | PECO | 1.3 | 1.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2029_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/5/2008 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | No
U2-030 | Four Mile Ridge Wind 138kV | Four Mile Ridge WF - 24 WT | MD | Garrett | In Service | APS | 60 | 60 | 7.8 | 40 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_030_csa.pdf | Document Posted | N/A | N/A | 11/20/2014 | 6/5/2008 | N/A | N/A | 11/20/2014 |  |  | 12/23/2017 | 12/23/2017 | 11/21/2014 | N | No
U2-031 | Kings Fork 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion | 30 | 30 | 24.75 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2031_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_031_csa.pdf | Document Posted | N/A | N/A |  | 6/9/2008 | N/A | N/A |  | 8/24/2010 | Customer Milestone Not Met | 6/1/2011 | 6/1/2011 |  | N | No
U2-032 | Elbow Mountain |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2008 | N/A | N/A |  | 12/4/2008 | Customer Milestone Not Met | 10/1/2010 |  |  | N | No
U2-033 925392 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 104 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/925392_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/925392_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/9/2008 | 1/1/2009 | 1/1/2010 |  | 4/28/2009 |  |  |  |  | FF | No
U2-034 925394 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 104 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/925394_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/925394_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/9/2008 | 1/1/2009 | 1/1/2010 |  | 4/28/2009 |  |  |  |  | FF | No
U2-035 925395 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 104 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/925395_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/925395_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/9/2008 | 1/1/2009 | 1/1/2010 |  | 4/28/2009 |  |  |  |  | FF | No
U2-036 925941 | PJM-NIPS |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/925941_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/10/2008 | 1/1/2009 | 1/1/2010 |  | 8/25/2008 |  |  |  |  | FF | No
U2-037 925947 | PJM_NIPS |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/925947_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/10/2008 | 1/1/2009 | 1/1/2010 |  | 8/25/2008 |  |  |  |  | FF | No
U2-038 926231 | PJM-CWLP |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/926231_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/11/2008 | 1/1/2009 | 1/1/2010 |  | 8/25/2008 |  |  |  |  | FF | No
U2-039 926237 | PJM-IPL |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/926237_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/11/2008 | 1/1/2009 | 1/1/2010 |  | 9/3/2008 |  |  |  |  | FF | No
U2-040 | Bridgewater-Middlesex 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/12/2008 | N/A | N/A |  | 8/17/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
U2-040A 926830 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 900 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/926830_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/926830_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/12/2008 | 6/1/2011 | 6/1/2016 |  | 4/7/2009 |  |  |  |  | FF | No
U2-040B 926832 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 1600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/926832_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/12/2008 | 6/1/2011 | 6/1/2012 |  | 8/25/2008 |  |  |  |  | FF | No
U2-041 | East Lima-Marysville 345kV | Hardin Wind Farm | OH | Hardin | Withdrawn | AEP | 166.4 | 166.4 | 21.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2041_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2041_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_041_csa.pdf | Document Posted | N/A | N/A |  | 6/13/2008 | N/A | N/A |  | 12/5/2019 |  | 12/31/2019 | 12/31/2019 |  | N | No
U2-042 | East Lima-South Kenton 138kV |  | OH | Hardin | Withdrawn | AEP | 201 | 201 | 26.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/13/2008 | N/A | N/A |  | 7/27/2010 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
U2-044 | Lewis 138kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/20/2008 | N/A | N/A |  | 11/21/2008 |  | 3/1/2011 |  |  | N | No
U2-045 | Huron 69kV | Fishermen's Atlantic City Windfarm (FACW) | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_045_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2008 | N/A | N/A |  | 3/12/2019 |  | 1/27/2019 | 1/27/2019 |  | N | No
U2-046 | Roseland 500kV |  | NJ | Essex | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 660/TWR 670 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2046_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2008 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 12/1/2013 |  |  | S | No
U2-047 | Deans 500kV |  | NJ | Unknown | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 660/TWR 672 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2008 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 12/1/2013 |  |  | S | No
U2-048 | Cox's Corner-Croydon 230kV |  | NJ | Burlington | Withdrawn | PSEG | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 5/15/2012 |  |  | N | No
U2-049 | Monmouth |  | NJ | Monmouth | Withdrawn | JCPL | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 2/9/2011 | Customer Initiated Withdrawal | 5/15/2012 |  |  | N | No
U2-050 | Lonesome Pine 138kV |  | VA | Tazewell | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2050_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-051 | Glen Lyn-Wythe 138kV |  | VA | Giles | Withdrawn | AEP | 60 | 60 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2051_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2051_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-052 | S. Bluefield-Wythe 69kV |  | VA | Bland | Withdrawn | AEP | 80 | 80 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 3/18/2009 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U2-053 | Martins Creek |  | PA | Northampton | Withdrawn | PPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 6/2/2009 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
U2-054 | Weissport | Beltzville Hydro Dam | PA | Carbon | Withdrawn | PPL | 2.6 | 2.6 | 2.6 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u2054_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/25/2008 | N/A | N/A |  | 2/26/2014 |  | 6/1/2014 | 6/1/2014 |  | N | No
U2-055 | Karthaus-Milesburg 230kV |  | PA | Centre | Withdrawn | APS | 89.1 | 89.1 | 11.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2055_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2055_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/27/2008 | N/A | N/A |  | 8/7/2013 | Customer Milestone Not Met | 7/1/2012 |  |  | N | No
U2-056 | West Point |  | VA | Unknown | Withdrawn | Dominion | 88.7 | 88.7 | 88.7 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2056_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2008 | N/A | N/A |  | 10/12/2010 | Customer Milestone Not Met | 12/1/2010 | 12/1/2010 |  | N | No
U2-057 | Hopewell 34.5kV |  | VA | City of Hopewell | Withdrawn | Dominion | 47.6 | 47.6 | 47.6 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2057_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2008 | N/A | N/A |  | 10/12/2010 | Customer Milestone Not Met | 12/1/2010 | 12/1/2010 |  | N | No
U2-058 | Kincaid Wind |  | IL | Christian | Withdrawn | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2008 | N/A | N/A |  | 7/20/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U2-059 | Foul Rift 13kV | Belvidere SP | NJ | Warren | In Service | JCPL | 2 | 2 | 0.76 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/7/2008 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 12/12/2011 | N | No
U2-060 | Camden | Pennsauk LF | NJ | Camden | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2060_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/7/2008 | N/A | N/A |  | 4/15/2009 | Customer Initiated Withdrawal | 12/15/2004 |  |  | N | No
U2-061 | Garrett County | Roth Rock WF | MD | Garrett | In Service | APS | 50 | 50 | 6.5 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_061_csa.pdf | Document Posted | N/A | N/A | 11/23/2010 | 7/7/2008 | N/A | N/A | 12/5/2010 |  |  | 1/5/2011 | 1/5/2011 | 12/1/2009 | N | No
U2-062 | Randolph 138kV |  | OH | Darke | Withdrawn | AEP | 187.5 | 187.5 | 24.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2062_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2062_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/9/2008 | N/A | N/A |  | 7/8/2013 | Customer Initiated Withdrawal | 9/30/2012 | 9/30/2012 |  | N | No
U2-063 | Croydon 230kV | Croydon Generating Station | PA | Bucks | In Service | PECO | 391 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2063_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_063_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/10/2008 | N/A | N/A |  |  |  | 7/1/2008 |  | 1/2/2014 | N | No
U2-064 | Branchburg-Ramapo 500kV |  | NJ | Sussex | Withdrawn | PSEG | 1000 | 1000 | 1000 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2008 | N/A | N/A |  | 8/17/2009 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
U2-065 | Kankakee 138kV |  | IL | Iroquois | Withdrawn | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2065_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2008 | N/A | N/A |  | 7/28/2010 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
U2-066 | Marysville-SW Lima 345kV |  | OH | Hardin | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2066_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2008 | N/A | N/A |  | 12/19/2011 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
U2-067 | Eldred-Pine Grove 69kV | Westwood Generation | PA | Bucks | In Service | PPL | 32.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/15/2008 | N/A | N/A |  |  |  | 7/1/2008 |  | 12/29/2008 | N | No
U2-068 | Mount Storm-Valley 500kV | Lost River WF | VA | Rockingham | Withdrawn | Dominion | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_068_csa.pdf | Document Posted | N/A | N/A |  | 7/21/2008 | N/A | N/A |  | 1/10/2014 |  | 6/1/2018 | 6/1/2018 |  | N | No
U2-069 | Frackville | Broad Mountain WF | PA | Schuylkill | Withdrawn | PPL | 56 | 56 | 7.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2069_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_069_csa.pdf | Document Posted | N/A | N/A |  | 7/21/2008 | N/A | N/A |  | 12/13/2010 | Customer Initiated Withdrawal | 6/1/2014 | 6/1/2014 |  | N | No
U2-070 | Somerset |  | PA | Somerset | Withdrawn | PENELEC | 7.5 | 7.5 | 0.98 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2070_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/21/2008 | N/A | N/A |  | 7/2/2009 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-071 | Tazewell-Saltville 138kV |  | VA | Tazewell | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2071_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2008 | N/A | N/A |  | 2/27/2009 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
U2-072 | East Lima-Marysville 345kV | Scioto Ridge Wind Farm | OH | Hardin | In Service | AEP | 250 | 250 | 32.5 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_072_csa.pdf | Document Posted | N/A | N/A | 4/1/2020 | 7/23/2008 | N/A | N/A | 12/17/2020 |  |  | 5/31/2021 | 5/31/2021 | 12/17/2020 | N | No
U2-073 | Frostburg 138kV II | Twin Ridges Wind Farm | PA | Somerset | In Service | APS | 139.4 | 139.4 | 18.1 | 139 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2073_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_073_csa.pdf | Document Posted | N/A | N/A |  | 7/23/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/21/2012 | N | No
U2-074 | Peach Bottom-Rock Springs 500kV |  | PA | Lancaster | Withdrawn | PECO | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2008 | N/A | N/A |  | 8/3/2012 | Customer Initiated Withdrawal | 10/1/2012 |  |  | N | No
U2-075 | Susquehanna-Roseland 500kV |  | PA | Lackawanna | Withdrawn | PPL | 636 | 636 | 636 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2008 | N/A | N/A |  | 4/13/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
U2-076 | Falls | Grows North LF | PA | Bucks | Withdrawn | PECO | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_076_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2008 | N/A | N/A |  | 1/7/2014 | Customer Milestone Not Met | 3/1/2011 | 3/1/2011 |  | N | No
U2-077 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 300 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 300; NF/TWR 330 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/u2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/25/2008 | N/A | N/A |  |  |  | 10/1/2009 |  | 6/1/2011 | S | No
U2-080 | South Portsmouth 138kV |  | KY | Greenup | Withdrawn | AEP | 134 | 134 | 134 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2080_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2080_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 7/13/2012 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
U2-081 | Chalk Point 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-082 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2082_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-083 | Chalk Point 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-084 | Dickerson |  | MD | Montgomery | Withdrawn | PEPCO | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-085 | Sakron-Prince #3 138kV |  | PA | Lancaster | Withdrawn | PPL | 11.4 | 11.4 | 11.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2085_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 4/15/2009 | Customer Milestone Not Met | 12/1/2009 |  |  | N | No
U2-086 | Airydale 500kV |  | PA | Huntingdon | Withdrawn | PENELEC | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 9/17/2010 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-087 | Juniata 500 MVAR SVC |  | PA | Dauphin | Withdrawn | PPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/u2087_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 7/6/2012 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-088 | Meadow Brook 500kV |  | VA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 1/5/2012 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-089 | Kemptown 500kV |  | PA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 9/16/2008 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-090 | Desoto-Tanners Creek 345kV | HeadwatersWF | IN | Randolph | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2090_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_090_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2008 | N/A | N/A |  |  |  | 10/31/2014 | 10/31/2014 | 10/27/2014 | N | No
U2-091 | Delaware-Richmond 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2091_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U2-092 | Delaware-Centerville 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2092_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U2-093 954414 | PJM-LGEE |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/954414_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/30/2008 | 1/1/2010 | 8/1/2015 |  | 3/12/2009 |  |  |  |  | FF | No
U2-094 | Foul Rift 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 19 | 19 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 9/2/2009 | Customer Initiated Withdrawal | 12/31/2010 | 12/31/2010 |  | N | No
U2-095 | Nelson 345kV |  | IL | Lee | Withdrawn | ComEd | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U2-096 | Lock Haven-Lycoming #1 69kV |  | PA | Lycoming | Withdrawn | PPL | 1.5 | 1.5 | 1.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 11/10/2008 | Customer Initiated Withdrawal | 3/31/2009 |  |  | N | No
U2-098 | South Amboy |  | NJ | Middlesex | Withdrawn | JCPL | 1320 | 1320 | 1320 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 8/27/2009 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
U2-099 | Martins Creek 230kV |  | PA | Northampton | Withdrawn | PPL | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2099_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 11/30/2009 | Customer Initiated Withdrawal | 5/1/2014 | 5/1/2014 |  | N | No
U2-100 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 800 |  |  |  | Energy | Merchant Transmission |  | AC | NF/TWR 800 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/26/2011 | Customer Initiated Withdrawal | 12/1/2011 |  |  | S | No
U2-101 | Nelson Bio |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 9/5/2012 | Customer Initiated Withdrawal | 12/31/2011 | 12/31/2011 |  | N | No
U2-102 955153 | CPLE-PJM |  | N/A | N/A | Confirmed |  | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/955153_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/955153_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/31/2008 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
U2-103 955155 | CPLE-PJM |  | N/A | N/A | Confirmed |  | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/955155_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/955155_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/31/2008 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
U2-104 955156 | CPLE-PJM |  | N/A | N/A | Confirmed |  | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/955156_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/955156_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/31/2008 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
U3-001 | Barbadoes 34kV | AES Energy Storage Unit | PA | Montgomery | Withdrawn | PECO | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u3001_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/11/2008 | N/A | N/A |  | 9/26/2018 |  | 8/31/2008 |  | 8/31/2008 | N | No
U3-002 | Deer Creek-Fisher Body-Mullin 138kV | Wildcat Wind Farm I | IN | Madison | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3002_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_002_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_002_csa.pdf | Document Posted | N/A | N/A | 6/1/2012 | 8/13/2008 | N/A | N/A | 10/8/2012 |  |  | 12/31/2012 | 12/31/2012 | 12/26/2012 | N | No
U3-003 | Mt. Olive 69kV | Worcester County Renewable Energy | MD | Worcester | Deactivated | DPL | 2 | 2 | 0 | 0.5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_003_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/14/2008 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 3/1/2012 | N | No
U3-004 | Cecil | Cecil County Landfill | MD | Cecil | Withdrawn | DPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3004_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u3004_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2008 | N/A | N/A |  | 10/4/2013 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
U3-005 | Meadow Brook |  | VA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u3005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u3005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2008 | N/A | N/A |  | 2/1/2012 | Customer Initiated Withdrawal | 12/31/2008 |  |  | S | No
U3-006 967853 | PJM-CPLW |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/967853_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/18/2008 | 6/1/2010 | 6/1/2015 |  | 10/23/2008 |  |  |  |  | FF | No
U3-007 967858 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/967858_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/18/2008 | 6/1/2010 | 6/1/2015 |  | 10/23/2008 |  |  |  |  | FF | No
U3-008 | Mt. Bethel 230kV |  | PA | Northampton | Withdrawn | ME | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2008 | N/A | N/A |  | 4/20/2010 | Customer Initiated Withdrawal | 1/1/2012 |  |  | N | No
U3-009 | Mt. Bethel 230kV |  | PA | Northampton | Withdrawn | ME | 595 | 595 | 595 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2008 | N/A | N/A |  | 4/20/2010 | Customer Initiated Withdrawal | 1/1/2014 |  |  | N | No
U3-010 | Towanda |  | PA | Bradford | Withdrawn | PENELEC | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/22/2008 | N/A | N/A |  | 3/9/2009 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
U3-011 975675 | CPLE-PJM |  | N/A | N/A | Retracted |  | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/975675_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/975675_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/26/2008 | 6/1/2012 | 6/1/2013 |  | 7/8/2009 |  |  |  |  | FF | No
U3-012 | Bradford 115kV |  | PA | McKean | Withdrawn | PENELEC | 85 | 85 | 11 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3012_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2008 | N/A | N/A |  | 3/9/2009 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
U3-013 | Clermont 115kV |  | PA | McKean | Withdrawn | PENELEC | 125 | 125 | 16.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2008 | N/A | N/A |  | 3/9/2009 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
U3-016 | Midlothian 230kV |  | VA | Goochland | Withdrawn | Dominion | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2008 | N/A | N/A |  | 2/23/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
U3-017 | Westvaco 138kV |  | PA | Allegheny | Withdrawn | APS | 12 | 4 | 0 |  | Energy | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3017_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2008 | N/A | N/A |  | 10/22/2010 | Customer Initiated Withdrawal | 8/22/2008 |  |  | N | No
U3-018 | Knieriem |  | PA | Somerset | Withdrawn | PENELEC | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2008 | N/A | N/A |  | 3/3/2009 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
U3-019 989861 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/989861_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2008 | 6/1/2012 | 6/1/2017 |  | 10/28/2008 |  |  |  |  | FF | No
U3-020 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
U3-021 | Silver Lake-Cherry Valley | Garden Prairie Energy Facility | IL | Boone | Withdrawn | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3021_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u3021_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_021_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_021_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2008 | N/A | N/A |  | 5/4/2022 |  | 4/30/2024 | 4/30/2024 |  | N | No
U3-022 | Sherman-Cumberland 138kV |  | NJ | Cumberland | Withdrawn | AEC | 14 | 14 | 5.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2008 | N/A | N/A |  | 2/20/2009 | Customer Initiated Withdrawal | 9/15/2009 |  |  | N | No
U3-023 | Printz 230kV |  | PA | Delaware | Withdrawn | PECO | 720 | 720 | 720 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2008 | N/A | N/A |  | 2/23/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
U3-025 | Elk Garden-Parr Run 138kV |  | WV | Mineral | Withdrawn | APS | 80 | 80 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3025_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2008 | N/A | N/A |  | 2/28/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
U3-026 | Collins |  | IL | Grundy | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u3026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u3026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/9/2008 | N/A | N/A |  | 4/10/2017 |  | 12/31/2020 | 12/31/2020 |  | S | No
U3-027 1010165 | PJM-NYIS |  | N/A | N/A | Withdrawn |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1010165_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/19/2008 | 1/1/2012 | 1/1/2022 |  | 12/2/2008 |  |  |  |  | FF | No
U3-029 | Beaver Valley #1 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 950 | 48 | 37 | 48 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_029_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2008 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 11/15/2013 | N | No
U3-030 | Beaver Valley #2 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 951 | 43 | 38 | 43 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_030_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2008 | N/A | N/A |  |  |  | 11/1/2012 | 11/1/2012 | 11/7/2012 | N | No
U3-031 | Lincoln Generating Facility | Lincoln Generating Facility | IL | Will | In Service | ComEd | 616 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3031_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_031_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/31/2008 | N/A | N/A |  |  |  | 10/31/2009 |  | 1/24/2013 | N | No
U3-032 | Traynor 34.5kV | Britton Road Solar Facility | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u3032_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2008 | N/A | N/A |  | 8/20/2018 |  | 6/1/2012 | 6/1/2012 |  | N | No
U3-033 1030332 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1030332_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/3/2008 | 1/1/2010 | 1/1/2011 |  | 12/19/2008 |  |  |  |  | FF | No
U3-034 1033525 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 905 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1033525_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1033525_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2008 | 6/1/2012 | 6/1/2017 |  | 3/9/2010 |  |  |  |  | FF | No
U4-001 | Howard 138kV | Black Fork Wind | OH | Richland | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4001_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_001_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2008 | N/A | N/A |  | 1/23/2019 |  | 11/3/2019 | 11/3/2019 |  | N | No
U4-002 | Pickens-Monterville 138kV |  | WV | Randolph | Withdrawn | APS | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4002_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2008 | N/A | N/A |  | 12/17/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U4-003 | Olive-Dequine 345kV |  | IN | Jasper | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4003_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2008 | N/A | N/A |  | 1/3/2013 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
U4-004 | York 115kV |  | PA | York | Withdrawn | ME | 162 | 120 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4004_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2008 | N/A | N/A |  | 10/16/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U4-005 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 700 | 700 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2008 | N/A | N/A |  | 11/25/2009 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
U4-006 | Mendota 138kV |  | IL | Lasalle | Withdrawn | ComEd | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2008 | N/A | N/A |  | 9/5/2012 | Customer Initiated Withdrawal | 3/31/2012 | 3/31/2012 |  | N | No
U4-007 | Jennings Randolph Dam |  | MD | Garrett | Withdrawn | APS | 14 | 14 | 13.4 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/11/2008 | N/A | N/A |  | 7/16/2013 | Customer Initiated Withdrawal | 7/2/2013 | 7/2/2013 |  | N | No
U4-008 | South Central Power | Suburban LF | OH | Perry | In Service | AEP | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4008_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4008_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2008 | N/A | N/A |  |  |  | 1/7/2011 | 1/7/2011 | 1/7/2011 | N | No
U4-009 | Louisa 230kV | Louisa Gas Turbines Units 1 through 5 | VA | Orange | In Service | Dominion | 144 | 3 | 3 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4009_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_009_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/17/2008 | N/A | N/A |  |  |  | 5/26/2009 | 5/26/2009 | 5/26/2009 | N | No
U4-009A 1041029 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 29 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1041029_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1041029_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/19/2008 | 6/1/2010 | 6/1/2012 | [6 empty] | FF | No
U4-010 | Pontiac-Latham 345kV |  | IL | Ford | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 1/1/2012 |  |  | N | No
U4-011 | Pontiac Midpoint I 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4011_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U4-012 | Pontiac Midpoint II 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4012_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U4-013 | North Lebanon 230kV |  | PA | Lebanon | Withdrawn | ME | 950 | 950 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/21/2008 | N/A | N/A |  | 6/8/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U4-014 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | In Service | PPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4014_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4014_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_014_csa.pdf | Document Posted | N/A | N/A |  | 11/24/2008 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 11/6/2012 | N | No
U4-015 | Rock Springs 500kV | Rocks Springs 1 & 2 | MD | Cecil | In Service | ODEC | 475 | 8.7 | 8.7 | 8.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/25/2008 | N/A | N/A |  |  |  | 5/7/2009 | 5/7/2009 | 5/31/2009 | N | No
U4-016 | Harwood |  | PA | Luzerne | Withdrawn | PPL | 213 | 48 | 48 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/26/2008 | N/A | N/A |  | 6/1/2009 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
U4-017 | Corder Crossing 138kV |  | WV | Barbour | Withdrawn | APS | 165 | 165 | 21.45 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2008 | N/A | N/A |  | 6/16/2009 | Customer Milestone Not Met | 12/1/2012 |  |  | N | No
U4-018 | Bedington-Harmony Jct 138kV |  | WV | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u4018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2008 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
U4-019 1049345 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 60 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2009 | 6/1/2014 |  | 12/11/2008 |  |  |  |  | FF | No
U4-020 1049348 | PJM-TVA |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1049348_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1049348_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 | [6 empty] | FF | No
U4-021 1049350 | PJM-TVA |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1049350_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 |  | 2/18/2009 |  |  |  |  | FF | No
U4-022 1049352 | PJM-TVA |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1049352_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1049352_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 | [6 empty] | FF | No
U4-023 1049355 | PJM-TVA |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1049355_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1049355_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 | [6 empty] | FF | No
U4-024 1052862 | PJM-TVA |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1052862_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/9/2008 | 6/1/2009 | 6/1/2010 |  | 2/18/2009 |  |  |  |  | FF | No
U4-025 1058858 | PJM-CWLP |  | N/A | N/A | Retracted |  | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1058858_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/18/2008 | 1/1/2010 | 1/1/2011 |  | 4/21/2009 |  |  |  |  | FF | No
U4-026 | Lowmoor-Lexington 230kV | Rocky Ford WF | VA | Botetourt | Withdrawn | Dominion | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4026_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4026_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_026_csa.pdf | Document Posted | N/A | N/A |  | 12/19/2008 | N/A | N/A |  | 8/23/2013 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
U4-027 | Normandy-Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4027_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/22/2008 | N/A | N/A |  | 5/29/2019 |  | 12/31/2018 | 12/31/2018 |  | N | No
U4-028 | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4028_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_028_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  | 11/5/2021 |  | 12/31/2020 | 12/31/2020 |  | N | No
U4-029 | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Withdrawn | AEP | 200 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4029_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4029_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_029_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  | 11/5/2021 |  | 12/31/2020 | 12/31/2020 |  | N | No
U4-030 | Sabrooke 138kV | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 153 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_030_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 6/23/2010 | 6/23/2010 | 6/23/2010 | N | No
U4-031 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2008 | N/A | N/A |  | 4/30/2009 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
U4-032 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 1063 | 400 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2008 | N/A | N/A |  | 5/28/2009 | Customer Milestone Not Met | 4/1/2013 |  |  | N | No
U4-033 | University Park North |  | IL | Will | In Service | ComEd | 540 | 36 | 36 | 36 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4033_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_033_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/31/2008 | N/A | N/A |  |  |  | 6/1/2009 |  | 1/21/2014 | N | No
U4-034 | Conesville #5 | Conesville #5 | OH | Coshocton | Deactivated | AEP | 400 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/2009 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 1/1/2010 | N | No
U4-035 | Conesville #6 | Conesville #6 | OH | Coshocton | Deactivated | AEP | 400 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_035_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/2009 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 1/1/2010 | N | No
U4-036 | Gloucester 26.4kV | Paradise SP | NJ | Gloucester | In Service | PSEG | 5.1 | 5.1 | 1.9 | 5.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_036_csa.pdf | Document Posted | N/A | N/A | 12/22/2010 | 1/28/2009 | N/A | N/A | 12/22/2010 |  |  | 1/4/2011 | 1/4/2011 | 12/31/2009 | N | No
U4-037 | Brokaw-Lanesville 345kV |  | IL | DeWitt | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2009 | N/A | N/A |  | 12/12/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U4-038 | Mullin-Greentown Tap 138kV |  | IN | Madison | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4038_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 5/7/2013 | Customer Initiated Withdrawal | 9/1/2013 |  |  | N | No
U4-039 | Greentown 138kV |  | IN | Madison | Withdrawn | AEP | 710 | 710 | 92.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4039_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 7/20/2015 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | No
U4-040 | Lincoln 13.2kV |  | PA | Adams | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4040_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4040_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-041 | Valley 13.2kV |  | PA | Adams | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4041_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-042 | Hanover 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4042_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-043 | Tolna 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4043_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-044 | Stoverstown 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4044_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-045 | Oil Creek 34.kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4045_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-046 | Teepleville 34.5kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4046_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-047 | Mill Village 34.5kV |  | PA | Erie | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4047_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4047_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-048 | Saegertown 34.5kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4048_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-049 1092401 | PJM-LGEE |  | N/A | N/A | Withdrawn |  | 99 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1092401_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1092401_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/30/2009 | 1/1/2010 | 1/1/2015 |  | 10/14/2009 |  |  |  |  | FF | No
V1-001 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
V1-002 1094626 | TVA-PJM |  | N/A | N/A | Annulled |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1094626_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1094626_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/2/2009 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
V1-003 1096809 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 480 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/4/2009 | 6/1/2012 | 6/1/2017 |  | 2/11/2009 |  |  |  |  | FF | No
V1-004 1102137 | NYIS-PJM |  | N/A | N/A | Retracted |  | 705 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1102137_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2009 | 6/1/2012 | 6/1/2017 |  | 4/21/2009 |  |  |  |  | FF | No
V1-005 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v1005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/v1005_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/12/2009 | N/A | N/A |  | 3/16/2010 | Customer Initiated Withdrawal | 1/1/2010 |  |  | S | No
V1-006 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2009 | N/A | N/A |  | 4/30/2009 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
V1-007 1104452 | PJM-IPL |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1104452_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/16/2009 | 1/1/2010 | 1/1/2011 |  | 4/21/2009 |  |  |  |  | FF | No
V1-008 1104456 | PJM-AMIL |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1104456_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/16/2009 | 1/1/2010 | 1/1/2011 |  | 4/21/2009 |  |  |  |  | FF | No
V1-009 | Gilbert 46kV |  | WV | Unknown | Withdrawn | AEP | 12 | 12 | 11 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1009_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2009 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 4/1/2012 |  |  | N | No
V1-010 | Howard-Fostoria Central 138kV |  | OH | Crawford | Withdrawn | AEP | 260 | 260 | 33.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2009 | N/A | N/A |  | 4/19/2012 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
V1-011 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | In Service | AEP | 100 | 100 | 13 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1011_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1011_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_011_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v1_011_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2009 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 9/10/2018 | N | No
V1-012 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1012_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1012_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v1_012_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2009 | N/A | N/A |  | 5/8/2018 |  | 12/31/2015 | 12/31/2015 |  | N | No
V1-013 | Springdale 138kV |  | PA | Allegheny | Withdrawn | APS | 580 | 580 | 580 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2009 | N/A | N/A |  | 9/11/2009 | Customer Initiated Withdrawal | 1/1/2012 |  |  | N | No
V1-014 1120188 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 130 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1120188_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1120188_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/10/2009 | 9/1/2011 | 9/1/2041 | [6 empty] | FF | No
V1-015 | New Liberty 138kV |  | OH | Hancock | Withdrawn | AEP | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2009 | N/A | N/A |  | 9/3/2009 | Customer Milestone Not Met | 2/1/2010 |  |  | N | No
V1-016 1125859 | PJM-IPL |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1125859_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1125859_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/19/2009 | 4/1/2010 | 4/1/2015 | [6 empty] | FF | No
V1-017 1125369 | TVA-PJM |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1125369_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/19/2009 | 6/1/2012 | 6/1/2013 |  | 6/8/2009 |  |  |  |  | FF | No
V1-018 1125370 | TVA-PJM |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1125370_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/19/2009 | 6/1/2012 | 6/1/2013 |  | 6/8/2009 |  |  |  |  | FF | No
V1-019 1126560 | MEC-PJM |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1126560_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1126560_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/20/2009 | 1/1/2010 | 1/1/2015 |  | 1/18/2010 |  |  |  |  | FF | No
V1-020 1126569 | MEC-PJM |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1126569_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1126569_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/20/2009 | 1/1/2010 | 1/1/2015 |  | 1/18/2010 |  |  |  |  | FF | No
V1-021 | Cape May County 12kV | Cape May County Municipal Utiltities Authority (CM | NJ | Cape May | In Service | AEC | 1.9 | 1.9 | 1.7 | 1.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/23/2009 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 10/22/2013 | N | No
V1-022 | Plano 345kV |  | IL | Kendall | Withdrawn | ComEd | 380 | 380 | 380 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2009 | N/A | N/A |  | 12/17/2013 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
V1-023 | Bridge 12kV | Charlston LF | WV | Kanawha | In Service | AEP | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1023_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v1023_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/6/2009 | N/A | N/A |  |  |  | 12/7/2010 | 12/7/2010 | 12/7/2010 | N | No
V1-024 | LaSalle 1 | LaSalle Nuclear Station Unit 1 | IL | Lasalle | In Service | ComEd | 1188 | 20 | 11.9 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1024_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1024_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_024_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 11/1/2010 |  | 5/21/2015 | N | No
V1-025 | LaSalle 2 | LaSalle Nuclear Station Unit 2 | IL | Lasalle | In Service | ComEd | 1191 | 20 | 10.9 | 2.5 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_025_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 3/1/2011 |  | 5/21/2015 | N | No
V1-026 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 1213 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_026_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 4/9/2009 | N/A | N/A |  | 7/7/2020 |  | 4/4/2011 | 4/4/2011 | 4/4/2011 | N | No
V1-027 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 1213 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_027_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 4/9/2009 | N/A | N/A |  | 7/7/2020 |  | 4/1/2011 |  | 6/12/2013 | N | No
V1-028 | North Wales | Morris Road | PA | Montgomery | Deactivated | PECO | 10 | 2 | 2 | 2 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_028_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/16/2009 | N/A | N/A | 4/30/2012 |  |  | 5/31/2009 |  | 5/2/2012 | N | No
V1-029 | Frackville-Fishbach 69kV |  | PA | Schuylkill | Withdrawn | PPL | 56 | 6 | 0.78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1029_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/23/2009 | N/A | N/A |  | 9/14/2009 | Customer Milestone Not Met | 7/1/2013 |  |  | N | No
V1-030 | PSE&G Area |  | NJ | Various | In Service | PSEG | 52 | 52 | 19.8 | 46.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v1030_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2009 | N/A | N/A |  |  |  | 6/22/2010 | 6/22/2010 | 12/27/2011 | N | No
V1-031 | Possum Point 230kV |  | VA | Prince William | Withdrawn | Dominion | 950 | 950 | 875 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1031_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2009 | N/A | N/A |  | 1/30/2012 | Customer Initiated Withdrawal | 4/1/2016 |  |  | N | No
V1-032 | Highland 69kV |  | OH | Highland | Withdrawn | AEP | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2009 | N/A | N/A |  | 4/14/2011 | Customer Milestone Not Met | 8/1/2010 | 8/1/2010 |  | N | No
V1-033 | Pumphrey 115kV | Fairfield Renewable Energy Facility | MD | Baltimore City | Withdrawn | BGE | 132 | 132 | 132 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v1_033_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2009 | N/A | N/A |  | 5/11/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V1-034 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | JCPL | 673 | 3 | 0 |  | Energy | Merchant Transmission |  | DC | NF/TWR 673 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/v1034_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/v1034_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/v1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/v1_034_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2009 | N/A | N/A |  |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
V1-035 | Kanawha 138kV | ST | WV | Fayette | Withdrawn | AEP | 53 | 53 | 53 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2009 | N/A | N/A |  | 1/14/2013 | Customer Milestone Not Met | 5/1/2011 |  |  | N | No
V2-001 | Bucyrus Center 138kV | 54 1.8 WT | OH | Crawford | Withdrawn | AEP | 91.8 | 91.8 | 11.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2001_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2009 | N/A | N/A |  | 3/18/2013 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V2-002 | Martinsburg |  | PA | Blair | Withdrawn | PENELEC | 2.65 | 2.65 | 2.65 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2002_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/6/2009 | N/A | N/A |  | 2/8/2010 | Customer Milestone Not Met | 6/30/2010 |  |  | N | No
V2-003 | Beasley 23kV |  | NJ | Atlantic | Withdrawn | AEC | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2003_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2003_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/7/2009 | N/A | N/A |  | 1/6/2014 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
V2-004 | Harwood-E. Hazleton #1 |  | PA | Schuylkill | Withdrawn | PPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2004_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/11/2009 | N/A | N/A |  | 12/4/2009 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
V2-005 | Pleasantville 12kV |  | NJ | Atlantic | Withdrawn | AEC | 7.33 | 1.91 | 1.91 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/15/2009 | N/A | N/A |  | 2/17/2010 | Customer Milestone Not Met | 12/31/2010 | 12/31/2010 |  | N | No
V2-006 | East Leipsic 138kV | Leipsic Wind Project | OH | Putnam | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_006_csa.pdf | Document Posted | N/A | N/A |  | 5/28/2009 | N/A | N/A |  | 2/21/2020 |  | 12/31/2021 | 12/31/2021 |  | N | No
V2-007 | Bedington-Harmony Jct 138kV |  | MD | Allegany | Withdrawn | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v2007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/v2007_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2009 | N/A | N/A |  | 2/10/2012 | Customer Initiated Withdrawal | 6/1/2010 |  |  | S | No
V2-008 | Kincaid 345kV |  | IL | Christian | Withdrawn | ComEd | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2009 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 10/1/2014 |  |  | N | No
V2-009 | Plainsboro & Devils Brook 13kV | Cranbury SP | NJ | Middlesex | Withdrawn | PSEG | 16.11 | 16.11 | 6.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2009_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2009_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/29/2009 | N/A | N/A | 6/1/2024 | 2/1/2024 |  | 6/1/2024 | 6/1/2024 |  | N | No
V2-010 | Stewartsville 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2010_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2010_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/5/2009 | N/A | N/A |  | 3/15/2013 | Customer Milestone Not Met | 6/30/2011 | 6/30/2011 |  | N | No
V2-011 | Sunbury-Milton 69kV |  | PA | Northumberland | Withdrawn | PPL | 5.63 | 5.63 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2009 | N/A | N/A |  | 8/18/2009 | Customer Initiated Withdrawal | 2/1/2010 |  |  | N | No
V2-012 | Essex 26.4kV | Essex SP | NJ | Essex | Withdrawn | PSEG | 6 | 2.8 | 2.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2012_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/9/2009 | N/A | N/A |  | 12/21/2009 | Customer Milestone Not Met | 3/5/2010 | 3/5/2010 |  | N | No
V2-013 | Farmingdale 12.47kV | Farmingdale Solar | NJ | Monmouth | Withdrawn | JCPL | 0.5 | 0.5 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2013_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2013_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/11/2009 | N/A | N/A |  | 1/11/2013 | Customer Milestone Not Met | 4/1/2011 | 4/1/2011 |  | N | No
V2-014 | Waretown 12.47kV |  | NJ | Ocean | Withdrawn | AEC | 5.065 | 5.065 | 1.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2009 | N/A | N/A |  | 2/17/2010 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
V2-015 | Lumberton 13.2kV |  | NJ | Burlington | Withdrawn | PSEG | 3.3 | 3.3 | 1.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2009 | N/A | N/A |  | 12/21/2009 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
V2-016 1179105 | DUK-PJM |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/15/2009 | 6/1/2010 | 6/6/2011 |  | 7/13/2009 |  |  |  |  | FF | No
V2-017 1179108 | DUK-PJM |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/15/2009 | 6/1/2010 | 6/1/2011 |  | 7/13/2009 |  |  |  |  | FF | No
V2-018 | Tuckahoe |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/17/2009 | N/A | N/A |  | 12/20/2010 | Customer Initiated Withdrawal | 11/1/2010 |  |  | N | No
V2-019 | Mansfield-S. Troy 115kV | AES Armenia Mountain Wind, LLC | PA | Bradford | In Service | PENELEC | 100.5 | 0.5 | 0 | 0.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/22/2010 | 6/18/2009 | N/A | N/A |  |  |  | 8/19/2010 |  | 8/19/2010 | N | No
V2-019A | Dumont 765kV |  | IN | Unknown | Withdrawn | AEP | 7900 |  |  |  | Energy | Merchant Transmission |  | DC | F/NF TIR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v2019a_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2009 | N/A | N/A |  | 5/25/2010 | Customer Milestone Not Met | 5/1/2015 |  |  | S | No
V2-020 | Howard-West End Fostoria 138kV |  | OH | Crawford | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/26/2009 | N/A | N/A |  | 3/10/2010 | Customer Milestone Not Met | 7/31/2012 | 7/31/2012 |  | N | No
V2-021 | Clayville |  | NJ | Cumberland | Withdrawn | AEC | 64 | 64 | 64 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2021_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/26/2009 | N/A | N/A |  | 5/4/2010 | Customer Milestone Not Met | 6/1/2014 |  |  | N | No
V2-022 | Galion-Leesburg 138kV |  | OH | Morrow | Withdrawn | AEP | 201 | 201 | 26.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2009 | N/A | N/A |  | 8/17/2009 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V2-023 | Galion-Muskingham River 345kV |  | OH | Morrow | Withdrawn | AEP | 250.5 | 250.5 | 37.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2009 | N/A | N/A |  | 4/7/2010 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
V2-025 | Turnpike 13.8kV | Kearny SP | NJ | Hudson | In Service | PSEG | 5 | 5 | 1.9 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2025_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2009 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 3/1/2012 | N | No
V2-026 | Denver 138kV |  | WV | Barbour | Withdrawn | APS | 164 | 164 | 21.32 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2009 | N/A | N/A |  | 12/11/2009 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V2-027 | South Milton |  | PA | Northumberland | Withdrawn | PPL | 1.62 | 1.62 | 1.62 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2027_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/8/2009 | N/A | N/A |  | 2/21/2013 | Customer Initiated Withdrawal | 9/1/2013 | 9/1/2013 |  | N | No
V2-028 | Vienna | Vienna Solar Facility | MD | Dorchester | Withdrawn | DPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_028_csa.pdf | Document Posted | N/A | N/A |  | 7/8/2009 | N/A | N/A |  | 2/9/2018 |  | 11/30/2018 | 11/30/2018 |  | N | No
V2-029 1194261 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 418 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/14/2009 | 1/1/2010 | 1/1/2020 |  | 7/29/2009 |  |  |  |  | FF | No
V2-030 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 950 | 950 | 875 | 950 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_030_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 7/14/2009 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
V2-031 1197326 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 66 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1197326_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1197326_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-032 1197340 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 65 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1197340_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1197340_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-033 1197345 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 1 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1197345_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1197345_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-034 1197351 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 45 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1197351_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1197351_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-035 | Pittsgrove | Pittsgrove Solar, LLC | NJ | Salem | In Service | AEC | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2035_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_035_csa.pdf | Document Posted | N/A | N/A |  | 7/20/2009 | N/A | N/A |  |  |  | 4/14/2014 | 4/14/2014 | 4/19/2014 | N | No
V2-036 1199525 | PJM-TVA |  | N/A | N/A | Retracted |  | 202 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1199525_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1199525_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/21/2009 | 1/1/2011 | 1/1/2016 | [6 empty] | FF | No
V2-037 | White Oak | White Oak | MD | Montgomery | In Service | PEPCO | 24 | 4.5 | 0 | 4.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/24/2009 | N/A | N/A |  |  |  | 5/3/2010 | 5/3/2010 | 3/31/2010 | N | No
V2-040 | Mountain Road 34.5kV | Henrico County Landfill | VA | Henrico | In Service | Dominion | 4 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_040_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2009 | N/A | N/A |  |  |  | 9/23/2010 | 9/23/2010 | 9/23/2010 | N | No
V2-041 | Clayville 12kV | Vineland-Mays Landing | NJ | Cumberland | In Service | AEC | 4 | 4 | 1.52 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2041_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2009 | N/A | N/A |  |  |  | 9/30/2011 | 9/30/2011 | 9/30/2011 | N | No
V2-042 | Calvert Cliffs 500kV |  | MD | Calvert | Withdrawn | BGE | 1640 | 1640 | 1640 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2009 | N/A | N/A |  | 9/6/2012 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
V2-042A_AT2 | Galion 138kV |  | OH | Morrow | Withdrawn | ATSI | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2042a_at2_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2042a_at2_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2009 | N/A | N/A |  | 4/14/2014 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V2-043 | Upper Deerfield Township I |  | NJ | Cumberland | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2043_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/30/2010 |  |  | N | No
V2-044 | Upper Deerfield Township II |  | NJ | Cumberland | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/30/2010 |  |  | N | No
V2-045 | Bayview |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 12.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2045_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 9/12/2011 | Customer Initiated Withdrawal | 10/1/2011 | 10/1/2011 |  | N | No
V2-046 | Pilesgrove Township 12kV | Pilesgrove SP | NJ | Salem | In Service | AEC | 19.9 | 19.9 | 7 | 18.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2046_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/31/2009 | N/A | N/A |  |  |  | 7/31/2011 | 7/31/2011 | 7/31/2011 | N | No
V2-047 | Maurice River Township |  | NJ | Cumberland | Withdrawn | AEC | 1.35 | 1.35 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2047_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 1/31/2013 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
V2-048 1205761 | PJM-LGEE |  | N/A | N/A | Withdrawn |  | 11 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1205761_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1205761_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/5/2009 | 10/1/2010 | 10/1/2015 |  | 4/6/2010 |  |  |  |  | FF | No
V3-001 | Burches Hill 500kV |  | MD | Prince George's | Withdrawn | PEPCO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3001_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/3/2009 | N/A | N/A |  | 3/2/2010 | Customer Milestone Not Met | 5/1/2015 |  |  | N | No
V3-002 | Ellicott City |  | MD | Howard | Withdrawn | BGE | 1.2 | 1.2 | 0.456 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2009 | N/A | N/A |  | 3/10/2010 | Customer Milestone Not Met | 6/30/2010 |  |  | N | No
V3-003 | Greentown-Jefferson 765kV |  | IN | Clinton | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/5/2009 | N/A | N/A |  | 2/10/2011 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
V3-004 | Siegfried |  | PA | Carbon | Withdrawn | PPL | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3004_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2009 | N/A | N/A |  | 4/7/2010 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
V3-005 | Morris 34.5kV |  | NJ | Morris | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3005_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 11/7/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
V3-006 | Linglestown |  | PA | Dauphin | Withdrawn | PPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3006_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 4/14/2011 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
V3-007 | Desoto-Tanners Creek #1 345kV | Headwaters II | IN | Randolph | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3007_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3007_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_007_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_007_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 8/10/2009 | N/A | N/A | 1/26/2021 |  |  | 9/1/2021 | 9/1/2021 | 1/26/2021 | N | No
V3-008 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3008_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3008_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 6/3/2016 | Customer Milestone Not Met | 5/18/2018 | 5/18/2018 |  | N | No
V3-009 | Desoto-Tanners Creek #2 345kV |  | IN | Randolph | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3009_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 6/3/2016 | Customer Milestone Not Met | 5/19/2019 | 5/19/2019 |  | N | No
V3-010 | Delaware-Modoc 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
V3-011 | Sussex 12.47kV | Sussex County Land Fill | NJ | Sussex | Deactivated | JCPL | 3.4 | 3.4 | 3.4 | 3.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3011_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/11/2009 | N/A | N/A | 6/2/2011 |  |  | 6/3/2011 | 6/3/2011 | 6/3/2011 | N | No
V3-012 1212383 | TVA-PJM |  | N/A | N/A | Annulled |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1212383_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1212383_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/11/2009 | 5/26/2014 | 6/1/2019 | [6 empty] | FF | No
V3-013 | Wilmington 69kV |  | OH | Clinton | Withdrawn | Dayton | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3013_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/18/2009 | N/A | N/A |  | 10/27/2011 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
V3-014 | Lee County |  | IL | Lee | Withdrawn | ComEd | 160.2 | 160.2 | 20.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/2009 | N/A | N/A |  | 2/23/2012 | Customer Milestone Not Met | 11/20/2011 |  |  | N | No
V3-015 | Keystone 345kV | Wells County Wind Farm | IN | Wells | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_015_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2009 | N/A | N/A |  | 4/19/2018 |  | 12/31/2014 | 12/31/2014 |  | N | No
V3-016 | Greenville-West Milton 138kV |  | OH | Darke | Withdrawn | Dayton | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3016_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/24/2009 | N/A | N/A |  | 4/9/2012 | Customer Initiated Withdrawal | 8/1/2012 |  |  | N | No
V3-017 | Morgantown-Oak Grove | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_017_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2009 | N/A | N/A |  |  |  | 11/1/2016 | 11/1/2016 | 11/25/2016 | N | No
V3-018 | Towanda 115kV |  | PA | Bradford | Withdrawn | PENELEC | 75 | 75 | 9.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2009 | N/A | N/A |  | 9/1/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V3-019 | Edinboro 13.8kV |  | PA | Erie | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3019_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/27/2009 | N/A | N/A |  | 3/24/2010 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
V3-020 | Mt. Storm-Valley 115kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v3020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-021 | Mt. Storm-Doubs 500kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v3021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-022 | 502 Junction-Meadowbrook 500kV |  | WV | Hardy | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-023 | Alburtis-Hosensack 500kV |  | PA | Unknown | Withdrawn | PPL | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v3023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-024 | Devils Brook 13.2kV | RE Cranbury Solar I, LLC | NJ | Middlesex | In Service | PSEG | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3024_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3024_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 9/27/2011 | 9/27/2011 | 9/27/2011 | N | No
V3-025 | Cranbury 13.8kV | English SP | NJ | Middlesex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3025_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 6/9/2010 | Customer Milestone Not Met | 5/31/2010 |  |  | N | No
V3-026 | Larrabee 230kV |  | NJ | Ocean | Withdrawn | JCPL | 550 |  |  |  | Energy | Merchant Transmission |  | DC | F/550 TIR/550 TWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v3026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/v3026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 1/1/2013 |  |  | S | No
V3-027 | Pickens 138kV |  | WV | Webster | Withdrawn | APS | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
V3-028 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | In Service | AEP | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_028_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2009 | N/A | N/A | 10/13/2020 |  |  | 6/1/2021 | 6/1/2021 | 9/29/2020 | N | No
V3-029 | Chatfield 138kV |  | OH | Crawford | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 7/27/2010 | Customer Milestone Not Met | 12/1/2013 |  |  | N | No
V3-030 | St. Benedict-Patton 46kV | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30.6 | 30.6 | 3.98 | 30.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_030_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 6/30/2013 | 6/30/2013 | 12/24/2012 | N | No
V3-031 | Germantown |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 4/9/2010 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
V3-032 | Darwin-Eugene 345kV |  | IL | Vermilion | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2009 | N/A | N/A |  | 7/26/2012 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
V3-034 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 921.5 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2009 | N/A | N/A |  | 7/21/2010 | Customer Initiated Withdrawal | 6/30/2011 |  |  | N | No
V3-036 | Ontario 23kV | Midtown Thermal Control Center | NJ | Atlantic | In Service | AEC | 5.5 | 5.5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3036_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_036_csa.pdf | Document Posted | N/A | N/A |  | 9/14/2009 | N/A | N/A |  |  |  | 12/1/2011 | 12/1/2011 | 12/1/2011 | N | No
V3-037 | Naval Academy Junction 13kV | Millersville Landfill & Resource Recovery Facility | MD | Anne Arundel | In Service | BGE | 4 | 4 | 4 | 3.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_037_csa.pdf | Document Posted | N/A | N/A |  | 9/14/2009 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 6/13/2012 | N | No
V3-038 | Turnpike 13kV | Turnpike SP | NJ | Hudson | Withdrawn | PSEG | 0.6 | 0.6 | 0.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3038_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3038_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/16/2009 | N/A | N/A |  | 1/10/2013 |  | 12/31/2010 | 12/31/2010 |  | N | No
V3-039 | Harrison 4kV | Harrison SP | NJ | Hudson | Withdrawn | PSEG | 1.2 | 1.2 | 0.45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3039_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/16/2009 | N/A | N/A |  | 1/10/2013 |  | 12/31/2010 | 12/31/2010 |  | N | No
V3-040 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | Withdrawn | PPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_040_csa.pdf | Document Posted | N/A | N/A |  | 9/17/2009 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 6/30/2016 | 6/30/2016 |  | N | No
V3-041 | Daleville | SECCRA Units 1, 2 & 3 | PA | Chester | In Service | PECO | 4 | 2 | 3.2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_041_csa.pdf | Document Posted | N/A | N/A |  | 9/21/2009 | N/A | N/A |  |  |  | 11/1/2011 | 11/1/2011 | 12/15/2010 | N | No
V3-042 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 84 | 84 | 10.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3042_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/2/2009 | N/A | N/A |  | 8/8/2014 | Customer Initiated Withdrawal | 9/30/2016 | 9/30/2016 |  | N | No
V3-044 | Glendon 34.5kV | Chrin LF | PA | Northampton | Deactivated | ME | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3044_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/28/2009 | N/A | N/A |  |  |  | 6/14/2011 | 6/14/2011 | 6/14/2011 | N | No
V3-045 | Zimmer-Spurlock 345kV | Meldahl Hydroelectric Plant | OH | Butler | In Service | DEOK | 112 | 112 | 112 | 112 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_045_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2009 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 11/1/2015 | N | No
V3-046 | Conemaugh-Juniata 500kV |  | PA | Cambria | Withdrawn | PENELEC | 741 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v3046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/v3046_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/v3_046_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2009 | N/A | N/A |  | 12/16/2014 | Customer Milestone Not Met | 7/1/2012 |  |  | S | No
V3-047 | Sutton Dam 69kV |  | WV | Braxton | Withdrawn | APS | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2009 | N/A | N/A |  | 3/1/2010 | Customer Milestone Not Met | 12/21/2010 |  |  | N | No
V3-050 | Penns Neck 13kV |  | NJ | Middlesex | Withdrawn | PSEG | 4.6 | 4.6 | 4.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3050_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/12/2009 | N/A | N/A |  | 8/5/2011 | Customer Milestone Not Met | 9/1/2011 | 9/1/2011 |  | N | No
V3-051 | Letort | Turkey Hill Dairy WF | PA | Lancaster | In Service | PPL | 3.2 | 3.2 | 0.4 | 3.2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_051_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_051_csa.pdf | Document Posted | N/A | N/A |  | 10/16/2009 | N/A | N/A |  |  |  | 1/17/2011 | 1/17/2011 | 1/17/2011 | N | No
V3-052 | NI HUB-DC Cook |  | N/A | N/A | In Service | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v3052_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v3052_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v3052_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/21/2009 | N/A | N/A |  |  |  | 2/1/2013 | 2/1/2013 | 5/2/2012 | EE | No
V3-053 | Desoto 138kV |  | IN | Delaware | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3053_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/22/2009 | N/A | N/A |  | 10/14/2013 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
V3-054 1246457 | PJM-LGEE |  | N/A | N/A | Withdrawn |  | 99 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1246457_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/22/2009 | 4/1/2010 | 4/1/2015 |  | 4/6/2010 |  |  |  |  | FF | No
V3-055 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3055_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/23/2009 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
V3-056 | Metropolitan Court 34.5kV |  | MD | Frederick | Withdrawn | APS | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3056_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 8/3/2010 | Customer Milestone Not Met | 10/1/2013 | 10/1/2013 |  | N | No
V3-057 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3057_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 5/20/2011 | Customer Milestone Not Met | 3/31/2011 | 3/31/2011 |  | N | No
V3-058 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_058_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/24/2011 | N | No
V3-059 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3059_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_059_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/24/2011 | N | No
V3-060 | Antioch |  | IL | Lake | Withdrawn | ComEd | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3060_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 7/26/2010 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
V3-061 | Bayview |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3061_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
V3-062 | McConnellsburg-Guilford 138kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3062_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
V3-063 | Dupont 69kV |  | VA | City of Martinsville | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3063_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 3/31/2012 |  |  | N | No
V3-064 | Rivesville-Pruntytown 138kV |  | WV | Marion | Withdrawn | APS | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3064_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 12/17/2011 | Customer Initiated Withdrawal | 12/1/2012 |  |  | N | No
V3-065 | Clay St. 4kV (Barringer) | Clay ST SP | NJ | Essex | In Service | PSEG | 0.549 | 0.549 | 0.21 | 0.549 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3065_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/1/2010 | N | No
V3-066 | Cook Road 13.8kV (Park) | Cook Rd SP | NJ | Essex | In Service | PSEG | 0.432 | 0.432 | 0.16 | 0.432 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3066_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 12/31/2010 | 12/31/2010 | 11/17/2010 | N | No
V3-067 | Norfolk St. 4kV (Central) | Newark I SP | NJ | Essex | In Service | PSEG | 0.773 | 0.773 | 0.29 | 0.773 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3067_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3067_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 3/16/2011 | 3/16/2011 | 2/16/2011 | N | No
V3-068 | Norfolk St. 4kV (New Central HS) | Newark II SP | NJ | Essex | In Service | PSEG | 0.425 | 0.425 | 0.16 | 0.425 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3068_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3068_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 12/20/2010 | 12/20/2010 | 12/31/2010 | N | No
V3-069 | Woodbridge 13kV (Matrix Bldg) | Woodbridge SP | NJ | Middlesex | In Service | PSEG | 2.308 | 2.308 | 0.877 | 2.308 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3069_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3069_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/31/2010 | 10/31/2010 | 1/26/2011 | N | No
V3-070 | J. Rinco 34.5kV | Lilac Site | NJ | Hunterdon | In Service | JCPL | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3070_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 1/2/2012 | N | No
V3-071 | Frenchtown 12.47kV | Frenchtown SP | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3071_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 6/21/2012 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | N | No
V4-001 | Lebanon 34.5kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4001_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/2/2009 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 1/2/2012 | N | No
V4-002 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 575 | 575 | 575 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2009 | N/A | N/A |  | 5/21/2010 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
V4-003 | Churchmans |  | DE | New Castle | Withdrawn | DPL | 14 | 14 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2009 | N/A | N/A |  | 5/17/2010 | Customer Milestone Not Met | 3/31/2010 |  |  | N | No
V4-004 | Roxbury 12.5kV |  | NJ | Morris | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4004_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2009 | N/A | N/A |  | 5/7/2010 | Customer Initiated Withdrawal | 7/1/2010 | 7/1/2010 |  | N | No
V4-005 | Southampton 13.8kV | Lumberton SP | NJ | Burlington | In Service | PSEG | 2.9 | 2.9 | 1.1 | 2.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4005_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/11/2009 | N/A | N/A |  |  |  | 11/10/2011 | 11/10/2011 | 8/1/2010 | N | No
V4-006 | Byron 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4006_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4006_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4006_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 2/18/2012 |  | 12/12/2011 | EE | No
V4-007 | Quad City 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4007_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4007_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4007_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-008 | Braidwood 1-AD Hub | Suburban Landfill | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4008_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2009 | N/A | N/A |  | 2/15/2012 |  |  |  |  | EE | No
V4-009 | Upper Deerfield | Deerfield Project | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4009_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4009_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/12/2009 | N/A | N/A |  | 11/25/2013 | Customer Milestone Not Met | 6/1/2014 | 6/1/2014 |  | N | No
V4-010 | Tiffin Center 138kV | Republic Wind LLC | OH | Seneca | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4010_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4010_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_010_csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  | 11/18/2021 |  | 12/31/2022 | 12/31/2022 |  | N | No
V4-011 | Granger Electric | Granger Electric of Hancock County | OH | Hancock | In Service | AEP | 3.2 | 3 | 0 | 3 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4011_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2009 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 3/31/2015 | N | No
V4-012 | Morgantown |  | PA | Berks | Withdrawn | PPL | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4012_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2009 | N/A | N/A |  | 11/8/2011 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
V4-013 | Gloucester 26kV |  | NJ | Gloucester | Withdrawn | PSEG | 5.2 | 5.2 | 1.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/18/2009 | N/A | N/A |  | 6/9/2010 | Customer Milestone Not Met | 9/30/2010 |  |  | N | No
V4-014 | Greenridge Landfill |  | PA | Westmoreland | Withdrawn | APS | 6.5 | 6.5 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2009 | N/A | N/A |  | 11/12/2010 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
V4-015 | Fostoria Central 138kV |  | OH | Hancock | Withdrawn | AEP | 66.6 | 66.6 | 8.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4015_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/23/2009 | N/A | N/A |  | 9/15/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
V4-016 | Valley 138kV |  | MI | Cass | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/25/2009 | N/A | N/A |  | 3/27/2015 | Customer Initiated Withdrawal | 11/30/2014 | 11/30/2014 |  | N | No
V4-017 | Woodruffs Gap 345kV |  | NJ | Sussex | Withdrawn | JCPL | 3.5 | 3.5 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4017_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/25/2009 | N/A | N/A |  | 2/15/2012 | Customer Milestone Not Met | 9/30/2010 |  |  | N | No
V4-018 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 1425 | 475 | 415 | 475 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4018_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4018_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_018_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 11/25/2009 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
V4-019 | Bergen 230kV | Bergen Generating Station | NJ | Bergen | In Service | PSEG | 1209 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/25/2009 | N/A | N/A |  |  |  | 6/1/2013 |  | 5/31/2013 | N | No
V4-020 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/25/2009 | N/A | N/A |  | 2/12/2014 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
V4-021 | Keystone 345kV |  | IN | Wells | Withdrawn | Dayton | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4021_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 2/23/2012 | Customer Milestone Not Met | 12/15/2014 | 12/15/2014 |  | N | No
V4-022 | Tasley | Tasley Solar | VA | Accomack | Withdrawn | ODEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4022_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4022_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 3/13/2019 |  | 11/30/2019 | 11/30/2019 |  | N | No
V4-023 | Upper Pittsgrove 1 | Upper Pittsgrove Project | NJ | Salem | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4023_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4023_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 9/30/2014 | Customer Initiated Withdrawal | 10/1/2015 | 10/1/2015 |  | N | No
V4-024 | Upper Pittsgrove 2 | Quinton Project | NJ | Salem | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4024_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4024_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4024_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 2/12/2015 | Customer Initiated Withdrawal | 11/30/2016 | 11/30/2016 |  | N | No
V4-025 | Upper Pittsgrove 3 | Beckett ProjectWoodstown Project | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4025_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4025_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 8/12/2015 | Customer Initiated Withdrawal | 10/1/2015 | 10/1/2015 |  | N | No
V4-026 | Pontiac-Dumont 345kV |  | IL | Unknown | Withdrawn | AEP | 3000 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v4026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2009 | N/A | N/A |  | 1/3/2013 | Customer Milestone Not Met | 6/30/2014 |  |  | S | No
V4-027 | Quarryville | Keystone Solar | PA | Lancaster | In Service | PPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/7/2009 | N/A | N/A |  |  |  | 12/30/2012 | 12/30/2012 | 9/17/2012 | N | No
V4-028 | Kuller Road 13.2kV | Kuller Road SP | NJ | Passaic | Withdrawn | PSEG | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4028_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 12/7/2009 | N/A | N/A |  | 1/10/2010 | Customer Milestone Not Met | 7/1/2010 |  |  | N | No
V4-029 | Mannington Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4029_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4029_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/7/2009 | N/A | N/A |  | 9/17/2013 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
V4-030 | Byron 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4030_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4030_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4030_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-031 | Quad 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4031_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4031_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4031_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-033 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Withdrawn | AEP | 299.2 | 299.2 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4033_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/11/2009 | N/A | N/A |  | 9/8/2016 | Customer Milestone Not Met | 12/31/2018 | 12/31/2018 |  | N | No
V4-035 | Yankee 12.5kV |  | OH | Montgomery | Withdrawn | Dayton | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2009 | N/A | N/A |  | 1/22/2010 | Customer Initiated Withdrawal | 4/30/2010 |  |  | N | No
V4-036 | Newport-South Millville 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4036_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/14/2009 | N/A | N/A |  | 3/20/2012 | Customer Initiated Withdrawal | 9/30/2012 | 9/30/2012 |  | N | No
V4-037 | Pilesgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2009 | N/A | N/A |  | 1/18/2013 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
V4-037A 1274879 | DUK-PJM |  | N/A | N/A | Retracted |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1274879_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1274879_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/15/2009 | 1/1/2012 | 1/1/2020 |  | 10/19/2010 |  |  |  |  | FF | No
V4-038 | Friendship Manor 34.5kV | Alpha Ridge Landfill | MD | Carroll | In Service | BGE | 1 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_038_csa.pdf | Document Posted | N/A | N/A |  | 12/16/2009 | N/A | N/A |  |  |  | 2/28/2013 | 2/28/2013 | 7/31/2012 | N | No
V4-039 | Church |  | MD | Queen Anne's | Withdrawn | DPL | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/18/2009 | N/A | N/A |  | 5/20/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
V4-039A_AT3 | MOABs A16, A17, A18 |  | OH | Sandusky | Withdrawn | ATSI | 22 | 22 | 22 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4039a_at3_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4039a_at3_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2009 | N/A | N/A |  | 7/27/2012 | Queue Not Required | 5/1/2010 |  |  | N | No
V4-040 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2009 | N/A | N/A |  | 5/28/2010 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
V4-041 | Upper Pittsgrove 4 | Upper Pittsgrove Township - Site 4 | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4041_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4041_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4041_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V4-042 | Upper Pittsgrove 5 | Upper Pittsgrove Township - Site 5 | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4042_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4042_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V4-043 | Shirley 12kV | Stewartstown Generating Facility | NJ | Salem | Withdrawn | AEC | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 10/27/2010 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
V4-044 | Mannington Township 2 |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 6/1/2010 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
V4-045 | Peach Bottom | Peach Bottom Units 2 & 3 | PA | York | In Service | PECO | 2665.8 | 133.8 | 206 | 133.8 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 10/3/2015 |  | 1/6/2016 | N | No
V4-046 | Byron 1 | Byron Nuclear Generating Station, Unit 1 | IL | Ogle | In Service | ComEd | 1232 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_046_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-047 | Byron 2 | Byron Nuclear Generating Station, Unit 2 | IL | Ogle | In Service | ComEd | 1210 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_047_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-048 | Braidwood 1 | Braidwood Nuclear Generating Station, Unit 1 | IL | Will | In Service | ComEd | 1240 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-049 | Braidwood 2 | Braidwood Nuclear Generating Station, Unit 2 | IL | Will | In Service | ComEd | 1214 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4049_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_049_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-050 1276187 | PJM-AMIL |  | N/A | N/A | Annulled |  | 225 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1276187_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1276187_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/17/2009 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
V4-051 1276193 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 225 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1276193_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/17/2009 | 6/1/2015 | 6/1/2045 |  | 3/4/2010 |  |  |  |  | FF | No
V4-052 | West Reading | The Reading Hospital and Medical Center | PA | Berks | In Service | ME | 10 | 10 | 6 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4052_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4052_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2009 | N/A | N/A |  |  |  | 7/12/2011 |  | 7/12/2011 | N | No
V4-053 | Double Toll Gate 138kV |  | VA | Clarke | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2009 | N/A | N/A |  | 11/28/2012 | Customer Initiated Withdrawal | 11/1/2011 | 11/1/2011 |  | N | No
V4-054 | Fairfield Township 12kV | NJ Oak Solar | NJ | Cumberland | In Service | AEC | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4054_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4054_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_054_csa.pdf | Document Posted | N/A | N/A |  | 12/31/2009 | N/A | N/A |  |  |  | 12/20/2011 | 12/20/2011 | 12/20/2011 | N | No
V4-055 | Meigs-Ravenswood 69kV |  | OH | Meigs | Withdrawn | AEP | 11 | 11 | 4.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2010 | N/A | N/A |  | 11/16/2010 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
V4-055A 926517 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 5 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/926517_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/926517_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/6/2010 | 6/1/2010 | 6/1/2017 | [6 empty] | FF | No
V4-056 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
V4-057 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
V4-058 | Collins HVDC |  | SD | Hand | Withdrawn | ComEd | 3500 |  |  |  | Energy | Merchant Transmission |  |  | F/1650/NF/1850 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v4058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2010 | N/A | N/A |  | 9/14/2012 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
V4-059 | Pine Creek 46kV |  | WV | Mingo | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4059_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2010 | N/A | N/A |  | 11/18/2010 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
V4-060 1297962 | MEC-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1297962_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1297962_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/15/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
V4-061 1297967 | MEC-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1297967_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1297967_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/15/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
V4-062 | Upper Pittsgrove 6 |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4062_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2010 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
V4-063 | Upper Pittsgrove 7 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4063_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2010 | N/A | N/A |  | 11/3/2010 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
V4-064 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4064_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/26/2010 | N/A | N/A |  | 12/11/2013 | Customer Initiated Withdrawal | 9/30/2012 | 9/30/2012 |  | N | No
V4-065 | Meadow Road 13kV | Edison Project | NJ | Middlesex | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4065_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/27/2010 | N/A | N/A |  | 2/8/2011 | Customer Milestone Not Met | 8/30/2011 | 8/30/2011 |  | N | No
V4-066 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 3.6 | 3.6 | 1.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2010 | N/A | N/A |  | 2/12/2010 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
V4-067 | Cates Road Egg Harbor Township 12kV | McKee City Solar | NJ | Atlantic | Deactivated | AEC | 2.6 | 2.6 | 0.98 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4067_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4067_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/28/2010 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 12/22/2011 | N | No
V4-068 | Murphy's 34.5kV |  | NC | Hertford | In Service | Dominion | 5 | 5 | 3.23 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_068_csa.pdf | Document Posted | N/A | N/A | 8/1/2011 | 1/29/2010 | N/A | N/A | 8/1/2011 |  |  | 12/31/2011 | 12/31/2011 | 12/29/2011 | N | No
V4-069 | Frenchtown 34.5kV | Frenchtown 1 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4069_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4069_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 3/1/2011 | 3/1/2011 | 12/31/2011 | N | No
V4-070 | Frenchtown 12.5kV | Frenchtown 2 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4070_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 1/2/2012 | N | No
V4-071 | Bixby 13.8kV |  | OH | Franklin | Withdrawn | AEP | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4071_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 7/30/2010 | Customer Milestone Not Met | 6/1/2010 | 6/1/2010 |  | N | No
V4-072 | Blue Ridge Landfill |  | PA | Franklin | Withdrawn | APS | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4072_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 5/7/2012 | Customer Initiated Withdrawal | 5/1/2012 | 5/1/2012 |  | N | No
V4-073 | Yankee 12.5kV |  | OH | Montgomery | In Service | Dayton | 2.5 | 2.5 | 0.95 | 0.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4073_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 5/28/2010 | 5/28/2010 | 5/28/2010 | N | No
V4-074 | Quad Cities Wind |  | IL | Hancock | Withdrawn | ComEd | 1000 | 1000 | 130 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 1/27/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
V4-075 | Warwick 12kV |  | PA | Lancaster | Withdrawn | PPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4075_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 3/1/2015 | 3/1/2015 |  | N | No
V4-076 | Carlisle Pike 23kV |  | PA | Cumberland | Withdrawn | PENELEC | 5.3 | 5.3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4076_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 8/25/2014 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
V4-077 | Montgomery Avenue 12.47kV |  | PA | Mifflin | Withdrawn | PENELEC | 13 | 13 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4077_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 8/25/2014 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
V4-078 | Hawks Bridge Road |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 3/15/2010 | Customer Initiated Withdrawal | 2/15/2011 |  |  | N | No
V4-081 1307470 | PJM-LGEE |  | N/A | N/A | Retracted |  | 110 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1307470_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/29/2010 | 1/1/2011 | 1/1/2016 |  | 4/9/2010 |  |  |  |  | FF | No
W1-001 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 15 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 15 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/w1_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/2/2010 | N/A | N/A |  |  |  | 3/31/2010 |  | 6/1/2011 | S | No
W1-002 | Tiltonsville-Windsor 138kV |  | OH | Jefferson | Withdrawn | AEP | 98 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w1002_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2010 | N/A | N/A |  | 7/20/2012 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
W1-003 | Oak Hall | Oak Hall Project A | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1003_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1003_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_003_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
W1-004 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1004_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1004_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_004_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
W1-005 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1005_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_005_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
W1-006 | Oak Hall | Oak Hall Project D | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_006_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
W1-007 | Oak Hall |  | VA | Accomack | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 8/23/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W1-008 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1008_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 9/30/2016 | 9/30/2016 |  | N | No
W1-009 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1009_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 8/23/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W1-010 | Cooper |  | PA | York | Withdrawn | PECO | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
W1-011 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 5/19/2011 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
W1-011A 1318109 | DUK2-PJM |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1318109_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/11/2010 | 6/1/2013 | 6/1/2014 |  | 5/3/2010 |  |  |  |  | FF | No
W1-012 | Millheim-Brush Jct 46kV |  | PA | Centre | Withdrawn | APS | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1012_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/12/2010 | N/A | N/A |  | 5/8/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W1-013 | Saint Thomas 34kV I |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2010 | N/A | N/A |  | 10/17/2011 | Customer Milestone Not Met | 12/15/2011 | 12/15/2011 |  | N | No
W1-014 | Saint Thomas 34kV II |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/18/2010 | N/A | N/A |  | 10/17/2011 | Customer Milestone Not Met | 12/15/2011 | 12/15/2011 |  | N | No
W1-015 | Shade Gap 115kV |  | PA | Unknown | Withdrawn | PENELEC | 60.8 | 60.8 | 7.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1015_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2010 | N/A | N/A |  | 5/14/2012 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
W1-016 1325338 | MEC-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1325338_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1325338_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
W1-017 1325402 | MEC-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1325402_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1325402_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
W1-018 1325455 | MEC-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1325455_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1325455_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2010 | 5/1/2010 | 5/1/2015 | [6 empty] | FF | No
W1-019 1325477 | MEC-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1325477_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1325477_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2010 | 5/1/2010 | 5/1/2015 | [6 empty] | FF | No
W1-020 1325503 | MEC-PJM |  | N/A | N/A | Confirmed |  | 46 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1325503_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1325503_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2010 | 5/1/2010 | 5/1/2015 | [6 empty] | FF | No
W1-021 | Fairton 69kV I |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1021_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2010 | N/A | N/A |  | 10/16/2013 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
W1-022 | Fairton 69kV II |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2010 | N/A | N/A |  | 7/30/2013 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
W1-023 | Fairton 69kV III |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1023_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/24/2010 | N/A | N/A |  | 2/18/2014 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
W1-024 | Manalapan 12.5kV | Village at Manalapan Solar Farm | NJ | Monmouth | In Service | JCPL | 4 | 4 | 1.5 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1024_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_024_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_024_csa.pdf | Document Posted | N/A | N/A |  | 2/24/2010 | N/A | N/A |  |  |  | 6/30/2012 | 6/30/2012 | 12/14/2011 | N | No
W1-025 | Mt. Storm-Valley 500kV |  | WV | Unknown | Withdrawn | Dominion | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-026 | Mt. Storm-Doubs 500kV |  | WV | Unknown | Withdrawn | Dominion | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-027 | 502 Junction-Meadowbrook 500kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-028 | Alburtis-Hosensack |  | PA | Unknown | Withdrawn | PPL | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 11/18/2010 | Customer Milestone Not Met | 12/31/2013 |  |  | S | No
W1-029 | Winfall 230kV | Desert Wind Farm | NC | Pasquotank | In Service | Dominion | 208 | 208 | 27 | 208 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1029_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1029_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_029_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 3/2/2017 | N | No
W1-030 | Pontiac Midpoint-Reynolds 345kV |  | IL | Ford | Withdrawn | ComEd | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W1-031 | Pontiac Midpoint-Reynolds 345kV |  | IL | Ford | Withdrawn | ComEd | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W1-032 | Millhurst 12.5kV | Millhurst Solar Farm | NJ | Monmouth | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_032_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_032_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 2/2/2016 | N | No
W1-033 | Pumphrey 115kV | Fairfield Renewable Energy Facility | MD | Baltimore City | Withdrawn | BGE | 157 | 25 | 25 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_033_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 5/11/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W1-034 | Burches Hill |  | MD | Prince George's | Withdrawn | PEPCO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1034_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 8/24/2010 | Customer Initiated Withdrawal | 5/1/2015 |  |  | N | No
W1-035 | Baker 345kV |  | KY | Lawrence | Withdrawn | AEP | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 11/22/2010 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W1-036 | Matt Funk-Tech Drive 138kV | Central Solar Park | VA | Roanoke | Withdrawn | AEP | 45 | 45 | 5.85 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1036_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 3/21/2012 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
W1-037 | East Lima-South Kenton 138kV |  | VA | Unknown | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 1/3/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W1-038 | Fairlawn 138kV |  | NJ | Bergen | Withdrawn | PSEG | 77 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1038_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 8/31/2010 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
W1-039 | Pedricktown 230kV | PCLP Facility | NJ | Salem | Deactivated | AEC | 120.3 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/26/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 3/7/2012 | N | No
W1-040 | LaSalle |  | IL | Lasalle | Withdrawn | ComEd | 2752 | 350 | 350 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 2/13/2012 | Customer Milestone Not Met | 4/10/2016 |  |  | N | No
W1-041 | W. Milton-Greenville |  | OH | Darke | Withdrawn | Dayton | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1041_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W1-042 | Hubar Road 1 |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011 | 12/15/2011 |  | N | No
W1-043 | Hubar Road 2 |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1043_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011 | 12/15/2011 |  | N | No
W1-044 | Mont Alto |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011 | 12/15/2011 |  | N | No
W1-045 | Roxbury 23 kV | Roxbury Solar Project | PA | Franklin | In Service | PENELEC | 13.5 | 13.5 | 5.13 | 13.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_045_csa.pdf | Document Posted | N/A | N/A |  | 3/4/2010 | N/A | N/A | 12/13/2019 |  |  | 12/31/2019 | 12/31/2019 | 12/31/2019 | N | No
W1-046 | Face Rock 69kV |  | PA | Lancaster | Withdrawn | PPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1046_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_046_csa.pdf | Document Posted | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 11/30/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
W1-048 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1048_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2010 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 3/15/2011 |  |  | N | No
W1-049 1342417 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1342417_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/9/2010 | 6/1/2014 | 6/1/2019 |  | 6/24/2010 |  |  |  |  | FF | No
W1-050 | Keller & Valley Camp Roads I |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2010 | N/A | N/A |  | 10/17/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W1-051 | St. Thomas 34kV III |  | PA | Franklin | Withdrawn | APS | 130 | 130 | 49.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2010 | N/A | N/A |  | 10/14/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W1-052 | Keller & Valley Camp Roads II |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W1-053 | Pleasant View 500kV |  | VA | Arlington | Withdrawn | Dominion | 229 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2010 | N/A | N/A |  | 9/14/2010 | Customer Milestone Not Met | 6/1/2013 |  |  | S | No
W1-054 | South Akron-Prince | Dart Container | PA | Lancaster | In Service | PPL | 11.4 | 11.4 | 11.4 | 11.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_054_csa.pdf | Document Posted | N/A | N/A |  | 3/16/2010 | N/A | N/A |  |  |  | 12/31/2011 |  | 10/6/2012 | N | No
W1-055 | Broadway 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2010 | N/A | N/A |  | 9/28/2011 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W1-056 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 66.7 | 18.4 | 2.4 | 18.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_056_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2010 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/15/2017 | N | No
W1-057 | Earleys 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1057_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1057_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/23/2010 | N/A | N/A |  | 12/14/2011 | Customer Milestone Not Met | 5/31/2011 |  |  | N | No
W1-058 1352721 | PJM-CPLE |  | N/A | N/A | Retracted |  | 7 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1352721_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/22/2010 | 1/1/2011 | 1/1/2016 |  | 6/15/2010 |  |  |  |  | FF | No
W1-058A_DK1 | AK Steel Middletown-AK Steel 1C 138kV |  | OH | Butler | Withdrawn | Duke | 134.5 | 134.5 | 134.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1058a_dk1_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1058A_dk1_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2010 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
W1-059 | Denville |  | NJ | Morris | Withdrawn | JCPL | 2 | 2 | 0.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1059_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/24/2010 | N/A | N/A |  | 4/19/2012 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W1-060 | Carneys Point Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1060_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2010 | N/A | N/A |  | 1/11/2011 | Customer Milestone Not Met | 5/31/2011 |  |  | N | No
W1-061 | Brambleton |  | VA | Loudoun | Withdrawn | Dominion | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2010 | N/A | N/A |  | 5/25/2010 |  | 6/1/2013 |  |  | S | No
W1-061A 1365383 | PJM-TVA |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1365383_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2010 | 12/1/2011 | 1/1/2032 |  | 6/15/2010 |  |  |  |  | FF | No
W1-061B 1365390 | PJM-TVA |  | N/A | N/A | Retracted |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1365390_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2010 | 12/1/2011 | 1/1/2032 |  | 6/15/2010 |  |  |  |  | FF | No
W1-062 | Clayton 138kV | Smyrna Units 1 & 2 | DE | Kent | In Service | DPL | 101 | 53 | 53 | 53 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_062_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2010 | N/A | N/A |  |  |  | 5/31/2012 | 5/31/2012 | 6/15/2012 | N | No
W1-063 | Branchburg-Elroy 500kV |  | NJ | Somerset | Withdrawn | PSEG | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w1063_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2010 | N/A | N/A |  | 6/10/2010 |  | 6/1/2011 |  |  | S | No
W1-064 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 1.6 | 1.6 | 1.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1064_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/31/2010 | N/A | N/A |  | 7/1/2014 | Customer Initiated Withdrawal | 1/31/2011 |  |  | N | No
W1-065 | Millstone |  | NJ | Monmouth | Withdrawn | JCPL | 1.99 | 1.99 | 0.756 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1065_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/31/2010 | N/A | N/A |  | 11/17/2011 | Customer Milestone Not Met | 3/31/2011 |  |  | N | No
W1-066 | New Brooklyn Road 12kV |  | NJ | Camden | Withdrawn | AEC | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1066_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2010 | N/A | N/A |  | 2/27/2012 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
W1-067 1373369 | PJM-EKPC |  | N/A | N/A | Retracted | PSEG | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1373369_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1373369_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A |  | Withdrawn |  | Withdrawn |  | 4/9/2010 | 6/1/2011 | 6/1/2016 |  | 2/25/2011 |  |  |  |  | FF | No
W1-068 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1068_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/16/2010 | N/A | N/A |  | 2/20/2014 | Customer Initiated Withdrawal | 4/1/2011 |  |  | N | No
W1-070 | Laurel 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1070_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1070_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/20/2010 | N/A | N/A |  | 1/6/2014 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W1-070A_AT4 | Ashtabula 138kV |  | OH | Ashtabula | Withdrawn | ATSI | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1070a_at4_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1070a_at4_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1070a_at4_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/20/2010 | N/A | N/A |  | 4/16/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W1-071 | Elk Road 12kV |  | NJ | Salem | Withdrawn | AEC | 1.03 | 1.04 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1071_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 10/31/2010 |  |  | N | No
W1-072A_AT5 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 640 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1072a_at5_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1072a_at5_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1072a_at5_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_072a_at5_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 4/11/2014 | N | No
W1-073 | Ladysmith CT 230kV |  | VA | Caroline | Withdrawn | Dominion | 1562 | 612 | 498 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1073_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2010 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
W1-074 | Remington CT 230kV |  | VA | Fauquier | Withdrawn | Dominion | 1370 | 610 | 498 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2010 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
W1-075 | Hunterstown 115kV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1075_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2010 | N/A | N/A |  | 9/12/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
W1-076 | Kingwood | Keller Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_076_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  | 5/16/2014 |  | 6/30/2012 | 6/30/2012 |  | N | No
W1-077 | Shacklefords 34.5kV | King and Queen | VA | King and Queen | In Service | Dominion | 14 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_077_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 9/1/2011 | N | No
W1-078 | Sammis-Wylie Ridge 345kV |  | OH | Jefferson | In Service | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w1078_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/w1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 5/30/2012 | S | No
W1-079 1394028 | EKPC-PJM |  | N/A | N/A | Confirmed |  | 70 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1394028_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1394028_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/28/2010 | 1/1/2011 | 6/1/2013 | [6 empty] | FF | No
W1-080 | Sutton Dam |  | WV | Braxton | Withdrawn | APS | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1080_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 4/12/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W1-081 | Mickleton 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1081_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 10/5/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W1-082 | Milford | Milford Solar | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1082_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 3/7/2018 |  | 2/17/2018 | 2/17/2018 |  | N | No
W1-083 | Deptford 13kV | West Deptford Solar | NJ | Gloucester | Withdrawn | PSEG | 4.6 | 4.6 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1083_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1083_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/10/2013 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W1-084 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W1-085 | Millville 1 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-086 | Millville 2 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-087 | Millville 3 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-088 | Millville 4 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-089 | Newport 69kV |  | NJ | Cumberland | Withdrawn | AEC | 18 | 18 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 1/7/2011 |  |  | N | No
W1-090 | Berlin 69kV |  | NJ | Camden | Withdrawn | AEC | 18 | 18 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1090_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 4/25/2011 |  |  | N | No
W1-091 | Berlin 12kV |  | NJ | Camden | Withdrawn | AEC | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1091_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 4/25/2011 |  |  | N | No
W1-092 | Mays Landing 12kV |  | NJ | Cumberland | Withdrawn | AEC | 8.7 | 8.7 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1092_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-093 | Cape May 12kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1093_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-094 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1094_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-095 | Buena 12kV |  | NJ | Atlantic | Withdrawn | AEC | 18 | 18 | 7.02 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-096 | Woodbine 12kV |  | NJ | Cape May | Withdrawn | AEC | 7 | 7 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-097 | Fairfield Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1097_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 12/30/2010 |  |  | N | No
W1-098 | Levittown 13kV | Levittown SP | NJ | Burlington | Withdrawn | PSEG | 0.965 | 0.965 | 0.367 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1098_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1098_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
W1-099 | Levittown 13kV | Levittown 2 SP | NJ | Burlington | Withdrawn | PSEG | 1.282 | 1.282 | 0.487 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
W1-100 | Minue Street 12kV | Rathway SP | NJ | Middlesex | Withdrawn | PSEG | 1.741 | 1.741 | 0.662 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1100_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1100_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
W1-101 | Bayonne 13kV | Bayonne SP | NJ | Hudson | In Service | PSEG | 1.4 | 1.4 | 0.532 | 1.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1101_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1101_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 3/14/2011 | 3/14/2011 | 3/14/2011 | N | No
W1-102 | Southampton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1.9 | 1.9 | 0.722 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 6/1/2010 | Customer Milestone Not Met | 2/1/2011 |  |  | N | No
W1-103 | Millville 12kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1103_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/27/2010 | Customer Initiated Withdrawal | 6/15/2011 |  |  | N | No
W1-104 | Bellefonte 12kV |  | PA | Centre | Withdrawn | APS | 0.65 | 0.65 | 0.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1104_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 9/4/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
W1-105 | Reamstown | Heatherwoods Solar Farm | PA | Lancaster | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1105_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1105_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 6/30/2017 | 6/30/2017 |  | N | No
W1-106 | West Carlisle | Shover Solar Farm | PA | Cumberland | Withdrawn | PPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1106_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 6/30/2017 | 6/30/2017 |  | N | No
W1-107 | Grove City Road 12kV | Grove City Road 12kV | PA | Butler | Withdrawn | APS | 2 | 2 | 0.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1107_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1107_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 10/12/2015 | Customer Milestone Not Met | 8/31/2015 | 8/31/2015 |  | N | No
W1-108 | Grays Ferry 230kV | Grays Ferry Cogeneration Partnership | PA | Philadelphia | In Service | PECO | 163 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 7/29/2013 | N | No
W1-109 | Bloom 138kV |  | IL | Cook | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1109_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 11/4/2011 | Customer Initiated Withdrawal | 1/20/2014 | 1/20/2014 |  | N | No
W1-110 | Galloway Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 3.21 | 3.21 | 1.19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/31/2010 | Customer Initiated Withdrawal | 9/3/2012 |  |  | N | No
W1-111 | Harwood-Berwick 69kV | Beacon Power Flywheel Station | PA | Luzerne | In Service | PPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1111_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1111_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_111_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 7/24/2014 | N | No
W1-112 | Holmdel | Holmdel SP | NJ | Monmouth | In Service | JCPL | 4 | 4 | 1.52 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1112_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 3/1/2013 | 3/1/2013 | 3/1/2013 | N | No
W1-113 | Millstone 2 | Northpark Solar Farm #1 | NJ | Monmouth | In Service | JCPL | 8 | 8 | 3 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_113_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 3/22/2016 | N | No
W1-114 | Port Carbon | East Norwegian Township Solar I | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1114_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 12/19/2016 |  | 12/31/2013 | 12/31/2013 |  | N | No
W1-115 | Tamanend | Ryan Township Solar I | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1115_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 12/19/2017 |  | 6/30/2014 | 6/30/2014 |  | N | No
W1-116 | Emmitsburg 34kV | Mount St. Mary's PV Park | MD | Frederick | In Service | APS | 14 | 14 | 5.32 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1116_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_116_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 4/30/2012 | 4/30/2012 | 7/5/2012 | N | No
W1-117 | Silica Spur 1 |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1117_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 1/29/2014 | Customer Initiated Withdrawal | 6/30/2011 |  |  | N | No
W1-118 | Silica Spur 2 |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1118_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 1/29/2014 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W1-119 | Pemberton Township 1 34.5 kV | Greenburg Solar | NJ | Burlington | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1119_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1119_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 6/16/2017 | N | No
W1-120 | Pemberton Township 2 34.5 kV | Perez Solar | NJ | Burlington | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1120_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1120_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 6/15/2017 | N | No
W1-121 | Crosswicks 13kV | Property #6 | NJ | Mercer | In Service | PSEG | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1121_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1121_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 1/1/2012 | 1/1/2012 | 12/14/2011 | N | No
W1-122 | Wantage 12.47kV | Lower Unionville Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 5.13 | 5.13 | 1.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1122_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1122_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/7/2014 |  | 12/31/2014 | 12/31/2014 |  | N | No
W1-123 | Mannington Township 1 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 9/1/2010 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W1-124 | Tinton Falls 34.5kV | Tinton Falls Solar | NJ | Monmouth | In Service | JCPL | 16.9 | 16.9 | 6.4 | 16.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1124_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_124_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_124_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 8/1/2014 | 8/1/2014 | 12/6/2012 | N | No
W1-125 | Mannington Township 2 12kV |  | NJ | Salem | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1125_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/26/2010 | Customer Milestone Not Met | 7/1/2011 |  |  | N | No
W1-126 | White | White Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_126_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 11/21/2012 | Customer Initiated Withdrawal | 12/30/2013 | 12/30/2013 |  | N | No
W1-127 | Phillipsburg 12.47kV | Harmony Solar Farm | NJ | Warren | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_127_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_127_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 6/30/2015 | N | No
W1-128 | Red School Lane 69kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 2/9/2011 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
W1-129 | Cookstown 34.5kV | Jacobstown Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1129_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_129_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_129_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 5/29/2014 | 5/29/2014 | 9/20/2014 | N | No
W1-130 | Vine Road 12kV | Cedar Branch Solar Farm | NJ | Cumberland | In Service | AEC | 9.2 | 9.2 | 3.5 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1130_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1130_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 10/27/2016 | N | No
W1-131 | Kenney |  | MD | Worcester | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1131_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 2/3/2011 | Customer Milestone Not Met | 4/30/2011 |  |  | N | No
W1-132 | Pittstown | Paunch Solar | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1132_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1132_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 12/6/2013 | N | No
W2-001 | Fostoria Central 138/kV |  | OH | Hancock | Withdrawn | AEP | 66.6 | 66.6 | 8.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2001_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/6/2010 | N/A | N/A |  | 9/15/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
W2-002 | Kennedyville 1 69kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2010 | N/A | N/A |  | 12/13/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W2-003 | Kennedyville 2 69kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2010 | N/A | N/A |  | 12/13/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W2-004 | Foundry St. 138kV |  | NJ | Essex | Withdrawn | PSEG | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2004_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2010 | N/A | N/A |  | 5/23/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
W2-005 | Pruntytown 138kV |  | WV | Taylor | Withdrawn | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2010 | N/A | N/A |  | 12/16/2010 | Customer Milestone Not Met | 10/30/2013 |  |  | N | No
W2-006 | Newburgh 12kV |  | NJ | Morris | Withdrawn | JCPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2010 | N/A | N/A |  | 11/19/2010 | Customer Milestone Not Met | 11/30/2010 |  |  | N | No
W2-007 | East Leipsic 138kV |  | OH | Putnam | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2007_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2010 | N/A | N/A |  | 1/29/2013 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W2-008 | Tiltonsville-Windsor 138kV |  | OH | Jefferson | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2010 | N/A | N/A |  | 4/12/2012 | Customer Initiated Withdrawal | 6/1/2011 |  |  | S | No
W2-009 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 18 | 18 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2009_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/19/2010 | N/A | N/A |  | 12/22/2010 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W2-010 | Conemaugh Unit 1 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 870 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2010 | N/A | N/A |  |  |  | 6/30/2013 |  | 7/9/2012 | N | No
W2-011 | Conemaugh Unit 2 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 870 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2011_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_011_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2010 | N/A | N/A |  |  |  | 6/30/2013 |  | 7/9/2012 | N | No
W2-013 | Branchburg-Elroy 500kV |  | NJ | Unknown | Withdrawn | PSEG | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w2013_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/w2013_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/24/2010 | N/A | N/A |  | 7/21/2014 | Customer Milestone Not Met | 6/1/2012 |  |  | S | No
W2-014 | Richmond |  | PA | Philadelphia | In Service | PECO | 98 | 2 | 2 | 2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/25/2010 | N/A | N/A |  |  |  | 11/25/2010 |  | 6/24/2014 | N | No
W2-015 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W2-016 | Frenchtown 34.5kV | Barbertown-Point Breeze Solar Farm | NJ | Hunterdon | In Service | JCPL | 15 | 15 | 5.7 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2016_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2016_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/25/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 12/31/2013 | N | No
W2-017 | Pennsville Township |  | NJ | Salem | Withdrawn | AEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 6/16/2010 |  | 6/1/2012 |  |  | N | No
W2-018 | Cumberland County Landfill | Cumberland County Landfill | PA | Cumberland | In Service | PENELEC | 11.2 | 4.8 | 4.8 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 4/22/2012 | N | No
W2-019 | Wrightstown 34.5kV | Shemesh Solar Farm | NJ | Burlington | In Service | JCPL | 6 | 6 | 2.3 | 4.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_019_csa.pdf | Document Posted | N/A | N/A | 9/22/2016 | 5/28/2010 | N/A | N/A | 10/1/2016 |  |  | 9/30/2016 | 9/30/2016 | 10/24/2016 | N | No
W2-020 | Deptford 13kV |  | NJ | Camden | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2020_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2020_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 8/28/2012 | Customer Milestone Not Met | 8/30/2011 | 8/30/2011 |  | N | No
W2-021 | Deptford 13kV |  | NJ | Camden | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2021_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 8/28/2012 | Customer Milestone Not Met | 8/30/2011 | 8/30/2011 |  | N | No
W2-022 | Pantego 115kV | Pantego Wind Farm | NC | Hyde | Withdrawn | Dominion | 73.6 | 73.6 | 9.57 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2022_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_022_csa.pdf | Document Posted | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 11/22/2016 | Customer Initiated Withdrawal | 10/15/2018 | 10/15/2018 |  | N | No
W2-023 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 625 | 625 | 625 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2023_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 2/24/2015 | Customer Initiated Withdrawal | 5/31/2017 | 5/31/2017 |  | N | No
W2-024 | Kearny 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 625 | 625 | 625 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 5/31/2014 |  |  | N | No
W2-025 | Oldmans Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 11/23/2010 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
W2-026 | Glassboro Road | Suncatcher Clean Energy | NJ | Gloucester | Withdrawn | AEC | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2026_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2026_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2026_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 5/14/2013 | Customer Milestone Not Met | 4/30/2013 | 4/30/2013 |  | N | No
W2-027 | Terrace 12kV |  | NJ | Gloucester | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2027_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 9/30/2011 | 9/30/2011 |  | N | No
W2-028 | Limerick #1 |  | PA | Montgomery | Withdrawn | PECO | 1218 | 5 | 5 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2028_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 6/1/2010 | N/A | N/A |  | 7/7/2020 |  | 12/31/2014 | 12/31/2014 |  | N | No
W2-029 | Limerick #2 |  | PA | Montgomery | Withdrawn | PECO | 1218 | 5 | 5 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2029_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 6/1/2010 | N/A | N/A |  | 7/7/2020 |  | 12/31/2014 | 12/31/2014 |  | N | No
W2-030 | Egg Harbor Township | 1307 Doughty Road | NJ | Atlantic | In Service | AEC | 9.6 | 9.6 | 3.65 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2030_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2030_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/3/2010 | N/A | N/A |  |  |  | 9/30/2016 | 9/30/2016 | 10/4/2016 | N | No
W2-031 | Gloucester 26kV |  | NJ | Gloucester | Withdrawn | PSEG | 8.5 | 8.5 | 3.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2031_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_031_csa.pdf | Document Posted | N/A | N/A |  | 6/10/2010 | N/A | N/A |  | 9/13/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W2-032 | Stow Creek Township |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2010 | N/A | N/A |  | 11/30/2010 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-033 1457548 | OVEC-PJM-MECS |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1457548_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1457548_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/14/2010 | 9/1/2010 | 9/1/2015 | [6 empty] | FF | No
W2-034 | Cohansey Road |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2034_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2010 | N/A | N/A |  | 2/2/2011 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
W2-035 | Cohansey Road |  | NJ | Salem | Withdrawn | AEC | 16 | 16 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2010 | N/A | N/A |  | 2/3/2014 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
W2-036 | Polhemus Lane 13kV | Central SP | NJ | Somerset | In Service | PSEG | 0.749 | 0.749 | 0.284 | 0.749 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2036_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2036_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/18/2010 | N/A | N/A |  |  |  | 3/21/2010 | 3/21/2010 | 3/21/2011 | N | No
W2-037 | Cookstown 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 7 | 7 | 2.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
W2-038 | East Frankfort-Crete | Powerton – Joliet SPS | IL | Will | In Service | ComEd | 800 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w2038_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/w2_038_csa.pdf | Document Posted | N/A | N/A |  | 6/22/2010 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 10/5/2011 | S | No
W2-039 | Clayville 69kV | Clayville Unit #1 | NJ | Cumberland | In Service | AEC | 63 | 63 | 63 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2039_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2039_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_039_csa.pdf | Document Posted | N/A | N/A |  | 6/28/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 11/1/2015 | N | No
W2-040 | Camden 69kV | Preble Solar Energy | OH | Preble | Withdrawn | Dayton | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_040_csa.pdf | Document Posted | N/A | N/A |  | 6/29/2010 | N/A | N/A |  | 1/23/2020 |  | 6/1/2018 | 6/1/2018 |  | N | No
W2-041 | Egg Harbor Township |  | NJ | Atlantic | Withdrawn | AEC | 2.6 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2010 | N/A | N/A |  | 8/2/2010 | Customer Initiated Withdrawal | 3/1/2011 |  |  | N | No
W2-042 | Dennis Township |  | NJ | Cape May | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 6/30/2011 |  |  | N | No
W2-043 | Albright-Snowy Creek 138kV |  | WV | Preston | Withdrawn | APS | 101 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w2043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 1/17/2012 | Customer Milestone Not Met | 4/1/2011 |  |  | S | No
W2-044 | Columbia 138kV |  | IN | Whitley | Withdrawn | AEP | 100.5 | 100.5 | 13.06 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 1/5/2011 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
W2-046 | Powerton-Goodings Grove 345kV |  | IL | Livingston | Withdrawn | ComEd | 450 | 450 | 58.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 12/7/2011 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W2-047 | Oldmans Township |  | NJ | Salem | Withdrawn | AEC | 7.5 | 7.5 | 2.85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2047_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 5/15/2014 | Customer Initiated Withdrawal | 8/31/2011 |  |  | N | No
W2-048 | Brokaw-Lanesville | Hilltopper Wind, LLC | IL | Logan | In Service | ComEd | 62.5 | 62.5 | 0 | 62.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_048_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2010 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 11/1/2018 | N | No
W2-049 | Reedy Creek 115kV | South Boston Energy Facility | VA | Halifax | In Service | Dominion | 47.4 | 47.4 | 47.4 | 47.4 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2049_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_049_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2010 | N/A | N/A |  |  |  | 5/30/2013 |  | 9/24/2013 | N | No
W2-050 | Flemington | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 10 | 0 | 8 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_050_csa.pdf | Document Posted | N/A | N/A | 4/1/2016 | 7/13/2010 | N/A | N/A |  |  |  | 4/1/2016 | 4/1/2016 | 3/22/2016 | N | No
W2-051 | Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 2 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2051_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/13/2010 | N/A | N/A |  | 11/30/2010 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-052 | Pierson Avenue 13kV |  | NJ | Middlesex | In Service | PSEG | 0.592 | 0.592 | 0.225 | 0.592 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2052_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2052_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/19/2010 | N/A | N/A |  |  |  | 3/14/2011 | 3/14/2011 | 3/14/2011 | N | No
W2-053 | West Waynesboro 34.5kV I |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W2-054 | West Waynesboro II 34.5kV II |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2054_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W2-056 | Lumberton 13kV | Reeves Station Road Solar | NJ | Burlington | In Service | PSEG | 11 | 11 | 4.18 | 11 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2056_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2056_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/23/2010 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 10/16/2012 | N | No
W2-057 | Laurel Mountain | Laurel Mountain BT | WV | Barbour | Deactivated | APS | 125 | 27.4 | 0 | 27.4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_057_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/28/2010 | N/A | N/A |  |  |  | 7/30/2011 | 7/30/2011 | 9/21/2011 | N | No
W2-058 | Southampton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2058_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 2/28/2012 | 2/28/2012 |  | N | No
W2-059 | Strasburg 12kV | Sight & Sound Theaters | PA | Lancaster | Withdrawn | PPL | 2.4 | 2.4 | 1 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 8/27/2012 | CIW | 12/31/2012 | 12/31/2012 |  | N | No
W2-060 | Burlington 26kV | Florence solar | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2060_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2060_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 5/30/2013 | Customer Initiated Withdrawal | 2/28/2014 | 2/28/2014 |  | N | No
W2-061 | Ringoes 12kV | Everitt Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2061_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2061_wmpa.pdf |  | Not Required | N/A | N/A | 5/23/2016 | 7/29/2010 | N/A | N/A | 5/23/2016 |  |  | 1/18/2017 | 1/18/2017 | 6/1/2016 | N | No
W2-062 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.1 | 12.1 | 12.1 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W2-063 | Millbrook Park 138kV |  | KY | Greenup | Withdrawn | AEP | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2063_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/11/2013 | Customer Initiated Withdrawal | 3/31/2014 | 3/31/2014 |  | N | No
W2-064 | Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2064_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 1/24/2012 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
W2-065 | Woodstown Road 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2065_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W2-067 | Amsterdam 138kV |  | OH | Darke | Withdrawn | Dayton | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-068 | Bluff Point 138kV |  | OH | Mercer | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2068_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-069 | Fishburn/Tanney 46kV |  | PA | Centre | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2069_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 5/4/2011 | Customer Initiated Withdrawal | 12/1/2012 | 12/1/2012 |  | N | No
W2-070 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2070_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/2/2010 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
W2-071 | Mt. Laurel 13kV |  | NJ | Burlington | In Service | PSEG | 2.8 | 2.8 | 1.06 | 2.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2071_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 10/31/2011 | 10/31/2011 | 12/15/2011 | N | No
W2-072 | Pilesgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2072_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-073 | New Canton 12kV | Ward's Nursery Solar Farm | NJ | Middlesex | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2073_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/17/2017 | Customer Initiated Withdrawal | 9/30/2017 | 9/30/2017 |  | N | No
W2-074 | Bennett 12kV | Hurley Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2074_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/7/2014 |  | 6/30/2014 | 6/30/2014 |  | N | No
W2-075 | Tolna Unit 2 | Tolna Unit 2 | PA | York | In Service | ME | 20 | 0.9 | 0.9 | 0 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2075_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_075_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 8/31/2010 |  | 7/28/2011 | N | No
W2-076 | Rocktown 4.8kV | West Amwell Mason Supply Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2076_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 11/15/2016 |  | 5/30/2017 | 5/30/2017 |  | N | No
W2-077 | Wrightstown 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 2.06 | 2.06 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/8/2010 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
W2-078 | Applegarth 12.5kV | Northpark Solar Farm #2 | NJ | Monmouth | In Service | JCPL | 9 | 9 | 3.4 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 3/22/2016 | N | No
W2-079 | Stillman Valley |  | IL | Winnebago | Withdrawn | ComEd | 19.4 | 19.4 | 7.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2079_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/30/2013 | Customer Milestone Not Met | 3/31/2011 |  |  | N | No
W2-080 | Stanton 12kV | Fisher Solar Farm | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0.8 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2080_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 6/25/2017 | 6/25/2017 | 5/30/2017 | N | No
W2-081 | Port Carbon 12kV |  | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2081_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 11/2/2011 | Customer Milestone Not Met | 2/22/2011 |  |  | N | No
W2-082 | Fort Dix-McGuire 34.5kV | North Hanover Solar Farm | NJ | Burlington | In Service | JCPL | 8 | 17 | 3 | 8.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2082_wmpa.pdf |  | Not Required | N/A | N/A | 3/17/2017 | 7/30/2010 | N/A | N/A | 3/17/2017 |  |  | 1/17/2017 | 1/17/2017 | 3/17/2017 | N | No
W2-083 | Frenchtown-Rosemont 34.5kV | Perotti Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 17 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2083_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2083_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
W2-084 | Branchville-Holiday Lakes 34.5kV | Roberts Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2084_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2084_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 2/19/2013 | Customer Milestone Not Met | 6/30/2014 | 6/30/2014 |  | N | No
W2-085 | Baptistown-Frenchtown 34.5kV | Gombasi Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2085_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 2/19/2013 | Customer Milestone Not Met | 6/30/2014 | 6/30/2014 |  | N | No
W2-086 | Baptistown-East Flemington 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2086_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 1/10/2011 |  |  | N | No
W2-087 | Mt. Holly 26kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2087_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 6/16/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W2-088 | Gravel Hill-Smithburg 34.5kV | Freehold Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 17 | 17 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
W2-089 | Cookstown-Fort Dix 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 20 | 17 | 6.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2089_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 6/8/2011 | Customer Milestone Not Met | 1/6/2012 |  |  | N | No
W2-090 | Lumberton 230kV | Stacy Haines Road | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2090_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2090_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 1/19/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W2-091 | Broadway-Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 0 | 8 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2091_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2091_wmpa.pdf |  | Not Required | N/A | N/A | 5/20/2016 | 7/30/2010 | N/A | N/A | 5/20/2016 |  |  | 6/13/2016 | 6/13/2016 | 5/31/2016 | N | No
W2-092 | Hunterstown 115kV II |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2092_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/12/2012 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W2-093 | Hunterstown 115kV III |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2093_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/12/2012 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W2-094 | Lincoln 13.2kV | Lincoln Solar Farm | PA | Adams | Withdrawn | ME | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2094_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2094_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 |  | N | No
W2-095 | Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 5/23/2011 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W2-096 | West Carlisle-Newville 1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2096_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2096_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W2-097 | West Carlisle-Newville 2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2097_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2097_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W2-098 | Hunterstown 115kV IV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2098_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2098_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/13/2012 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W2-099 | Kenney 69kV |  | MD | Worcester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2099_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 5/4/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W2-100 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 11/19/2010 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W2-101 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2101_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 10/16/2014 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
W2-102 | Mt. Holly 26.4kV | West Pemberton Solar | NJ | Burlington | In Service | PSEG | 7 | 7 | 2.66 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_102_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 7/3/2014 | N | No
W3-001 | Gilbert-Morris Park 34.5kV | Alpha Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3001_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/28/2010 | N/A | N/A |  | 9/28/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-002 | Occoquan 34.5kV | I-95 Landfill Phase 2 | VA | Fairfax | In Service | Dominion | 3.2 | 3.2 | 2.9 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3002_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_002_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/2/2010 | N/A | N/A |  |  |  | 4/1/2011 | 4/1/2011 | 4/1/2011 | N | No
W3-003 | East Flemington-Frenchtown 34.5kV | Quakertown Solar Farm #1 | NJ | Hunterdon | In Service | JCPL | 8.8 | 8.8 | 0 | 10 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_003_csa.pdf | Document Posted | N/A | N/A |  | 8/3/2010 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 10/30/2018 | N | No
W3-004 | Ridgefield 13kV |  | NJ | Bergen | Withdrawn | PSEG | 1.261 | 1.261 | 0.479 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3004_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/3/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/15/2011 |  |  | N | No
W3-005 | Fostoria Central-Galion (FE) 345kV |  | OH | Huron | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3005_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/3/2010 | N/A | N/A |  | 6/18/2014 | Customer Initiated Withdrawal | 11/30/2013 |  |  | N | No
W3-006 | Newburgh 12kV |  | NJ | Morris | Withdrawn | JCPL | 6 | 5 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/5/2010 | N/A | N/A |  | 3/7/2011 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W3-007 | Reed 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-008 | Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3008_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2010 | N/A | N/A |  | 9/12/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-009 | Fairton |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2010 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-010 | Hans Meadow 12.47KV |  | VA | Montgomery | Withdrawn | AEP | 0.34 | 0.34 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3010_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 6/16/2011 | Customer Milestone Not Met | 8/1/2010 |  |  | Y | No
W3-011 | East Lima-Fostoria Central 345kV |  | OH | Hancock | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 9/2/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-012 | East Lima-Fostoria Central 345kV |  | OH | Hancock | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3012_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-013 | Miami |  | OH | Miami | Withdrawn | Dayton | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 3/16/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-014 | Galion-Fostoria Central 345kV |  | OH | Crawford | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 4/19/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W3-015 | Egg Harbor Township |  | NJ | Atlantic | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 3/1/2011 |  |  | N | No
W3-016 | Pilesgrove |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-017 | Pilesgrove |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/21/2011 |  |  | N | No
W3-018 | Deepwater-Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2010 | N/A | N/A |  | 8/23/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-019 | Fentress-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3019_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/2010 | N/A | N/A |  | 7/29/2011 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W3-021 | Jacksons Ferry-Peak Creek 138kV |  | VA | Pulaski | Withdrawn | AEP | 70 | 70 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2010 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W3-021A | Corry East 115kV |  | PA | Crawford | Withdrawn | PENELEC | 70 | 70 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3021a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3021a_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2010 | N/A | N/A |  | 10/1/2012 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-022 | Frackville-Eldred #1 230kV |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3022_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_022_csa.pdf | Document Posted | N/A | N/A |  | 8/25/2010 | N/A | N/A |  | 3/25/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W3-023 | Frackville-Eldred #2 230kV |  | PA | Schuylkill | Withdrawn | PPL | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2010 | N/A | N/A |  | 10/3/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-024 | Columbia 138kV |  | IN | Whitley | Withdrawn | AEP | 149.4 | 149.4 | 19.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3024_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2010 | N/A | N/A |  | 4/25/2013 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
W3-025 | Wrightstown 34.5kV | Saylors Pond Solar Farm | NJ | Burlington | Withdrawn | JCPL | 2.06 | 2.06 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3025_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 6/22/2016 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-026 | Burlington 13kV | 1900 River Road | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3026_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3026_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 7/23/2013 | Customer Milestone Not Met | 3/1/2013 | 3/1/2013 |  | N | No
W3-027 | Meadowbrook 500kV |  | VA | Frederick | Withdrawn | APS | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w3027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w3027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/w3027_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 12/9/2013 | Customer Initiated Withdrawal | 6/1/2011 |  |  | S | No
W3-028 | Cedar 230kV | New Jersey Offshore Wind Project | NJ | Atlantic | Withdrawn | AEC | 348 | 348 | 45 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3028_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_028_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 5/12/2016 | Customer Initiated Withdrawal | 1/1/2019 | 1/1/2019 |  | N | No
W3-029 | Buckeye-Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | In Service | JCPL | 8.4 | 8.4 | 3.2 | 8.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3029_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 6/4/2018 | N | No
W3-030 | Southampton 13kV | 1626 Route 70 | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3030_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 4/30/2012 | 4/30/2012 |  | N | No
W3-031 | Medford 69kV |  | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2010 | N/A | N/A |  | 10/27/2010 | Customer Initiated Withdrawal | 2/6/2012 |  |  | N | No
W3-032 | Stewartsville-West Portal 34.5kV | New Village Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3032_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  | 12/24/2013 | Customer Milestone Not Met | 9/1/2014 | 9/1/2014 |  | N | No
W3-032A | Cartanza 230kV | Garrison Energy Center | DE | New Castle | In Service | DPL | 309.2 | 309.2 | 309.2 | 309.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3032a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3032a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3032a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_032a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_032a_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 5/21/2015 | N | No
W3-033 | Egg Harbor Township 1 |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | 7.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3033_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 10/1/2014 | Customer Initiated Withdrawal | 3/31/2018 | 3/31/2018 |  | N | No
W3-034 | Egg Harbor Township 2 |  | NJ | Atlantic | Withdrawn | AEC | 10 | 7.5 | 7.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3034_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 8/10/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-035 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 7 | 7 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 2/23/2011 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
W3-036 | Pemberton 12kV |  | MD | Wicomico | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 3/2/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-037 | Delmar 12kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 3/8/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-038 | Lumberton 13kV | Trotter Property | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3038_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3038_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 5/9/2012 | Customer Initiated Withdrawal | 6/30/2013 | 6/30/2013 |  | N | No
W3-039 | Bayonne 26kV |  | NJ | Hudson | Withdrawn | PSEG | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3039_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 6/3/2013 | Customer Initiated Withdrawal | 10/10/2012 | 10/10/2012 |  | N | No
W3-040 | Martinsburg |  | PA | Blair | Withdrawn | PENELEC | 3.8 | 3.8 | 3.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 4/22/2011 | Customer Milestone Not Met | 1/30/2012 |  |  | N | No
W3-041 | Burlington 26kV | Springfield Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3041_wmpa.pdf |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/2/2013 | Customer Milestone Not Met | 7/1/2012 | 7/1/2012 |  | N | No
W3-042 | Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-043 | Pendleton 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 8/16/2011 | Customer Milestone Not Met | 11/30/2017 |  |  | N | No
W3-044 | Washington 34.5kV | McCullough Road Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3044_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3044_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A | 6/27/2019 |  |  | 6/30/2019 | 6/30/2019 | 6/27/2019 | N | No
W3-045 | Fairfield 12kV | Fairfield at Howell Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3045_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 10/28/2016 |  | 9/1/2014 | 9/1/2014 |  | N | No
W3-046 | Powerton 345kV |  | IL | Mason | Withdrawn | ComEd | 207.5 | 207.5 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3046_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 5/17/2018 |  | 12/31/2015 | 12/31/2015 |  | N | No
W3-047 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 1464 | 39 | 60 | 39 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_047_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 8/31/2010 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
W3-048 | Hope Creek 500kV | Hope Creek Generating Station | NJ | Salem | In Service | PSEG | 1275 | 50 | 50 | 50 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3048_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  |  |  | 6/1/2012 |  | 1/23/2013 | N | No
W3-049 | Carneys Point 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 2/23/2011 | Customer Initiated Withdrawal | 5/31/2012 |  |  | N | No
W3-050 | Kelford 34.5kV |  | NC | Bertie | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3050_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 12/14/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W3-051 | Dorton 138kV |  | KY | Pike | Withdrawn | AEP | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/5/2012 | Customer Milestone Not Met | 9/30/2013 |  |  | N | No
W3-052 | Tazewell-Kendall 345kV |  | IL | Woodford | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W3-053 | Trowbridge 230kV |  | NC | Washington | Withdrawn | Dominion | 260 | 260 | 33.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 2/25/2011 | Customer Initiated Withdrawal | 9/30/2013 |  |  | N | No
W3-054 | Mackeys-Riders Creek 115kV |  | NC | Tyrell | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3054_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3054_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 5/28/2012 | Customer Initiated Withdrawal | 9/30/2013 |  |  | N | No
W3-054A | Oak Hall 138kV |  | VA | Accomack | Withdrawn | ODEC | 95 | 95 | 12.35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3054a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3054a_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/22/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W3-055 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3055_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/1/2010 | N/A | N/A |  | 9/7/2011 | Customer Initiated Withdrawal | 11/30/2011 |  |  | N | No
W3-056 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3056_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/1/2010 | N/A | N/A |  | 9/7/2011 | Customer Milestone Not Met | 3/1/2013 | 3/1/2013 |  | N | No
W3-057 | Lumberton 69kV | Warfield II | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3057_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/1/2010 | N/A | N/A |  | 1/5/2016 | Customer Initiated Withdrawal | 10/1/2015 | 10/1/2015 |  | N | No
W3-058 | Rio Grande 12kV |  | NJ | Cape May | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3058_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-059 | Quinton 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3059_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W3-059A_AT6 | Avery-Greenfield 138kV |  | OH | Erie | Withdrawn | ATSI | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3059a_at6_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3059a_at6_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3059a_at6_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 11/7/2014 | Customer Initiated Withdrawal | 9/9/2017 | 9/9/2017 |  | N | No
W3-059B_AT7 | Allen Junction-Lyons 138kV |  | OH | Fulton | Withdrawn | ATSI | 97.6 | 97.6 | 12.69 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3059b_at7_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 2/2/2012 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
W3-059C_AT8 | Allen Junction 138kV |  | OH | Fulton | Withdrawn | ATSI | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3059c_at8_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 6/15/2011 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
W3-060 | Kendallville 138kV |  | IN | Noble | Withdrawn | AEP | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3060_fea.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2010 | N/A | N/A |  | 11/14/2011 | Customer Milestone Not Met | 11/1/2012 |  |  | N | No
W3-061 | Church 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2010 | N/A | N/A |  | 2/28/2011 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W3-062 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2010 | N/A | N/A | [6 empty] | S | No
W3-063 | South Fultonham 4kV | Zanesville Energy | OH | Muskingum | Deactivated | AEP | 0.85 | 0.85 | 0 | 0.85 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3063_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/17/2010 | N/A | N/A |  | 9/8/2018 |  | 5/31/2011 | 5/31/2011 | 5/31/2011 | N | No
W3-064 | Hunterstown 115kV V |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-065 | Braidwood-Cook |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/w3065_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2010 | N/A | N/A |  | 4/4/2013 |  |  |  |  | EE | No
W3-066 | Shawboro 230kV | Hales Lake Energy Center | NC | Camden | Withdrawn | Dominion | 300 | 300 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3066_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_066_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2010 | N/A | N/A |  | 8/1/2016 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
W3-067 | Gardners-Hunterstown 115kV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-068 | Cumberland-W. Shore 3 #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3068_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2010 | N/A | N/A |  | 5/23/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-069 | Cumberland-W. Shore 3 #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3069_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2010 | N/A | N/A |  | 5/23/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-070 | Metropolitan Court 34.5kV |  | MD | Frederick | Withdrawn | APS | 52 | 52 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3070_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2010 | N/A | N/A |  | 3/25/2013 | Customer Initiated Withdrawal | 10/31/2013 |  |  | N | No
W3-071 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 12.54 | 12.54 | 4.77 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3071_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 3/21/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-072 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3072_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 9/12/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-073 | West Cape May 12kV |  | NJ | Cape May | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3073_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 8/12/2011 | Customer Milestone Not Met | 3/1/2011 |  |  | N | No
W3-075 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 8/12/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W3-076 | Morris Park-Stewartsville 34.5kV | South Main Street Solar Farm | NJ | Warren | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3076_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W3-077 | Broadway-Stewartsville 34.5kV | Franklin Township Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3077_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A | 12/4/2019 |  |  | 1/31/2020 | 1/31/2020 | 1/10/2020 | N | No
W3-078 | Twin Rivers-Windsor 34.5kV | East Windsor Solar Farm | NJ | Mercer | Withdrawn | JCPL | 13 | 13 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3078_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3078_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 10/21/2014 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-079 | Allenwood-Larabee 34.5kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 7 | 7 | 2.6 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3079_wmpa.pdf |  | Not Required | N/A | N/A | 3/11/2016 | 9/30/2010 | N/A | N/A |  |  |  | 10/6/2016 | 10/6/2016 | 4/19/2016 | N | No
W3-080 | Burlington 26kV | Cedar Lane | NJ | Burlington | In Service | PSEG | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3080_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  |  |  | 11/15/2016 | 11/15/2016 | 12/29/2016 | N | No
W3-081 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 11 | 11 | 4.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3081_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 7/26/2011 | Customer Milestone Not Met | 2/15/2012 |  |  | N | No
W3-082 | Woodbine Township |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3082_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-083 1650070 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 84 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1650070_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1650070_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/8/2010 | 10/1/2011 | 10/1/2016 | [6 empty] | FF | No
W3-084 | Clinton-Round Valley 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 16.6 | 16.6 | 6.31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2010 | N/A | N/A |  | 12/3/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W3-085 | Chatfield-South Tiffin 138kV |  | OH | Crawford | Withdrawn | AEP | 185 | 185 | 24 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2010 | N/A | N/A |  | 5/7/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W3-086 | Townsend 138kV |  | DE | New Castle | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/18/2010 | N/A | N/A |  | 8/16/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-087 | Cartanza 230kV |  | DE | Kent | Withdrawn | DPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/18/2010 | N/A | N/A |  | 3/15/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-088 | South West Lima 345kV | Long Prairie Wind I, LLC | OH | Van Wert | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_088_csa.pdf | Document Posted | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 10/28/2016 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
W3-089 | Carneys Point 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W3-090 | Carneys Point 12kV 1 |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3090_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-092 | Carneys Point 12kV 2 |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-093 | Lyon Station |  | PA | Berks | Withdrawn | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3093_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/25/2010 | N/A | N/A |  | 3/5/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
W3-095 | Broadway-Stewartsville#2 34.5kV | Stewartsville Solar Farm | NJ | Warren | Withdrawn | JCPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3095_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 9/18/2014 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-096 | Perkiomen |  | PA | Montgomery | Withdrawn | PECO | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 11/2/2011 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
W3-097 | Russelville OH |  | OH | Brown | Withdrawn | AEP | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 10/10/2011 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
W3-098 | Hillsboro-Kenton (KU) 138kV |  | OH | Brown | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 10/24/2011 | Customer Initiated Withdrawal | 6/30/2013 |  |  | N | No
W3-099 | Erie East-Erie South 230 kV | Greenfield Wind Farm | PA | Erie | Withdrawn | PENELEC | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3099_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3099_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_099_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2010 | N/A | N/A |  | 9/10/2018 |  | 12/31/2019 | 12/31/2019 |  | N | No
W3-100 | Daretown Road 12kV |  | NJ | Salem | Withdrawn | AEC | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2010 | N/A | N/A |  | 3/3/2011 | Customer Initiated Withdrawal | 6/30/2012 |  |  | N | No
W3-101 | East Elmer Road 12kV | Elmer Road | NJ | Cumberland | Withdrawn | AEC | 3.2 | 3.2 | 1.21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3101_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3101_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2010 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 9/15/2012 |  |  | N | No
W3-102 | East Carbondale-Lackawanna 69kV |  | PA | Wayne | Withdrawn | PPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3102_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2010 | N/A | N/A |  | 5/19/2011 | Customer Initiated Withdrawal | 5/30/2011 |  |  | N | No
W3-103 | Upper Deerfield Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3103_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/16/2011 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
W3-104 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3104_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-105 | Dickerson 230kV | Dickerson CT1 (D-CT1) | MD | Montgomery | Deactivated | PEPCO | 18 | 5 | 5 | 5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3105_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_105_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 8/23/2011 | N | No
W3-106 | Sussex-Wykertown 34.5kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 9.9 | 0 | 9.9 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3106_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3106_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3106_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 1/22/2016 | N | No
W3-107 | Ringoes-Texas Eastern 34.5kV | Garboski I Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3107_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3107_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 1/27/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-108 | Ringoes #2 34.5kV | Garboski I Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3108_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3108_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/21/2011 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-109 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 0.625 | 0.625 | 0.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3109_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/3/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-110 | Sussex | Wantage Solar Farm | NJ | Sussex | In Service | JCPL | 7.5 | 7.5 | 2.85 | 7.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3110_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3110_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 11/15/2013 | N | No
W3-111 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3111_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3111_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_111_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2018 |  | 4/16/2017 | 4/16/2017 |  | N | No
W3-112 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 35 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3112_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3112_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_112_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2018 |  | 4/16/2018 | 4/16/2018 |  | N | No
W3-113 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 49.9 | 14.9 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3113_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3113_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_113_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2018 |  | 4/16/2019 | 4/16/2019 |  | N | No
W3-113A 1685913 | PJM-TVA |  | N/A | N/A | Retracted |  | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1685913_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/29/2010 | 1/1/2012 | 1/1/2017 |  | 2/9/2011 |  |  |  |  | FF | No
W3-114 | Venango I |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3114_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-115 | Venango II |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3115_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-116 | Venango III |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-117 | Clarion |  | PA | Clarion | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-118 | Venango IV |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-119 | Venango V |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-120 | Cookstown-Great Adventure 34.5kV | Polizzi Solar Farm | NJ | Ocean | Withdrawn | JCPL | 17 | 17 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3120_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3120_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/16/2014 |  | 12/31/2014 | 12/31/2014 |  | N | No
W3-121 | Queen Anne County 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3121_fea.pdf | Document Posted |  | Withdrawn |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/8/2011 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
W3-122 | Brandon Shores-Riverside 230kV |  | MD | Unknown | Withdrawn | BGE | 236 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w3122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w3122_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/w3122_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/w3_122_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/20/2013 | Customer Initiated Withdrawal | 12/1/2014 | 12/1/2014 |  | S | No
W3-123 | Brandon Shores |  | MD | Unknown | Withdrawn | BGE |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w3123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w3123_imp2.pdf | Interim Study |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/w3_123_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/20/2013 | Customer Initiated Withdrawal | 7/26/2011 | 7/26/2011 | 2/29/2012 | S | No
W3-124 | Devils Brook 13kV | Matrix-Stults Road | NJ | Middlesex | In Service | PSEG | 2.85 | 2.85 | 1.08 | 2.85 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3124_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3124_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 6/30/2011 | 6/30/2011 | 6/17/2011 | N | No
W3-125 | Eagle Point 230kV |  | NJ | Gloucester | Withdrawn | PSEG | 195 | 27.9 | 27.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3125_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/8/2011 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W3-126 | Branchville-Holiday Lakes 34.5kV | Syncarpha Ty Solar Farm | NJ | Sussex | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3126_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3126_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 1/3/2014 | Customer Milestone Not Met | 9/1/2014 | 9/1/2014 |  | N | No
W3-127 | City of Columbus 14.4kV |  | OH | Franklin | Withdrawn | AEP | 1 | 1 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3127_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/3/2012 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
W3-128 | Sporn-Waterford 345kV |  | OH | Meigs | Withdrawn | AEP | 652 | 652 | 652 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/22/2017 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
W3-129 | Beaver Brook 13kV | Blackwood Solar | NJ | Camden | Withdrawn | PSEG | 7.3 | 7.3 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3129_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3129_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/27/2012 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W3-130 | Crosswicks 13kV | Mansfield Solar | NJ | Burlington | Withdrawn | PSEG | 8.3 | 8.3 | 3.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3130_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3130_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/27/2012 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W3-131 | Alpha #2 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 7.6 | 7.6 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/21/2010 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
W3-132 | Stillman Valley |  | IL | Winnebago | Withdrawn | ComEd | 19.4 | 19.4 | 7.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3132_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/30/2013 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-133 | Kewanee |  | IL | Stark | Withdrawn | ComEd | 19.5 | 19.5 | 2.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/15/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-134 | South Joliet 34.5kV | Brandon Road Lock & Dam | IL | Will | Withdrawn | ComEd | 10.6 | 10.6 | 10.6 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3134_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3134_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A | 10/1/2021 | 4/20/2021 |  | 1/31/2022 | 1/31/2022 |  | N | No
W3-135 | Goose Lake 34.5kV | Dresden Island Lock & Dam | IL | Grundy | Withdrawn | ComEd | 12.1 | 12.1 | 12.1 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3135_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3135_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A | 10/1/2022 | 2/21/2022 |  | 1/31/2022 | 1/31/2022 |  | N | No
W3-136 | Andover-Kittatinny #2 34.5kV | Hibler Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3136_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3136_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-137 | Furnace Brook 12kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3137_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/25/2011 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
W3-138 | Blairstown-Kittatinny 34.5kV | Stillwater Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3138_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3138_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2012 | 9/1/2012 |  | N | No
W3-139 | Broadway-Stewartsville #3 34.5kV | Broadway Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3139_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 1/17/2018 | Customer Initiated Withdrawal | 5/31/2017 | 5/31/2017 |  | N | No
W3-140 | Sussex #2 | Roy Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3140_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3140_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-141 | Knowlton #1 12kV |  | NJ | Warren | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3141_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/18/2011 | Customer Initiated Withdrawal | 3/31/2012 |  |  | N | No
W3-142 | Lopatcong |  | NJ | Warren | Withdrawn | JCPL | 18 | 18 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3142_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2011 | Customer Initiated Withdrawal | 3/31/2012 |  |  | N | No
W3-143 | Knowlton #2 |  | NJ | Warren | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/3/2012 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-144 | Pequest-Washington 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3144_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 4/11/2012 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
W3-145 | Branchville-Newton 34.5kV | Hampton Township Solar Farm | NJ | Sussex | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3145_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3145_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-146 | Andover-Kittatinny 34.5kV | Kerrs Corner Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3146_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3146_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/15/2014 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-147 | Baptistown-Frenchtown #2 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3147_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/30/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-148 | Baptistown 12kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6 | 6 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3148_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/25/2011 | Customer Milestone Not Met | 11/15/2011 |  |  | N | No
W3-149 | Frenchtown-Rosemont 34.5kV | Route 519 Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3149_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3149_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/7/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W3-150 | Flemington 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3150_fea.pdf | Document Posted |  | Withdrawn |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 3/15/2012 |  |  | N | No
W3-151 | Phillipsburg 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 16 | 16 | 6.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3151_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 3/15/2012 |  |  | N | No
W3-152 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3152_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/21/2011 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
W3-153 | Heaton 34kV |  | PA | Montgomery | Withdrawn | PECO | 2.6 | 2.6 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3153_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/2/2011 | Customer Milestone Not Met | 6/4/2011 |  |  | N | No
W3-154 | Broadway 12kV | Schanzlin Solar Farm | NJ | Warren | Withdrawn | JCPL | 1.6 | 1.6 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3154_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3154_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/1/2014 | Customer Milestone Not Met | 9/1/2014 | 9/1/2014 |  | N | No
W3-155 | Alabama 13.8kV |  | DC | N/A | Withdrawn | PEPCO | 20 | 20 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3155_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2013 | Customer Milestone Not Met | 2/28/2014 |  |  | N | No
W3-156 | Englishtown-Texas Road 34.5kV | Swayles Solar Farm | NJ | Middlesex | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3156_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3156_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-157 | Stow Creek Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.7 | 1.7 | 0.65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3157_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-158 | Great Adventure-Great Adventure Tap 34kV | Millstone Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3158_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3158_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/26/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W3-159 | Hornerstown-Windsor 34kV | Monmouth West Solar I | NJ | Monmouth | Withdrawn | JCPL | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3159_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3159_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/5/2016 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | No
W3-160 | Worcester 25kV | Worcester Solar Facility | MD | Worcester | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3160_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3160_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/24/2015 | Customer Initiated Withdrawal | 10/31/2017 | 10/31/2017 |  | N | No
W3-161 | Kanawha River 138kV |  | WV | Fayette | Withdrawn | AEP | 13 | 13 | 13 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3161_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/16/2012 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
W3-162 | Baker 345kV | Riverside Generating Stations | KY | Lawrence | In Service | AEP | 993 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3162_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_162_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 2/8/2010 | 2/8/2010 | 9/9/2011 | N | No
W3-163 | Upper Pittsgrove 138kV 1 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3163_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-164 | Upper Pittsgrove 138kV 2 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3164_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-165 | Upper Pittsgrove 138kV 3 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3165_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-166 | Nottingham I |  | PA | Chester | Withdrawn | PECO | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3166_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/22/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-167 | Nottingham II |  | PA | Chester | Withdrawn | PPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3167_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/26/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-168 | Germantown 13.2 kV |  | PA | Adams | Withdrawn | ME | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3168_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-169 | North Hanover 12.5kV |  | PA | Adams | Withdrawn | ME | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3169_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-170 | Buckskin 69kV |  | OH | Putnam | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3170_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3170_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/12/2014 | Customer Milestone Not Met | 9/30/2015 | 9/30/2015 |  | N | No
W3-171 | Levittown 13kV | Rancocas Road Solar Project | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3171_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3171_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 4/10/2012 | Customer Initiated Withdrawal | 4/30/2012 | 4/30/2012 |  | N | No
W3-172 | Hay Road 230kV 1 |  | DE | New Castle | Withdrawn | DPL | 402 | 402 | 402 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3172_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/2/2011 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W3-173 | Hay Road 230kV 2 |  | DE | New Castle | Withdrawn | DPL | 218 | 218 | 218 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3173_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/2/2011 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
W3-174 | Churchtown 230kV 1 |  | NJ | Salem | Withdrawn | AEC | 193.5 | 193.5 | 193.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3174_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 4/15/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
W3-175 | Churchtown 230kV 2 | Deepwater | NJ | Salem | Withdrawn | AEC | 371 | 371 | 371 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3175_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3175_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_175_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/7/2019 |  | 12/1/2021 | 12/1/2021 |  | N | No
W4-001 | Clover |  | VA | Halifax | Withdrawn | Dominion | 7 | 7 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2010 | N/A | N/A |  | 1/20/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-001A_AT9 | Lowellville 69kV | Carbon Limestone Landfil Gas to Electricity Facility | OH | Mahoning | Deactivated | ATSI | 24 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4001a_at9_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4001a_at9_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_001a_at9_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2010 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 9/19/2012 | N | No
W4-003 | Marengo-Pleasant Valley |  | IL | McHenry | Withdrawn | ComEd | 164 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2010 | N/A | N/A |  | 11/28/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
W4-004 | Madison-Tanners Creek 138kV | Flat Rock-WF-1 | IN | Henry | Withdrawn | AEP | 90 | 90 | 11.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4004_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4004_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/W4_004_csa.pdf | Document Posted | N/A | N/A |  | 11/10/2010 | N/A | N/A |  | 10/22/2018 |  | 7/1/2021 | 7/1/2021 |  | N | No
W4-004A_AT10 | Oberlin Road 69kV | Lorain | OH | Lorain | Deactivated | ATSI | 19.2 | 19.2 | 19.2 | 19.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4004a_at10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4004a_at10_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4004a_at10_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/12/2010 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 5/31/2012 | N | No
W4-004B_AT11 | Perry 345kV | Perry Nuclear Power Plant | OH | Lake | In Service | ATSI | 1297.8 | 16 | 16 | 16 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4004b_at11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4004b_at11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_004B_at11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2010 | N/A | N/A | [5 empty] | 4/26/2013 | N | No
W4-005 | Blue Mound-Latham | Radford's Run Wind Farm | IL | Macon | In Service | ComEd | 306 | 306 | 39.8 | 306 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4005_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_005_csa.pdf | Document Posted | N/A | N/A |  | 11/17/2010 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 12/14/2017 | N | No
W4-006 | S. Hicksville-Lockwood Road 138kV |  | OH | Defiance | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/19/2010 | N/A | N/A |  | 4/19/2012 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-007 | Afton 138kV |  | WV | Preston | Withdrawn | APS | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/19/2010 | N/A | N/A |  | 5/31/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-008 | Madison-Tanners Creek 138kV | Flat Rock - WF-1 | IN | Henry | Withdrawn | AEP | 180 | 90 | 11.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4008_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4008_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_008_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_008_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  | 10/22/2018 |  | 7/1/2021 | 7/1/2021 |  | N | No
W4-009 | Raritan River 230kV | Woodbridge Energy Center | NJ | Middlesex | In Service | JCPL | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4009_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_009_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_009_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 12/4/2015 | N | No
W4-010 | White Oak |  | MD | Montgomery | In Service | PEPCO | 53 | 29.1 | 0 | 29.1 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_010_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 5/8/2014 | N | No
W4-011 | Larabee 34.5kV | Solar Wind Energy Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4011_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/24/2010 | N/A | N/A |  | 2/22/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
W4-012 | Whetstone 115kV |  | PA | Elk | Withdrawn | PENELEC | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4012_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/2010 | N/A | N/A |  | 5/31/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-013 | Frack-Orwigsburg 69kV |  | PA | Schuylkill | Withdrawn | PPL | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/2010 | N/A | N/A |  | 11/13/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-014 | Stewartsville-Captive Plastics 34.5kV | Stewartsville II Solar Farm | NJ | Warren | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4014_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4014_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/29/2010 | N/A | N/A |  | 1/21/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-015 | Mickleton 230kV 1 | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 860 | 210 | 136 | 210 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 1/16/2015 | N | No
W4-016 | Mickleton 230kV 2 | West Deptford Energy Station | NJ | Gloucester | Withdrawn | AEC | 1095 | 235 | 235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4016_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4016_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_016_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_016_csa.pdf | Document Posted | N/A | N/A |  | 11/29/2010 | N/A | N/A |  | 11/20/2018 |  | 6/1/2019 | 6/1/2019 |  | N | No
W4-017 | Kings Creek-Crisfield 69kV |  | MD | Somerset | Withdrawn | DPL | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2010 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
W4-018 | Monroeville 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 3/15/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W4-019 | Mendota |  | IL | Bureau | Withdrawn | ComEd | 40 | 40 | 9.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4019_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 1/30/2012 | Customer Initiated Withdrawal | 10/1/2012 |  |  | N | No
W4-020 | Mt. Zion 13.8kV |  | MD | Montgomery | Withdrawn | PEPCO | 10.08 | 10.08 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 9/18/2012 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W4-021 | Atlantic-South River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 738.4 | 738.4 | 738.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4021_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4021_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 9/11/2013 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
W4-021A | Richland & Crawford |  | OH | Richland | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4021a_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 9/18/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
W4-022 | Hunterstown 230kV |  | PA | Adams | Withdrawn | ME | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2010 | N/A | N/A |  | 7/29/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-023 | Kearny 138kV |  | NJ | Hudson | Withdrawn | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2010 | N/A | N/A |  | 5/21/2012 |  | 5/31/2014 |  |  | N | No
W4-024 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2010 | N/A | N/A |  | 6/5/2012 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
W4-025 | Cookstown-Fort Dix 34.5kV | North Run Solar | NJ | Burlington | In Service | JCPL | 7 | 7 | 2.6 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_025_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2010 | N/A | N/A |  |  |  | 5/29/2014 | 5/29/2014 | 2/4/2015 | N | No
W4-026 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2010 | N/A | N/A |  | 11/28/2011 | Customer Initiated Withdrawal | 5/31/2012 |  |  | N | No
W4-027 | Minotola 12kV | Minotola 2 Solar Facility | NJ | Atlantic | Withdrawn | AEC | 7.9 | 7.9 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4027_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4027_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/15/2010 | N/A | N/A |  | 5/20/2016 | Customer Initiated Withdrawal | 6/1/2018 | 6/1/2018 |  | N | No
W4-028 | Quinton 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/15/2010 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 6/30/2011 |  |  | N | No
W4-029 | Medford 13kV | Reeve's Station North | NJ | Burlington | Withdrawn | PSEG | 2.4 | 2.4 | 0.91 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4029_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/17/2010 | N/A | N/A |  | 10/31/2018 |  | 12/31/2014 | 12/31/2014 |  | N | No
W4-030 | Jessup |  | MD | Howard | Withdrawn | BGE | 0.008 | 0.008 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4030_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/20/2010 | N/A | N/A |  | 7/20/2012 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
W4-031 | Perryville 12.5kV | Pattenburg Quarry Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2.6 | 2.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4031_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4031_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/22/2010 | N/A | N/A |  | 11/23/2015 |  | 12/31/2014 | 12/31/2014 |  | N | No
W4-032 | West Portal 4.8kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4032_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 4/4/2012 | Customer Initiated Withdrawal | 12/22/2011 |  |  | N | No
W4-033 | Wilmington | Lincoln Solar | IL | Will | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4033_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4033_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 12/8/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W4-034 | Essex 26.4kV |  | NJ | Essex | Withdrawn | PSEG | 3 | 3 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4034_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 9/1/2011 | Customer Milestone Not Met | 3/1/2011 |  |  | N | No
W4-035 | Martinsville |  | OH | Clinton | Withdrawn | Dayton | 20 | 20 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 12/12/2011 | Customer Initiated Withdrawal | 5/31/2012 |  |  | N | No
W4-036 | Buckskin 12kV | Ohio Solar I | OH | Ross | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4036_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4036_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 1/2/2018 |  | 1/31/2019 | 1/31/2019 |  | N | No
W4-037 | Bismark 500kV | New Creek Mountain Energy Storage | WV | Grant | Withdrawn | Dominion | 160 | 32 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4037_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4037_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_037_csa.pdf | Document Posted | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 11/5/2018 |  | 12/31/2018 | 12/31/2018 | 12/26/2016 | N | No
W4-038 | Hudson 230kV | Hudson Generating Station | NJ | Hudson | Deactivated | PSEG | 677.5 | 24 | 24 | 12 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/30/2010 | N/A | N/A |  |  |  | 8/31/2018 | 8/31/2018 | 11/1/2012 | N | No
W4-039 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 6/22/2012 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
W4-040 | Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 9.7 | 9.7 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 6/2/2014 | Customer Initiated Withdrawal | 5/13/2012 |  |  | N | No
W4-041 | Carlls Corner 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4041_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 1/31/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
W4-042 | McConnellsburg 34.5kV | Cove Creek Solar Project | PA | Fulton | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4042_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 7/23/2013 | Customer Initiated Withdrawal | 12/15/2014 | 12/15/2014 |  | N | No
W4-043 | Roberts 34.5kV |  | OH | Marion | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2010 | N/A | N/A |  | 1/18/2011 |  | 9/1/2012 |  |  | N | No
W4-044 | Kelson Ridge 230kV |  | MD | Charles | Withdrawn | PEPCO | 1450 | 725 | 725 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4044_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/5/2011 | N/A | N/A |  | 7/31/2013 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
W4-045 | Great Adventure-Great Adventure Tap 34.5kV | Red Valley Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4045_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/11/2011 | N/A | N/A |  | 7/26/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W4-046 | Washington-Mobile Chemical 34.5kV | Hengst Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 3.8 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4046_wmpa.pdf |  | Not Required | N/A | N/A | 6/17/2016 | 1/11/2011 | N/A | N/A | 6/29/2016 |  |  | 11/28/2016 | 11/28/2016 | 7/13/2016 | N | No
W4-047 1855230 | PJM-LGEE |  | N/A | N/A | Withdrawn |  | 700 |  |  |  | Energy | Long-Term Firm Transmission | [7 empty] | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2014 | 6/1/2024 |  | 3/1/2011 |  |  |  |  | FF | No
W4-048 | Doremus Place 13kV |  | NJ | Essex | Withdrawn | PSEG | 1.05 | 1.05 | 0.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4048_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/18/2011 | N/A | N/A |  | 6/27/2011 | Customer Initiated Withdrawal | 6/30/2011 |  |  | N | No
W4-049 1878104 | CPLE-PJM |  | N/A | N/A | Confirmed |  | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1878104_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1878104_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
W4-050 1878108 | CPLE-PJM |  | N/A | N/A | Annulled |  | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1878108_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1878108_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
W4-051 | Packer 13kV |  | PA | Philadelphia | Withdrawn | PECO | 12 | 12 | 10.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2011 | N/A | N/A |  | 11/3/2011 | Customer Milestone Not Met | 9/1/2011 |  |  | N | No
W4-052 1885494 | TVA-PJM |  | N/A | N/A | Retracted |  | 900 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1885494_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/1885494_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2014 | [6 empty] | FF | No
W4-053 | Rocktown 4.8kV | Green Power West Amwell Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4053_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4053_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/24/2011 | N/A | N/A |  | 10/20/2015 |  | 12/31/2014 | 12/31/2014 |  | N | No
W4-054 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 12 | 12 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4054_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2011 | N/A | N/A |  | 5/24/2011 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
W4-054A 1893487 | EKPC-PJM |  | N/A | N/A | Retracted |  | 42 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/1893487_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2014 |  | 4/21/2011 |  |  |  |  | FF | No
W4-055 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2011 | N/A | N/A |  | 12/13/2011 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
W4-056 | Pittsgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4056_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 4/15/2012 |  |  | N | No
W4-057 | Pittsgrove 2 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4057_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 4/15/2012 |  |  | N | No
W4-058 | Lawrence 13kV | Rider University | NJ | Mercer | In Service | PSEG | 0.702 | 0.702 | 0.267 | 0.702 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4058_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 12/16/2011 | N | No
W4-059 | Kuller Road 13kV | Metro Division Headquarters | NJ | Passaic | In Service | PSEG | 0.6 | 0.6 | 0.228 | 0.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4059_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 6/30/2012 | 6/30/2012 | 7/5/2012 | N | No
W4-060 | Midland-Werner 34.5kV | Old Bridge Solar Farm | NJ | Middlesex | In Service | JCPL | 10 | 10 | 3.8 | 8.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4060_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4060_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/31/2018 | 3/31/2018 | 8/4/2018 | N | No
W4-061 | Lawrence 26kV |  | NJ | Mercer | Withdrawn | PSEG | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4061_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/27/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W4-062 | Tabernacle 69kV |  | NJ | Burlington | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4062_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W4-063 | Huron 69kV | Fishermen's Atlantic City Windfarm (FACW) | NJ | Cape May | Withdrawn | AEC | 25 | 5 | 0.65 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4063_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4063_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_063_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_063_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 3/12/2019 |  | 1/27/2019 | 1/27/2019 |  | N | No
W4-064 | N. Newton 12kV | Augusta Solar Farm | NJ | Sussex | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4064_wmpa.pdf |  | Not Required | N/A | N/A | 5/10/2016 | 1/31/2011 | N/A | N/A | 5/13/2016 |  |  | 6/12/2016 | 6/12/2016 | 5/31/2016 | N | No
W4-065 | Sussex 12kV | Layton Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4065_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 5/3/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
W4-066 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4066_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/4/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-067 | Vernon 12kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W4-068 | Hazen-Pequest River 34.5kV | White Township Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4068_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4068_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-069 | Lycoming |  | PA | Lycoming | Withdrawn | PPL | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 4/29/2011 | Customer Initiated Withdrawal | 4/1/2012 |  |  | N | No
W4-070 | Morgantown |  | PA | Berks | Withdrawn | PPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4070_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/27/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W4-071 | Garrett |  | PA | Somerset | Withdrawn | PENELEC | 2.25 | 2.25 | 0.29 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/17/2011 | Customer Milestone Not Met | 3/30/2012 |  |  | N | No
W4-072 | Englishtown-Rt. 33 Sw Point 34.5kV | Big Hill Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4072_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 10/23/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-073 | Phillipsburg 34.5kV | Hamptons at Pohatcong Solar Farm | NJ | Warren | In Service | JCPL | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4073_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A | 12/31/2019 |  |  | 12/31/2019 | 12/31/2019 | 1/10/2020 | N | No
W4-074 | Cox’s Corner 13kV | CleanLight Medford Solar Project | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4074_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 4/30/2012 | 4/30/2012 |  | N | No
W4-075 | Trenton 26kV | CleanLight Mansfield Solar Project | NJ | Burlington | Withdrawn | PSEG | 9 | 9 | 3.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4075_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/7/2012 |  | 6/30/2012 | 6/30/2012 |  | N | No
W4-076 | Ritchie |  | MD | Prince George's | Withdrawn | PEPCO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4076_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/7/2011 | Customer Milestone Not Met | 11/1/2011 |  |  | N | No
W4-078 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
W4-079 | Lebanon |  | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4079_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/30/2012 | Customer Milestone Not Met | 10/31/2011 |  |  | N | No
W4-080 | Metuchen 26.4kV | IRL Landfill Solar Project | NJ | Middlesex | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4080_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/4/2016 |  | 11/30/2012 | 11/30/2012 |  | N | No
W4-081 | Manchester |  | NJ | Ocean | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/2/2011 | Customer Milestone Not Met | 10/31/2011 |  |  | N | No
W4-082 | Libertyville 12kV | Countryside Landfill | IL | Lake | Deactivated | ComEd | 7.99 | 7.99 | 7.99 | 7.99 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 4/1/2001 |  | 7/16/2012 | N | No
W4-083 | Quinton 69kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4083_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
W4-084 | Dixon 12kV | Dixon/Lee Landfill | IL | Lee | Deactivated | ComEd | 3.95 | 3.95 | 3.95 | 3.95 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/1/2001 |  | 4/16/2013 | N | No
W4-085 | Grays Ferry |  | PA | Philadelphia | Withdrawn | PECO | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4085_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/17/2014 | Customer Initiated Withdrawal | 5/15/2011 |  |  | N | No
W4-086 | Goose Lake 34.5kV | Morris Landfill | IL | Grundy | Deactivated | ComEd | 2.1 | 2.1 | 2.1 | 2.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4086_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_086_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/1/2001 |  | 5/16/2013 | N | No
W4-087 | South Holland |  | IL | Cook | Withdrawn | ComEd | 3.07 | 3.07 | 3.07 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 12/13/2012 | Customer Initiated Withdrawal | 4/1/1998 |  |  | N | No
W4-088 | Salem-Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4088_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
W4-089 | Vineland #1 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4089_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/19/2014 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W4-090 | Vineland #2 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.34 | 1.34 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/19/2014 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W4-091 | Andover-Kittatinny 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4091_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 8/1/2012 |  |  | N | No
W4-092 | Englishtown 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/3/2011 | Customer Milestone Not Met | 8/1/2012 |  |  | N | No
W4-093 | Frenchtown 34.5kV | Dotoli Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 7 | 7 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4093_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4093_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 5/7/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-094 | Millhurst-Raceway Mall 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 6 | 6 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/11/2012 | Customer Initiated Withdrawal | 3/15/2012 |  |  | N | No
W4-095 | Beckett 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5.2 | 5.2 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 3/31/2013 |  |  | N | No
W4-096 | Piney Grove 25kV |  | MD | Wicomico | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
W4-097 | Hawks 12.5kV | Wetteland Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4097_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 7/31/2016 | 7/31/2016 | 1/6/2016 | N | No
W4-098 | U.S. Silica #1 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4098_Imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/18/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W4-099 | U.S. Silica #2 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/22/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W4-100 | Exxon-NewYork Life 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 7/8/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-101 | Limecrest-Newton 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 7/6/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-102 | Lappans 34.5kV | Lappans 34.5kV Project | MD | Washington | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_102_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 11/29/2012 | N | No
W4-103 | Burlington 26kV | North American Solar | NJ | Burlington | In Service | PSEG | 7 | 7 | 2.66 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4103_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4103_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 8/15/2016 | 8/15/2016 | 3/3/2016 | N | No
X1-001 | South Millville 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1001_fea.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2011 | N/A | N/A |  | 10/4/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-003 | Belvidere |  | NJ | Warren | Withdrawn | JCPL | 1.9 | 1.9 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1003_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 4/27/2012 | Customer Milestone Not Met | 3/30/2012 |  |  | N | No
X1-004 | Asbury |  | NJ | Hunterdon | Withdrawn | JCPL | 9.7 | 9.7 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1004_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 1/11/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-005 | Port Murray | Meadows at Mansfield Solar Farm | NJ | Warren | Withdrawn | JCPL | 9.7 | 9.7 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1005_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 11/21/2013 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X1-006 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 4.8 | 4.8 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1006_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 1/31/2012 |  |  | N | No
X1-007 | Hackettstown |  | NJ | Burlington | Withdrawn | JCPL | 5.8 | 5.8 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
X1-008 | Mansfield |  | NJ | Warren | Withdrawn | JCPL | 7.8 | 7.8 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1008_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 1/31/2012 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
X1-009 | Sterling 69kV |  | OH | Allen | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1009_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 9/19/2011 | Customer Initiated Withdrawal | 12/1/2012 |  |  | N | No
X1-012 | Branchville-Sussex 34.5kV | Frankford Solar Farm | NJ | Sussex | In Service | JCPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1012_wmpa.pdf |  | Not Required | N/A | N/A | 3/2/2016 | 2/22/2011 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 3/3/2016 | N | No
X1-013 | N. Lebanon 230kV |  | PA | Lebanon | Withdrawn | ME | 1018 | 1018 | 951 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1013_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2011 | N/A | N/A |  | 12/2/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
X1-014 | Peters Mountain 13kV |  | WV | Monroe | Withdrawn | AEP | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2011 | N/A | N/A |  | 9/19/2011 | Customer Milestone Not Met | 3/15/2013 |  |  | N | No
X1-015 | Kenney-Rock Springs 500kV |  | MD | Cecil | Withdrawn | NAEA | 360 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x1015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x1015_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 8/21/2013 | Customer Initiated Withdrawal | 7/1/2013 |  |  | S | No
X1-016 | Upper Pittsgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 9/16/2011 | Customer Milestone Not Met | 1/1/2013 |  |  | N | No
X1-017 | Cedar 230kV |  | NJ | Atlantic | Withdrawn | AEC | 720 | 720 | 93 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 2/7/2012 | Customer Initiated Withdrawal | 9/30/2016 |  |  | N | No
X1-018 | Lewistown 230kV |  | PA | Mifflin | Withdrawn | PENELEC | 75 | 75 | 9.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 1/10/2012 | Customer Milestone Not Met | 8/15/2013 |  |  | N | No
X1-019 | Sunbury-Dauphin 69kV |  | PA | Dauphin | Withdrawn | PPL | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1019_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 8/29/2011 | Customer Milestone Not Met | 8/15/2013 |  |  | N | No
X1-020 | Dumont-Greentown 765kV |  | IN | Cass | Withdrawn | AEP | 1500 | 1500 | 195 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 7/25/2018 |  | 8/31/2018 | 8/31/2018 |  | N | No
X1-021 | Deptford 13kV | Deptford Solar | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 10/27/2017 |  | 9/1/2017 | 9/1/2017 |  | N | No
X1-022 | Park Hall |  | MD | St. Mary's | Withdrawn | PEPCO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 4/8/2011 | Queue Not Required | 4/30/2012 |  |  | N | No
X1-023 | Mechanicsville |  | MD | St. Mary's | Withdrawn | PEPCO | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 4/8/2011 | Queue Not Required | 4/30/2012 |  |  | N | No
X1-024 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 9/21/2011 | Customer Milestone Not Met | 4/30/2012 |  |  | N | No
X1-025 | Leonardtowne |  | MD | St. Mary's | Withdrawn | PEPCO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 4/8/2011 | Queue Not Required | 4/30/2012 |  |  | N | No
X1-026 | Brick |  | NJ | Ocean | Withdrawn | JCPL | 6.25 | 6.25 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2011 | N/A | N/A |  | 9/7/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-027 | Hanging Rock 138kV |  | OH | Scioto | Withdrawn | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2011 | N/A | N/A |  | 3/9/2012 | Customer Initiated Withdrawal | 6/30/2014 |  |  | N | No
X1-027A_AT12 | Davis Besse-Beaver 345kV | Emerson Creek Wind Farm | OH | Huron | Withdrawn | ATSI | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1027a_at12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1027a_at12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1027a_at12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_027a_at12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_027A_at12_csa.pdf | Document Posted | N/A | N/A |  | 3/3/2011 | N/A | N/A |  | 7/18/2018 |  | 4/1/2018 | 4/1/2018 |  | N | No
X1-028 | Upton 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2011 | N/A | N/A |  | 11/29/2011 | Customer Initiated Withdrawal | 11/30/2012 |  |  | N | No
X1-029 | Dorchester County |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2011 | N/A | N/A |  | 9/30/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-030 1998623 | TVA-PJM |  | N/A | N/A | Retracted |  | 500 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2014 | 6/1/2019 | [6 empty] | FF | No
X1-031 1998624 | TVA-PJM |  | N/A | N/A | Retracted |  | 500 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2014 | 6/1/2019 |  | 4/20/2011 |  |  |  |  | FF | No
X1-032 | Costen 25kV | Somerset Solar Project | MD | Worcester | In Service | DPL | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1032_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/16/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 1/9/2013 | N | No
X1-033 | NCEC Sycamore 69/12.47kV |  | OH | Wyandot | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1033_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2011 | N/A | N/A |  | 11/27/2012 | Customer Milestone Not Met | 3/31/2012 |  |  | N | No
X1-034 | Stoney Brook 12kV | Renaissance at Hanover Solar Farm | NJ | Morris | Withdrawn | JCPL | 1.25 | 1.25 | 0.475 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1034_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1034_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/22/2011 | N/A | N/A |  | 4/9/2013 |  | 12/21/2014 | 12/21/2014 |  | N | No
X1-035 | Piney 34.5kV I |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1035_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/24/2011 | N/A | N/A |  | 5/22/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-036 | Piney 34.5kV II |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1036_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/24/2011 | N/A | N/A |  | 5/22/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-037 | Howell | Howell Solar Farm | NJ | Middlesex | In Service | JCPL | 17 | 17 | 6.46 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1037_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/28/2011 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 11/20/2014 | N | No
X1-038 | Union Camp 115kV | Franklin Mill Power Facility | VA | City of Franklin | In Service | Dominion | 35 | 35 | 0 | 35 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_038_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 6/6/2012 | N | No
X1-039 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 190 | 22.9 | 22.9 | 22.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 9/6/2012 | 9/6/2012 | 9/6/2012 | N | No
X1-040 | Collingwood-Hiple 345kV |  | IN | DeKalb | Withdrawn | AEP | 360 | 360 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2011 | N/A | N/A |  | 3/5/2013 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X1-041 | Dumont-Sorensen 345kV |  | IN | Marshall | Withdrawn | AEP | 252 | 262 | 32.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1041_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2011 | N/A | N/A |  | 5/14/2012 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
X1-042 | Watervliet | Orchard Hills | MI | Berrien | In Service | AEP | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1042_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 11/30/2012 | 11/30/2012 | 3/4/2013 | N | No
X1-043 | Cox's Corner 13kV | All American Self Storage | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1043_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/30/2011 | N/A | N/A |  | 1/10/2013 | Customer Milestone Not Met | 3/31/2012 | 3/31/2012 |  | N | No
X1-044 | Minotola 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2011 | N/A | N/A |  | 9/23/2011 | Customer Milestone Not Met | 4/6/2012 |  |  | N | No
X1-045 | Dresden | Dresden Nuclear Generation Station, Units 2 & 3 | IL | Grundy | In Service | ComEd | 1917 | 3 | 3 | 3 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  |  |  | 12/1/2012 |  | 8/13/2013 | N | No
X1-046 | Branchville-N Newton #1 34kV | Morris Solar Farm | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1046_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-047 | Delaware City 69kV |  | DE | New Castle | Withdrawn | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 12/16/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
X1-048 | Kenvil 12.5kV |  | NJ | Morris | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/19/2011 |  | 12/31/2012 |  |  | N | No
X1-049 | Englishtown 12.5kV | Monroe Sun Club | NJ | Middlesex | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1049_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1049_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 3/13/2017 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-050 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1050_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-051 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1051_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-052 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-053 | Suffolk 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/19/2011 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
X1-054 | Burlington 26kV | Mansfield Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1054_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 3/5/2013 | Customer Initiated Withdrawal | 3/31/2013 | 3/31/2013 |  | N | No
X1-055 | Robbinsville |  | NJ | Mercer | Withdrawn | JCPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1055_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/8/2011 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
X1-056 2079795 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2079795_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2079795_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2017 |  | 5/14/2019 |  |  |  |  | FF | No
X1-057 2079798 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2079798_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2079798_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2017 |  | 5/14/2019 |  |  |  |  | FF | No
X1-058 2079800 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2079800_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2079800_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2017 |  | 5/14/2019 |  |  |  |  | FF | No
X1-058A_DK2 | Todhunter 69kV |  | OH | Butler | Withdrawn | Duke | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1058a_dk2_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/5/2011 | N/A | N/A |  | 2/22/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X1-059 2103861 | PJM-DUK |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2103861_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2103861_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-060 2103863 | PJM-CPLE |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2103863_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2103863_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-061 2103865 | PJM-DUK |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2103865_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2103865_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-062 2103868 | PJM-CPLE |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2103868_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2103868_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-063 2103869 | PJM-DUK |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2103869_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2103869_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-064 2103870 | PJM-CPLE |  | N/A | N/A | Retracted |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2103870_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2103870_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-064A_AT13 | Barberton-Star 138kV |  | OH | Summit | Withdrawn | ATSI | 268 | 268 | 268 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1064a_at13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1064a_at13_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/11/2011 | N/A | N/A |  | 1/16/2013 | Customer Initiated Withdrawal | 1/10/2014 |  |  | N | No
X1-065 2120850 | EKPC-PJM |  | N/A | N/A | Confirmed |  | 70 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2120850_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2120850_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/12/2011 | 6/1/2012 | 6/1/2019 | [6 empty] | FF | No
X1-066 | Galloway Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1066_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2011 | N/A | N/A |  | 7/11/2013 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
X1-067 | Plymouth |  | NC | Washington | Withdrawn | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1067_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/19/2011 | N/A | N/A |  | 11/21/2012 | Customer Milestone Not Met | 9/30/2013 | 9/30/2013 |  | N | No
X1-068 | Red Oak 230kV | Red Oak | NJ | Middlesex | In Service | JCPL | 776 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_068_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/20/2011 | N/A | N/A |  |  |  | 4/19/2011 |  | 12/3/2012 | N | No
X1-069 | Frenchtown |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1069_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2011 | N/A | N/A |  | 10/20/2011 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
X1-070 | Levittown 138kV | Mill Creek | NJ | Burlington | In Service | PSEG | 3.5 | 3.5 | 1.33 | 3.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1070_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/25/2011 | N/A | N/A |  |  |  | 1/9/2012 | 1/9/2012 | 9/15/2011 | N | No
X1-071 | Cinnaminson 138kV | Southern Division Headquarters | NJ | Burlington | In Service | PSEG | 0.93 | 0.93 | 0.35 | 0.93 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/25/2011 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 10/7/2013 | N | No
X1-072 | Hackensack 4kV | Hackensack Solar Farm | NJ | Bergen | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1072_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/26/2011 | N/A | N/A |  |  |  | 3/31/2013 | 3/31/2013 | 1/11/2013 | N | No
X1-073 | Alpha-Gilbert 34kV | Pohatcong II Solar Farm | NJ | Warren | Withdrawn | JCPL | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1073_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1073_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2011 | N/A | N/A |  | 5/3/2016 | Customer Milestone Not Met | 6/30/2015 | 6/30/2015 |  | N | No
X1-074 | Hay Road 230kV | Edge Moor Units EM6, EM7; Hay Road Units 5,6,7,8 | DE | New Castle | Withdrawn | DPL | 856 | 291 | 291 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1074_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1074_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_074_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2011 | N/A | N/A |  | 11/14/2017 | Customer Initiated Withdrawal | 6/18/2018 |  |  | N | No
X1-075 | Sussex 12kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2011 | N/A | N/A |  | 9/7/2011 | Customer Milestone Not Met | 12/30/2011 |  |  | N | No
X1-076 | East Greenwich Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1076_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 10/6/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-077 | Wrightstown 34.5kV | Saylos Pond Solar Farm | NJ | Burlington | Withdrawn | JCPL | 2.06 | 0 | 0.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1077_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 6/22/2016 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
X1-078 | Deans (Poseidon) 500kV | Poseidon | NJ | Middlesex | Withdrawn | PSEG | 525 |  |  |  | Energy | Merchant Transmission |  | DC | F/TWR 525 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x1078_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x1078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/x1_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/x1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 4/23/2018 |  | 5/1/2020 | 5/1/2020 |  | S | No
X1-079 | Baptistown-Frenchtown #2 34kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1079_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 3/5/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-080 | Poe-Suffolk 115kV |  | VA | Prince George | Withdrawn | Dominion | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1080_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1080_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 6/25/2014 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
X1-081 | Andover 12kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 9/8/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-082 | Hazen Switch Point-Warren 34kV | Quarry Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1082_wmpa.pdf |  | Withdrawn | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 4/29/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X1-083 | Salem 12kV |  | NJ | Salem | Withdrawn | AEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 1/17/2012 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
X1-084 | Altavista 115kV | Altavista Power Station | VA | Campbell | In Service | Dominion | 60 | 60 | 60 | 60 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2011 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 5/7/2013 | N | No
X1-085 | Hornerstown-Windsor 34kV | Upper Freehold Solar | NJ | Monmouth | In Service | JCPL | 5 | 5 | 1.9 | 2.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1085_wmpa.pdf |  | Not Required | N/A | N/A | 5/12/2016 | 4/29/2011 | N/A | N/A | 5/13/2016 |  |  | 2/29/2016 | 2/29/2016 | 5/18/2016 | N | No
X1-086 | Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 9.7 | 9.7 | 3.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1086_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 1/10/2012 | Customer Milestone Not Met | 3/31/2012 |  |  | N | No
X1-087 | Stillman Valley | Orchard Hills Renewable Energy Station | IL | Ogle | Deactivated | ComEd | 15.3 | 15.3 | 15.3 | 15.3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1087_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1087_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 11/17/2016 | N | No
X1-088 | Franklin #2 | Flemington Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 17 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1088_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/13/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-089 | Franklin #3 |  | NJ | Warren | Withdrawn | JCPL | 17 | 17 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1089_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/1/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-090 | Yardville 138kV | BKB Properties | NJ | Mercer | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1090_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1090_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/18/2012 | Customer Initiated Withdrawal | 3/31/2012 | 3/31/2012 |  | N | No
X1-091 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.91 | 1.91 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1091_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 10/6/2011 | Customer Milestone Not Met | 8/31/2012 |  |  | N | No
X1-092 | Newport 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.91 | 1.91 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 10/6/2011 | Customer Milestone Not Met | 8/31/2012 |  |  | N | No
X1-093 | Pequest 12kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1093_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/9/2011 | Customer Milestone Not Met | 1/31/2012 |  |  | N | No
X1-094 | Flanders-Saxton Fall 34kV | Mount Olive Solar Farm | NJ | Morris | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1094_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1094_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1094_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/18/2015 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
X1-095 | Bernardsville 12kV | Bernards Township Solar Farm | NJ | Somerset | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1095_wmpa.pdf |  | Not Required | N/A | N/A | 9/8/2016 | 4/29/2011 | N/A | N/A | 9/8/2016 |  |  | 9/20/2017 | 9/20/2017 | 10/3/2016 | N | No
X1-096 | Loretto-Kings Creek 138kV | Great Bay Wind Farm | MD | Somerset | Withdrawn | DPL | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1096_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1096_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_096_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/26/2015 |  | 12/31/2018 | 12/31/2018 |  | N | No
X1-097 | Red Lion 138kV | Red Lion Energy Center | DE | New Castle | In Service | DPL | 24.9 | 24.9 | 23.3 | 24.9 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_097_csa.pdf | Document Posted | N/A | N/A | 12/12/2012 | 4/29/2011 | N/A | N/A | 12/12/2012 |  |  | 3/15/2013 | 3/15/2013 | 12/12/2012 | N | No
X1-098 | Cook Road 13kV | Montgomery Recycling | NJ | Essex | Withdrawn | PSEG | 0.5 | 0.5 | 0.5 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1098_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 3/31/2012 | 3/31/2012 |  | N | No
X1-099 | Woodhill 12kV |  | IL | Will | Withdrawn | ComEd | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1099_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 11/22/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
X1-100 | Branchville 12kV | Mattison Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1100_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1100_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 3/7/2014 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-101 | Clinton-Round Valley 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/9/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
X1-102 | Stewartsville-Captive Plastics 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 9.5 | 9.5 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1102_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/29/2011 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
X1-103 | Branchville-Sussex 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1103_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/9/2011 | Customer Milestone Not Met | 2/28/2012 |  |  | N | No
X1-104 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2.45 | 2.45 | 0.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/6/2011 | Customer Milestone Not Met | 2/28/2012 |  |  | N | No
X1-105 | Branchville-Holiday Lakes 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 11.2 | 11.2 | 4.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1105_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 4/25/2012 | Customer Milestone Not Met | 2/28/2012 |  |  | N | No
X1-106 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 16.8 | 16.8 | 6.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1106_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 4/11/2012 | Customer Milestone Not Met | 1/31/2012 |  |  | N | No
X1-107 | Hopatcong |  | NJ | Sussex | Withdrawn | JCPL | 2.8 | 2.8 | 1.06 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1107_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/6/2011 | Customer Initiated Withdrawal | 2/28/2012 |  |  | N | No
X1-108 | Martins Creek 230kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 600 | 33 | 33 | 33 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1108_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1108_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 1/31/2013 | 1/31/2013 | 12/15/2012 | N | No
X1-109 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 850 | 850 | 765 | 850 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1109_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1109_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_109_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 2/29/2016 | 2/29/2016 | 3/28/2016 | N | No
X1-110 | Lower Township 12kV | Lower Township, NJ | NJ | Cape May | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1110_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1110_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 11/23/2015 | Customer Milestone Not Met | 12/1/2014 | 12/1/2014 |  | N | No
X1-111 | Jackson |  | NJ | Ocean | Withdrawn | JCPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/14/2011 | Customer Milestone Not Met | 7/1/2011 |  |  | N | No
X1-112 | Pennsville 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 4.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1112_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-113 | Lawrence 26kV | Bristol-Myers | NJ | Mercer | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1113_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/25/2012 | Customer Initiated Withdrawal | 12/1/2013 | 12/1/2013 |  | N | No
X1-114 | Holiday Lakes 12kV | Sandyston Solar Farm | NJ | Sussex | Withdrawn | JCPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1114_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 5/3/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X1-115 | Andover |  | NJ | Sussex | Withdrawn | JCPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1115_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/18/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X1-116 | Branchville-N Newton #2 34kV | Frankford Solar Farm | NJ | Sussex | Withdrawn | JCPL | 7 | 7 | 2.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1116_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-117 | Hampton |  | NJ | Sussex | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X1-118 | Hampton #2 |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X1-119 | Andover #2 |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X2-001 | Howell |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2001_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2011 | N/A | N/A |  | 2/14/2012 | Customer Milestone Not Met | 5/13/2012 |  |  | N | No
X2-002 | Somerville 13kV |  | NJ | Somerset | Withdrawn | PSEG | 11.2 | 11.2 | 4.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2011 | N/A | N/A |  | 11/4/2011 | Customer Initiated Withdrawal | 2/28/2012 |  |  | N | No
X2-003 | East Rutherford 13kV |  | NJ | Bergen | Withdrawn | PSEG | 2.1 | 2.1 | 0.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2011 | N/A | N/A |  | 9/14/2011 | Customer Initiated Withdrawal | 2/28/2012 |  |  | N | No
X2-004 | Cumberland-W. Shore #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2004_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2011 | N/A | N/A |  | 11/14/2011 | Customer Milestone Not Met | 12/15/2012 |  |  | N | No
X2-005 | Cumberland-W. Shore #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2011 | N/A | N/A |  | 11/14/2011 | Customer Milestone Not Met | 12/15/2012 |  |  | N | No
X2-006 | Baker 345kV | Riverside Generating Station | KY | Lawrence | Withdrawn | AEP | 999 | 0 | 0 | 0 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_006_csa.pdf | Document Posted | N/A | N/A |  | 5/6/2011 | N/A | N/A |  | 2/22/2019 |  | 6/1/2021 | 6/1/2021 |  | N | No
X2-007 | Peckville-Varden 69kV |  | PA | Wayne | Withdrawn | PPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2007_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2007_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/12/2011 | N/A | N/A |  | 8/3/2012 | Customer Initiated Withdrawal | 6/30/2012 |  |  | N | No
X2-008 | Pruntytown 138kV |  | WV | Taylor | Withdrawn | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/16/2011 | N/A | N/A |  | 5/17/2012 |  | 12/31/2013 |  |  | N | No
X2-009 | Cedar Grove-Clifton 230kV |  | VA | Fairfax | Withdrawn | PSEG | 206 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x2009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x2009_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/17/2011 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X2-011 | Fairlawn 138kV | Elmwood | NJ | Bergen | Deactivated | PSEG | 73 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2011_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_011_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 9/28/2012 | N | No
X2-012 | Clinton 230kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 850 | 850 | 765 | 850 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2012_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2012_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/x2_012_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_012_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 7/30/2016 | 7/30/2016 | 7/13/2016 | N | No
X2-013 | Thorofare 13kV | Mantua Creek Frequency Regularor | NJ | Gloucester | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_013_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 1/17/2013 | N | No
X2-014 | Trenton 26kV | Hedding Road Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2014_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2014_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/23/2011 | N/A | N/A |  | 8/9/2012 | Customer Initiated Withdrawal | 6/30/2013 | 6/30/2013 |  | N | No
X2-015 | Mt. Holly 26kV |  | NJ | Burlington | Withdrawn | PSEG | 2.25 | 2.25 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2015_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/23/2011 | N/A | N/A |  | 1/5/2012 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
X2-016 | Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 5/17/2013 |  |  | N | No
X2-017 | Elk Township 12kV #1 |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 2/28/2013 |  |  | N | No
X2-018 | Elk Township 12kV #2 |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 2/28/2013 |  |  | N | No
X2-019 | Silver Lake 345kV |  | IL | Lake | Withdrawn | ComEd | 225 | 225 | 180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2019_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2011 | N/A | N/A |  | 7/8/2013 | Customer Initiated Withdrawal | 5/31/2015 |  |  | N | No
X2-020 | Erie East 230 kV |  | PA | Erie | Withdrawn | PENELEC | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2011 | N/A | N/A |  | 5/25/2012 | Customer Initiated Withdrawal | 10/31/2014 |  |  | N | No
X2-021 | Erie East 230kV |  | PA | Erie | Withdrawn | PENELEC | 153.75 | 153.75 | 19.98 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2021_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2011 | N/A | N/A |  | 1/18/2013 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
X2-022 | Brokaw-Lanesville | Hilltopper Wind Farm | IL | Logan | In Service | ComEd | 250 | 187.5 | 0 | 187.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2022_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_022_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 11/1/2018 | N | No
X2-023 | North Mashoppen-Mehoopany 115kV |  | PA | Sullivan | Withdrawn | PENELEC | 51 | 51 | 6.63 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 1/22/2013 | Customer Milestone Not Met | 10/15/2013 |  |  | N | No
X2-024 | Lower Alloways Creek 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 1/11/2012 | Customer Milestone Not Met | 11/1/2011 |  |  | N | No
X2-025 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 416 | 416 | 416 | 416 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_025_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/18/2018 | N | No
X2-026 | Leola |  | PA | Lancaster | Withdrawn | PPL | 3.2 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 7/12/2011 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X2-027 | Quinton 12kV | Quinton-Alloway | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_027_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 12/15/2017 |  | 11/1/2016 | 11/1/2016 |  | N | No
X2-028 | Quinton Township 12kV |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2028_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 2/20/2014 | Customer Initiated Withdrawal | 3/15/2012 |  |  | N | No
X2-029 | Danville-East Danville 138kV |  | VA | Pittsylvania | Withdrawn | AEP | 55 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x2029_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 8/7/2014 | Customer Initiated Withdrawal | 1/30/2014 | 1/30/2014 |  | S | No
X2-030 | Morgantown-Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 830 | 830 | 830 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 2/1/2012 | Customer Milestone Not Met | 1/1/2016 |  |  | N | No
X2-031 | Krayn 115kV | Highland III Wind Farm | PA | Cambria | Withdrawn | PENELEC | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2031_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_031_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 11/29/2016 |  | 12/31/2015 | 12/31/2015 |  | N | No
X2-032 |  |  | NJ | Atlantic | Withdrawn | JCPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/2/2011 | N/A | N/A |  | 9/26/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-033 | Trenton 26kV | Ward Avenue Solar | NJ | Burlington | Withdrawn | PSEG | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2033_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2033_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/3/2011 | N/A | N/A |  | 1/4/2013 | Customer Initiated Withdrawal | 6/30/2013 | 6/30/2013 |  | N | No
X2-034 | Laplume |  | PA | Lackawanna | Withdrawn | PPL | 0.032 | 0.032 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2034_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/3/2011 | N/A | N/A |  | 1/18/2012 | Customer Initiated Withdrawal |  |  |  | N | No
X2-035 | Sunnymeade Road 13kV) | Valley Road Solar | NJ | Somerset | Withdrawn | PSEG | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2035_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2035_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/6/2011 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 7/31/2013 | 7/31/2013 |  | N | No
X2-036 | Whitehouse |  | NJ | Hunterdon | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2011 | N/A | N/A |  | 1/5/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X2-037 | Lewis 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 45.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2011 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal |  |  |  | N | No
X2-038 | Halfway 12.5kV | Washington County Renewable Energy Project | MD | Washington | Withdrawn | APS | 2 | 2 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2038_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2038_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/10/2011 | N/A | N/A |  | 1/14/2016 | Customer Initiated Withdrawal | 10/31/2013 | 10/31/2013 |  | N | No
X2-039 | Brookside-Cloverdale 138kV |  | OH | Ashland | Withdrawn | ATSI | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2039_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2011 | N/A | N/A |  | 12/9/2011 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
X2-040 | Wurno 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2040_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 6/22/2011 | N/A | N/A |  | 3/15/2012 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X2-041 2403941 | TVA-PJM |  | N/A | N/A | Retracted |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2403941_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/24/2011 | 6/1/2012 | 6/1/2022 |  | 9/12/2011 |  |  |  |  | FF | No
X2-042 2403944 | CIN-PJM |  | N/A | N/A | Confirmed |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2403944_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2403944_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/24/2011 | 6/1/2012 | 9/1/2019 | [6 empty] | FF | No
X2-043 2403946 | MECS-PJM |  | N/A | N/A | Retracted |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2403946_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/24/2011 | 6/1/2012 | 6/1/2022 |  | 9/12/2011 |  |  |  |  | FF | No
X2-044 | Winslow 12kV |  | NJ | Camden | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2011 | N/A | N/A |  | 1/3/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
X2-045 | Kenney-Mt. Olive 69kV |  | MD | Worcester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2045_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/27/2011 | N/A | N/A |  | 5/21/2012 |  | 6/30/2013 |  |  | N | No
X2-046 | Sussex County |  | DE | Sussex | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2046_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/27/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 1/1/2013 |  |  | N | No
X2-047 | Oldmans Township 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 5/10/2012 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
X2-048 | South Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2048_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 5/10/2012 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
X2-049 | S. Reading-Birdsboro 64kV |  | PA | Berks | Withdrawn | ME | 9.6 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2049_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 1/3/2012 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
X2-050 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 705 | 705 | 660 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A | 2/1/2016 | 6/28/2011 | N/A | N/A |  | 11/20/2013 | Customer Initiated Withdrawal | 5/31/2016 | 5/31/2016 |  | N | No
X2-051 |  |  | OH | Unknown | Withdrawn | AEP | 8 | 6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 9/22/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-052 | Dumont-Olive 345kV | St. Joseph Energy Center, LLC | IN | St. Joseph | In Service | AEP | 675 | 675 | 675 | 675 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2052_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2052_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_052_csa.pdf | Document Posted | N/A | N/A | 7/1/2017 | 6/29/2011 | N/A | N/A | 12/28/2017 |  |  | 4/29/2018 | 4/29/2018 | 4/1/2018 | N | No
X2-053 | Amsterdam 69kV |  | OH | Jefferson | Withdrawn | AEP | 6.4 | 6.4 | 6.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2053_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/29/2011 | N/A | N/A |  | 5/15/2012 | Customer Milestone Not Met | 1/31/2013 |  |  | N | No
X2-054 | Franklin | Quakertown Solar Farm #2 | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2054_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 7/15/2016 | Customer Initiated Withdrawal | 4/13/2016 | 4/13/2016 |  | N | No
X2-055 | Cedar Grove-Clifton "B" 230kV |  | VA | Fairfax | Withdrawn | PSEG | 206 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x2055_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x2055_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X2-056 | Greenwich 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.94 | 1.94 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2056_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 1/11/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X2-057 | White |  | NJ | Warren | Withdrawn | JCPL | 4.1 | 4.1 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2057_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 11/21/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X2-058 | Buckley Road 138kV |  | OH | Hancock | Withdrawn | AEP | 149.5 | 149.5 | 19.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2058_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 7/10/2013 | Customer Milestone Not Met | 11/15/2012 |  |  | N | No
X2-059 | Freehold | Cloverleaf Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 7/15/2015 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X2-060 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | City of Covington | In Service | Dominion | 30 | 30 | 0 | 30 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_060_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2011 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 10/15/2013 | N | No
X2-061 | Lawrenceville 34.5kV |  | VA | Brunswick | Withdrawn | Dominion | 15 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 12/14/2011 | Customer Initiated Withdrawal | 6/1/2012 | 6/1/2012 |  | N | No
X2-062 | North Hanover |  | NJ | Burlington | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2062_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 11/18/2011 | Customer Milestone Not Met | 10/30/2012 |  |  | N | No
X2-063 2459943 | TVA-PJM |  | N/A | N/A | Retracted |  | 220 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2459943_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2011 | 6/1/2012 | 6/1/2013 |  | 10/12/2011 |  |  |  |  | FF | No
X2-064 2459958 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 720 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2011 | 6/1/2013 | 6/1/2015 |  | 8/5/2011 |  |  |  |  | FF | No
X2-065 2459960 | TVA-PJM |  | N/A | N/A | Retracted |  | 720 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2459960_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/6/2011 | 6/1/2013 | 6/1/2017 |  | 10/12/2011 |  |  |  |  | FF | No
X2-066 | S. Harrington-N. Seaford 138kV |  | DE | Sussex | Withdrawn | DPL | 312 | 312 | 309 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2066_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/18/2011 | N/A | N/A |  | 1/15/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
X2-067 | Cartanza 230kV |  | DE | Kent | Withdrawn | DPL | 309 | 309 | 309 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2067_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/18/2011 | N/A | N/A |  | 2/26/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
X2-068 | Lopatcong |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2068_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 11/30/2011 | Customer Milestone Not Met | 5/31/2013 |  |  | N | No
X2-069 | Swedesboro |  | NJ | Gloucester | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2069_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 1/3/2012 | Customer Milestone Not Met | 5/31/2013 |  |  | N | No
X2-070 | Hightstown |  | NJ | Mercer | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 8/15/2011 | Customer Initiated Withdrawal | 5/31/2013 |  |  | N | No
X2-071 | Beckett |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2071_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 1/3/2012 |  | 5/31/2013 |  |  | N | No
X2-072 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 9/22/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-073 2533204 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 120 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2533204_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/21/2011 | 1/1/2013 | 1/1/2033 |  | 9/23/2011 |  |  |  |  | FF | No
X2-074 | Gibbsboro 12kV |  | NJ | Camden | Withdrawn | AEC | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/25/2011 | N/A | N/A |  | 5/8/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X2-075 | Flemington | Junction Road Solar Farm | NJ | Hunterdon | In Service | JCPL | 6 | 6 | 2.28 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2075_wmpa.pdf |  | Not Required | N/A | N/A | 5/3/2016 | 7/26/2011 | N/A | N/A | 5/18/2016 |  |  | 6/12/2017 | 6/12/2017 | 5/19/2016 | N | No
X2-076 | Carson-Wake 500kV | Brunswick Combined Cycle Power Station | VA | Brunswick | In Service | Dominion | 1525.5 | 1525.5 | 1376 | 1525.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_076_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2011 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 3/7/2016 | N | No
X2-077 | Hursch Road 69kV |  | OH | Darke | Withdrawn | Dayton | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 2/14/2012 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X2-078 | Ringoes |  | NJ | Hunterdon | Withdrawn | JCPL | 0.38 | 0.38 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2078_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 5/11/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X2-079 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 9/27/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-080 |  |  | NJ | Cumberland | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 9/27/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-081 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 1.5 | 1.5 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 2/1/2012 |  |  | N | No
X2-082 | Chesterfield 230kV |  | VA | Chesterfield | Withdrawn | Dominion | 1575 | 1575 | 1420 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2082_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_082_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_082_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 12/5/2012 | Customer Initiated Withdrawal | 12/1/2015 |  |  | N | No
X2-083 | Newark 12kV | Brookside Energy Center | DE | New Castle | In Service | DPL | 3 | 3 | 3 | 3 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2083_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2083_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2083_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 8/15/2012 | 8/15/2012 | 6/21/2012 | N | No
X2-084 | East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 19.6 | 19.6 | 7.45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 5/10/2012 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
X2-085 | Barberton–Seiberling 23kV | Barberton Solar | OH | Summit | Withdrawn | ATSI | 14 | 14 | 5.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2085_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 6/12/2014 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
X2-086 | Mt. Storm 115kV |  | WV | Grant | Withdrawn | Dominion | 77 | 77 | 74 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2086_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/9/2012 | Customer Milestone Not Met | 12/1/2014 |  |  | N | No
X2-087 | Doremus 13kV | Food Bank Solar | NJ | Union | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2087_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2087_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 8/18/2012 | N | No
X2-088 | Devils Brook 13kV | Black Rock Solar | NJ | Middlesex | In Service | PSEG | 2.356 | 2.356 | 0.895 | 2.356 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 3/26/2012 | N | No
X2-089 | Pierson Avenue 13kV | Summit Associates Solar | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0.76 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2089_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2089_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 12/31/2011 | N | No
X2-090 | Dewey-Inez 69kV |  | KY | Martin | Withdrawn | AEP | 21 | 19 | 11.4 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2090_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/12/2012 | Customer Milestone Not Met | 8/31/2012 |  |  | N | No
X2-091 | Hegewisch 34kV |  | IL | Cook | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2091_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013 |  |  | N | No
X2-092 | Cornell 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2092_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013 |  |  | N | No
X2-093 | Pontiac-Midpoint 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2093_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013 |  |  | N | No
X2-094 | Green Brook 13kV |  | NJ | Middlesex | Withdrawn | PSEG | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/12/2012 | Customer Milestone Not Met | 1/31/2013 |  |  | N | No
X2-095 | Cape May Court House 12kV |  | NJ | Cape May | Withdrawn | AEC | 1.82 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X2-096 | Wantage |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 7/31/2013 |  |  | N | No
X2-097 | Andover |  | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 7/31/2013 |  |  | N | No
X2-098 | Lopatcong #2 |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 7/31/2013 |  |  | N | No
X2-099 | Sparta-Woodruff's Gap 34kV | Sparta Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2099_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 3/14/2013 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X2-100 | Woodstown-Laurel 69kV |  | NJ | Salem | Withdrawn | AEC | 14.4 | 14.4 | 1.87 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2100_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/18/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
X2-101 | Upper Pittsgrove 138kV |  | NJ | Salem | Withdrawn | AEC | 18 | 18 | 2.34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/18/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
X3-001 | West Melrose 34.5kV | Edgewood | OH | Hancock | Withdrawn | AEP | 1.82 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3001_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/1/2011 | N/A | N/A |  | 11/10/2016 | Customer Initiated Withdrawal | 7/15/2014 | 7/15/2014 |  | N | No
X3-002 | Greenville 12kV | Greenville Solar | OH | Darke | Withdrawn | Dayton | 3.38 | 3.38 | 1.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3002_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3002_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/1/2011 | N/A | N/A |  | 9/17/2018 |  | 12/31/2017 | 12/31/2017 |  | N | No
X3-002A 2590376 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2590376_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/2/2011 | 1/1/2013 | 1/1/2014 |  | 10/25/2011 |  |  |  |  | FF | No
X3-003 | Mehoopany II 115 kV | Mehoopany Plant | PA | Wyoming | In Service | PENELEC | 64 | 20 | 0 | 20 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_003_csa.pdf | Document Posted | N/A | N/A |  | 8/3/2011 | N/A | N/A |  |  |  | 10/17/2013 | 10/17/2013 | 11/15/2013 | N | No
X3-004 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 710 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_004_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 8/8/2011 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
X3-005 | Wildwood 12kV | City Solar | IL | Cook | In Service | ComEd | 9 | 9 | 3.4 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3005_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_005_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/8/2011 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 9/26/2013 | N | No
X3-006 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 800 | 150 | 110 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3006_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2011 | N/A | N/A |  | 2/13/2014 | Customer Milestone Not Met | 6/1/2014 |  |  | N | No
X3-007 | Bustleton 13kV | LB Solar | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3007_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3007_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/8/2011 | N/A | N/A |  | 1/28/2015 | Customer Milestone Not Met | 9/30/2014 | 9/30/2014 |  | N | No
X3-008 | Todd 69kV | Dorchester County Solar 1 Project | MD | Anne Arundel | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3008_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3008_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3008_wmpa.pdf |  | Not Required | N/A | N/A | 3/15/2021 | 8/12/2011 | N/A | N/A | 3/15/2021 |  |  | 7/31/2021 | 7/31/2021 | 4/8/2021 | N | No
X3-009 | New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2011 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
X3-010 | Franklin #1 |  | NJ | Warren | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2011 | N/A | N/A |  | 3/9/2012 | Customer Initiated Withdrawal | 8/30/2013 |  |  | N | No
X3-011 | Franklin #2 | Beidelman Solar Farm | NJ | Warren | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3011_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/15/2011 | N/A | N/A |  | 7/21/2015 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | No
X3-012 2654202 | AMIL-PJM |  | N/A | N/A | Retracted |  | 315 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/15/2011 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
X3-013 | Wildwood Crest 12kV |  | NJ | Cape May | Withdrawn | AEC | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2011 | N/A | N/A |  | 3/12/2012 | Customer Initiated Withdrawal | 11/1/2012 |  |  | N | No
X3-014 | South Harrington-North Seaford 138kV |  | DE | Sussex | Withdrawn | DPL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/16/2011 | N/A | N/A |  | 4/27/2012 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
X3-015 | West Cambridge-Vienna 69kV | Linkwood Solar | MD | Dorchester | Withdrawn | DPL | 19.5 | 19.5 | 7.41 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3015_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_015_csa.pdf | Document Posted | N/A | N/A |  | 8/22/2011 | N/A | N/A |  | 10/10/2017 |  | 9/1/2017 | 9/1/2017 |  | N | No
X3-016 | Carneys Point Township 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2011 | N/A | N/A |  | 3/13/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
X3-017 | Elsinboro Township 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/14/2012 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
X3-018 | Vineland 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 10/11/2011 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
X3-019 2713235 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 485 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2713235_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/26/2011 | 6/1/2014 | 6/1/2019 |  | 10/27/2011 |  |  |  |  | FF | No
X3-020 2722964 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 180 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2722964_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2722964_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/29/2011 | 6/1/2014 | 6/1/2019 | [6 empty] | FF | No
X3-021 2723695 | MECS-PJM |  | N/A | N/A | Annulled |  | 660 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2723695_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2723695_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/29/2011 | 6/1/2016 | 6/1/2023 | [6 empty] | FF | No
X3-022 | Hunterstown-Jackson 138kV |  | PA | Adams | Withdrawn | ME | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/22/2012 | Customer Milestone Not Met | 12/31/2014 |  |  | N | No
X3-023 | S. Greenwich-Willard 69kV | 6011 Greenwich Windpark, LLC | OH | Huron | Withdrawn | AEP | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3023_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 8/5/2016 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
X3-024 | Cape May Court House |  | NJ | Cape May | Withdrawn | AEC | 1.82 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/14/2012 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X3-025 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 4.32 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/14/2012 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X3-026 | Buena Vista Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/12/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X3-027 | Ocean |  | NJ | Ocean | Withdrawn | AEC | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 5/2/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X3-028 | X3-028 Sullivan 345 kV |  | IN | Sullivan | Withdrawn | AEP | 3500 |  |  |  | Energy | Merchant Transmission |  | DC | FTIR 1500; NFTIR 2000 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x3028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x3028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x3028_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 9/30/2019 |  | 12/31/2016 |  |  | S | No
X3-029 | Belvidere | CHP Belvidere Generation Facility | NJ | Warren | In Service | JCPL | 11.15 | 11.15 | 0 | 11.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_029_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2011 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 12/17/2013 | N | No
X3-030 | Shelby-S.W. Lima 345kV |  | OH | Marion | Withdrawn | Dayton | 245 | 245 | 31.85 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 5/30/2013 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
X3-031 | Southwest Lima-West Moulton 138kV |  | OH | Allen | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 5/31/2013 | Customer Initiated Withdrawal | 9/30/2015 |  |  | N | No
X3-032 | Poe-Suffolk 115kV |  | VA | Prince George | Withdrawn | Dominion | 155 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3032_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3032_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 6/25/2014 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
X3-033 | Green |  | NJ | Sussex | Withdrawn | JCPL | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3033_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 2/7/2012 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
X3-034 | Hunterstown-Jackson 130kV |  | PA | Washington | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3034_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 9/27/2012 | Customer Milestone Not Met | 8/1/2012 |  |  | N | No
X3-035 | Mansfield |  | NJ | Warren | Withdrawn | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 3/23/2012 | Customer Milestone Not Met | 7/4/2012 |  |  | N | No
X3-036 | William 138kV |  | WV | Grant | Withdrawn | APS | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 3/22/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X3-037 | Krendale-Seneca 138kV |  | OH | Richland | Withdrawn | APS | 46 |  |  |  | Energy | Merchant Transmission |  |  | AC | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x3037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x3037_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 8/14/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-038 | Manchester |  | NJ | Ocean | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3038_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 2/10/2012 | Customer Milestone Not Met | 9/30/2013 |  |  | N | No
X3-039 | Geneva 115kV |  | PA | Crawford | Withdrawn | PENELEC | 96 | 96 | 96 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 6/19/2013 | Customer Initiated Withdrawal | 7/7/2014 |  |  | N | No
X3-040 | Weirwood-Eastville 69kV |  | VA | Northampton | Withdrawn | ODEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 8/13/2014 | Customer Initiated Withdrawal | 6/30/2016 | 6/30/2016 |  | N | No
X3-041 | Milton | Milton | DE | Sussex | Withdrawn | DPL | 14.9 | 14.9 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3041_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 12/19/2014 | Customer Initiated Withdrawal | 9/2/2018 | 9/2/2018 |  | N | No
X3-042 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2011 | N/A | N/A |  | 9/29/2011 |  |  |  |  | N | No
X3-043 | Lumberton 69kV | Warfield I | NJ | Burlington | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3043_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/12/2011 | N/A | N/A |  | 1/5/2015 | Customer Initiated Withdrawal | 10/15/2015 | 10/15/2015 |  | N | No
X3-044 | Three Mile Island |  | PA | Dauphin | Withdrawn | ME | 860 | 15 | 15 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3044_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/14/2011 | N/A | N/A |  | 7/16/2014 | Customer Initiated Withdrawal | 6/30/2013 |  |  | N | No
X3-045 | Dresden |  | IL | Grundy | Withdrawn | ComEd | 1984 | 32 | 32 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3045_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2011 | N/A | N/A |  | 3/4/2013 | Customer Initiated Withdrawal | 6/1/2014 | 6/1/2014 |  | N | No
X3-046 | Quad Cities |  | IL | Rock Island | Withdrawn | ComEd | 1984 | 32 | 32 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3046_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2011 | N/A | N/A |  | 3/4/2013 | Customer Initiated Withdrawal | 6/1/2014 | 6/1/2014 |  | N | No
X3-047 | Bayview 25kV |  | VA | Northampton | Withdrawn | ODEC | 5 | 5 | 0.65 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2011 | N/A | N/A |  | 4/12/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X3-048 2852305 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2852305_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/26/2011 | 6/1/2013 | 6/1/2014 |  | 12/20/2011 |  |  |  |  | FF | No
X3-049 2852306 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2852306_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/26/2011 | 6/1/2012 | 6/1/2013 |  | 12/20/2011 |  |  |  |  | FF | No
X3-050 2852309 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/2852309_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/2852309_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/26/2011 | 6/1/2015 | 6/1/2020 |  | 2/1/2018 |  |  |  |  | FF | No
X3-051 | Flatlick 765kV |  | OH | Unknown | Withdrawn | AEP | 1460 | 610 | 610 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3051_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3051_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/27/2011 | N/A | N/A |  | 5/23/2016 | Customer Milestone Not Met | 3/1/2017 | 3/1/2017 |  | N | No
X3-052 | Essex 26.4kV | Essex County Correctional Facility | NJ | Essex | In Service | PSEG | 6.2 | 3 | 0 | 3 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_052_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2011 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 9/10/2014 | N | No
X3-053 | Homer-Seville 69kV |  | OH | Medina | Withdrawn | ATSI | 17.68 | 17.68 | 6.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2011 | N/A | N/A |  | 8/2/2012 | Customer Milestone Not Met | 7/1/2013 |  |  | N | No
X3-054 | Sussex | Hough Solar Farm | NJ | Sussex | Withdrawn | JCPL | 4.9 | 4.9 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3054_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/29/2011 | N/A | N/A |  | 11/13/2013 | Customer Milestone Not Met | 6/30/2015 | 6/30/2015 |  | N | No
X3-055 | Occoquan 34.5kV |  | VA | Fairfax | Withdrawn | Dominion | 10 | 10 | 0 |  | Energy | Generation Interconnection | Diesel |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2011 | N/A | N/A |  | 11/14/2011 | Queue Not Required | 2/28/2013 |  |  | N | No
X3-056 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 1310 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3056_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2011 | N/A | N/A |  | 9/13/2013 | Customer Initiated Withdrawal | 10/31/2011 |  |  | N | No
X3-057 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 1310 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3057_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2011 | N/A | N/A |  | 9/13/2013 | Customer Initiated Withdrawal | 10/31/2011 |  |  | N | No
X3-058 2890646 | PJM-DUK |  | N/A | N/A | Retracted |  | 120 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/5/2011 | 1/1/2013 | 1/1/2033 |  | 11/8/2011 |  |  |  |  | FF | No
X3-059 | Roberts 34.5kV |  | OH | Marion | Withdrawn | ATSI | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3059_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/10/2011 | N/A | N/A |  | 10/16/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X3-060 | Fairfield Twp 1 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2011 | N/A | N/A |  | 11/2/2011 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
X3-061 | Fairfield Twp 2 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2011 | N/A | N/A |  | 11/2/2011 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
X3-062 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3062_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X3-063 2919169 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 500 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/11/2011 | 1/1/2015 | 1/1/2018 |  | 10/28/2011 |  |  |  |  | FF | No
X3-064 | Fredericksburg-Mine Road 230kV |  | VA | City of Fredericksburg | Withdrawn | Dominion | 237 | 237 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x3064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x3064_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x3064_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 10/12/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-065 | Bristers-Ox 500kV |  | VA | Fauquier | Withdrawn | Dominion | 183 | 183 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x3065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x3065_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x3065_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 10/12/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-066 | Church Hill 69kV | Church Hill Solar Farm | MD | Queen Anne's | In Service | DPL | 6 | 6 | 2.28 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3066_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3066_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/13/2011 | N/A | N/A |  |  |  | 9/1/2015 | 9/1/2015 | 5/19/2016 | N | No
X3-067 | Church Hill 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/2011 | N/A | N/A |  | 2/29/2012 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
X3-068 | Graceton 230kV |  | PA | York | Withdrawn | BGE | 678 | 678 | 678 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3068_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/14/2011 | N/A | N/A |  | 6/4/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
X3-069 | Hamilton |  | NJ | Atlantic | Withdrawn | JCPL | 4 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2011 | N/A | N/A |  | 11/4/2011 |  |  |  |  | N | No
X3-070 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 72 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_070_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 12/12/2013 | N | No
X3-071 | Sussex County 12kV | Burbage Property | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3071_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 11/12/2013 | Customer Milestone Not Met | 10/31/2018 | 10/31/2018 |  | N | No
X3-072 | Lafayette |  | NJ | Sussex | Withdrawn | JCPL | 10.5 | 10.5 | 3.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3072_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 3/1/2013 |  |  | N | No
X3-073 | Massey 69kV |  | MD | Kent | Withdrawn | DPL | 9.8 | 9.8 | 3.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3073_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 3/12/2012 | Customer Milestone Not Met | 3/31/2013 |  |  | N | No
X3-074 | Chestertown 69kV |  | MD | Kent | Withdrawn | DPL | 11.9 | 11.9 | 4.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 8/15/2012 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X3-075 | Runnemede 13kV | Owens Corning Solar | NJ | Camden | In Service | PSEG | 3 | 3 | 0 | 3 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3075_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  |  |  | 2/16/2017 | 2/16/2017 | 5/11/2017 | N | No
X3-076 | Loudoun-Meadowbrook 500kV |  | VA | Fauquier | Withdrawn | Dominion | 1270 | 510 | 412 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3076_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 6/7/2013 | Customer Initiated Withdrawal | 5/1/2015 |  |  | N | No
X3-077 | Sussex County 12kV | Baxter Property | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3077_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 11/12/2013 | Customer Milestone Not Met | 10/31/2018 | 10/31/2018 |  | N | No
X3-078 | Harrisburg 12kV |  | PA | Dauphin | Withdrawn | PPL | 4 | 4 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3078_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 4/11/2012 | Customer Initiated Withdrawal | 8/15/2014 |  |  | N | No
X3-079 | Oyster Creek-Waretown 34kV | Volunteer Way Solar Farm | NJ | Ocean | Withdrawn | JCPL | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3079_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 12/21/2012 |  | 6/30/2015 | 6/30/2015 |  | N | No
X3-080 | Fairton Township |  | NJ | Cumberland | Withdrawn | AEC | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3080_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 3/13/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X3-081 | Upper Darby 13kV | Astra Foods | PA | Delaware | Withdrawn | PECO | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 8/27/2018 |  | 12/30/2012 | 12/30/2012 |  | N | No
X3-082 | Marble Hill-Morris Park 34kV | Lopatcong Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3082_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 4/29/2016 | Customer Milestone Not Met | 6/30/2015 | 6/30/2015 |  | N | No
X3-083 | Andover-Kittatinny 34kV | Andover Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3083_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3083_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 4/29/2016 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
X3-084 | Wantage |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 3/9/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X3-085 | Sussex 34kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3085_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 2/27/2013 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
X3-086 | Lafayette |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 11/17/2011 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X3-087 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Withdrawn | PEPCO | 894 | 894 | 744 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_087_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2011 | N/A | N/A | 6/30/2023 | 12/23/2020 |  | 3/1/2022 | 3/1/2022 |  | N | No
X3-088 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 440 | 440 | 440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3088_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 6/21/2012 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
X3-089 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 744 | 744 | 744 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3089_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 5/3/2012 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
X3-090 3023526 | PJM-DUK |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023526_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3023526_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 8/29/2012 |  |  |  |  | FF | No
X3-091 3023529 | PJM-DUK |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023529_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-092 3023530 | PJM-DUK |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023530_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-093 3023531 | PJM-DUK |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023531_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-094 3023533 | PJM-DUK |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023533_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-095 3023618 | AMIL-PJM |  | N/A | N/A | Retracted |  | 338 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023618_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-096 3023630 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 268 | 268 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023630_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3023630_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 12/15/2019 |  | 12/15/2019 |  |  |  |  | FF | No
X3-097 3023634 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 202 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023634_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3023634_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
X3-098 3023635 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 94 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023635_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3023635_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2020 |  | 10/18/2019 |  |  |  |  | FF | No
X3-099 3023636 | AMIL-PJM |  | N/A | N/A | Retracted |  | 602 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023636_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-100 3023637 | AMIL-PJM |  | N/A | N/A | Retracted |  | 336 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023637_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-101 3023638 | AMIL-PJM |  | N/A | N/A | Retracted |  | 259 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3023638_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-102 | Burches Hill-Possum Point 500kV |  | MD | Charles | Withdrawn | PEPCO | 971.2 | 971.2 | 937 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3102_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 6/20/2012 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
X3-103 | Oakgrove-Morgantown 230kV |  | MD | Charles | Withdrawn | PEPCO | 971.2 | 971.2 | 971.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 11/18/2011 | Queue Not Required | 6/1/2016 |  |  | N | No
X4-001 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4001_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X4-002 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4002_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X4-003 | Mill Creek-Riverview 138kV |  | OH | Washington | Withdrawn | AEP | 56 | 56 | 56 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 11/26/2012 | Customer Initiated Withdrawal | 3/31/2015 |  |  | N | No
X4-004 | Woodbury 26.4kV | Johnson Matthey | NJ | Gloucester | Withdrawn | PSEG | 5 | 5 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_004_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 6/7/2016 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
X4-005 | Raritan River 230kV |  | NJ | Middlesex | In Service | JCPL | 785 | 60 | 0 | 60 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4005_fea.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_005_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2011 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 12/4/2015 | N | No
X4-006 | Kelson Ridge 230kV | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 785 | 60 | 0 | 35 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_006_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2011 | N/A | N/A |  |  |  | 11/1/2016 | 11/1/2016 | 1/28/2017 | N | No
X4-007 | Kelson Ridge 230kV |  | MD | Charles | Withdrawn | PEPCO | 785 | 60 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4007_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4007_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/3/2011 | N/A | N/A |  | 7/31/2013 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
X4-008 3131895 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/16/2011 | 6/1/2013 | 6/1/2023 |  | 12/19/2011 |  |  |  |  | FF | No
X4-009 | Cumberland - W. Shore #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2011 | N/A | N/A |  | 7/1/2013 | Customer Initiated Withdrawal | 7/1/2014 | 7/1/2014 |  | N | No
X4-010 | Cumberland - W. Shore #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2011 | N/A | N/A |  | 5/29/2012 | Customer Initiated Withdrawal | 12/15/2012 |  |  | N | No
X4-011 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4011_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/15/2012 |  |  | N | No
X4-012 | Branchville-Sussex 34kV | Plains Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4012_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/21/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | No
X4-013 | Pleasant View-Edwards Ferry 230kV |  | VA | Prince William | Withdrawn | Dominion | 200 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x4013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x4013_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x4013_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 11/28/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
X4-014 | Kellam - Bayview 69kV |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2011 | N/A | N/A |  | 7/3/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X4-015 | Cookstown-Fort Dix 34kV | Jacobstown III Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4015_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4015_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/28/2011 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 9/28/2015 | N | No
X4-016 | Bayonne 138kV | Bayonne Cogen | NJ | Hudson | Deactivated | PSEG | 168 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4016_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_016_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/2011 | N/A | N/A |  |  |  | 9/30/2013 | 9/30/2013 | 9/30/2013 | N | No
X4-017 | Fruitland 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
X4-018 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 660 | 110 | 110 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 6/5/2012 | Customer Initiated Withdrawal | 5/31/2015 |  |  | N | No
X4-019 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 643 | 227 | 227 | 227 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4019_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4019_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_019_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/18/2018 | N | No
X4-020 | Peach Bottom-TMI #1 500kV I |  | PA | York | Withdrawn | PPL | 800 | 800 | 760 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
X4-021 | Peach Bottom-TMI #2 500kV II |  | PA | York | Withdrawn | PPL | 320 | 320 | 304 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4021_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4021_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
X4-022 | Mount Storm 230kV |  | WV | Grant | Withdrawn | Dominion | 358 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x4022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x4022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X4-023 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 155 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x4023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x4023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x4023_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/x4_023_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 3/28/2014 |  | 6/1/2015 |  |  | S | No
X4-024 | Rock Springs 500kV |  | MD | Cecil | Withdrawn | NAEA | 109 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/x4024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/x4024_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/x4024_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 8/21/2013 | Customer Initiated Withdrawal | 7/1/2013 |  |  | S | No
X4-025 | Millbrook Park 138kV |  | KY | Greenup | Withdrawn | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_025_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 9/18/2017 |  | 12/31/2018 | 12/31/2018 |  | N | No
X4-026 | Aquasco 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 792 | 792 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 8/2/2012 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
X4-027 | Linwood 230kV | Phillips Island CT1, CT2,CT3 & ST4 | PA | Delaware | In Service | PECO | 852 | 12 | 35 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/8/2011 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 6/1/2018 | N | No
X4-028 | Northerly Island |  | IL | Cook | Withdrawn | ComEd | 0.103 | 0.103 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 12/13/2011 | N/A | N/A |  | 8/30/2012 | Customer Milestone Not Met | 12/12/2011 |  |  | Y | No
X4-029 | Upper Deerfield 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2011 | N/A | N/A |  | 6/8/2012 | Customer Initiated Withdrawal | 1/2/2013 |  |  | N | No
X4-029A 3396286 | ALTE-PJM |  | N/A | N/A | Retracted |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
X4-029B 3396289 | ALTE-PJM |  | N/A | N/A | Retracted |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2013 | 6/1/2014 | [6 empty] | FF | No
X4-029C 3396292 | ALTE-PJM |  | N/A | N/A | Retracted |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3396292_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2014 | 6/1/2015 | [6 empty] | FF | No
X4-029D 3396293 | ALTE-PJM |  | N/A | N/A | Confirmed |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3396293_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3396293_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2015 | 6/1/2016 | [6 empty] | FF | No
X4-030 | Freemont 69kV |  | OH | Sandusky | Withdrawn | AEP | 13.75 | 13.75 | 5.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2011 | N/A | N/A |  | 8/27/2012 | Customer Milestone Not Met | 4/1/2013 | 4/1/2013 |  | N | No
X4-031 | Bennett-Farmingdale 34kV | Skudera Solar Farm | NJ | Monmouth | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4031_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4031_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/30/2011 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 6/17/2015 | Y | No
X4-032 | Zach |  | PA | Montgomery | Withdrawn | PECO | 10 | 4 | 4 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4032_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2011 | N/A | N/A |  | 12/31/2012 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
X4-033 | Braid 24kV BR-1-Cook 765kV |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2012 | N/A | N/A |  | 11/12/2012 |  |  |  |  | EE | No
X4-034 | Dravosburg–Rankin 23kV |  | PA | Allegheny | Withdrawn | DL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4034_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/19/2012 | N/A | N/A |  | 11/16/2012 |  | 8/31/2013 |  |  | N | No
X4-035 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 735.5 | 735.5 | 735.5 | 735.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4035_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_035_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2012 | N/A | N/A |  |  |  | 6/15/2018 | 6/15/2018 | 5/21/2018 | N | No
X4-036 | Braidwood-Cook |  | N/A | N/A | Withdrawn | ComEd | 250 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/x4036_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 9/3/2014 |  |  |  |  | EE | No
X4-037 | Dresden-DEOK Zone |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/x4037_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 9/3/2014 |  |  |  |  | EE | No
X4-038 | TMI-PPL |  | N/A | N/A | Withdrawn | PPL | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/x4038_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/x4038_arr-fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 11/18/2014 |  |  |  |  | EE | No
X4-039 | Pleasant View-Brambleton 230kV | Stonewall Energy Park | VA | Loudoun | In Service | Dominion | 800 | 800 | 750 | 800 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4039_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4039_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_039_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2012 | N/A | N/A |  |  |  | 10/1/2017 | 10/1/2017 | 4/28/2017 | N | No
X4-040 | Sussex County 12kV |  | DE | Sussex | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4040_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 12/8/2014 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | Y | No
X4-041 3618197 | AMIL-PJM |  | N/A | N/A | Confirmed | Dominion | 143 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3618197_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3618197_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-4/3618197_ltf4.pdf | Executed Agreement and/or Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-4/3618197_ltf4.pdf | Executed Agreement and/or Study |  | 1/31/2012 | 1/1/2015 | 1/1/2024 | [5 empty] | 4/9/2013 | FF | No
X4-042 | Footedale 12kV |  | PA | Fayette | Withdrawn | APS | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4042_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 7/17/2013 | Customer Milestone Not Met | 5/31/2013 |  |  | N | No
X4-043 | Clinton | Allerton Road Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4043_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 9/19/2012 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | No
X4-044 | Aldene 230kV | EF Kenilworth LLC | NJ | Union | In Service | PSEG | 17.9 | 17.9 | 9.9 | 17.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_044_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 5/1/2015 | 5/1/2015 | 6/11/2015 | N | No
X4-045 | Southwark 13kV |  | PA | Philadelphia | Withdrawn | PECO | 0.5 | 0.5 | 0.07 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 4/29/2013 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
X4-046 | E Street (Sub 18) 13kV |  | DC | N/A | In Service | PEPCO | 19.5 | 19.5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4046_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 9/1/2015 | 9/1/2015 | 2/4/2019 | N | No
X4-047 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X4-048 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1000 | 1000 | 1000 | 1000 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_048_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/8/2018 | N | No
Y1-001 | BL England 138kV | B.L. England Station | NJ | Cape May | Withdrawn | AEC | 452 | 452 | 447 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_001_csa.pdf | Document Posted | N/A | N/A |  | 2/3/2012 | N/A | N/A | 6/1/2021 | 12/18/2019 |  | 6/1/2021 | 6/1/2021 |  | N | No
Y1-002 3641682 | NIPS-PJM |  | N/A | N/A | Confirmed |  | 575 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3641682_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3641682_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/3/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-003 | Deep Creek-Penn Mar 115kV | Winding Ridge Wind Farm | MD | Garrett | Withdrawn | APS | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1003_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1003_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_003_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2012 | N/A | N/A |  | 1/25/2017 |  | 10/31/2017 | 10/31/2017 |  | N | No
Y1-004 3673272 | TVA-PJM |  | N/A | N/A | Confirmed |  | 720 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3673272_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3673272_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/7/2012 | 6/1/2023 | 6/1/2028 | [6 empty] | FF | No
Y1-005 | LaSalle |  | IL | Lasalle | Withdrawn | ComEd | 2729 | 350 | 350 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2012 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 4/10/2016 |  |  | N | No
Y1-006 | Jubal Early-Austinville 138kV | Poplar Camp | VA | Carroll | Withdrawn | AEP | 72 | 72 | 9.36 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_006_csa.pdf | Document Posted | N/A | N/A |  | 2/14/2012 | N/A | N/A |  | 10/17/2021 |  | 3/1/2023 | 3/1/2023 |  | N | No
Y1-007 3721881 | TVA-PJM |  | N/A | N/A | Confirmed |  | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/3721881_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/3721881_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/14/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-008 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1008_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2012 | N/A | N/A |  | 3/26/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Y1-009 | Yardville 13kV |  | NJ | Mercer | Withdrawn | PSEG | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1009_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/21/2012 | N/A | N/A |  | 9/26/2012 | Customer Milestone Not Met | 11/30/2012 |  |  | N | No
Y1-010 | Quinton 12kV |  | NJ | Salem | Withdrawn | AEC | 3.9 | 1.9 | 1.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2012 | N/A | N/A |  | 9/12/2012 | Customer Milestone Not Met | 5/17/2012 |  |  | N | No
Y1-011 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2012 | N/A | N/A |  | 9/11/2012 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Y1-012 | Geneva | Geneva Renewable Energy Facility | OH | Ashtabula | In Service | ATSI | 6.48 | 6.48 | 6.48 | 6.48 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1012_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/23/2012 | N/A | N/A |  |  |  | 8/1/2013 | 8/1/2013 | 7/22/2013 | N | No
Y1-013 | McAlpin 12kV |  | WV | Harrison | Withdrawn | APS | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2012 | N/A | N/A |  | 3/28/2012 | Customer Initiated Withdrawal | 9/9/2013 |  |  | N | No
Y1-014 | Worton 12kV |  | MD | Kent | Withdrawn | DPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1014_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2012 | N/A | N/A |  | 8/17/2012 | Customer Initiated Withdrawal | 6/15/2012 |  |  | N | No
Y1-015 | Shenango-Hoytdale 345kV |  | PA | Lawrence | Withdrawn | ATSI | 1000 | 1000 | 870 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1015_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/24/2012 | N/A | N/A |  | 7/29/2014 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
Y1-016 | Baker-Hardy 138kV |  | WV | Hardy | Withdrawn | APS | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 4/4/2013 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
Y1-017 | Tabernacle |  | NJ | Burlington | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 8/27/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
Y1-018 | Conesville #5 | Conesville #5 | OH | Muskingum | Deactivated | AEP | 405 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/1/2013 | N | No
Y1-019 | Conesville #6 | Conesville #6 | OH | Muskingum | Deactivated | AEP | 405 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 6/1/2013 |  | 6/1/2013 | N | No
Y1-020 | Sussex 34kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 0 | 3.72 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1020_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1020_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 1/22/2016 | N | No
Y1-021 | Fredericksburg-Cranes Corner 230kV |  | VA | City of Fredericksburg | Withdrawn | Dominion | 64 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 3/28/2012 |  | 6/1/2013 |  |  | S | No
Y1-022 | Cooper |  | PA | York | Withdrawn | PECO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 6/21/2013 | Customer Initiated Withdrawal | 10/21/2013 |  |  | N | No
Y1-023 | Felicity 69kV |  | OH | Unknown | Withdrawn | Duke | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 10/17/2012 | Customer Initiated Withdrawal | 10/22/2013 |  |  | N | No
Y1-024 | Felicity 12.5kV |  | OH | Unknown | Withdrawn | Duke | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 10/17/2012 | Customer Initiated Withdrawal | 10/22/2013 |  |  | N | No
Y1-025 | Raritan River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 785 | 785 | 725 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1025_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 6/4/2013 | Customer Initiated Withdrawal | 5/15/2015 |  |  | N | No
Y1-026 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 0 | 160 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1026_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1026_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  |  |  | 3/1/2012 |  | 6/1/2018 | N | No
Y1-027 | Belmon 12.5kV | Westmoreland Landfill Gas Plant | PA | Fayette | Withdrawn | APS | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1027_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 7/11/2016 |  | 12/31/2016 | 12/31/2016 |  | N | No
Y1-028 | Lewis Run 115kV |  | PA | McKean | Withdrawn | PENELEC | 125 | 125 | 16.25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 10/19/2012 | Customer Milestone Not Met | 12/1/2014 |  |  | N | No
Y1-029 | Waynesboro-Dooms 115kV |  | VA | Accomack | Withdrawn | Dominion | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 8/29/2012 | Customer Initiated Withdrawal | 9/15/2014 |  |  | N | No
Y1-030 | Forest 69kV |  | OH | Wyandot | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1030_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 2/18/2015 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y1-031 | Erie East 230kV |  | PA | Clarion | Withdrawn | PENELEC | 101.47 | 101.47 | 13.19 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 3/13/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
Y1-032 | Potter-Gold 115kV |  | PA | Potter | Withdrawn | PENELEC | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1032_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 5/8/2013 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
Y1-033 | Penn Mar-Rock Wood 115kV |  | PA | Somerset | In Service | PENELEC | 38.3 | 38.3 | 4.98 | 38.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_033_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2012 | N/A | N/A |  |  |  | 3/27/2017 | 3/27/2017 | 12/14/2016 | N | No
Y1-034 | Everson 23kV | Purdys Run Plant | WV | Harrison | Withdrawn | APS | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1034_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1034_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 6/7/2016 | Customer Initiated Withdrawal | 1/1/2015 | 1/1/2015 |  | N | No
Y1-035 | Eastlake 138kV |  | OH | Lake | Withdrawn | ATSI | 462 | 462 | 462 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1035_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/8/2012 | N/A | N/A |  | 7/23/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
Y1-036 | Eastlake 345kV |  | OH | Lake | Withdrawn | ATSI | 462 | 462 | 462 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1036_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/8/2012 | N/A | N/A |  | 7/23/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
Y1-037 |  |  | NJ | Unknown | Withdrawn | JCPL | 6 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2012 | N/A | N/A |  | 4/4/2012 | Customer Milestone Not Met |  |  |  | N | No
Y1-038 | Sparta |  | NJ | Sussex | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1038_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2012 | N/A | N/A |  | 8/28/2012 | Customer Milestone Not Met | 8/31/2013 |  |  | N | No
Y1-039 | Kings Creek 69kV |  | MD | Somerset | Withdrawn | DPL | 5.2 | 5.2 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2012 | N/A | N/A |  | 9/12/2012 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
Y1-039A_EKPC1 | JK Smith 138 KV |  | KY | Clark | Withdrawn | EKPC | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1039a_ekpc1_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2012 | N/A | N/A |  | 7/16/2013 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Y1-040 4012244 | PJM-LGEE |  | N/A | N/A | Withdrawn |  | 103 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2012 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
Y1-041 4019603 | ALTE-PJM |  | N/A | N/A | Confirmed |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4019603_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4019603_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/27/2012 | 6/1/2016 | 6/1/2017 | [6 empty] | FF | No
Y1-042 | Vineland 12kV |  | NJ | Cumberland | Withdrawn | AEC | 3.5 | 3.5 | 1.33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1042_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 8/28/2012 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
Y1-043 | Mackeys-Creswell 115kV |  | NC | Washington | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 3/26/2013 | Customer Initiated Withdrawal | 5/31/2015 |  |  | N | No
Y1-044 | Belmont 138kV | Willow Island Hydro Generation Project | WV | Pleasants | In Service | APS | 43.2 | 6.8 | 6.8 | 6.8 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2012 | N/A | N/A |  |  |  | 7/31/2015 | 7/31/2015 | 11/15/2015 | N | No
Y1-045 | Friendship Manor |  | MD | Howard | Withdrawn | BGE | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1045_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 8/16/2018 |  | 9/1/2017 | 9/1/2017 |  | Y | No
Y1-046 | New Prospect Road 12kV |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 6/18/2012 | Customer Initiated Withdrawal | 3/13/2013 |  |  | N | No
Y1-047 | North Meshoppen 34.5kV | Roundtop Energy Project | PA | Wyoming | In Service | PENELEC | 15.4 | 15.4 | 15.4 | 15.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_047_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2012 | N/A | N/A |  |  |  | 4/1/2015 | 4/1/2015 | 10/15/2015 | N | No
Y1-048 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | Withdrawn | Dominion | 372 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/2/2012 | N/A | N/A |  | 1/10/2014 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
Y1-049 | Wurno 34.5kV | New River Resource Authority Waste Management Facility IRD LEG-E | VA | Pulaski | In Service | AEP | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1049_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_049_csa.pdf | Document Posted | N/A | N/A |  | 4/6/2012 | N/A | N/A |  |  |  | 3/31/2013 | 3/31/2013 | 12/1/2014 | N | No
Y1-050 4089954 | AMIL-PJM |  | N/A | N/A | Retracted |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/6/2012 | 6/1/2013 | 6/1/2015 |  | 5/16/2012 |  |  |  |  | FF | No
Y1-051 4089967 | CIN-PJM |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/6/2012 | 6/1/2014 | 6/1/2023 |  | 5/16/2012 |  |  |  |  | FF | No
Y1-052 4089969 | AMIL-PJM |  | N/A | N/A | Retracted |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/6/2012 | 6/1/2014 | 6/1/2022 |  | 5/16/2012 |  |  |  |  | FF | No
Y1-053 4126399 | PJM-NYIS |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4126399_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/11/2012 | 1/1/2014 | 1/1/2019 |  | 7/9/2012 |  |  |  |  | FF | No
Y1-054 | Rochelle 138kV | Rochelle Plant | OH | Hamilton | In Service | DEOK | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/16/2012 | N/A | N/A |  |  |  | 5/1/2013 |  | 5/30/2013 | N | No
Y1-055 | Brick-Lanes Mill 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1055_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/16/2012 | N/A | N/A |  | 8/10/2012 | Customer Milestone Not Met | 6/30/2015 |  |  | N | No
Y1-056 | TMI |  | PA | York | Withdrawn | ME | 879 | 19 | 19 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1056_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/16/2012 | N/A | N/A |  | 6/10/2013 | Customer Initiated Withdrawal | 6/30/2013 |  |  | N | No
Y1-057 | Barbadoes 34kV | Barbadoes Energy Storage Unit | PA | Montgomery | Deactivated | PECO | 2 | 1 | 0.1 | 1 | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_057_csa.pdf | Document Posted | N/A | N/A | 9/4/2013 | 4/25/2012 | N/A | N/A |  |  |  | 12/1/2013 | 12/1/2013 | 9/30/2013 | N | No
Y1-058 4231012 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 33 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4231012_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4231012_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/25/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-059 4231038 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 33 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4231038_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4231038_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/25/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-060 | Aulander 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 15 | 15 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1060_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/25/2012 | N/A | N/A |  | 1/18/2013 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
Y1-061 4239695 | CPLE-PJM |  | N/A | N/A | Retracted |  | 55 |  |  | 55 | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4239695_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2013 | 6/1/2015 |  | 7/9/2012 |  |  |  |  | FF | No
Y1-062 4239873 | CPLE-PJM |  | N/A | N/A | Retracted |  | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4239873_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2013 | 6/1/2014 |  | 7/9/2012 |  |  |  |  | FF | No
Y1-063 | Trenton 34.5kV |  | OH | Delaware | Deactivated | AEP | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1063_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1063_wmpa.pdf | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 3/31/2014 | 3/31/2014 | 3/31/2014 | N | No
Y1-064 | Berkshire 34.5kV | Berkshire 3.4kV | OH | Delaware | Withdrawn | AEP | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1064_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  | 10/31/2013 | Customer Initiated Withdrawal | 3/31/2015 | 3/31/2015 |  | N | No
Y1-065 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 834.1 | 834.1 | 805 | 834.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1065_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1065_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_065_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 9/21/2017 | 9/21/2017 | 7/26/2017 | N | No
Y1-066 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | In Service | Dominion | 182 | 0 | 13.3 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1066_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_066_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 9/1/2013 | N | No
Y1-067 | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 64.6 | 64.6 | 8.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2012 | N/A | N/A |  | 11/30/2012 | Customer Milestone Not Met | 11/1/2013 |  |  | N | No
Y1-068 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | Unknown | In Service | Dominion | 50 | 20 | 0 | 20 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_068_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 10/15/2013 | N | No
Y1-069 | Bay Shore-Fostoria Central 345kV & Bayshore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 799 | 799 | 799 | 799 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_069_csa.pdf | Document Posted | N/A | N/A | 3/15/2016 | 4/27/2012 | N/A | N/A | 3/9/2017 |  |  | 5/15/2017 | 5/15/2017 | 6/23/2017 | N | No
Y1-070 | Shenango-Hoytdale 345kV |  | PA | Lawrence | Withdrawn | ATSI | 825 | 825 | 825 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1070_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 4/24/2013 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Y1-071 | Burma 25kV | Kelly Generation Facility | PA | Lawrence | Withdrawn | APS | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 3/10/2017 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
Y1-072 | Glen Gardner 12kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 0 | 0.76 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 12/23/2011 |  | 5/30/2013 | N | No
Y1-073 | Riders Creek |  | NC | Tyrell | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1073_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 9/4/2012 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
Y1-074 | Martin 12kV |  | OH | Summit | Withdrawn | ATSI | 7.8 | 7.8 | 2.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 2/25/2013 | Customer Initiated Withdrawal | 11/1/2013 |  |  | N | No
Y1-075 | Medford 13kV | Reeve's Station South | NJ | Burlington | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1075_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 12/19/2013 | N | No
Y1-076 | BL England 138kV |  | NJ | Cape May | Withdrawn | AEC | 452 | 18.1 | 18.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 5/29/2012 |  | 6/1/2015 |  |  | N | No
Y1-077 | BL England 138kV | Cape May Energy Center (CMEC) | NJ | Cape May | Withdrawn | AEC | 486 | 34 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_077_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A | 6/1/2023 | 12/18/2019 |  | 6/1/2021 | 6/1/2021 |  | N | No
Y1-078 | Crawford 138kV |  | IL | Cook | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1078_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 2/7/2014 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
Y1-079 | Wye Mills 69kV | Wye Mills Solar Site | MD | Talbot | In Service | DPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1079_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1079_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 7/29/2016 | 7/29/2016 | 8/24/2016 | N | No
Y1-080 | Dorchester 12kV | Constellation Solar Maryland II, LLC Solar Facility | MD | Dorchester | In Service | DPL | 3.38 | 3.38 | 1.28 | 3.38 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1080_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 4/30/2015 | 4/30/2015 | 4/30/2015 | N | No
Y1-081 | Wye Mills 12kV |  | MD | Talbot | Withdrawn | DPL | 3.38 | 3.38 | 1.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 9/10/2012 | Customer Initiated Withdrawal | 11/1/2013 |  |  | N | No
Y1-082 | Longwood-Wye Mills 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y1082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y1082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y1_082_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 5/2/2016 | S | No
Y1-084 | East Newton–Blairstown 34.5kV | Fredon Solar Farm | NJ | Sussex | Withdrawn | JCPL | 1.99 | 1.99 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1084_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1084_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 5/16/2017 |  | 5/30/2015 | 5/30/2015 |  | N | No
Y1-085 | Kings Creek 25kV |  | MD | Somerset | Withdrawn | DPL | 4.4 | 4.4 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 10/4/2012 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
Y1-086 | Morgans Corner | Morgan's Corner Solar | NC | Pasquotank | In Service | Dominion | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_086_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 1/30/2016 | 1/30/2016 | 12/26/2015 | N | No
Y1-087 | New Hope |  | MD | Wicomico | Withdrawn | DPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 9/6/2012 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Y1-088 4273094 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
Y1-089 4273103 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 61 | 61 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4273103_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4273103_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2015 | 12/15/2019 |  | 12/15/2019 |  |  |  |  | FF | No
Y1-090 4273104 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4273104_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4273104_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-091 4273111 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 57 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4273111_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4273111_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2015 | 6/1/2020 |  | 10/18/2019 |  |  |  |  | FF | No
Y2-001 | Gosport | SPSA Navy Power Plant | VA | City of Portsmouth | Deactivated | Dominion | 53.8 | 3.8 | 40 | 3.8 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/2/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 5/22/2014 | N | No
Y2-002 |  |  | PA | Adams | Withdrawn | PPL | 350 |  |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2012 | N/A | N/A |  | 5/24/2012 | Customer Milestone Not Met |  |  |  | N | No
Y2-003 | Chicago Battery |  | IL | Unknown | Withdrawn | ComEd | 0.6 | 0.6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2003_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/16/2012 | N/A | N/A |  | 3/28/2016 | Customer Milestone Not Met | 8/31/2014 | 8/31/2014 |  | Y | No
Y2-004 4392716 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4392716_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4392716_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2016 | 6/1/2022 |  | 2/1/2019 |  |  |  |  | FF | No
Y2-005 4392723 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 117 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4392723_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4392723_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2016 | 1/1/2022 | [6 empty] | FF | No
Y2-006 4392735 | IPL-PJM |  | N/A | N/A | Withdrawn |  | 237 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4392735_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4392735_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2016 | 6/1/2021 |  | 2/1/2019 |  |  |  |  | FF | No
Y2-007 4393092 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4393092_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4393092_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2013 | 6/1/2015 |  | 10/25/2013 |  |  |  |  | FF | No
Y2-008 4393106 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4393106_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/16/2012 | 1/1/2013 | 1/1/2015 |  | 8/19/2013 |  |  |  |  | FF | No
Y2-009 4436881 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4436881_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/22/2012 | 1/1/2013 | 1/1/2015 |  | 7/30/2012 |  |  |  |  | FF | No
Y2-010 | Olive-Meadow Lake 345kV |  | IN | White | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2012 | N/A | N/A |  | 2/6/2014 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y2-011 | Brunot Island I 138kV |  | PA | Allegheny | Withdrawn | DL | 20 | 20 | 15 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 5/24/2012 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | No
Y2-012 | Brunot Island II 138kV |  | PA | Allegheny | Withdrawn | DL | 20 | 20 | 15 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 5/24/2012 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | No
Y2-013 | Linden VFT-Tosco 230kV |  | NJ | Union | Withdrawn | PSEG | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/30/2012 | N/A | N/A |  | 5/20/2013 | Customer Initiated Withdrawal | 5/1/2017 |  |  | N | No
Y2-014 4465462 | MECS-PJM |  | N/A | N/A | Retracted |  | 542 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4465462_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/30/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y2-015 | Eldred-Frackville #1 230kV |  | PA | Schuylkill | Withdrawn | PPL | 344 | 344 | 337 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2015_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/31/2012 | N/A | N/A |  | 10/2/2017 |  | 12/31/2018 | 12/31/2018 |  | N | No
Y2-016 |  |  | PA | Adams | Withdrawn | PENELEC | 68 |  |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2012 | N/A | N/A |  | 6/12/2012 | Customer Initiated Withdrawal |  |  |  | N | No
Y2-017 4469835 | WEC-PJM |  | N/A | N/A | Withdrawn |  | 578 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4469835_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/11/2012 | 1/1/2014 | 6/1/2019 |  | 8/16/2012 |  |  |  |  | FF | No
Y2-018 | Pequest River 34.5kV | Warren County Landfill | NJ | Warren | In Service | JCPL | 3.8 | 3.8 | 2.3 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2012 | N/A | N/A |  |  |  | 5/31/2016 | 5/31/2016 | 5/12/2014 | N | No
Y2-019 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 755 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_019_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 6/21/2012 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
Y2-020 4474313 | ALTE-PJM |  | N/A | N/A | Retracted |  | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4474313_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/26/2012 | 6/1/2016 | 6/1/2017 | [6 empty] | FF | No
Y2-021 4474676 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 160 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-022 4474678 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-023 4474686 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-024 4474688 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 13 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-025 4474691 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 160 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-026 4474692 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-027 4474693 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 75 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-028 4474695 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 38 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-029 | Ringoes 12kV |  | NJ | Atlantic | Withdrawn | JCPL | 0.38 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2012 | N/A | N/A |  | 8/16/2012 |  |  |  |  | N | No
Y2-030 4476631 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 167 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4476631_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4476631_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/3/2012 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
Y2-031 4476636 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 167 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4476636_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4476636_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/3/2012 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
Y2-032 4476638 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 167 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4476638_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4476638_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/3/2012 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
Y2-033 4476971 | TVA-PJM |  | N/A | N/A | Confirmed |  | 93 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4476971_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4476971_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/4/2012 | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
Y2-034 4476972 | DUK-PJM |  | N/A | N/A | Confirmed |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4476972_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4476972_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/4/2012 | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
Y2-035 4479078 | DUK-PJM |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4479078_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4479078_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/10/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y2-036 4479079 | DUK-PJM |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4479079_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4479079_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/10/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y2-037 | Tuscarora 12kV #1 | Blythe Township Solar Farm #1 | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2037_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/11/2012 | N/A | N/A |  | 9/10/2013 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | N | Yes
Y2-038 | Tuscarora 12kV #2 |  | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2012 | N/A | N/A |  | 8/23/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
Y2-039 4480171 | PJM-NYIS |  | N/A | N/A | Retracted |  | 6 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/13/2012 | 9/1/2012 | 9/1/2017 | [6 empty] | FF | No
Y2-040 4480173 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 660 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4480173_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/13/2012 | 6/1/2014 | 6/1/2019 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-041 4482430 | PJM-NYIS |  | N/A | N/A | Withdrawn |  | 6 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/20/2012 | 9/1/2012 | 9/1/2013 | [6 empty] | FF | No
Y2-042 | Oxbow 34.5 kV | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 18.3 | 18.3 | 18.3 | 18.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2042_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/23/2012 | N/A | N/A | 10/31/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/16/2019 | N | No
Y2-043 | Kickapoo | Grand Ridge Battery Storage | IL | Lasalle | Deactivated | ComEd | 15.7 | 4.5 | 0 | 1.5 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_043_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2012 | N/A | N/A | 12/21/2012 |  |  | 12/31/2012 |  | 12/21/2012 | N | No
Y2-044 4485276 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 83 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4485276_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4485276_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/31/2012 | 6/1/2016 | 6/1/2021 |  | 6/18/2018 |  |  |  |  | FF | No
Y2-045 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 999 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/2/2012 | N/A | N/A |  |  |  | 7/8/2015 | 7/8/2015 | 1/8/2016 | N | No
Y2-046 4486124 | TVA-PJM |  | N/A | N/A | Retracted |  | 800 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4486124_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/3/2012 | 1/1/2014 | 1/1/2024 | [6 empty] | FF | No
Y2-047 | Peach Bottom-BGE |  | N/A | N/A | Withdrawn | PECO | 200 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/y2047_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2012 | N/A | N/A |  | 7/15/2015 |  | 1/1/2013 |  |  | EE | No
Y2-048 | Haumesser Road |  | IL | DeKalb | Withdrawn | ComEd | 240 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2012 | N/A | N/A |  | 11/5/2013 | Customer Initiated Withdrawal | 3/29/2013 |  |  | N | No
Y2-049 4487235 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 542 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4487235_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4487235_ltf2.pdf | Revised |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/8/2012 | 6/1/2015 | 6/1/2020 |  | 9/18/2014 |  |  |  |  | FF | No
Y2-050 | Tidd–Canton Central | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 742 | 742 | 672 | 742 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_050_csa.pdf | Document Posted | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 11/1/2017 | 11/1/2017 | 9/25/2017 | N | No
Y2-051 | Brick-Lane Mill 34.5kV | French's Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2051_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2051_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/22/2014 | N | Yes
Y2-052 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 704 | 0 | 34.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2012 | N/A | N/A |  | 7/17/2013 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | N | No
Y2-053 | Lemoyne 138kV |  | OH | Wood | Withdrawn | ATSI | 675 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2053_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/15/2012 | N/A | N/A |  | 1/6/2015 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
Y2-054 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 354 | 13.7 | 13.7 | 13.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/10/2014 | N | No
Y2-055 | Elm Street 34.5kV | United Refining Company Oil Refinery | PA | Warren | Withdrawn | PENELEC | 29 | 29 | 29 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2055_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2055_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2055_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/16/2012 | N/A | N/A |  | 2/15/2019 |  | 1/1/2018 | 1/1/2018 |  | N | No
Y2-056 4489283 | ALTE-PJM |  | N/A | N/A | Retracted |  | 468 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4489283_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4489283_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/17/2012 | 6/1/2017 | 6/1/2022 |  | 6/4/2014 |  |  |  |  | FF | No
Y2-057 | Wyandot 13kV |  | OH | Wyandot | Withdrawn | AEP | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2012 | N/A | N/A |  | 9/14/2012 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
Y2-058 | Broadford-Jackson's Ferry 765kV |  | VA | Unknown | Withdrawn | AEP | 762 | 762 | 668 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2058_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2012 | N/A | N/A |  | 6/2/2015 | Customer Initiated Withdrawal | 5/15/2017 |  |  | N | No
Y2-059 | Kingston-Westover 69kV |  | MD | Somerset | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2059_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2012 | N/A | N/A |  | 3/11/2013 | Customer Initiated Withdrawal | 9/1/2015 |  |  | N | No
Y2-060 | North Meshoppen 34.5kv II | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 18.9 | 3.5 | 3.5 | 3.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_060_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2012 | N/A | N/A |  |  |  | 4/1/2015 | 4/1/2015 | 10/15/2015 | N | No
Y2-061 | Cumberland-West Shore 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2012 | N/A | N/A |  | 3/19/2013 | Customer Initiated Withdrawal | 7/1/2014 |  |  | N | Yes
Y2-062 | East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2012 | N/A | N/A |  | 1/14/2013 | Customer Initiated Withdrawal | 12/1/2014 |  |  | N | No
Y2-063 | Eldred-Frackville #2 230kV |  | PA | Schuylkill | Withdrawn | PPL | 344 | 344 | 337 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2063_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2063_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/20/2012 | N/A | N/A |  | 4/14/2015 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y2-064 | Printz | Liberty Electric | PA | Delaware | In Service | PECO | 606.5 | 65.5 | 19 | 65.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_064_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/24/2012 | N/A | N/A |  |  |  | 9/30/2014 | 9/30/2014 | 10/5/2015 | N | No
Y2-065 | Valley-Raccoon 138kV |  | PA | Beaver | Withdrawn | DL | 205 | 205 | 97 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2065_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2012 | N/A | N/A |  | 3/26/2013 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
Y2-066 | Suffolk 34.5kV | Suffolk Landfill Units 1-10 | VA | City of Suffolk | Withdrawn | Dominion | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_066_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2012 | N/A | N/A |  | 6/5/2015 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | Yes
Y2-067 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 626 | 12 | 12 | 12 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2012 | N/A | N/A |  |  |  | 11/1/2012 |  | 3/28/2014 | N | No
Y2-068 4504469 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 3081 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4504469_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4504469_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/12/2012 | 6/1/2016 | 6/1/2022 |  | 5/19/2014 |  |  |  |  | FF | No
Y2-069 4505354 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4505354_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-070 4505355 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4505355_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-071 4505356 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4505356_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-072 4505357 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4505357_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-073 4505680 | NYISJK-PJM-NYISBC |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4505680_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4505680_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/16/2012 | 6/1/2017 | 6/1/2022 |  | 1/8/2013 |  |  |  |  | FF | No
Y2-074 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 401 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2074_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_074_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/19/2012 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/1/2013 | N | No
Y2-075 | Solar City |  | MD | Frederick | Withdrawn | APS | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2075_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/19/2012 | N/A | N/A |  | 5/13/2013 | Customer Milestone Not Met | 4/5/2013 |  |  | Y | Yes
Y2-076 | Clover 230kV | Clover Power Station Unit 1 | VA | Halifax | In Service | Dominion | 445 | 4 | 13.7 | 4 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_076_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/22/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 6/1/2014 | N | No
Y2-077 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 401 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/23/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 12/20/2017 | N | No
Y2-078 | Lakewood #1 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_078_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 6/1/2015 | N | No
Y2-079 | Lakewood #2 230kV | Ocean Peaking Power | NJ | Ocean | In Service | JCPL | 395.6 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_079_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2012 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 6/1/2015 | N | No
Y2-080 | Rhodes Lane 500kV |  | PA | Westmoreland | Withdrawn | APS | 1065 | 1065 | 1065 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2080_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2012 | N/A | N/A |  | 11/23/2015 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Y2-081 | Deptford 13kV | Deptford (Kinsley Solar)13kV | NJ | Gloucester | In Service | PSEG | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2012 | N/A | N/A |  |  |  | 11/1/2014 | 11/1/2014 | 1/14/2015 | N | Yes
Y2-082 4510276 | MECS-PJM |  | N/A | N/A | Annulled |  | 1200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4510276_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4510276_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/30/2012 | 6/1/2019 | 6/1/2024 |  | 5/18/2016 |  |  |  |  | FF | No
Y2-083 | Essex 138kV |  | NJ | Essex | Withdrawn | PSEG | 218 | 218 | 198 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 5/29/2013 | Customer Initiated Withdrawal | 5/31/2016 |  |  | N | No
Y2-084 | Dequine 345kV |  | IN | Tippecance | Withdrawn | AEP | 64 | 64 | 3.33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 3/14/2014 | Customer Initiated Withdrawal | 2/28/2014 |  |  | N | No
Y2-085 | Sammis–Star 345kV |  | OH | Carroll | Withdrawn | ATSI | 1050 | 1050 | 1050 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2085_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 7/3/2013 | Customer Initiated Withdrawal | 1/1/2017 |  |  | N | No
Y2-086 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 11/10/2014 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
Y2-087 | Raystown-Lewistown 230kV |  | PA | Mifflin | Withdrawn | PENELEC | 150.4 | 150.4 | 19.55 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 8/28/2014 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
Y2-088 | Garards Fort 25kV | Bayles-Garards Fort 25kV | PA | Greene | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2088_imp.pdf | Document Posted |  | Withdrawn | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 1/20/2017 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | Yes
Y2-089 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1370 | 370 | 370 | 370 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_089_csa.pdf | Document Posted | N/A | N/A | 9/30/2017 | 10/31/2012 | N/A | N/A | 3/1/2018 |  |  | 4/1/2019 | 4/1/2019 | 10/2/2018 | N | No
Y2-090 4510751 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2012 | 6/1/2017 | 6/1/2018 | [6 empty] | FF | No
Y2-091 | Toledo Solar |  | OH | Lucas | Withdrawn | ATSI | 0.332 | 0.332 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 1/13/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
Y2-092 | Walbridge Solar |  | OH | Wood | Withdrawn | ATSI | 0.3 | 0.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 1/13/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
Y2-093 | Easton-Easton Tap 69kV |  | PA | Northampton | Withdrawn | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 12/7/2012 | Queue Not Required | 6/1/2013 |  |  | S | No
Y2-094 | 4 Quad Cities-1-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 250 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/y2094_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Y2-095 | Sullivan 765 kV |  | IL | Randolph | Withdrawn | AEP | 1211 | 1211 | 1211 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 9/10/2013 | Customer Initiated Withdrawal | 10/24/2013 |  |  | N | No
Y2-096 | Balenger Sewage-Thomas Bakery 34.5kV |  | MD | Frederick | Withdrawn | APS | 47.2 | 47.2 | 47.2 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 12/2/2014 | Customer Initiated Withdrawal | 8/18/2016 |  |  | N | No
Y2-097 | Brunswick 500kV |  | VA | Brunswick | Withdrawn | Dominion | 3102 | 1551 | 1376 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2097_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 11/18/2013 | Customer Initiated Withdrawal | 12/1/2018 |  |  | N | No
Y2-098 | Freemansburg #1 12kV | Bethlehem Landfill | PA | Northampton | Deactivated | PPL | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2098_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_098_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  |  |  | 11/1/2012 |  | 8/10/2016 | N | No
Y2-099 | Warrenton 34.5kV | Fauquier County Landfill Units 1 & 2 | VA | Fauquier | Withdrawn | Dominion | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_099_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 3/11/2016 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | Yes
Y2-100 | Otter Point 34.5kV | Eastern Landfill Gas | MD | Baltimore County | In Service | BGE | 4 | 4 | 4 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_100_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  |  |  | 4/30/2013 | 4/30/2013 | 11/18/2016 | N | No
Y2-101 | Freemansburg #2 12kV |  | PA | Northampton | Withdrawn | PPL | 3.2 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 4/4/2013 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
Y2-102 | Deepwater 138kV |  | NJ | Salem | Withdrawn | AEC | 193 | 193 | 193 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2102_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2012 | N/A | N/A |  | 7/10/2013 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Y2-103 | Zion Energy Center |  | IL | Lake | Withdrawn | ComEd | 945 | 360 | 360 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2103_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/1/2012 | N/A | N/A |  | 12/24/2019 |  | 6/1/2016 |  |  | N | No
Y2-104 | Russell Hill-N. Meshoppen 34.5kV |  | PA | Wyoming | Withdrawn | PENELEC | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2012 | N/A | N/A |  | 7/25/2013 | Customer Initiated Withdrawal | 3/1/2014 |  |  | N | No
Y2-105 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 253 | 63 | 50 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_105_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 3/25/2015 | N | No
Y2-106 4511112 | ALTE-PJM |  | N/A | N/A | Retracted |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/1/2012 | 6/1/2017 | 6/1/2018 | [6 empty] | FF | No
Y2-107 | Robison Park-Argenta 345 kV |  | IN | LeGrange | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2107_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 8/19/2013 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
Y2-108 | Crisfield 25kV |  | MD | Somerset | Withdrawn | DPL | 12 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2108_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 12/11/2014 | Customer Initiated Withdrawal | 3/31/2015 | 3/31/2015 |  | N | No
Y2-109 | Bayview 25kV | Bayview | VA | Northampton | In Service | ODEC | 12.5 | 0.5 | 0.5 | 0.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 7/19/2013 | 7/19/2013 | 7/19/2013 | N | No
Y2-110 | BL England 138kV |  | NJ | Cape May | Withdrawn | AEC | 565 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2110_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 3/7/2016 | Customer Initiated Withdrawal | 1/1/2016 |  |  | N | No
Y2-111 | Tait 69kV | AES Tait Energy Storage | OH | Montgomery | Deactivated | Dayton | 12 | 12 | 0 | 12 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 3/27/2014 | 3/27/2014 | 8/27/2013 | N | Yes
Y2-112 | Keystone 345kV |  | IN | Wells | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2112_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 8/21/2013 | Customer Milestone Not Met | 3/1/2013 |  |  | N | No
Y2-113 | Morris 138kV | Morris Cogen | IL | Grundy | In Service | ComEd | 120 | 12.6 | 12.6 | 12.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 10/31/2012 |  | 3/14/2014 | N | No
Y2-114 4511399 | CIN-PJM |  | N/A | N/A | Confirmed |  | 95 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4511399_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4511399_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2012 | 6/1/2016 | 1/1/2024 | [6 empty] | FF | No
Y2-115 4511400 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 102 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4511400_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4511400_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/2/2012 | 6/1/2016 | 1/1/2024 |  | 2/1/2019 |  |  |  |  | FF | No
Y2-116 | Sullivan 765 kV |  | IL | Randolph | Withdrawn | AEP | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2116_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 9/10/2013 | Customer Initiated Withdrawal | 10/24/2013 |  |  | N | No
Y2-117 | Perryman Solar | Perryman Solar Farm | MD | Harford | Withdrawn | BGE | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2117_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2117_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 8/2/2018 |  | 12/31/2017 | 12/31/2017 |  | N | No
Y3-001 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 705 | 705 | 660 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3001_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2012 | N/A | N/A |  | 1/21/2014 | Customer Milestone Not Met | 5/31/2017 | 5/31/2017 |  | N | No
Y3-002 4512681 | MECS-PJM |  | N/A | N/A | Retracted |  | 103 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/6/2012 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
Y3-003 4514773 | PJM-LGEE |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/12/2012 | 1/1/2015 | 1/1/2016 | [6 empty] | FF | No
Y3-004 4520247 | ALTE-PJM |  | N/A | N/A | Retracted |  | 468 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/30/2012 | 6/1/2017 | 6/1/2018 |  | 4/1/2013 |  |  |  |  | FF | No
Y3-005 4520326 | PJM-LGEE |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/30/2012 | 1/1/2015 | 1/1/2021 |  | 4/1/2013 |  |  |  |  | FF | No
Y3-006 4522077 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4522077_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2014 | 1/1/2024 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-007 4522091 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4522091_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2014 | 1/1/2024 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-008 4522102 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4522102_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2015 | 1/1/2023 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-009 4522107 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4522107_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2015 | 1/1/2023 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-010 | Brush Junction-Millheim 46kV |  | PA | Centre | Withdrawn | APS | 70 | 70 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2012 | N/A | N/A |  | 9/23/2013 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Y3-011 4524473 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 468 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4524473_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/17/2012 | 6/1/2017 | 6/1/2018 |  | 12/26/2013 |  |  |  |  | FF | No
Y3-012 | Huron 69kV | Marina Thermal Facility | NJ | Atlantic | In Service | AEC | 15.5 | 7.5 | 0 | 7.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3012_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_012_csa.pdf | Document Posted | N/A | N/A |  | 12/21/2012 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 1/31/2014 | N | Yes
Y3-013 | Zion Energy Center | Zion Energy Center | IL | Lake | In Service | ComEd | 585 | 0 | 90 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_013_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/27/2012 | N/A | N/A |  |  |  | 9/1/2021 | 9/1/2021 | 1/12/2021 | N | No
Y3-014 4526965 | TVA-PJM |  | N/A | N/A | Retracted |  | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4526965_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-015 4526966 | TVA-PJM |  | N/A | N/A | Retracted |  | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4526966_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-016 4526971 | TVA-PJM |  | N/A | N/A | Retracted |  | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4526971_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-017 4526972 | AMIL-PJM |  | N/A | N/A | Retracted |  | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4526972_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-018 4526973 | AMIL-PJM |  | N/A | N/A | Retracted |  | 38 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4526973_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-019 4530042 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 275 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4530042_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/9/2013 | 6/1/2015 | 6/1/2020 |  | 3/21/2013 |  |  |  |  | FF | No
Y3-020 4530044 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 87 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4530044_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/9/2013 | 6/1/2015 | 6/1/2020 |  | 3/21/2013 |  |  |  |  | FF | No
Y3-021 4530045 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 87 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4530045_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/9/2013 | 6/1/2015 | 6/1/2020 |  | 3/21/2013 |  |  |  |  | FF | No
Y3-022 4531285 | PJM-LGEE |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4531285_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4531285_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/14/2013 | 1/1/2015 | 1/1/2021 | [6 empty] | FF | No
Y3-023 | Country Side 12kV | Wabash Valley Power Association, Inc. | IN | Elkhart | In Service | AEP | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3023_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3023_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/18/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/1/2015 | N | Yes
Y3-024 | Bluff Point 12kV | Wabash Valley Power Association, Inc. | IN | Jay | In Service | AEP | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3024_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3024_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/18/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/1/2015 | N | Yes
Y3-025 | Bridge-South Park 12kV | Charleston Clean Energy | WV | Kanawha | In Service | AEP | 3.18 | 3.18 | 3.18 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_025_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/22/2013 | N/A | N/A |  |  |  | 5/29/2015 | 5/29/2015 | 5/29/2019 | N | No
Y3-026 | Burlington 26kV | Burlington (L&D Solar) 26kV | NJ | Burlington | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_026_csa.pdf | Document Posted | N/A | N/A |  | 1/25/2013 | N/A | N/A |  |  |  | 9/24/2015 | 9/24/2015 | 1/26/2016 | N | Yes
Y3-027 | Camden 26kV | Camden (Cinnaminson Solar) 26kV | NJ | Burlington | Withdrawn | PSEG | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3027_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/25/2013 | N/A | N/A |  | 2/18/2015 | Customer Initiated Withdrawal | 5/28/2015 | 5/28/2015 |  | N | Yes
Y3-028 4534356 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4534356_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4534356_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/25/2013 | 6/1/2017 | 6/1/2022 |  | 7/14/2014 |  |  |  |  | FF | No
Y3-029 | Damascus-Mt. Airy 34.5kV | Hickory Plains Hydroponics | MD | Frederick | Withdrawn | APS | 4.375 | 4.375 | 4.375 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3029_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/1/2013 | N/A | N/A |  | 4/4/2018 |  | 12/31/2017 | 12/31/2017 |  | N | Yes
Y3-030 | Sandy Springs-High Ridge 230kV |  | MD | Unknown | Withdrawn | BGE | 127 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y3030_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/4/2013 | N/A | N/A |  | 4/3/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
Y3-031 | Riders Creek 115kV |  | NC | Tyrell | Withdrawn | Dominion | 130.9 | 130.9 | 17 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2013 | N/A | N/A |  | 9/16/2013 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
Y3-031A_EKPC2 | Flemingsburg 138 KV |  | KY | Unknown | Withdrawn | EKPC | 150.28 | 150.28 | 19.53 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3031a_ekpc2_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3031a_ekpc2_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2013 | N/A | N/A |  | 5/1/2014 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y3-032 4540149 | MECS-PJM |  | N/A | N/A | Annulled |  | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4540149_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4540149_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/19/2013 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Y3-033 | Chestertown-Millington 69kV | Mills Branch Wind Farm | MD | Kent | Withdrawn | DPL | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_033_csa.pdf | Document Posted | N/A | N/A |  | 2/19/2013 | N/A | N/A |  | 1/20/2017 | Customer Initiated Withdrawal | 4/30/2018 | 4/30/2018 |  | N | No
Y3-034 | Eldred-Pine Grove 690kV | Stonegate Renewable Energy | PA | Schuylkill | In Service | PPL | 10.5 | 0 | 1.8 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/20/2013 | N/A | N/A |  |  |  | 12/31/2013 |  | 12/26/2013 | N | No
Y3-035 | Mole Creek 345kV |  | IL | Marshall | Withdrawn | ComEd | 97.5 | 97.5 | 12.675 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2013 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
Y3-036 | Gavin Unit 2 | Gavin Unit #2 | OH | Gallia | In Service | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_036_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A | 10/1/2020 |  |  | 12/31/2014 | 12/31/2014 | 1/14/2015 | N | No
Y3-037 | Amos Unit 3 | John Amos Generating Plant Unit No. 3 | WV | Putnam | In Service | AEP | 1336 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 4/1/2015 | N | No
Y3-038 | Rockport Unit 1 | Rockport Unit #1 | IN | Spencer | In Service | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 6/30/2017 | N | No
Y3-039 | Clinch River Unit 1 | Clinch River Power Plant | VA | Russell | In Service | AEP | 250 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 4/15/2016 | 4/15/2016 | 5/27/2016 | N | No
Y3-040 | Clinch River Unit 2 | Clinch River Power Plant | VA | Russell | In Service | AEP | 250 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/6/2016 | 6/6/2016 | 5/23/2016 | N | No
Y3-041 | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 62 | 62 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3041_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3041_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 1/29/2015 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
Y3-042 | Elrama 69kV |  | PA | Washington | Withdrawn | DL | 460 | 460 | 460 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 10/22/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
Y3-043 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 760 | 760 | 760 | 760 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_043_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/11/2018 | N | No
Y3-044 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 206 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-045 | Bergen | Bergen Genertating Station | NJ | Bergen | In Service | PSEG | 1235 | 0 | 5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/29/2015 | N | No
Y3-046 | Linden | Linden Generating Station | NJ | Union | Withdrawn | PSEG | 178 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_046_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 6/30/2017 |  | 3/31/2015 | 3/31/2015 | 2/13/2015 | N | No
Y3-047 | Essex |  | NJ | Essex | Withdrawn | PSEG | 299 | 10 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3047_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_047_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 7/22/2014 | Customer Initiated Withdrawal | 5/31/2013 |  |  | N | No
Y3-048 | Burlington | Burlington Generating Station | NJ | Burlington | In Service | PSEG | 207 | 2 | 3 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-049 | Edison |  | NJ | Middlesex | Withdrawn | PSEG | 582 | 0 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3049_fea.pdf | Document Posted |  |  |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_049_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 7/22/2014 | Customer Initiated Withdrawal | 5/31/2013 |  |  | N | No
Y3-050 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 497 | 24 | 21 | 24 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-051 | Linden | Linden Generating Station | NJ | Union | In Service | PSEG | 1626 | 47 | 4 | 47 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3051_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3051_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 8/29/2016 | N | No
Y3-052 | Bergen |  | NJ | Bergen | In Service | PSEG | 1285 | 50 | 10 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3052_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3052_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_052_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/29/2015 | N | No
Y3-053 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 537 | 40 | 13 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_053_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/21/2015 | N | No
Y3-054 | Milford 138kV | Milford Solar | DE | Kent | Withdrawn | DPL | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3054_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/5/2013 | N/A | N/A |  | 5/16/2016 |  | 12/31/2014 | 12/31/2014 |  | N | No
Y3-055 4543017 | PJM-TVA |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4543017_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/5/2013 | 1/1/2015 | 1/1/2017 |  | 5/16/2013 |  |  |  |  | FF | No
Y3-056 | Pioneer Crossing 69kV | Pioneer Crossing | PA | Berks | In Service | ME | 8 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/12/2013 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 9/1/2013 | N | No
Y3-057 | Forest Park |  | MD | Charles | Withdrawn | PEPCO | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2013 | N/A | N/A |  | 4/12/2013 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
Y3-058 | Rockawalkin 69kV | Rockfish Solar Power Plant | MD | Wicomico | In Service | DPL | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3058_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/13/2013 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 2/22/2016 | N | No
Y3-059 4545202 | PJM-MECS |  | N/A | N/A | Confirmed |  | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4545202_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4545202_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/14/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Y3-060 4545220 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 89 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4545220_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/14/2013 | 1/1/2014 | 1/1/2019 | [6 empty] | FF | No
Y3-061 4545319 | DUK-PJM |  | N/A | N/A | Retracted |  | 409 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/14/2013 | 6/1/2016 | 6/1/2021 |  | 4/8/2013 |  |  |  |  | FF | No
Y3-062 | Erie East 34.5kV | North East Wind Farm | PA | Erie | Withdrawn | PENELEC | 18.7 | 18.7 | 2.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3062_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3062_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/18/2013 | N/A | N/A |  | 12/17/2014 | Customer Milestone Not Met | 12/31/2016 | 12/31/2016 |  | N | No
Y3-063 | State Line 138kV |  | IN | Lake | Withdrawn | ComEd | 1161 | 1161 | 1161 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3063_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2013 | N/A | N/A |  | 9/9/2013 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
Y3-064 | Pierce-Beckjord 138kV |  | OH | Clermont | In Service | DEOK | 160 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 155 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3064_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y3064_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y3_064_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2013 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/20/2019 | S | No
Y3-065 4548142 | PJM-CIN |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2013 | 1/1/2015 | 1/1/2021 |  | 4/18/2013 |  |  |  |  | FF | No
Y3-066 4548245 | AMIL-PJM |  | N/A | N/A | Retracted |  | 580 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4548245_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2013 | 6/1/2017 | 6/1/2022 |  | 6/7/2013 |  |  |  |  | FF | No
Y3-067 4548247 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4548247_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4548247_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/26/2013 | 6/1/2016 | 6/1/2017 |  | 7/23/2014 |  |  |  |  | FF | No
Y3-068 | George Washington 138kV | Moundsville Power, LLC | WV | Marshall | Withdrawn | AEP | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_068_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2013 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
Y3-069 4549810 | NIPS-PJM |  | N/A | N/A | Confirmed |  | 233 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4549810_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4549810_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/2/2013 | 6/1/2017 | 1/1/2024 | [6 empty] | FF | No
Y3-070 4549811 | NIPS-PJM |  | N/A | N/A | Withdrawn |  | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4549811_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/2/2013 | 1/1/2015 | 1/1/2024 |  | 6/10/2013 |  |  |  |  | FF | No
Y3-071 4549812 | NIPS-PJM |  | N/A | N/A | Withdrawn |  | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4549812_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/2/2013 | 1/1/2015 | 1/1/2024 |  | 6/10/2013 |  |  |  |  | FF | No
Y3-072 4549813 | NIPS-PJM |  | N/A | N/A | Confirmed |  | 233 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4549813_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4549813_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/2/2013 | 6/1/2017 | 1/1/2024 | [6 empty] | FF | No
Y3-073 | W.H. Zimmer Station |  | OH | Clermont | Withdrawn | DEOK | 1350 | 50 | 50 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3073_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/10/2013 | N/A | N/A |  | 2/24/2016 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
Y3-074 | Ashton 480V |  | MD | Montgomery | In Service | BGE | 0.372 | 0.372 | 0 | 0.37 | Energy | Generation Interconnection | Hydro |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3074_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/12/2013 | N/A | N/A |  |  |  | 7/1/2014 | 7/1/2014 | 10/1/2014 | Y | No
Y3-075 4553095 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2015 | 6/1/2016 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-076 4553097 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2016 | 6/1/2021 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-077 4553099 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [9 empty] | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2016 | 6/1/2021 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-078 4553101 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 500 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2016 | 6/1/2021 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-079 4553350 | DUK-PJM |  | N/A | N/A | Retracted |  | 409 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/16/2013 | 6/1/2017 | 6/1/2022 |  | 5/7/2013 |  |  |  |  | FF | No
Y3-080 | Tait 69kV | AES Tait Energy Storage | OH | Montgomery | Deactivated | Dayton | 20 | 8 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3080_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_080_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/19/2013 | N/A | N/A |  |  |  | 3/27/2014 | 3/27/2014 | 9/24/2013 | N | No
Y3-081 |  |  | OH | Adams | Withdrawn | ATSI | 0.11 |  |  |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2013 | N/A | N/A |  | 4/25/2013 |  |  |  |  | N | No
Y3-082 | Easton-Trappe Tap 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y3082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y3_082_csa.pdf | Document Posted | N/A | N/A |  | 4/19/2013 | N/A | N/A |  |  |  | 6/1/2014 |  | 1/29/2016 | S | No
Y3-083 4554680 | MECS-PJM |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4554680_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4554680_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/22/2013 | 6/1/2016 | 6/1/2017 |  | 5/12/2015 |  |  |  |  | FF | No
Y3-084 4555130 | AMIL-PJM |  | N/A | N/A | Retracted |  | 4 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4555130_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/24/2013 | 6/1/2014 | 6/1/2019 |  | 6/11/2013 |  |  |  |  | FF | No
Y3-085 4555141 | AMIL-PJM |  | N/A | N/A | Retracted |  | 4 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4555141_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/24/2013 | 6/1/2014 | 6/1/2019 |  | 6/11/2013 |  |  |  |  | FF | No
Y3-086 4555143 | MEC-PJM |  | N/A | N/A | Retracted |  | 4 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4555143_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/24/2013 | 6/1/2014 | 6/1/2019 |  | 6/11/2013 |  |  |  |  | FF | No
Y3-087 | Beaverbrook 13kV | Beaverbrook (Kinsley Solar) | NJ | Gloucester | In Service | PSEG | 3.8 | 3.8 | 1.44 | 3.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3087_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_087_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 6/30/2015 |  | 1/14/2015 | N | No
Y3-088 | Kendall I | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1158.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_088_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-089 | Kendall II | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1178.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-090 | Kendall III | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1198.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_090_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-091 | Kendall IV | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1218.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3091_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_091_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-092 | Erie West 345kV | ITC Lake Erie Connector | PA | Erie | Withdrawn | PENELEC | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 1000; NF/TWR 1000 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y3092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/y3_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y3_092_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2013 | N/A | N/A |  | 8/6/2022 |  | 3/31/2024 | 3/31/2024 |  | S | No
Y3-093 | Erie West 345kV |  | PA | Erie | Withdrawn | PENELEC | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 1000; F/TWR 1000 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3093_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2013 | N/A | N/A |  | 10/9/2013 | Customer Initiated Withdrawal | 1/1/2017 | 1/1/2017 |  | S | No
Y3-094 4556115 | CIN-PJM |  | N/A | N/A | Annulled |  | 223 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4556115_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4556115_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/29/2013 | 6/1/2017 | 6/1/2022 |  | 8/23/2016 |  |  |  |  | FF | No
Y3-095 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 5/24/2013 | Customer Initiated Withdrawal | 9/25/2013 |  |  | N | No
Y3-096 | Hanging Rock 765kV |  | OH | Lawrence | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 4/23/2015 | Customer Initiated Withdrawal | 3/31/2015 | 3/31/2015 |  | N | No
Y3-097 | Trent (Jug St.) 34.5kV |  | OH | Delaware | Deactivated | AEP | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3097_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 9/30/2015 |  |  | N | Yes
Y3-098 | Printz |  | PA | Delaware | Withdrawn | PECO | 735 | 735 | 735 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 9/26/2013 | Customer Initiated Withdrawal | 10/1/2017 |  |  | N | No
Y3-099 | Beckjord 2 MW-1 | Beckjord Battery #1 | OH | Clermont | In Service | DEOK | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_099_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2013 | N/A | N/A |  |  |  | 5/1/2015 | 5/1/2015 | 1/21/2015 | N | No
Y3-100 | Beckjord 2 MW-2 | Beckjord Battery #2 | OH | Clermont | Deactivated | DEOK | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_100_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2013 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
Y3-101 | Cedar 12kV |  | NJ | Ocean | Withdrawn | AEC | 5.7 | 5.7 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 9/30/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Y3-102 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 1000 | 166 | 135 | 166 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_102_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 8/21/2017 | 8/21/2017 | 7/27/2017 | N | No
Y3-103 | Valley-Raccoon 138kV | Pennsylvania Chemicals Generating Facility | PA | Beaver | In Service | DL | 205 | 205 | 97 | 205 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_103_csa.pdf | Document Posted | N/A | N/A | 11/12/2019 | 4/30/2013 | N/A | N/A | 6/1/2021 |  |  | 11/30/2021 | 11/30/2021 | 6/22/2021 | N | No
Y3-104 | Sullivan Trail-Stanton 69kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3104_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3104_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 1/22/2015 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
Y3-105 | Belvidere-Gilbert-115kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3105_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
Y3-106 | Belleville-Rutland 138kV | Belleville Hydroelectric Plant | WV | Wood | In Service | AEP | 49 | 7 | 7 | 3 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3106_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_106_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 12/31/2014 | N | No
Y3-107 | Bergen 230kV |  | NJ | Bergen | In Service | PSEG | 1220 | 35 | 45 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_107_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 4/1/2015 |  | 10/29/2015 | N | No
Y3-108 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 1420 | 110 | 107 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3108_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 11/20/2013 | Customer Initiated Withdrawal | 3/1/2014 |  |  | N | No
Y3-109 | Nyswaner 25kV | Red Glen Generator | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3109_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3109_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 1/25/2018 |  | 12/31/2016 | 12/31/2016 |  | N | Yes
Y3-110 | North Salisbury-Worcester 69kV |  | MD | Wicomico | Withdrawn | DPL | 15.7 | 15.7 | 15.7 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 10/9/2013 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Y3-111 | Harborcreek Township 34kV |  | PA | Erie | Withdrawn | PENELEC | 18.7 | 18.7 | 2.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 9/22/2013 | Customer Milestone Not Met | 4/1/2014 |  |  | N | No
Y3-112 | Butler-Shanor Manor 138kV |  | PA | Armstrong | Withdrawn | APS | 43 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3112_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 4/25/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | S | No
Y3-113 | Russell Hill-W. Meshoppen |  | PA | Wyoming | Withdrawn | PENELEC | 10 | 3.4 | 3.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3113_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 7/25/2013 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
Y3-114 |  |  | PA | Adams | Withdrawn | PENELEC | 19.9 |  |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 4/30/2013 | Customer Initiated Withdrawal |  |  |  | N | No
Y3-115 4556438 | PJM-WEC |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4556438_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4556438_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 5/1/2014 |  |  |  |  | FF | No
Y3-116 4556441 | PJM-AMIL |  | N/A | N/A | Retracted |  | 75 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4556441_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 7/10/2013 |  |  |  |  | FF | No
Y3-117 4556443 | PJM-NIPS |  | N/A | N/A | Retracted |  | 175 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4556443_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 7/10/2013 |  |  |  |  | FF | No
Y3-118 4556445 | PJM-AMIL |  | N/A | N/A | Retracted |  | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4556445_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 7/10/2013 |  |  |  |  | FF | No
Y3-119 | E. Lynchburg-Peaks View 34.5kV |  | VA | City of Lynchburg | Withdrawn | AEP | 19 | 19 | 7 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3119_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 11/12/2014 | Customer Milestone Not Met | 9/30/2015 |  |  | N | Yes
Y3-120 | Conowingo 230kV |  | MD | Harford | Withdrawn | PECO | 617 | 45 | 45 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 9/27/2013 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-001 | Blairsville East-Social Hall 138kV |  | PA | Westmoreland | Withdrawn | APS | 15.69 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2013 | N/A | N/A |  | 9/3/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | S | No
Z1-002 4558624 | DUK-PJM |  | N/A | N/A | Retracted |  | 409 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4558624_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/8/2013 | 6/1/2017 | 6/1/2022 |  | 7/30/2013 |  |  |  |  | FF | No
Z1-003 4558888 | NYIS-PJM |  | N/A | N/A | Retracted |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/9/2013 | 1/1/2016 | 1/1/2023 |  | 5/30/2013 |  |  |  |  | FF | No
Z1-004 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2013 | N/A | N/A |  | 5/14/2013 | Queue Not Required |  |  |  | S | No
Z1-005 4559728 | ALTE-PJM |  | N/A | N/A | Retracted |  | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4559728_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/13/2013 | 6/1/2014 | 6/1/2015 |  | 7/30/2013 |  |  |  |  | FF | No
Z1-006 | NIPSCO-BOCGASE2 |  | N/A | N/A | Withdrawn | AEP | 25 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z1006_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2014 | N/A | N/A |  | 5/29/2015 |  |  |  |  | EE | No
Z1-007 4561037 | CIN-PJM |  | N/A | N/A | Annulled |  | 87 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4561037_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4561037_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2017 | 6/1/2022 |  | 2/21/2017 |  |  |  |  | FF | No
Z1-008 4561044 | LGEE-PJM |  | N/A | N/A | Retracted |  | 59 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2016 | 6/1/2021 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-009 4561079 | NIPS-PJM |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 1/1/2015 | 1/1/2023 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-010 4561082 | NIPS-PJM |  | N/A | N/A | Retracted |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2017 | 6/1/2023 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-011 4561084 | CIN-PJM |  | N/A | N/A | Retracted |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2016 | 6/1/2023 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-012 4561085 | CIN-PJM |  | N/A | N/A | Retracted |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 1/1/2016 | 1/1/2023 |  | 6/7/2013 |  |  |  |  | FF | No
Z1-013 4561088 | AMIL-PJM |  | N/A | N/A | Retracted |  | 44 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2016 | 6/1/2022 |  | 6/7/2013 |  |  |  |  | FF | No
Z1-014 4561089 | ALTE-PJM |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/17/2013 | 1/1/2016 | 1/1/2021 |  | 6/7/2013 |  |  |  |  | FF | No
Z1-015 | Springdale 3, 4, 5 | Springdale | PA | Allegheny | In Service | APS | 590 | 0 | 26 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/21/2015 | N | No
Z1-016 | Hanna-Juniper 345kV |  | OH | Portage | Withdrawn | ComEd | 140 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2013 | N/A | N/A |  | 6/13/2013 | Queue Not Required |  |  |  | S | No
Z1-017 | Limerick-Peach Bottom |  | PA | Montgomery | Withdrawn | PECO | 181 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/z1017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2013 | N/A | N/A |  | 2/20/2014 | Customer Milestone Not Met | 6/1/2014 |  |  | S | No
Z1-018 | Richland III 138kV |  | OH | Defiance | Withdrawn | ATSI | 591 | 591 | 591 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2013 | N/A | N/A |  | 4/1/2014 | Customer Initiated Withdrawal | 5/15/2016 |  |  | N | No
Z1-019 4566427 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4566427_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4566427_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/5/2013 | 1/1/2016 | 1/1/2023 |  | 6/18/2018 |  |  |  |  | FF | No
Z1-020 | Richland I 138kV |  | OH | Defiance | Withdrawn | ATSI | 48 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2013 | N/A | N/A |  | 4/22/2014 | Customer Milestone Not Met | 4/30/2014 |  |  | N | No
Z1-021 | Richland II 138kV |  | OH | Defiance | Withdrawn | ATSI | 390 | 36 | 36 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2013 | N/A | N/A |  | 4/22/2014 | Customer Milestone Not Met | 4/30/2014 |  |  | N | No
Z1-022 | Stryker 138kV |  | OH | Defiance | Withdrawn | ATSI | 22 | 5 | 5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2013 | N/A | N/A |  | 4/1/2014 | Customer Initiated Withdrawal | 4/30/2014 |  |  | N | No
Z1-023 4566738 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4566738_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4566738_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/6/2013 | 1/1/2016 | 1/1/2024 |  | 5/12/2014 |  |  |  |  | FF | No
Z1-024 4566952 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/7/2013 |  |  |  | 6/30/2013 |  |  |  |  | FF | No
Z1-025 4566958 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 206 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4566958_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4566958_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/7/2013 | 6/1/2017 | 6/1/2022 |  | 2/1/2019 |  |  |  |  | FF | No
Z1-026 4566959 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/7/2013 |  |  |  | 6/30/2013 |  |  |  |  | FF | No
Z1-027 4566961 | NIPS-PJM |  | N/A | N/A | Confirmed |  | 124 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4566961_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4566961_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/7/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-028 4566962 | NIPS-PJM |  | N/A | N/A | Withdrawn |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/7/2013 |  |  |  | 6/30/2013 |  |  |  |  | FF | No
Z1-029 4567977 | CIN-PJM |  | N/A | N/A | Annulled |  | 59 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4567977_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4567977_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/11/2013 | 6/1/2016 | 6/1/2021 |  | 2/21/2017 |  |  |  |  | FF | No
Z1-030 | Bay Shore 138kV |  | OH | Lucas | Withdrawn | ATSI | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2013 | N/A | N/A |  | 4/1/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Z1-031 | Lake Nelson-Middlesex 230kV |  | NJ | Unknown | Withdrawn | JCPL | 56 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/z1031_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/25/2013 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 7/31/2014 |  |  | S | No
Z1-032 4571836 | PJM-IPL |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 4/1/2015 | 4/1/2020 | [6 empty] | FF | No
Z1-033 | Hudson 230kV |  | NJ | Unknown | Withdrawn | PSEG | 400 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 400; F/TWR 410 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/2013 | N/A | N/A |  | 12/18/2013 | Customer Initiated Withdrawal | 10/30/2017 |  |  | S | No
Z1-034 | Niles 138kV |  | OH | Trumbull | Withdrawn | ATSI | 217 | 217 | 217 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2013 | N/A | N/A |  | 7/31/2013 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Z1-035 | Lake Road 11.5 kV |  | OH | Unknown | Withdrawn | ATSI | 18 | 18 | 2.34 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1035_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/5/2013 | N/A | N/A |  | 2/7/2022 |  | 9/30/2017 |  |  | N | No
Z1-036 | WinFall-Chowan 230kV | Timbermill Wind Farm | NC | Perquimans | In Service | Dominion | 189 | 189 | 24.5 | 189 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1036_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_036_csa.pdf | Document Posted | N/A | N/A | 11/5/2024 | 7/23/2013 | N/A | N/A | 11/8/2024 |  |  | 3/31/2025 | 3/31/2025 | 12/13/2024 | N | No
Z1-037 | Krendale-Shanor Manor 138kV |  | PA | Butler | Withdrawn | APS | 43 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/z1037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/25/2013 | N/A | N/A |  | 5/6/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | S | No
Z1-038 | Florey Knob 34.5kV | Florey Knob Generating Station | PA | Wyoming | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_038_csa.pdf | Document Posted | N/A | N/A |  | 8/1/2013 | N/A | N/A |  | 2/21/2019 |  | 3/31/2017 | 3/31/2017 |  | N | No
Z1-039 4582175 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 260 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/6/2013 | 6/1/2017 | 6/1/2023 | [6 empty] | FF | No
Z1-040 4582207 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 260 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/6/2013 | 1/1/2017 | 1/1/2022 |  | 8/22/2013 |  |  |  |  | FF | No
Z1-041 | Rock Springs 500kV | Rock Springs Units #1 & #2 | MD | Cecil | In Service | Essential Power | 327 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_041_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/14/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 5/28/2015 | N | No
Z1-042 | Belleville/New Holland-Logan 46kV |  | PA | Mifflin | Withdrawn | PENELEC | 46 | 46 | 9.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/16/2013 | N/A | N/A |  | 11/3/2014 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
Z1-043 4585350 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 260 | 260 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4585350_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4585350_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/22/2013 | 6/1/2017 | 6/1/2022 |  | 10/18/2019 |  |  |  |  | FF | No
Z1-044 4586363 | PJM-MECS |  | N/A | N/A | Withdrawn |  | 894 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/27/2013 | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
Z1-045 4586409 | PJM-MECS |  | N/A | N/A | Retracted |  | 894 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4586409_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4586409_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/27/2013 | 6/1/2016 | 6/1/2021 |  | 6/11/2014 |  |  |  |  | FF | No
Z1-046 4586438 | TVA-PJM |  | N/A | N/A | Confirmed |  | 240 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4586438_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4586438_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/27/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-047 | Albright |  | PA | Mifflin | Withdrawn | PENELEC | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2013 | N/A | N/A |  | 4/23/2014 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
Z1-048 | Rivesville |  | WV | Marion | Withdrawn | APS | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2013 | N/A | N/A |  | 4/28/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Z1-049 | Willow Island |  | WV | Pleasants | Withdrawn | APS | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2013 | N/A | N/A |  | 4/23/2014 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
Z1-050 | Kittatinny 230kV | Yards Creek Pumped Storage Hydro-electric Generating Station | NJ | Warren | In Service | JCPL | 420 | 20 | 20 | 20 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 3/1/2014 |  | 5/1/2014 | N | No
Z1-051 | DC Cook Unit 2 | D.C. Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 1192 | 102 | 83 | 102 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 11/18/2016 | 11/18/2016 | 1/14/2017 | N | No
Z1-052 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 800 | 64.5 | 44.5 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_052_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 8/15/2018 | 8/15/2018 | 7/23/2018 | N | No
Z1-053 | Monocacy 12.47 KV - Worman Mill Feeder |  | MD | Frederick | Withdrawn | APS | 0.3 | 0.3 | 0 | 20 | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/5/2013 | N/A | N/A |  | 9/25/2013 | Customer Initiated Withdrawal | 4/15/2014 |  |  | Y | No
Z1-054 | Byron-Cherry Valley |  | IL | Ogle | Withdrawn | ComEd | 26 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/z1054_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2013 | N/A | N/A |  | 4/9/2015 | Customer Initiated Withdrawal | 9/30/2014 |  |  | S | No
Z1-055 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 714 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1055_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_055_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/11/2013 | N/A | N/A |  |  |  | 6/1/2016 |  | 1/31/2017 | N | No
Z1-056 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 720 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/11/2013 | N/A | N/A |  |  |  | 6/1/2016 |  | 1/31/2017 | N | No
Z1-057 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 252 | 0 | 15.9 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_057_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 10/1/2013 |  | 5/6/2014 | N | No
Z1-058 | Linden 1 - 138kV | Linden Generating Station | NJ | Union | In Service | PSEG | 491 | 23 | 36 | 23 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1058_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 8/29/2016 | N | No
Z1-059 | Linden 2 - 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 800 | 23 | 18 | 23 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_059_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/29/2016 | N | No
Z1-060 4593055 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 101 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4593055_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/30/2013 | 6/1/2018 | 6/1/2023 |  | 12/10/2013 |  |  |  |  | FF | No
Z1-061 4593064 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 61 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4593064_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/30/2013 | 6/1/2018 | 6/1/2023 |  | 12/10/2013 |  |  |  |  | FF | No
Z1-062 4593068 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 139 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4593068_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/30/2013 | 6/1/2018 | 6/1/2023 |  | 12/10/2013 |  |  |  |  | FF | No
Z1-063 | Kirk 34.5kV |  | OH | Licking | Withdrawn | AEP | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1063_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  | 10/5/2016 | Customer Milestone Not Met | 12/31/2016 | 12/31/2016 |  | N | Yes
Z1-064 | Shannon 13.2kV |  | OH | Franklin | Withdrawn | AEP | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1064_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  | 10/5/2016 | Customer Milestone Not Met | 12/31/2016 | 12/31/2016 |  | N | Yes
Z1-065 | Wiley 34.5kV | Willey Energy Storage Project | OH | Hamilton | In Service | DEOK | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_065_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2013 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/1/2015 | N | Yes
Z1-066 | Arnold 115kV | Green Mountain Battery | PA | Somerset | In Service | PENELEC | 10.4 | 10.4 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1066_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  |  |  | 3/1/2016 | 3/1/2016 | 12/30/2015 | N | No
Z1-067 4593370 | DUK-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4593370_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4593370_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/1/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-068 | Birdneck 34.5kV |  | VA | City of Virginia Beach | In Service | Dominion | 12 | 12 | 1.5 | 12 | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1068_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1068_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/10/2013 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 | 9/26/2020 | N | Yes
Z1-069 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 70 | 70 | 13.3 | 70 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_069_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2013 | N/A | N/A | 8/22/2019 |  |  | 10/31/2019 | 10/31/2019 | 11/20/2019 | N | No
Z1-070 4598661 | AMIL-PJM |  | N/A | N/A | Retracted |  | 1045 | 1045 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4598661_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4598661_ltf2.pdf | Executed Agreement and/or Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-3/4598661_ltf3.pdf | Executed Agreement and/or Study | https://www.pjm.com/pjmfiles/N/A | N/A | N/A |  | Withdrawn |  | Withdrawn |  | 10/25/2013 | 6/1/2017 | 6/1/2022 |  | 6/28/2016 |  |  |  |  | FF | No
Z1-071 4598677 | TVA-PJM |  | N/A | N/A | Confirmed |  | 82 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4598677_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4598677_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/25/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-072 | Crescent Ridge | Crescent Ridge Wind Farm | IL | Bureau | In Service | ComEd | 54.45 | 0 | 9.7 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 6/1/2016 | N | No
Z1-073 | Mendota Hills |  | IL | Lee | In Service | ComEd | 50.4 | 0 | 5.2 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1073_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_073_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 8/5/2015 | N | No
Z1-074 | Garrett-Jenning 34.5kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2013 | N/A | N/A |  | 4/23/2014 | Customer Milestone Not Met | 12/18/2015 |  |  | N | No
Z1-075 4599518 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
Z1-076 | Stockton 1 69kV |  | MD | Worcester | Withdrawn | DPL | 14 | 14 | 5.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1076_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 7/25/2017 | Customer Initiated Withdrawal | 6/30/2018 | 6/30/2018 |  | N | No
Z1-077 | Stockton 2 69kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 7/25/2017 | Customer Initiated Withdrawal | 6/30/2018 | 6/30/2018 |  | N | No
Z1-078 | Broadford-Jackson Ferry Phase II 765kV |  | VA | Unknown | Withdrawn | AEP | 777 | 777 | 777 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 11/10/2014 | Customer Initiated Withdrawal | 6/15/2018 |  |  | N | No
Z1-079 | Todhunter-Foster 345kV | Middletown Energy Center | OH | Butler | In Service | DEOK | 513 | 513 | 513 | 513 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_079_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 6/1/2018 |  | 2/6/2018 | N | No
Z1-080 | Clinton County 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1080_fea.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_080_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 8/29/2016 | N | Yes
Z1-081 | Church 25kV | Sunfish Solar Project | MD | Queen Anne's | Withdrawn | DPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1081_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1081_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/3/2017 | Customer Initiated Withdrawal | 7/15/2017 | 7/15/2017 |  | N | Yes
Z1-082 | Lawnside 13kV | Lawnside Battery | NJ | Camden | In Service | PSEG | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1082_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 8/1/2014 | 8/1/2014 | 1/13/2015 | Y | Yes
Z1-083 | Salem Unit 1-PSEG Zone |  | NJ | Salem | Withdrawn | PSEG | 300 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z1083_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 9/2/2015 |  |  |  |  | EE | No
Z1-084 | Quad Cities 1-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 475 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z1084_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z1-085 | Quad Cities 2-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 525 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z1085_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z1-086 | Heritage-Carson | Greensville Generating Facility | VA | Greensville | In Service | Dominion | 1681 | 1681 | 1630 | 1681 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_086_csa.pdf | Document Posted | N/A | N/A | 1/21/2018 | 10/30/2013 | N/A | N/A | 7/20/2018 |  |  | 6/1/2019 | 6/1/2019 | 12/8/2018 | N | No
Z1-087 | Glade 230kV | Seneca Pumped Storage Generating Station | PA | Warren | In Service | PENELEC | 485 | 17 | 17 | 13 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_087_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 4/21/2017 | N | No
Z1-088 | Allegheny Dam 5 | Allegheny River Lock & Dam # 5 | PA | Armstrong | In Service | APS | 8 | 0 | 5 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1088_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_088_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 3/25/2015 | N | No
Z1-089 | Allegheny Dam 6 138kV | Allegheny River Lock & Dam #6 | PA | Armstrong | In Service | APS | 9 | 0 | 5 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1089_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 3/25/2015 | N | No
Z1-090 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 1024 | 381 | 381 | 381 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_090_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/24/2018 | N | No
Z1-091 | Lenox 34kV | Hop Bottom Generating Station | PA | Lackawanna | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1091_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1091_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 12/15/2018 |  | 3/31/2017 | 3/31/2017 |  | N | No
Z1-092 | Milan 34kV | Milan Energy | PA | Lackawanna | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_092_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A | 2/20/2017 |  |  | 2/2/2017 | 2/2/2017 | 2/20/2017 | N | No
Z1-093 | Woodville Battery 34.5kV |  | OH | Sandusky | Withdrawn | ATSI | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1093_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 10/31/2014 | Customer Initiated Withdrawal | 12/30/2014 |  |  | N | No
Z1-094 | Jugg 34.5kV |  | OH | Licking | Withdrawn | AEP | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 10/5/2016 | Customer Milestone Not Met | 5/18/2018 | 5/18/2018 |  | N | Yes
Z1-095 | North Woodcock 34.5kV |  | OH | Allen | Withdrawn | AEP | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/27/2015 | Customer Initiated Withdrawal | 12/30/2014 |  |  | N | No
Z1-096 | Trenton 26kV | Parkland Solar | NJ | Burlington | In Service | PSEG | 7.84 | 7.84 | 2.98 | 7.84 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1096_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1096_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/15/2014 |  | 1/14/2015 | N | Yes
Z1-097 | Adkins 345kV | Darby Generating Station Unites, 1,2,3,4,5,6 | OH | Madison | In Service | AEP | 564 | 0 | 30 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_097_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 12/15/2014 | N | No
Z1-098 | Peckville-Jackson 69kV | Valley View Flywheel Station | PA | Lackawanna | Withdrawn | PPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1098_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1098_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_098_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_098_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 11/6/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | Yes
Z1-099 | North Street 69kV | City of Dover Generating Facilities | DE | Kent | In Service | DPL | 182 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 9/22/2016 | N | No
Z1-100 | Oak Hall | Oak Hal lProject A | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_100_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
Z1-101 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_101_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
Z1-102 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1102_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_102_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
Z1-103 | Oak Hall |  | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_103_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
Z1-104 | Somerset County 25kV |  | MD | Somerset | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 4/30/2013 |  |  | N | No
Z1-105 | Emlenton 34.5kV |  | PA | Clarion | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1105_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 2/27/2015 | Customer Initiated Withdrawal | 7/1/2015 |  |  | N | Yes
Z1-106 | West Chicago 34kV | West Chicago Energy Storage | IL | Du Page | Deactivated | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1106_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 9/22/2015 | N | Yes
Z1-107 | Joliet 34kV |  | IL | Will | Deactivated | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1107_fea.pdf | Document Posted |  |  |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1107_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 8/26/2015 | N | Yes
Z1-108 | McHenry 34kV | McHenry Energy Storage | IL | McHenry | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1108_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1108_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1108_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/17/2015 | N | Yes
Z1-109 | Tosco-VFT 230kV |  | NJ | Union | Withdrawn | PSEG | 208 | 208 | 208 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1109_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1109_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 3/16/2016 | Customer Initiated Withdrawal | 6/30/2016 |  |  | N | No
Z1-110 | Grover 34kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1110_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/5/2016 | 10/31/2013 | N/A | N/A | 5/5/2016 |  |  | 12/31/2016 | 12/31/2016 | 6/7/2016 | N | No
Z1-111 4600025 | AMIL-PJM |  | N/A | N/A | Retracted |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4600025_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2013 | 1/1/2015 | 1/1/2017 |  | 1/16/2014 |  |  |  |  | FF | No
Z1-112 4600034 | MEC-PJM |  | N/A | N/A | Withdrawn |  | 108 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4600034_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4600034_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/31/2013 | 6/1/2015 | 6/1/2020 |  | 5/30/2019 |  |  |  |  | FF | No
Z1-113 | West Winchester 13kV | HP Hood Generation Facility | VA | Rockingham | In Service | APS | 12 | 12 | 5 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1113_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 3/30/2015 | 3/30/2015 | 5/11/2015 | N | Yes
Z1-114 | Oxford 13kV |  | PA | York | Withdrawn | ME | 6 | 6 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1114_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | Yes
Z1-115 | Crescentville 13kV |  | PA | Philadelphia | Withdrawn | PECO | 2 | 2 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1115_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/13/2014 | Customer Milestone Not Met | 12/31/2014 |  |  | N | Yes
Z1-116 | Metuchen 230kV | CPV Keasbey Energy Center | NJ | Middlesex | Withdrawn | PSEG | 675 | 675 | 671 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1116_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1116_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_116_csa.pdf | Document Posted | N/A | N/A | 8/1/2026 | 10/31/2013 | N/A | N/A | 1/1/2027 | 10/2/2023 |  | 1/1/2027 | 1/1/2027 |  | N | No | This project slid to the next queue
Z1-117 | Pocomoke 1 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1117_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-118 | Pocomoke 2 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1118_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-119 | Pocomoke 3 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1119_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-120 | Loretto 1 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-121 | Loretto 2 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1121_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-122 | Loretto 3 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1122_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-123 | Piney Grove 1 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-124 | Piney Grove 2 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1124_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-125 | Piney Grove 3 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1125_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-126 | Piney Grove 4 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1126_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-127 | University Park |  | IL | Will | In Service | ComEd | 320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 2/10/2014 | N | No
Z2-001 | Burlington 26 kV | Recovery Road Solar Farm | NJ | Burlington | Withdrawn | PSEG | 7.1 | 7.1 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2001_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/1/2013 | N/A | N/A |  | 3/29/2018 |  | 6/30/2018 | 6/30/2018 |  | N | No
Z2-002 | Linden 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 1049 | 61 | 54 | 61 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2002_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2002_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_002_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 5/16/2018 | N | No
Z2-003 4601556 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 299 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/7/2013 | 7/1/2014 | 7/1/2015 | [6 empty] | FF | No
Z2-004 | Mantua Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2004_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2013 | N/A | N/A |  | 9/24/2014 | Customer Initiated Withdrawal | 8/4/2014 |  |  | N | Yes
Z2-005 4604093 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/19/2013 | 1/1/2015 | 1/1/2022 |  | 12/12/2013 |  |  |  |  | FF | No
Z2-006 4604623 | PJM-MECS |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/20/2013 | 3/1/2015 | 3/1/2023 |  | 12/14/2013 |  |  |  |  | FF | No
Z2-007 | East Palmerton-Harwood 230kV |  | PA | Carbon | Withdrawn | PPL | 212.5 | 212.5 | 27 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/2013 | N/A | N/A |  | 10/1/2014 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
Z2-008 | East Palmerton-Wagner 69kV |  | PA | Carbon | Withdrawn | PPL | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2013 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
Z2-009 | East Hazelton-Harwood 69kV |  | PA | Luzerne | Withdrawn | PPL | 52 | 52 | 6.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2009_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/23/2013 | N/A | N/A |  | 1/14/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Z2-010 4612032 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4612032_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/24/2013 | 1/1/2014 | 1/1/2020 |  | 3/13/2014 |  |  |  |  | FF | No
Z2-011 | Canton 34.5kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2011_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2011_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_011_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_011_csa.pdf | Document Posted | N/A | N/A | 2/20/2017 | 12/30/2013 | N/A | N/A | 2/27/2017 |  |  | 6/30/2017 | 6/30/2017 | 2/27/2017 | N | No
Z2-012 | Weirwood-Eastville 69kV | Hecate Energy Cherrydale | VA | Northampton | In Service | ODEC | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2012_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_012_csa.pdf | Document Posted | N/A | N/A |  | 12/31/2013 | N/A | N/A |  |  |  | 4/1/2017 | 4/1/2017 | 9/7/2017 | N | No
Z2-013 | Frostburg 138kV | Twin Ridges Wind Farm | PA | Somerset | In Service | APS | 139.4 | 0 | 4.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_013_csa.pdf | Document Posted | N/A | N/A |  | 1/9/2014 | N/A | N/A |  |  |  | 12/31/2014 |  | 12/15/2014 | N | No
Z2-014 | St. Benedict-Patton | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30.6 | 0 | 1.35 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/9/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 2/13/2015 | N | No
Z2-015 | Dans Mountain 138kV |  | PA | Allegheny | Withdrawn | APS | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/15/2014 | N/A | N/A |  | 2/12/2014 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
Z2-016 | Blairsville-Social Hall 138kV |  | PA | Westmoreland | Withdrawn | PENELEC | 15.69 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z2016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | S | No
Z2-017 | Bristers Ox 500kV |  | VA | Unknown | In Service | Dominion | 237 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 733 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/z2017_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/z2_017_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 3/25/2015 | S | No
Z2-018 | South Canton-Harmon 345kV |  | OH | Unknown | Withdrawn | ATSI | 82 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2014 | N/A | N/A |  | 4/21/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
Z2-019 | Fairborn 12.47kV | Dovetail Biogas Facility | OH | Greene | Withdrawn | ATSI | 0.85 | 0.85 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2019_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2019_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/7/2014 | N/A | N/A |  | 7/7/2015 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | Y | No
Z2-020 | New Franklin 12.47kV |  | OH | Summit | Withdrawn | ATSI | 0.85 | 0.85 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2020_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/7/2014 | N/A | N/A |  | 11/10/2017 |  | 6/30/2015 | 6/30/2015 |  | Y | No
Z2-021 4626426 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
Z2-022 4626428 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
Z2-023 4626437 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/11/2014 | 6/1/2014 | 6/1/2015 | [6 empty] | FF | No
Z2-024 4626439 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/11/2014 | 6/1/2014 | 6/1/2015 | [6 empty] | FF | No
Z2-025 4626594 | PJM-MECS |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/12/2014 | 1/1/2015 | 1/1/2016 | [6 empty] | FF | No
Z2-026 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2014 | N/A | N/A |  | 4/8/2016 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
Z2-027 | Pasquotank 34.5kV | Elizabeth City Solar Park | NC | Pasquotank | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_027_csa.pdf | Document Posted | N/A | N/A |  | 2/20/2014 | N/A | N/A |  |  |  | 2/15/2015 | 2/15/2015 | 12/31/2014 | N | No
Z2-028 | Highland-Sammis 345kV & Highland-Mansfield 345kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 800 | 800 | 800 | 800 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2028_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_028_csa.pdf | Document Posted | N/A | N/A | 9/12/2017 | 2/21/2014 | N/A | N/A | 12/22/2017 |  |  | 12/28/2018 | 12/28/2018 | 8/15/2018 | N | No
Z2-029 | Stuart 4 | Stuart Electric Generating Station | OH | Brown | Deactivated | Dayton | 585 | 20.5 | 20.5 | 20.5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_029_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/25/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 10/1/2015 | N | No
Z2-030 | Double Toll Gate 34.5kV | Double Tollgate Solar Project | VA | Clarke | In Service | APS | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2030_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/26/2014 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 7/12/2017 | N | No
Z2-031 4630443 | PJM-MECS |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/26/2014 | 6/1/2015 | 6/1/2023 |  | 3/19/2014 |  |  |  |  | FF | No
Z2-032 | Clean River Power MR-1 (Devola) |  | OH | Washington | Withdrawn | AEP | 5.21 | 5.21 | 5.21 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Z2-033 | Clean River Power MR-2 (Lowell) |  | OH | Washington | Withdrawn | AEP | 5.21 | 5.21 | 5.21 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2033_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-034 | Clean River Power MR-3 (Beverly) |  | OH | Washington | Withdrawn | AEP | 3.95 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2034_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Z2-035 | Clean River Power MR-5 (Malta) |  | OH | Morgan | Withdrawn | AEP | 3.95 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-036 | Clean River Power MR-6 (Rokeby) |  | OH | Morgan | Withdrawn | AEP | 3.95 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-037 | Clean River Power MR-7 (Philo) |  | OH | Muskingum | Withdrawn | AEP | 3.95 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-038 | Ridgeley-Frostburg 138kV | Dan's Mountain Solar Project | MD | Allegany | Withdrawn | APS | 19.9 | 19.9 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_038_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 12/22/2017 |  | 3/31/2018 | 3/31/2018 |  | N | No
Z2-039 | PF Hydro | Warren Hydro Station; Newport Hydro Station; Luray Hydro Station; Shenandoah Hydro Station | VA | Warren | In Service | APS | 4.61 | 0 | 2.82 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2039_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2014 | N/A | N/A |  |  |  | 5/31/2015 | 5/31/2015 | 5/13/2015 | N | No
Z2-040 | PF Hydro | Dam 4 Hydro Generation Facility; Dam 5 Hydro Generation Facility; Millville Hydroelectric Facility | WV | Jefferson | In Service | APS | 5.75 | 0 | 3.5 | 5.75 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2014 | N/A | N/A |  |  |  | 3/31/2014 |  | 4/17/2015 | N | No
Z2-041 | Silver Lake |  | IL | McHenry | Withdrawn | ComEd | 455 | 455 | 435 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2041_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 10/2/2014 | Customer Initiated Withdrawal | 5/1/2018 |  |  | N | No
Z2-042 | Wurno-Clayor 138kV |  | VA | Pulaski | Withdrawn | AEP | 180 | 180 | 23.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2042_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2014 | N/A | N/A |  | 10/25/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
Z2-043 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2043_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2043_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_043_csa.pdf | Document Posted | N/A | N/A |  | 3/5/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | Yes
Z2-044 | Whitakers 34.5kV | Whitakers Solar Park | NC | Nash | In Service | Dominion | 12 | 12 | 8.4 | 12 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_044_csa.pdf | Document Posted | N/A | N/A |  | 3/5/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | Yes
Z2-045 | Cedar Grove-Roseland 230kV |  | NJ | Unknown | Withdrawn | PSEG | 42 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-046 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 1050 | 900 | 1050 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_046_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 2/20/2018 | N | No
Z2-047 | Steel City 230kV |  | PA | Northampton | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2014 | N/A | N/A |  | 6/9/2014 | Customer Initiated Withdrawal | 7/1/2014 |  |  | S | No
Z2-048 | George Washington 138kV | Moundsville Power, LLC | WV | Marshall | Withdrawn | AEP | 545 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2048_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_048_csa.pdf | Document Posted | N/A | N/A |  | 3/26/2014 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
Z2-049 | Cedar Grove-Williams 230kV |  | NJ | Unknown | Withdrawn | PSEG | 21 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-050 | Easton-Trappe Tap 69kV |  | MD | Talbot | Withdrawn | DPL | 13 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-051 | Red Lion-Cedar Creek 230kV |  | DE | New Castle | Withdrawn | DPL | 83 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-052 | Preston-Tanyard 69kV |  | MD | Caroline | Withdrawn | DPL | 20 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-053 | Bridgewater-S. River |  | N/A | N/A | Withdrawn | PSEG | 156.1 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z2053_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-054 | Roseland-Williams 230kV |  | NJ | Unknown | Withdrawn | PSEG | 44 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-055 | Cedar Grove-Clifton 230kV |  | NJ | Unknown | Withdrawn | PSEG | 42 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-056 | Crossmans-Werner 34.5kV |  | NJ | Middlesex | In Service | JCPL | 20 | 0.5 | 0 | 0.5 | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 8/4/2016 | Y | No
Z2-057 4637968 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 35 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/31/2014 | 6/1/2015 | 6/1/2021 |  | 5/5/2014 |  |  |  |  | FF | No
Z2-058 4637969 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 6 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/31/2014 | 6/1/2015 | 6/1/2021 |  | 5/5/2014 |  |  |  |  | FF | No
Z2-059 4637970 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 37 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/31/2014 | 6/1/2015 | 6/1/2021 |  | 5/5/2014 |  |  |  |  | FF | No
Z2-060 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Withdrawn | PEPCO | 927 | 33 | 116 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_060_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2014 | N/A | N/A | 6/30/2023 | 12/23/2020 |  | 3/1/2022 | 3/1/2022 |  | N | No
Z2-061 | Spurlock-Zimmer 345kV |  | KY | Mason | Withdrawn | DEOK | 88 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2014 | N/A | N/A |  | 4/1/2014 |  |  |  |  | S | No
Z2-062 | Gloucester 26kV | Camden County Energy Recovery Associates | NJ | Camden | In Service | PSEG | 24.5 | 0 | 3 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_062_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/2/2014 | N/A | N/A |  |  |  | 5/1/2015 |  | 11/19/2014 | N | No
Z2-063 4639216 | PJM-WEC |  | WI | Unknown | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4639216_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4639216_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/7/2014 | 6/1/2017 | 6/1/2027 |  | 6/1/2015 |  |  |  |  | FF | No
Z2-064 | Smith-N. Fayette 138kV |  | PA | Washington | Withdrawn | APS | 651 | 651 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2064_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/10/2014 | N/A | N/A |  | 6/25/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
Z2-065 4641473 | CPLE-PJM |  | N/A | N/A | Annulled |  | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4641473_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4641473_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-066 4641474 | CPLE-PJM |  | N/A | N/A | Annulled |  | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4641474_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4641474_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-067 4641475 | CPLE-PJM |  | N/A | N/A | Annulled |  | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4641475_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4641475_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-068 4641477 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 87 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 |  | 4/24/2014 |  |  |  |  | FF | No
Z2-069 | Bridgewater-Hoboken |  | N/A | N/A | Withdrawn | PSEG | 105 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z2069_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-070 | Worcester-Ocean Pines 69kV |  | MD | Worcester | Withdrawn | DPL | 25 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
Z2-071 | Piney Grove-New Church 138kV |  | MD | Wicomico | Withdrawn | DPL | 55 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
Z2-072 | Indian River-New Church |  | N/A | N/A | Withdrawn | DPL | 204.6 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/z2072_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-073 | Chestertown West 25kV |  | MD | Kent | Withdrawn | DPL | 5 | 5 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2073_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-074 | Chestertown East 25kV |  | MD | Kent | Withdrawn | DPL | 6 | 6 | 4.03 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-075 | Lynch East 25kV |  | MD | Kent | Withdrawn | DPL | 5.5 | 5.5 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-076 | Worcester South 25kV | Worcester South | MD | Worcester | In Service | DPL | 2.64 | 2.64 | 1.76 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2076_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2076_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/22/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 5/29/2019 | N | Yes
Z2-077 | Worcester North 25kV | Worcester North | MD | Worcester | In Service | DPL | 5 | 5 | 3.33 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2077_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2077_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/22/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/15/2019 | N | No
Z2-078 4642907 | DUK-PJM |  | N/A | N/A | Annulled |  | 90 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4642907_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4642907_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/24/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-079 | Pleasant View - Edwards Ferry 230kV |  | VA | Loudoun | Withdrawn | Dominion | 31 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/25/2014 | N/A | N/A |  | 9/8/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
Z2-080 4643119 | PJM-NIPS |  | N/A | N/A | Retracted |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/25/2014 | 1/1/2015 | 1/1/2022 | [6 empty] | FF | No
Z2-081 | Streator 34.5kV | Livingston Landfill Gas to Energy Facility | IL | Livingston | In Service | ComEd | 13.3 | 13.3 | 13.3 | 12 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2081_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_081_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2014 | N/A | N/A |  |  |  | 12/1/2014 |  | 4/4/2017 | N | No
Z2-082 | Cape May County 12kV | Cape May County Municipal Utilities Authority Landfill | NJ | Cape May | Deactivated | AEC | 2 | 0 | 0.3 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 6/1/2015 | N | No
Z2-083 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 1104 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2083_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_083_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
Z2-084 | JK Smith 345kV |  | KY | Nelson | Withdrawn | EKPC | 207.8 | 207.8 | 207.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2014 | N/A | N/A |  | 10/7/2014 | Customer Milestone Not Met | 12/1/2016 |  |  | N | No
Z2-085 | Mahoning Valley Hydro 25kV | Mahoning Creek Hydroelectric Plant | PA | Clarion | In Service | APS | 7.5 | 1.5 | 1.5 | 7.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2085_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_085_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 11/1/2014 | 11/1/2014 | 10/10/2014 | N | No
Z2-086 |  |  | IL | Adams | Withdrawn | ComEd | 200 |  |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2014 | N/A | N/A |  | 5/21/2014 | Customer Milestone Not Met |  |  |  | N | No
Z2-087 | Pontiac MidPoint-Brokaw 345kV | Bright Stalk Generating Facility | IL | Livingston | In Service | ComEd | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_087_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2014 | N/A | N/A | 12/16/2019 |  |  | 12/30/2019 | 12/30/2019 | 12/16/2019 | N | No
Z2-088 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 80 | 30.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_088_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/21/2015 | N | No
Z2-089 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 568 | 541 | 568 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_089_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 5/2/2018 | N | No
Z2-090 | Blackhawk 12.5kV |  | IL | Winnebago | Withdrawn | ComEd | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2090_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2090_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 6/13/2016 | Customer Initiated Withdrawal | 10/1/2014 |  |  | N | Yes
Z2-091 | Woodsdale Road |  | OH | Butler | Withdrawn | DEOK | 36 | 36 | 36 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Z2-092 | Bennett-Farmingdale 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 4 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 10/1/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
Z2-093 | Hawks 12kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6.5 | 3.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/29/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Z2-094 | Washington-Mobile Chemical 34kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 7/15/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Z2-095 | Branchville-Sussex 34kV |  | NJ | Sussex | Withdrawn | JCPL | 20 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 10/1/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
Z2-096 | Lynch West 25kV |  | MD | Kent | Withdrawn | DPL | 10 | 10 | 7.07 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-097 | Church 25kV | Church | MD | Kent | Withdrawn | DPL | 5 | 5 | 3.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2097_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2097_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2097_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2097_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 3/5/2019 |  | 9/28/2019 | 9/28/2019 |  | N | Yes
Z2-099 | Boykins 34.5kV | Boykins Solar | VA | Southampton | Withdrawn | Dominion | 8.5 | 8.5 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2099_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 1/25/2018 |  | 5/31/2019 | 5/31/2019 |  | N | No
Z2-100 | Boykin 115kV |  | VA | Unknown | Withdrawn | Dominion | 20 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/9/2014 | Customer Initiated Withdrawal |  |  |  | N | No
Z2-101 | Frackville-Fishbach 69kV |  | PA | Schuylkill | Withdrawn | PPL | 67.5 | 67.5 | 8.78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/15/2015 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
Z2-102 | Argonne-New Lisbon 34.5kV | Dix Solar Farm | NJ | Burlington | In Service | JCPL | 13 | 13 | 4.94 | 13 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2102_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2102_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 8/24/2017 | 8/24/2017 | 7/13/2017 | N | No
Z2-103 | North Meshoppen 34.5kV III | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 19.9 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 1/28/2016 | N | No
Z2-104 | Oxbow 34.5 kV II | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 19.9 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2104_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2104_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A | 10/30/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/16/2019 | N | No
Z2-105 | Bell-Mariana 25kV | Ten Mile Generation Facility | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2105_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2105_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 2/25/2015 | Customer Initiated Withdrawal | 7/1/2016 | 7/1/2016 |  | N | Yes
Z2-106 | Washington-Bell 25kV | Amity Generation Facility | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2106_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 1/29/2019 |  | 6/30/2017 | 6/30/2017 |  | N | Yes
Z2-107 | East Carbondale-Lackawanna 69kV | Waymart Battery Energy Storage System | PA | Wayne | Withdrawn | PPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_107_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A | 12/15/2023 | 12/22/2022 |  | 12/15/2020 | 12/15/2020 |  | N | No
Z2-108 | Meyersdale North 115kV | Meyersdale Wind Farm & Battery Energy Storage System | PA | Somerset | In Service | PENELEC | 48 | 18 | 0 | 18 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/17/2015 | N | No
Z2-109 | South River 230kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 460 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_109_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 3/21/2019 |  | 5/16/2019 | 5/16/2019 |  | N | No
Z2-110 4644137 | PJM-DUK |  | N/A | N/A | Withdrawn |  | 78 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4644137_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2014 | 1/1/2016 | 1/1/2021 |  | 7/9/2014 |  |  |  |  | FF | No
Z2-111 4644159 | PJM-WEC |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4644159_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4644159_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/30/2014 | 6/1/2018 | 6/1/2023 |  | 11/20/2014 |  |  |  |  | FF | No
Z2-112 | Waterford 345kV |  | OH | Washington | In Service | AEP | 1007 | 97 | 64.5 | 97 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 6/15/2015 | N | No
Z2-113 | Watervliet 12.47kV | Watervliet Solar Facility | MI | Berrien | In Service | AEP | 4.6 | 4.6 | 2.3 | 4.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2113_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2113_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2016 | 12/15/2016 | 11/8/2016 | N | Yes
Z2-114 | Olive 12.47kV | Olive Solar Facility | IN | St. Joseph | In Service | AEP | 5 | 5 | 2.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2114_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2114_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2016 | 12/15/2016 | 8/26/2016 | N | Yes
Z2-115 | Deer Creek 12.47kV | Deer Creek Solar Facility | IN | Grant | In Service | AEP | 2.5 | 2.5 | 1.25 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2115_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 3/1/2016 | 3/1/2016 | 1/6/2016 | N | Yes
Z2-116 | Twin Branch 12.47kV | Twin Branch Solar Facility | IN | St. Joseph | In Service | AEP | 2.6 | 2.6 | 1.3 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2116_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2116_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 7/31/2016 | 7/31/2016 | 8/18/2016 | N | No
AA1-001 4645310 | AMIL-PJM |  | N/A | N/A | Confirmed |  | 78 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4645310_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4645310_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/5/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-002 4645653 | MECS-PJM |  | N/A | N/A | Retracted |  | 65 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4645653_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4645653_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/7/2014 | 6/1/2017 | 6/1/2023 |  | 4/27/2015 |  |  |  |  | FF | No
AA1-003 4646885 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 575 | 575 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4646885_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4646885_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/13/2014 | 1/1/2016 | 1/1/2025 |  | 5/10/2016 |  |  |  |  | FF | No
AA1-004 4646887 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 225 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4646887_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4646887_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/13/2014 | 1/1/2016 | 1/1/2025 |  | 2/1/2019 |  |  |  |  | FF | No
AA1-005 4646888 | CIN-PJM |  | N/A | N/A | Retracted |  | 550 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4646888_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4646888_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/13/2014 | 1/1/2016 | 1/1/2025 |  | 5/21/2015 |  |  |  |  | FF | No
AA1-006 | Erie County Landfill | Erie County Landfill | OH | Erie | In Service | ATSI | 2.3 | 0.8 | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1006_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/2/2014 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 12/31/2015 | N | No
AA1-007 | Smith Gap Regional Landfill |  | VA | Roanoke | Withdrawn | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/19/2014 | N/A | N/A |  | 1/7/2016 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
AA1-008 4656596 | AMIL-PJM |  | N/A | N/A | Retracted |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-009 4656601 | AMIL-PJM |  | N/A | N/A | Retracted |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-010 4656602 | AMIL-PJM |  | N/A | N/A | Retracted |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-011 4656605 | AMIL-PJM |  | N/A | N/A | Retracted |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-012 4656606 | AMIL-PJM |  | N/A | N/A | Retracted |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-013 | Hanging Rock 765kV | Cornu | OH | Lawrence | In Service | AEP | 1250 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_013_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
AA1-014 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 625 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
AA1-015 | Fayette II | Fayette Energy Facility | PA | Fayette | In Service | APS | 661 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 1/1/2016 | 1/1/2016 | 12/14/2015 | N | No
AA1-016 | Portland 1 |  | PA | Monroe | Withdrawn | ME | 158 | 158 | 158 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1016_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/25/2014 | N/A | N/A |  | 11/18/2015 | Customer Milestone Not Met | 6/1/2017 | 6/1/2017 |  | N | No
AA1-017 | Portland 2 |  | PA | Monroe | Withdrawn | ME | 243 | 243 | 243 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1017_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/25/2014 | N/A | N/A |  | 11/18/2015 | Customer Milestone Not Met | 6/1/2017 | 6/1/2017 |  | N | No
AA1-018 | Powerton-Goodings Grove | Otter Creek Wind Farm | IL | Livingston | In Service | ComEd | 150 | 150 | 19.5 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1018_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1018_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_018_csa.pdf | Document Posted | N/A | N/A |  | 6/25/2014 | N/A | N/A | 12/20/2019 |  |  | 1/17/2020 | 1/17/2020 | 1/9/2020 | N | No
AA1-019 | Beaverbrook 13kV | Gloucester Solar Farm | NJ | Camden | Withdrawn | PSEG | 7.3 | 7.3 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1019_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1019_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/9/2014 | N/A | N/A |  | 7/27/2017 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | Yes
AA1-020 | Andersontown Road #2 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 8/18/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
AA1-021 | Andersontown Rd #2 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 8/18/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
AA1-022 | Andersontown Rd #3 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 8/18/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
AA1-023 | Andersontown Rd #4 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 11/25/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | Y | No
AA1-024 4661444 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 6 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4661444_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/10/2014 | 6/1/2018 | 6/1/2023 |  | 9/18/2014 |  |  |  |  | FF | No
AA1-025 | Oak Hall A |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_025_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
AA1-026 | Oak Hall B |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_026_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
AA1-027 | Oak Hall C |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_027_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
AA1-028 | Oak Hall D |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_028_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
AA1-029 | Carson Rawlings 500kV |  | VA | Brunswick | Withdrawn | Dominion | 315 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2014 | N/A | N/A |  | 9/8/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-030 | Zion-Zion Energy Center |  | IL | Lake | Withdrawn | ComEd | 133 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/aa1030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2014 | N/A | N/A |  | 4/3/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-031 4662618 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 3000 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4662618_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/15/2014 | 6/1/2017 | 6/1/2022 |  | 9/11/2014 |  |  |  |  | FF | No
AA1-032 | Kingsport Mill | Kingsport Mill | TN | Sullivan | Deactivated | AEP | 50 | 0 | 45 | 0 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_032_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/21/2014 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 5/24/2017 | N | No
AA1-033 | Hay Road 230kV |  | DE | New Castle | Withdrawn | DPL | 371 | 80 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1033_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2014 | N/A | N/A |  | 10/21/2015 | Customer Initiated Withdrawal | 6/18/2018 |  |  | N | No
AA1-034 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 880 | 120 | 70 | 72.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_034_csa.pdf | Document Posted | N/A | N/A |  | 7/24/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/11/2018 | N | No
AA1-035 | Edgecomb-Roanoke Valley |  | N/A | N/A | Withdrawn | Dominion | 60 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/aa1035_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2014 | N/A | N/A |  | 3/31/2016 |  |  |  |  | EE | No
AA1-036 | Mountain 230kV |  | PA | Luzerne | Withdrawn | UGI | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1036_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/11/2014 | N/A | N/A |  | 4/6/2016 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA1-037 | Piney Hydro 34.5kV | Piney Station (Piney 1-3) | PA | Clarion | In Service | PENELEC | 33.26 | 5.26 | 5.26 | 5.26 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/13/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 6/19/2015 | N | No
AA1-038 | Lexington-Low Moor 230kV | Rocky Forge Wind | VA | Botetourt | Under Construction | Dominion | 78.2 | 78.2 | 10.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_038_csa.pdf | Document Posted | N/A | N/A | 6/15/2026 | 8/19/2014 | N/A | N/A | 7/13/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AA1-039 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa1039_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2014 | N/A | N/A |  | 3/30/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AA1-040 | Morris | Morris Cogen | IL | Grundy | In Service | ComEd | 140 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/27/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/28/2016 | N | No
AA1-041 | Tioga 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1041_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2014 | N/A | N/A |  | 4/2/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA1-042 | Ontelaunee |  | PA | Bradford | Withdrawn | ME | 574 | 0 | 52.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2014 | N/A | N/A |  | 11/18/2015 | Customer Initiated Withdrawal | 11/4/2016 |  |  | N | No
AA1-043 | Ontelaunee 230kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 591.1 | 34.1 | 19.6 | 34.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/aa1_043_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_043_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2014 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 9/30/2017 | N | No
AA1-044 | Shenango-Hoytdale 345kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 1000 | 1000 | 870 | 1000 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_044_csa.pdf | Document Posted | N/A | N/A | 4/22/2019 | 8/27/2014 | N/A | N/A | 11/15/2019 |  |  | 3/30/2020 | 3/30/2020 | 10/31/2019 | N | No
AA1-045 | McConnellsburg-Guilford 138kV |  | PA | Venango | Withdrawn | APS | 308 | 308 | 308 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1045_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 11/3/2015 | Customer Milestone Not Met | 12/18/2015 |  |  | N | No
AA1-046 | Somerset-Allegheny 115kV | Kimberly Run Wind Farm | PA | Somerset | Withdrawn | PENELEC | 80 | 80 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_046_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 6/21/2018 |  | 12/29/2018 | 12/29/2018 |  | N | No
AA1-047 | Hazelton-Jennings 138kV | Garrett County Wind Facility | MD | Garrett | Withdrawn | APS | 69.1 | 69.1 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_047_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 1/12/2020 |  | 12/1/2018 | 12/1/2018 |  | N | No
AA1-048 | Kendall |  | IL | Grundy | Withdrawn | ComEd | 800 | 800 | 780 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 4/13/2015 | Customer Milestone Not Met | 12/1/2018 |  |  | N | No
AA1-049 | Shawboro-Sligo 230kV | Shawboro East Ridge Solar Park | NC | Currituck | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1049_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_049_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2014 | N/A | N/A |  | 6/5/2017 | Customer Milestone Not Met | 11/30/2019 | 11/30/2019 |  | N | No
AA1-050 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 0 | 25.6 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_050_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2014 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/21/2015 | N | No
AA1-051 4671936 | PJM-WEC |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4671936_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4671936_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-052 4671937 | PJM-IPL |  | N/A | N/A | Confirmed |  | 400 | 400 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4671937_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4671937_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-053 4671938 | PJM-MEC |  | N/A | N/A | Withdrawn |  | 700 | 700 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4671938_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4671938_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2017 | 6/1/2022 |  | 1/23/2017 |  |  |  |  | FF | No
AA1-054 4671939 | PJM-CIN |  | N/A | N/A | Confirmed |  | 700 | 700 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4671939_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4671939_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-055 4671943 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 1100 | 1100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4671943_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4671943_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2017 | 6/1/2022 |  | 2/26/2018 |  |  |  |  | FF | No
AA1-056 | Bay Shore-Fostoria 345kV & Bay Shore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 960 | 161 | 46 | 8.8571 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_056_isa.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/15/2016 | 9/10/2014 | N/A | N/A | 6/22/2017 |  |  | 5/15/2017 | 5/15/2017 | 6/23/2017 | N | No
AA1-057 | Sunbury-Milton 69kV | Northumberland Wood Fired Power Plant | PA | Northumberland | Withdrawn | PPL | 16 | 16 | 16 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_057_csa.pdf | Document Posted | N/A | N/A |  | 9/10/2014 | N/A | N/A |  | 9/30/2019 |  | 9/30/2019 | 9/30/2019 |  | N | No
AA1-058 4675070 | CPLE-PJM |  | N/A | N/A | Withdrawn |  | 6 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4675070_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4675070_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/15/2014 | 6/1/2016 | 6/1/2018 |  | 6/1/2018 |  |  |  |  | FF | No
AA1-059 | Crisfield 25kV | Ibis | MD | Somerset | Withdrawn | DPL | 6 | 6 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1059_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1059_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/16/2014 | N/A | N/A |  | 5/23/2018 |  | 6/30/2020 | 6/30/2020 |  | N | No
AA1-060 | Great Adventure 34.5kV | Plumsted Energy Storage Facility | NJ | Monmouth | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_060_csa.pdf | Document Posted | N/A | N/A |  | 9/22/2014 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 12/11/2018 | N | Yes
AA1-061 | Jacktown-East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1061_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2014 | N/A | N/A |  | 4/24/2018 |  | 12/31/2016 |  |  | N | No
AA1-062 | Williams 138kV | Mt. Storm Wind Force | WV | Grant | Withdrawn | APS | 150 | 150 | 22.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1062_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1062_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_062_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2014 | N/A | N/A |  | 9/25/2020 |  | 12/31/2018 | 12/31/2018 |  | N | No
AA1-063 | Huntsville (Cabin Creek) 69kV |  | IN | Randolph | Withdrawn | AEP | 3.6 | 3.6 | 3.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1063_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/26/2014 | N/A | N/A |  | 4/6/2016 | Customer Initiated Withdrawal | 3/31/2016 |  |  | N | No
AA1-063A | Carolina–Seaboard 115kV | Spuds Lane Solar Park | NC | Northhampton | In Service | Dominion | 74.9 | 74.9 | 50.9 | 74.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1063a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1063a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1063a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_063a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_063a_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2014 | N/A | N/A |  |  |  | 8/17/2018 | 8/17/2018 | 11/8/2018 | N | No
AA1-064 | Carson-Wake 500kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1064_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1064_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2014 | N/A | N/A |  | 2/1/2017 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
AA1-065 | Earleys 230kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 80 | 80 | 53.6 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_065_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A | 1/9/2019 |  |  | 12/31/2018 | 12/31/2018 | 1/9/2019 | N | No
AA1-066 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 0 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_066_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 8/31/2018 | N | No
AA1-067 | Everetts 34.5kV | Williamston Speight Solar | NC | Martin | In Service | Dominion | 15 | 15 | 10.5 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_067_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 1/24/2017 | N | No
AA1-068 | Wilson 34.5kV |  | MD | Washington | Withdrawn | Unknown | 3.5 | 3.5 | 2.33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1068_fea.pdf | Document Posted |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/1/2014 | N/A | N/A |  | 6/17/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | Yes
AA1-070 | Hatfield 500kV | Hatfield Ferry, Units 1, 2, and 3 | PA | Greene | Withdrawn | APS | 1710 | 1710 | 1590 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_070_csa.pdf | Document Posted | N/A | N/A |  | 10/6/2014 | N/A | N/A |  | 11/23/2016 | Customer Initiated Withdrawal | 6/1/2019 | 6/1/2019 |  | N | No
AA1-071 4680722 | MEC-PJM |  | N/A | N/A | Confirmed |  | 72 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4680722_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4680722_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/13/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-072 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 23.1 | 3.1 | 2.1 | 3.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_072_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/13/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | No
AA1-073 | Metuchen 26kV | Middlesex Plant | NJ | Middlesex | Withdrawn | PSEG | 5.6 | 5.6 | 3.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1073_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/14/2014 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 12/16/2016 | 12/16/2016 |  | N | Yes
AA1-074 4681626 | PJM-MECS |  | N/A | N/A | Confirmed |  | 300 | 300 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4681626_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4681626_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/16/2014 | 6/1/2018 | 6/1/2025 | [6 empty] | FF | No
AA1-075 | Huron 23kV |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | 7.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2014 | N/A | N/A |  | 5/29/2015 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | Yes
AA1-076 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1050 | 1050 | 1000 | 1050 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_076_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2014 | N/A | N/A | 9/13/2019 |  |  | 3/1/2021 | 3/1/2021 | 9/22/2019 | N | No
AA1-077 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1483 | 113 | 34 | 113 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1077_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_077_csa.pdf | Document Posted | N/A | N/A |  | 10/23/2014 | N/A | N/A |  |  |  | 4/1/2019 | 4/1/2019 | 1/21/2019 | N | No
AA1-078 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 560 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1078_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/23/2014 | N/A | N/A |  |  |  | 10/14/2015 |  | 6/1/2016 | N | No
AA1-079 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 1342 | 74 | 74 | 74 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_079_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 9/13/2016 | N | No
AA1-080 | Wilson 34.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1080_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1080_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  | 3/3/2019 |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-081 | Cooksville 13kV |  | MD | Howard | Withdrawn | BGE | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1081_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  | 5/1/2015 | Customer Milestone Not Met | 5/1/2016 |  |  | N | Yes
AA1-082 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 907.5 | 57.5 | 0 | 57.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  |  |  | 1/29/2016 | 1/29/2016 | 8/25/2016 | N | No
AA1-083 | Four Rivers 230kV | Doswell Facility | VA | Hanover | In Service | Dominion | 746 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1083_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_083_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2014 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/31/2015 | N | No
AA1-084 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 252 | 0 | 10 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 6/19/2015 | N | No
AA1-085 | Moshannon-Milesburg 230kV | Centre County Wind Facility | PA | Centre | Withdrawn | APS | 82 | 82 | 10.66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1085_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1085_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_085_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 12/11/2018 |  | 6/1/2019 | 6/1/2019 |  | N | No
AA1-086 | Blue Mound-Latham |  | IL | Macon | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1086_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 2/23/2016 | Customer Milestone Not Met | 10/1/2017 |  |  | N | No
AA1-087 | Timblin-Trade City 115kV |  | PA | Jefferson | Withdrawn | PENELEC | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/aa1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/12/2015 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | S | No
AA1-088 | USAP-Woodville 138kV |  | PA | Allegheny | Withdrawn | DL | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/aa1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/11/2015 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
AA1-089 | Dravosburg-W Mifflin |  | PA | Allegheny | Withdrawn | DL | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/aa1089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/11/2015 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
AA1-090 | Cheswick 24kV Unit 1-AEP-Dayton HUB |  | N/A | N/A | Withdrawn | DL | 565 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/aa1090_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 5/25/2016 |  |  |  |  | EE | No
AA1-091 | Dover 12kV |  | DE | Kent | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1091_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 3/6/2015 | Customer Initiated Withdrawal | 11/1/2015 |  |  | Y | Yes
AA1-092 | Halfway 34.5kV | Perennial Solar Project | MD | Washington | Withdrawn | APS | 12 | 12 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1092_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_092_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A | 10/1/2024 | 5/20/2024 |  | 12/31/2024 | 12/31/2024 |  | N | Yes
AA1-093 | Clear Spring 12.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1093_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1093_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 10/18/2019 |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-094 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 6 | 6 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1094_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/19/2015 | Customer Milestone Not Met | 5/1/2016 |  |  | N | Yes
AA1-095 | Halfway-Marlowe 34.5kV | Pinesburg Solar Project | MD | Washington | In Service | APS | 4.25 | 4.25 | 2.9 | 4.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1095_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_095_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_095_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A | 4/24/2020 |  |  | 1/16/2020 | 1/16/2020 | 5/27/2020 | N | Yes
AA1-096 | Wilson 12.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1096_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1096_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/7/2019 |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-097 | Oyster Creek 230kV |  | NJ | Ocean | Withdrawn | JCPL | 186 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1097_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 4/14/2015 | Customer Milestone Not Met | 6/1/2018 |  |  | N | No
AA1-098 | Raritan River-Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 560 | 560 | 560 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1098_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 11/2/2016 | Customer Initiated Withdrawal | 5/30/2018 |  |  | N | No
AA1-099 | Clinton Co. 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 10 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_099_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 8/29/2016 | N | No
AA1-100 | Warrior Run 138kV | AES Warrior Run Energy Storage | PA | Allegheny | Deactivated | APS | 11 | 11 | 0 | 11 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_100_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 10/15/2015 | N | No
AA1-101 | Tait 69kV |  | OH | Montgomery | Withdrawn | Dayton | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1101_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_101_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 12/13/2017 |  | 5/1/2018 | 5/1/2018 |  | N | No
AA1-102 | Kings Creek-Loretto 138kV | Perry Road Solar | MD | Somerset | Partially in Service - Under Construction | DPL | 150 | 150 | 57 | 118 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1102_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_102_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A | 12/28/2017 |  |  | 12/31/2023 | 12/31/2023 | 12/28/2017 | N | No
AA1-103 | Harwood-Siegfried 230kV |  | PA | Carbon | Withdrawn | PPL | 208.5 | 208.5 | 27 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1103_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 9/15/2016 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
AA1-104 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1104_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 11/20/2018 |  | 6/30/2017 | 6/30/2017 |  | N | No
AA1-105 | Thorofare 13kV |  | NJ | Gloucester | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1105_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/19/2015 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | Yes
AA1-106 | Grover II 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1106_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1106_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 2/2/2019 |  | 12/31/2016 |  |  | N | No
AA1-107 | Kings Creek-Pocomoke 138kV |  | MD | Somerset | Withdrawn | DPL | 19.9 | 19.9 | 15.9 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/31/2015 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AA1-108 | Churchtown 230kV | Deepwater | NJ | Salem | Withdrawn | AEC | 529 | 158 | 158 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1108_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1108_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_108_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 2/7/2019 |  | 12/1/2021 | 12/1/2021 |  | N | No
AA1-109 | Cotoctin-Troutville Junction 34.5kV | Frederick Road Solar | MD | Frederick | In Service | APS | 9 | 9 | 4.5 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_109_csa.pdf | Document Posted | N/A | N/A | 10/13/2017 | 10/31/2014 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 10/23/2017 | N | Yes
AA1-110 | Massey 25kV | Blue Star Solar Project | MD | Kent | Withdrawn | DPL | 6 | 6 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1110_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1110_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1110_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 8/17/2017 |  | 10/17/2019 | 10/17/2019 |  | N | Yes
AA1-111 | Moshannon-East Towanda 230kV | Renovo Energy Center | PA | Clinton | Withdrawn | PENELEC | 463 | 463 | 463 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1111_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1111_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_111_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/20/2023 |  | 6/30/2025 | 6/30/2025 |  | N | No | This project slid to the next queue
AA1-112 | Westmoreland 25kV | Westmoreland Landfill Project | PA | Westmoreland | Withdrawn | APS | 7.2 | 7.2 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1112_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 2/21/2017 | Customer Initiated Withdrawal | 8/16/2017 | 8/16/2017 |  | N | Yes
AA1-113 | Frackville-Hauto 69kV |  | PA | Schuylkill | Withdrawn | PPL | 68 | 68 | 8.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1113_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/7/2015 | Customer Milestone Not Met | 12/30/2017 |  |  | N | No
AA1-114 | Harwood-East Hazelton #2 69kV |  | PA | Carbon | Withdrawn | PPL | 60 | 60 | 7.72 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1114_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1114_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 9/20/2016 | Customer Initiated Withdrawal | 12/30/2017 |  |  | N | No
AA1-115 | Thirty First Street 115kV |  | PA | Blair | Withdrawn | PENELEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1115_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1115_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/17/2016 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA1-116 | Kensington/Kankakee |  | IL | Kankakee | Withdrawn | ComEd | 18.4 | 18.4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1116_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_116_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_116_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/11/2018 |  | 6/1/2016 |  |  | N | No
AA1-117 | Kensington/Kankakee |  | IL | Kankakee | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1117_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_117_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_117_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/11/2018 |  | 9/1/2016 | 9/1/2016 |  | N | No
AA1-118 | Picway 69kV |  | OH | Pickaway | Withdrawn | AEP | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1118_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 5/15/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA1-119 | Sunset Lake-Mardela |  | N/A | N/A | Withdrawn | DPL | 139 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/aa1119_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/30/2017 |  |  |  |  | EE | No
AA1-120 | Fowler-LaPorte |  | N/A | N/A | Withdrawn | AEP | 64 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/aa1120_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/8/2017 |  |  |  |  | EE | No
AA1-121 | South Granville 12kV | Denison University | OH | Licking | Withdrawn | AEP | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1121_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1121_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/18/2017 | Customer Initiated Withdrawal | 1/31/2018 | 1/31/2018 |  | N | No
AA1-122 | Antietam 34.5kV |  | MD | Washington | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1122_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/3/2015 | Customer Milestone Not Met | 9/2/2016 |  |  | N | Yes
AA1-123 | Highland-Sammis 345kV | South Field Energy Power Plant | OH | Columbiana | In Service | ATSI | 1152 | 1152 | 1105 | 1152 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1123_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1123_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_123_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A | 4/1/2021 |  |  | 7/29/2021 | 7/29/2021 | 6/14/2021 | N | No
AA1-124 | Englishtown-Monroe 34kV |  | NJ | Middlesex | Withdrawn | JCPL | 1.5 | 1.5 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1124_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/13/2015 | Customer Initiated Withdrawal | 8/1/2016 |  |  | N | Yes
AA1-125 | Seaman 138kV |  | OH | Brown | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1125_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/7/2015 | Customer Initiated Withdrawal | 10/1/2016 |  |  | N | No
AA1-126 | Hillcrest 138kV |  | OH | Brown | Withdrawn | DEOK | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1126_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/5/2015 | Customer Milestone Not Met | 10/1/2016 |  |  | N | No
AA1-127 | Andersontown Road 25kV |  | MD | Caroline | Withdrawn | DPL | 6 | 6 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1127_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/24/2015 | Customer Initiated Withdrawal | 8/1/2016 |  |  | N | Yes
AA1-128 | Glen Lyn |  | VA | Giles | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/24/2015 | Customer Initiated Withdrawal | 10/1/2016 |  |  | N | No
AA1-129 | Northbrook-Skokie |  | IL | Cook | Withdrawn | ComEd | 27 | 27 | 27 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1129_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/1/2016 | Customer Milestone Not Met | 6/1/2018 |  |  | N | No
AA1-130 | St. Claire 13kV |  | OH | Franklin | Withdrawn | AEP | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1130_fea.pdf | Document Posted |  | Withdrawn |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 3/31/2016 | Customer Milestone Not Met | 11/1/2015 |  |  | N | No
AA1-131 | N. Towanda 34.5kV | Bradford Natural Gas Facility | PA | Bradford | Withdrawn | PENELEC | 8 | 8 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1131_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1131_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/3/2015 | Customer Initiated Withdrawal | 12/1/2016 | 12/1/2016 |  | N | No
AA1-132 | Shawboro-Sligo 230kV | Shawboro East Ridge Solar Park | NC | Currituck | Withdrawn | Dominion | 80 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1132_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1132_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_132_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/5/2017 | Customer Milestone Not Met | 10/31/2015 |  |  | N | No
AA1-133 | Hickory-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1133_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 2/1/2017 | Customer Initiated Withdrawal | 10/31/2015 |  |  | N | No
AA1-134 | Sunbury-WinFall 230kV |  | NC | Gates | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1134_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_134_isa2.pdf | Interim Study | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 2/15/2017 | Customer Initiated Withdrawal | 10/31/2015 |  |  | N | No
AA1-135 | Earleys-Everetts 230kV | Aulander Earleys Solar | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1135_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1135_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_135_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_135_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 5/11/2017 | Customer Milestone Not Met | 11/15/2019 | 11/15/2019 |  | N | No
AA1-136 | Cashie-E. Trowbridge 230kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Milestone Not Met | 10/31/2015 |  |  | N | No
AA1-137 | Earleys-Northampton 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Milestone Not Met | 10/31/2015 |  |  | N | No
AA1-138 | Earleys-Suffolk 230kV | Haslett Solar Park | NC | Gates | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1138_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1138_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_138_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/7/2017 | Customer Milestone Not Met | 11/15/2019 | 11/15/2019 |  | N | No
AA1-139 | Hickory-Shawboro 230kV | Summit Farms Solar and Ranchland Solar | NC | Currituck | In Service | Dominion | 120 | 120 | 84 | 120 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1139_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_139_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 2/28/2018 | 2/28/2018 | 3/6/2018 | N | No
AA1-140 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1140_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1140_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/27/2017 |  | 6/30/2018 | 6/30/2018 |  | N | No
AA1-141 | Kenney 25kV |  | MD | Worcester | Withdrawn | DPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1141_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1141_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/27/2017 |  | 10/31/2016 |  |  | N | No
AA1-142 | Vienna-Laurel 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1142_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/29/2015 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
AA1-143 | Easton-Wye Mills 69kV |  | MD | Talbot | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/29/2015 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
AA1-144 | East Towanda-Grover 230kV | Gateway Bradford Plant | PA | Bradford | Withdrawn | PENELEC | 163 | 163 | 163 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1144_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1144_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_144_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_144_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A | 4/30/2022 | 10/12/2021 | Customer Milestone Not Met | 11/30/2021 | 11/30/2021 |  | N | No
AA1-145 | Four Rivers 230kV | Doswell SC Units 2 & 3 | VA | Hanover | In Service | Dominion | 340 | 340 | 340 | 340 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1145_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1145_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_145_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 7/1/2018 | 7/1/2018 | 5/30/2018 | N | No
AA1-146 | Nelson | Invenergy Nelson Expansion LLC | IL | Lee | In Service | ComEd | 190 | 190 | 157 | 190 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1146_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1146_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_146_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_146_csa.pdf | Document Posted | N/A | N/A | 10/17/2022 | 11/1/2014 | N/A | N/A | 3/17/2023 |  |  | 5/31/2023 | 5/31/2023 | 5/20/2023 | N | No
AA1-147 | Marion 345kV |  | NJ | Camden | Withdrawn | PSEG | 400 |  |  |  | Energy | Merchant Transmission |  | AC | TWR/400 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA2-001 | Reusens 34.5kV |  | VA | Campbell | Withdrawn | AEP | 12.5 | 12.5 | 2 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2014 | N/A | N/A |  | 9/10/2015 | Customer Milestone Not Met | 12/8/2014 |  |  | N | No
AA2-002 4686172 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2016 | 6/1/2017 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-003 4686173 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 312 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2017 | 6/1/2018 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-004 4686175 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2016 | 6/1/2017 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-005 4686176 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 456 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2018 | 6/1/2019 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-006 4686643 | PJM-DUK |  | N/A | N/A | Retracted |  | 150 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4686643_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/5/2014 | 1/1/2017 | 1/1/2032 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-007 4686662 | PJM-DUK |  | N/A | N/A | Retracted |  | 58 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4686662_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/5/2014 | 1/1/2017 | 1/1/2032 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-008 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 907 | 57 | 0 | 57 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2008_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/aa2_008_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/6/2014 | N/A | N/A |  |  |  | 9/1/2016 | 9/1/2016 | 9/1/2016 | N | No
AA2-009 4691199 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 1045 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4691199_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/21/2014 | 6/1/2016 | 6/1/2017 |  | 2/3/2015 |  |  |  |  | FF | No
AA2-010 4691202 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 1045 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/21/2014 | 6/1/2017 | 6/1/2018 |  | 2/3/2015 |  |  |  |  | FF | No
AA2-011 | Winslow Township |  | NJ | Camden | Withdrawn | AEC | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/2014 | N/A | N/A |  | 9/9/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA2-012 4692026 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4692026_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/24/2014 | 6/1/2016 | 6/1/2017 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-013 4692027 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4692027_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/24/2014 | 6/1/2017 | 6/1/2018 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-014 4692029 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4692029_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/24/2014 | 6/1/2017 | 6/1/2018 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-015 4692036 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 12/11/2014 |  |  |  |  | FF | No
AA2-016 4692037 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 12/11/2014 |  |  |  |  | FF | No
AA2-017 | East Palmerton-Acahela 69kV | Penn Forest Wind Project | PA | Carbon | Withdrawn | PPL | 98 | 98 | 12.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_017_csa.pdf | Document Posted | N/A | N/A |  | 11/26/2014 | N/A | N/A |  | 10/13/2021 |  | 12/31/2020 | 12/31/2020 |  | N | No
AA2-018 4694146 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4694146_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2014 | 6/1/2018 | 6/1/2019 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-019 4694147 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4694147_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2014 | 6/1/2019 | 6/1/2020 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-020 | Albright-Cross School 138kV |  | MD | Garrett | Withdrawn | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2014 | N/A | N/A |  | 10/29/2015 | Customer Milestone Not Met | 5/30/2017 |  |  | N | No
AA2-021 | Steele 25kV |  | MD | Caroline | Withdrawn | DPL | 7 | 7 | 2.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2014 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
AA2-022 4694704 | CPLE-PJM |  | N/A | N/A | Retracted |  | 45 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4694704_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/5/2014 | 1/1/2015 | 1/1/2026 |  | 3/9/2015 |  |  |  |  | FF | No
AA2-023 4695929 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/11/2014 | 6/1/2015 | 6/1/2016 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-024 4696138 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2015 | 6/1/2016 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-025 4696140 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 156 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2017 | 6/1/2018 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-026 4696144 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 24 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2016 | 6/1/2017 |  | 1/13/2015 |  |  |  |  | FF | No
AA2-027 4696146 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 24 |  |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2017 | 6/1/2018 |  | 1/13/2015 |  |  |  |  | FF | No
AA2-028 4696147 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 1/13/2015 |  |  |  |  | FF | No
AA2-029 | Everetts 34.5kV |  | NC | Martin | Withdrawn | Dominion | 28 | 8 | 5.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/18/2014 | N/A | N/A |  | 10/2/2015 | Customer Initiated Withdrawal | 12/15/2015 |  |  | N | No
AA2-030 | Nelson | Invenergy Nelson Expansion LLC | IL | Lee | In Service | ComEd | 380 | 190 | 157 | 190 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_030_csa.pdf | Document Posted | N/A | N/A | 10/31/2022 | 12/24/2014 | N/A | N/A | 3/31/2023 |  |  | 5/31/2023 | 5/31/2023 | 5/20/2023 | N | No
AA2-031 4697572 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 1/13/2015 |  |  |  |  | FF | No
AA2-032 4697573 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 1/13/2015 |  |  |  |  | FF | No
AA2-033 4698486 | NYIS-PJM |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4698486_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4698486_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/23/2014 | 1/1/2016 | 1/1/2023 |  | 12/11/2015 |  |  |  |  | FF | No
AA2-034 4698488 | NYIS-PJM |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4698488_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4698488_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/23/2014 | 1/1/2017 | 1/1/2024 |  | 12/11/2015 |  |  |  |  | FF | No
AA2-035 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1098.3 | 1019.3 | 1019.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2035_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2014 | N/A | N/A |  | 10/15/2018 |  | 6/30/2019 |  |  | N | No
AA2-036 | West Cambridge 12kV |  | MD | Dorchester | Withdrawn | DPL | 14 | 14 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2015 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
AA2-037 | Preston 12kV |  | MD | Caroline | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2015 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
AA2-038 4703464 | ALTE-PJM |  | N/A | N/A | Retracted |  | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4703464_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4703464_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 1/16/2015 | 6/1/2016 | 6/1/2021 |  | 1/20/2016 |  |  |  |  | FF | No
AA2-039 | Kewanee 138 kV |  | IL | Henry | Withdrawn | ComEd | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2015 | N/A | N/A |  | 4/16/2020 |  | 12/1/2016 |  |  | N | No
AA2-040 | Kings Fork 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion |  |  |  |  | Energy | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2015 | N/A | N/A |  | 2/24/2015 | Customer Milestone Not Met | 8/31/2015 |  |  | N | No
AA2-041 | Tidd-Collier |  | OH | Jefferson | Withdrawn | AEP | 225 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 3/16/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AA2-042 | Conastone-Northwest 230kV |  | MD | Harford | Withdrawn | BGE | 102 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa2042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 9/21/2015 |  | 6/1/2016 |  |  | S | No
AA2-043 | Smith-N. Fayette 138kV |  | PA | Washington | Withdrawn | APS | 718 | 67 | 99 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 6/25/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AA2-044 | Sherman Avenue 69kV |  | NJ | Cumberland | Withdrawn | AEC | 13.5 | 13.5 | 7.3 |  | Capacity | Generation Interconnection | Solar; Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2044_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/6/2015 | N/A | N/A |  | 8/30/2017 | Customer Milestone Not Met | 12/1/2016 |  |  | N | No
AA2-045 4709031 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 2/12/2015 |  |  |  |  | FF | No
AA2-046 4709032 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 2/12/2015 |  |  |  |  | FF | No
AA2-047 4709033 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [9 empty] | 2/12/2015 |  |  |  |  | FF | No
AA2-048 | Allenwood-Larrabee 34kV | Lakewood-Farmingdale Road Solar Farm & Storage Facility | NJ | Monmouth | In Service | JCPL | 7 | 7 | 0 | 7 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2048_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2048_wmpa.pdf |  | Not Required | N/A | N/A | 10/3/2022 | 2/19/2015 | N/A | N/A | 10/30/2022 |  |  | 8/31/2022 | 8/31/2022 | 3/17/2023 | N | No
AA2-049 | Atlantic-Oceanview 34kV | Tinton Falls Solar & Storage Facility | NJ | Monmouth | Withdrawn | JCPL | 19.9 | 3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2049_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_049_csa.pdf | Document Posted | N/A | N/A |  | 2/18/2015 | N/A | N/A |  | 1/6/2020 |  | 6/30/2017 | 6/30/2017 |  | N | No
AA2-050 | Penrose #1 230klV |  | PA | Philadelphia | Withdrawn | PECO | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/18/2015 | N/A | N/A |  | 3/10/2015 | Customer Milestone Not Met | 5/1/2018 |  |  | N | No
AA2-051 | Penrose #2 230kV |  | PA | Philadelphia | Withdrawn | PECO | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2015 | N/A | N/A |  | 3/10/2015 | Customer Milestone Not Met | 5/1/2018 |  |  | N | No
AA2-052 | Essex 26kV |  | NJ | Essex | In Service | PSEG | 3 | 0 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_052_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 2/20/2015 | N/A | N/A |  |  |  | 2/12/2015 |  | 9/11/2015 | N | No
AA2-053 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 74.9 | 74.9 | 52.4 | 74.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_053_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A | 7/10/2019 |  |  | 6/19/2019 | 6/19/2019 | 7/10/2019 | N | No
AA2-054 | Pumphrey 230kV |  | MD | Anne Arundel | In Service | BGE | 155 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 65.7 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/aa2054_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/aa2_054_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A |  |  |  | 1/1/2016 |  | 6/7/2017 | S | No
AA2-055 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2015 | N/A | N/A |  | 5/4/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA2-056 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2015 | N/A | N/A |  | 5/4/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA2-057 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 66 | 66 | 44.7 | 66 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2057_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2057_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_057_csa.pdf | Document Posted | N/A | N/A | 9/1/2019 | 2/26/2015 | N/A | N/A | 11/18/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/26/2019 | N | No
AA2-058 | Mount Rose 13kV | Hopewell Valley Solar | NJ | Mercer | In Service | PSEG | 1 | 1 | 0.3 | 2.9 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2058_wmpa.pdf |  | Not Required | N/A | N/A | 11/30/2015 | 2/28/2015 | N/A | N/A | 12/15/2015 |  |  | 5/1/2016 | 5/1/2016 | 12/30/2015 | N | No
AA2-059 | Edenton 15kV | Edenton Solar | NC | Chowan | Withdrawn | Dominion | 10 | 10 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2059_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2059_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 4/5/2018 |  | 12/31/2018 | 12/31/2018 |  | N | No
AA2-060 | Branchville-Sussex #1 34kV | Roy Road Battery Storage Facility | NJ | Sussex | In Service | JCPL | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2060_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_060_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2015 | N/A | N/A | 7/17/2023 |  |  | 7/31/2023 | 7/31/2023 | 8/14/2023 | N | No
AA2-061 | Branchville-Sussex #2 34.5kV | Roy Road Battery Storage Facility | NJ | Sussex | In Service | JCPL | 14 | 8 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_061_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2015 | N/A | N/A | 7/17/2023 |  |  | 7/31/2023 | 7/31/2023 | 8/14/2023 | N | No
AA2-062 | Branchville-N. Newton #1 34.kV |  | NJ | Sussex | Withdrawn | JCPL | 7 | 7 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2062_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 5/6/2016 | Customer Milestone Not Met | 12/1/2015 |  |  | N | No
AA2-063 | Branchville-N. Newton #2 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2063_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 5/6/2016 | Customer Milestone Not Met | 12/1/2015 |  |  | N | No
AA2-064 | Branchville-N. Newton #3 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 17 | 17 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2064_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2064_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 4/3/2017 | Customer Milestone Not Met | 12/1/2015 |  |  | N | No
AA2-065 | Hazen Switch Point-Washington 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2065_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 9/2/2016 | Customer Milestone Not Met | 12/1/2015 |  |  | N | Yes
AA2-066 | Penns Neck 13kV | Princeton Hospital NRG Energy Center | NJ | Mercer | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2066_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 8/16/2017 | Y | No
AA2-067 | Belvidere |  | IL | Boone | Withdrawn | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 11/29/2016 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA2-068 | South Justice 115kV | N301 Solar | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2068_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2068_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2068_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 4/3/2018 |  | 8/31/2018 | 8/31/2018 |  | N | No
AA2-069 | Cartanza 230kV | Garrison Energy Center | DE | New Castle | Withdrawn | DPL | 760.2 | 451 | 451 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_069_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 6/5/2023 |  | 6/1/2024 | 6/1/2024 |  | N | No
AA2-069A | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 64.6 | 64.6 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 3/26/2015 |  |  |  |  | N | No
AA2-070 | Smith Mountain 138kV | Smith Mountain Hydro | VA | Henry | In Service | AEP | 649 | 34 | 34 | 34 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2070_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_070_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
AA2-071 4714642 | TVA-PJM |  | N/A | N/A | Retracted |  | 700 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4714642_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/2/2015 | 1/1/2017 | 1/1/2024 |  | 5/21/2015 |  |  |  |  | FF | No
AA2-072 | Kingsville 13kV | Kingsville Solar | MD | Harford | In Service | BGE | 1.1 | 1.1 | 0 | 1.1 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2072_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/9/2015 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 6/14/2016 | Y | No
AA2-073 4716842 | PJM-MEC |  | N/A | N/A | Retracted |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4716842_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/9/2015 | 6/1/2016 | 6/1/2021 |  | 5/21/2015 |  |  |  |  | FF | No
AA2-074 4717004 | CPLE-PJM |  | N/A | N/A | Confirmed |  | 45 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4717004_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4717004_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/10/2015 | 1/1/2015 | 1/1/2026 | [6 empty] | FF | No
AA2-075 | Southwest Lima 345kV |  | OH | Van Wert | Withdrawn | AEP | 250 | 250 | 33 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2015 | N/A | N/A |  | 1/27/2017 | Customer Initiated Withdrawal | 3/14/2022 |  |  | N | No
AA2-076 | Linwood 230kV | Phillips Island CT1, CT2, CT3 & ST4 | PA | Delaware | In Service | PECO | 852 | 0 | 18 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2076_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_076_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2015 | N/A | N/A |  |  |  | 4/27/2021 |  | 7/6/2017 | N | No | This project slid to the next queue
AA2-077 | Penrose #1 230kV |  | PA | Philadelphia | Withdrawn | PECO | 220 | 220 | 220 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2077_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/27/2015 | N/A | N/A |  | 5/31/2018 |  | 5/1/2018 |  |  | N | No
AA2-078 | Penrose #2 230kV |  | PA | Philadelphia | Withdrawn | PECO | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2015 | N/A | N/A |  | 11/12/2015 | Customer Milestone Not Met | 5/1/2018 |  |  | N | No
AA2-079 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 668 | 28 | 0 | 28 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2079_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_079_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2015 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 7/27/2016 | N | No
AA2-080 | Ellsworth-Eppler Junction 25kV |  | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2080_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 12/2/2015 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA2-081 | Niles Valley 34.5kV | Niles Valley 34.5kV | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2081_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2081_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_081_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_081_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 3/15/2018 |  | 8/28/2018 | 8/28/2018 |  | N | No
AA2-082 | Alpha 34.5kV | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2082_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_082_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  |  |  | 10/20/2018 | 10/20/2018 | 1/28/2019 | N | No
AA2-083 | South Troy 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2083_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 5/5/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-084 | Lappans Road 12.5kV |  | MD | Washington | Withdrawn | APS | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2084_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 9/20/2016 | Customer Initiated Withdrawal | 11/2/2016 |  |  | N | No
AA2-085 | General Office 12.5kV |  | MD | Washington | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2085_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_085_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 9/6/2019 |  | 9/5/2016 |  |  | N | No
AA2-086 | Boykins 34.5kV | Boykins Solar | VA | Southampton | Withdrawn | Dominion | 13 | 4.5 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2086_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2086_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 1/25/2018 |  | 10/31/2017 | 10/31/2017 |  | N | No
AA2-087 | Boykins 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 10/5/2015 | Customer Milestone Not Met | 9/5/2016 |  |  | N | No
AA2-088 | Boykins-Handsome 115kV | Newsoms Solar | VA | Southampton | In Service | Dominion | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_088_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  |  |  | 12/1/2017 | 12/1/2017 | 12/15/2017 | N | No
AA2-089 4725077 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725077_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4725077_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/14/2015 | 1/1/2017 | 1/1/2025 |  | 12/8/2015 |  |  |  |  | FF | No
AA2-090 4725079 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725079_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4725079_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/14/2015 | 1/1/2018 | 1/1/2025 |  | 12/8/2015 |  |  |  |  | FF | No
AA2-091 4725081 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 15 | 15 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725081_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/14/2015 | 1/1/2018 | 1/1/2025 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-092 4725288 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725288_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4725288_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/15/2015 | 1/1/2016 | 1/1/2024 |  | 12/8/2015 |  |  |  |  | FF | No
AA2-093 4725500 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 20 | 20 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725500_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-094 4725501 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 22 | 22 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725501_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-095 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [14 empty] | FF | No
AA2-096 4725504 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 16 | 16 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725504_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-097 4725505 | CIN-PJM |  | N/A | N/A | Withdrawn |  | 21 | 21 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4725505_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-098 | George Washington (Moundsville) |  | WV | Marshall | Withdrawn | AEP | 565 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AA2-099 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 0 | 32 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2099_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2099_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_099_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2015 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 6/5/2018 | N | No
AA2-100 | Brown 34.5kV | Bio Energy Landfill Facility | OH | Brown | In Service | DEOK | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2100_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2100_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2100_wmpa.pdf | Not Required | N/A | N/A |  | 4/22/2015 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 5/10/2017 | N | No
AA2-101 4726899 | PJM-MECS |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4726899_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4726899_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/22/2015 | 6/1/2019 | 6/1/2025 | [6 empty] | FF | No
AA2-102 4726900 | PJM-MECS |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4726900_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4726900_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/22/2015 | 6/1/2019 | 6/1/2025 | [6 empty] | FF | No
AA2-103 | Backbone Mountain 138kV | Backbone Mountain Energy Storage | WV | Tucker | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_103_csa.pdf | Document Posted | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 10/31/2022 |  | 7/31/2022 | 7/31/2022 |  | N | No
AA2-104 | Bigby 115kV |  | PA | Somerset | Withdrawn | PENELEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 7/27/2016 | Customer Milestone Not Met | 12/30/2016 |  |  | N | No
AA2-105 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2105_fea.pdf | Document Posted |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_105_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 9/28/2016 | Customer Initiated Withdrawal | 3/31/2017 | 3/31/2017 |  | N | No
AA2-106 | Bluff Point 69kV |  | IN | Jay | Withdrawn | AEP | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2106_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 3/13/2018 |  | 12/31/2018 | 12/31/2018 |  | N | No
AA2-107 | Waterman 34kV |  | IL | DeKalb | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2107_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 10/22/2018 |  | 12/1/2016 |  |  | N | No
AA2-108 | Plano 765kV |  | IL | Kendall | Withdrawn | ComEd | 2060 |  |  |  | Energy | Merchant Transmission |  | DC | 2060 FTIR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa2108_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 10/26/2015 | Customer Milestone Not Met | 9/30/2021 |  |  | S | No
AA2-109 | Rock Springs-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PECO | 1100 | 1100 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2109_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AA2-110 | Eddystone 230kV |  | PA | Delaware | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AA2-111 | Cochranville-Peach Bottom 230kV |  | PA | Lancaster | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AA2-112 | Tiffany 34.5kV |  | PA | Susquehanna | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2112_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2112_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 11/14/2017 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA2-113 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2113_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2015 | N/A | N/A |  | 9/28/2016 | Customer Initiated Withdrawal | 3/31/2017 | 3/31/2017 |  | N | No
AA2-114 | Furnace Brook-Hazen Switch Point 34kV |  | NJ | Union | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2114_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2015 | N/A | N/A |  | 5/2/2016 | Customer Initiated Withdrawal | 4/1/2016 |  |  | N | Yes
AA2-115 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 450 | 450 | 450 | 450 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2115_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2115_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_115_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2015 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 2/7/2019 | N | No
AA2-116 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | In Service | AEP | 994 | 994 | 994 | 994 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2116_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2116_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_116_csa.pdf | Document Posted | N/A | N/A | 6/24/2021 | 4/28/2015 | N/A | N/A | 12/27/2021 |  |  | 3/15/2022 | 3/15/2022 | 12/27/2021 | N | No
AA2-117 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 16 | 16 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2117_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2015 | N/A | N/A |  | 6/2/2016 | Customer Milestone Not Met | 5/2/2016 |  |  | N | No
AA2-118 | Murphy-Tunis 115kV |  | NC | Hertford | Withdrawn | Dominion | 35.2 | 35.2 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 5/6/2015 | Customer Initiated Withdrawal | 6/30/2017 |  |  | N | No
AA2-119 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2119_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2119_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_119_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_119_csa.pdf | Document Posted | N/A | N/A | 11/11/2027 | 4/30/2015 | N/A | N/A | 7/31/2028 |  |  | 1/31/2029 | 1/31/2029 |  | N | No
AA2-120 | Tower Hill 115kV |  | PA | Tioga | Withdrawn | PENELEC | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2120_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 5/25/2016 | Customer Milestone Not Met | 6/1/2020 |  |  | N | No
AA2-121 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I | WV | Brooke | Withdrawn | APS | 685 | 685 | 685 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2121_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2121_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_121_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_121_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2015 | N/A | N/A | 12/31/2022 | 10/10/2020 |  | 8/3/2021 | 8/3/2021 |  | N | No
AA2-122 | Parlin 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 143.5 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2122_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 5/24/2016 | Customer Milestone Not Met | 5/1/2016 |  |  | N | No
AA2-123 | Marengo 34kV | Marengo Battery Storage | IL | McHenry | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2123_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2123_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2015 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 | 11/19/2018 | N | No
AA2-124 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 576 | 576 | 553 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2124_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 9/10/2015 | Customer Initiated Withdrawal | 5/31/2019 |  |  | N | No
AA2-125 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 580.1 | 580.08 | 504 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2125_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 9/9/2015 | Customer Initiated Withdrawal | 5/31/2017 |  |  | N | No
AA2-126 | Thorofare 13kV |  | NJ | Gloucester | Withdrawn | PSEG | 5 | 5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 6/5/2015 | Customer Initiated Withdrawal | 4/1/2016 |  |  | N | No
AA2-127 | Bear Garden 230kV | Bear Garden Facility | VA | Buckingham | In Service | Dominion | 682 | 7 | 32.2 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2127_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 5/1/2016 | N | No
AA2-128 | Raritan River-Werner 115kV |  | NJ | Middlesex | Withdrawn | JCPL | 175 | 175 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 8/24/2017 | Customer Initiated Withdrawal | 6/27/2017 |  |  | N | No
AA2-129 | New Church 138kV |  | VA | Accomack | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2129_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 6/8/2018 |  | 12/31/2016 |  |  | N | No
AA2-130 | Kings Creek-Crisfield 69kV | CleanBay Biomass Generator | MD | Somerset | Withdrawn | DPL | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2130_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2130_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2130_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/8/2019 |  | 9/25/2018 | 9/25/2018 |  | N | No
AA2-131 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 354 | 0 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2131_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_131_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/30/2018 | 3/30/2018 | 5/25/2018 | N | No
AA2-132 | Thompson 34.5kV | Thompson 34.5kV | PA | Susquehanna | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2132_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2132_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_132_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 12/7/2020 |  | 9/28/2018 | 9/28/2018 |  | N | No
AA2-133 | Wyalusing 34.5kV | Wyalusing 34.5kV | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_133_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 2/21/2019 | N | No
AA2-134 | Andrew Shaft-84 Junction 25kV |  | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2134_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/29/2015 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-135 | East Towanda 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2135_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/17/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-136 | Kendall |  | IL | Kendall | Withdrawn | ComEd | 1228.8 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2136_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/2/2015 | Customer Milestone Not Met | 5/1/2016 |  |  | N | No
AA2-137 | Hanging Rock 765kV - Power Block 1 | Cornu | OH | Lawrence | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2137_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_137_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2019 |  | 12/2/2016 | N | No
AA2-138 | Hanging Rock 765kV - Power Block 2 | Cornu | OH | Lawrence | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2138_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_138_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2019 | 5/1/2019 | 12/2/2016 | N | No
AA2-139 | Ronco 500kV | Fayette Energy Facility | PA | Fayette | In Service | APS | 706 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2139_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_139_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 10/1/2017 | 10/1/2017 | 4/21/2017 | N | No
AA2-140 | Printz 230kV | Liberty Electric | PA | Delaware | In Service | PECO | 641.5 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2140_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_140_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2016 |  | 6/30/2017 | N | No
AA2-141 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2141_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 8/31/2016 | 8/31/2016 | 12/2/2016 | N | No
AA2-142 | Branchburg-Deans 500kV |  | NJ | Somerset | Withdrawn | PSEG | 1377 | 1377 | 1278 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2142_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 2/2/2016 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AA2-143 | Catoctin 12.5kV |  | MD | Frederick | Withdrawn | APS | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2143_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/26/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-144 | East New Market 12kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2144_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-145 | Catoctin 34.5kV | Hessong Birdge Solar Facility | MD | Frederick | Withdrawn | APS | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2145_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_145_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/22/2019 |  | 9/15/2017 | 9/15/2017 |  | N | No
AA2-146 | Catoctin 34.5kV |  | MD | Frederick | Withdrawn | APS | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2146_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/13/2016 | Customer Milestone Not Met | 9/15/2016 |  |  | N | No
AA2-147 | Todd 12kV |  | MD | Dorchester | Withdrawn | DPL | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2147_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-148 | Madison-Tanners Creek 138kV |  | IN | Fayette | Withdrawn | AEP | 175 | 174.2 | 22.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2148_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/20/2021 |  | 12/31/2017 | 12/31/2017 |  | N | No
AA2-149 | Carolina-Seaboard 115kV |  | NC | Northhampton | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2149_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/15/2015 |  |  | N | No
AA2-150 | Trappe 12kV |  | MD | Talbot | Withdrawn | DPL | 10 | 10 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2150_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-151 | Delano-Scioto Trail 138kV |  | OH | Ross | Withdrawn | AEP | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/18/2015 |  | 6/30/2016 |  |  | N | No
AA2-152 | Keeney-Steel 230kV |  | MD | Caroline | Withdrawn | DPL | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/20/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-153 | Yellow Springs 34.5kV |  | MD | Frederick | Withdrawn | APS | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2153_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 8/22/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-154 | Watkins Corner 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2154_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/2/2015 | Customer Initiated Withdrawal | 11/30/2015 |  |  | N | No
AA2-155 | Mt. Lena 12.5kV |  | MD | Washington | Withdrawn | APS | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2155_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-156 | Aydlett-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-157 | Cashie-Trowbridge 230kV |  | NC | Martin | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-158 | Louisa 34.5kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
AA2-159 | Downsville 34.5kV | Route 632 Washington Solar Facility | MD | Washington | Withdrawn | APS | 16 | 16 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2159_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_159_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_159_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 6/30/2021 | 7/21/2020 |  | 9/15/2017 | 9/15/2017 |  | N | No
AA2-160 | Bridgeville 12kV |  | DE | Sussex | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/18/2015 |  | 11/30/2015 |  |  | N | No
AA2-161 | Yukon-Robbins 138kV | Allegheny Energy Center LLC | PA | Allegheny | Withdrawn | APS | 541 | 541 | 513 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2161_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_161_csa.pdf | Document Posted | N/A | N/A |  | 5/1/2015 | N/A | N/A | 6/1/2024 | 10/17/2023 |  | 9/1/2027 | 9/1/2027 |  | N | No
AA2-162 | Elizabeth City-Shawboro 230kV |  | NC | Camden | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met |  |  |  | N | No
AA2-163 | Wakefield 12.5kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
AA2-164 | Murphy 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
AA2-165 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 74.9 | 8.9 | 5.3 | 8.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2165_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2165_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_165_csa.pdf | Document Posted | N/A | N/A | 9/1/2019 | 4/30/2015 | N/A | N/A | 11/18/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/26/2019 | N | No
AA2-166 | Shenango-Bedford 69kV |  | PA | Lawrence | Withdrawn | ATSI | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2166_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-167 | East Sayre 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2167_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-168 | Prince George's County |  | MD | Prince George's | Withdrawn | PEPCO | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 8/27/2015 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
AA2-169 | Five Forks 115kV | Five Forks Solar | NC | Warren | Withdrawn | Dominion | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2169_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2169_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2169_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2169_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/3/2018 |  | 8/31/2018 | 8/31/2018 |  | N | No
AA2-170 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Withdrawn | PEPCO | 1038.1 | 111.1 | 92 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2170_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2170_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_170_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_170_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 6/30/2023 | 12/23/2020 |  | 3/1/2022 | 3/1/2022 |  | N | No
AA2-171 | Sunbury #1 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 1121 | 97 | 60 | 97 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2171_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_171_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/15/2018 | 3/15/2018 | 6/1/2018 | N | No
AA2-172 | ATSI-PSEG |  | N/A | N/A | Withdrawn | ATSI | 115 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2015 |  |  |  |  | EE | No
AA2-173 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 515 | 515 | 515 | 515 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2173_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2173_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_173_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 3/16/2021 |  |  | 5/9/2021 | 5/9/2021 | 4/1/2021 | N | No
AA2-174 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 79.9 | 5 | 2.4 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_174_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 7/10/2019 |  |  | 4/22/2019 | 4/22/2019 | 7/10/2019 | N | No
AA2-175 | Suffolk-Sunbury 230kV |  | NC | Gates | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-176 | Indian River-Piney Grove 230kV |  | DE | Sussex | Withdrawn | DPL | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-177 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2177_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2177_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_177_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_177_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/13/2017 |  | 11/15/2021 | 11/15/2021 |  | N | No
AA2-178 | Mackeys 230kV | Ablemarle Beach Solar | NC | Washington | In Service | Dominion | 80 | 80 | 56 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2178_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2178_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_178_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_178_csa.pdf | Document Posted | N/A | N/A | 10/27/2020 | 4/30/2015 | N/A | N/A | 12/23/2020 |  |  | 4/20/2021 | 4/20/2021 | 12/23/2020 | N | No
AA2-179 | Creswell-Mackeys 115kV |  | NC | Washington | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2015 |  |  | N | No
AA2-180 | Hickory 34.5kV | Chesapeake Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2180_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2180_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_180_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_180_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 9/29/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
AA2-181 | Earleys-Northampton 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-182 | Sunbury #2 500kV |  | PA | Snyder | Withdrawn | PPL | 1030 | 1030 | 977 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2182_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2182_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/4/2020 |  | 9/2/2019 |  |  | N | No
AA2-183 | Tosco-VFT 230kV |  | NJ | Union | Withdrawn | PSEG | 234 | 234 | 230 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2183_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 2/11/2016 |  | 6/1/2019 |  |  | N | No
AA2-184 | Atlantic-Red Bank 34kV | Atlantic-RedBank 34.5kV Solar | NJ | Monmouth | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2184_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_184_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 11/30/2019 |  |  | 12/5/2019 | 12/5/2019 | 12/31/2019 | N | No
AA2-185 | Independent Hill 115kV |  | VA | Prince William | Withdrawn | Dominion | 1.9 | 1.6 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 9/15/2015 | Customer Initiated Withdrawal | 1/31/2016 |  |  | Y | No
AA2-186 | Forest 69kV |  | OH | Hardin | Withdrawn | AEP | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2186_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/11/2017 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AB1-001 | Absecon 12 kV | Oak Street Landfill Solar Project | NJ | Atlantic | In Service | AEC | 2.3 | 2.3 | 0.87 | 2.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1001_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1001_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1001_wmpa.pdf | Not Required | N/A | N/A |  | 5/1/2015 | N/A | N/A | 9/22/2020 |  |  | 3/30/2020 | 3/30/2020 | 9/30/2020 | Y | No
AB1-002 | Atlantic-South River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 909 | 909 | 765 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2015 | N/A | N/A |  | 4/25/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AB1-003 | Keystone-Conemaugh 500kV |  | PA | Indiana | Withdrawn | PENELEC | 1474 | 1474 | 1474 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1003_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2015 | N/A | N/A |  | 4/18/2016 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AB1-004 | Solar Holler |  | N/A | N/A | Withdrawn | AEP | 0.4 | 0.4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2015 | N/A | N/A |  | 5/19/2015 |  | 10/1/2015 |  |  | Y | No
AB1-005 | Harrisonville 13kV |  | MD | Baltimore County | Withdrawn | BGE | 1.3 | 1.3 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1005_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/18/2015 | N/A | N/A | 10/1/2020 | 7/2/2021 |  | 12/1/2021 | 12/1/2021 |  | Y | No
AB1-006 | Meadow Lake 345kV | Meadow Lake Wind Farm VI | IN | White | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_006_csa.pdf | Document Posted | N/A | N/A |  | 5/22/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/21/2018 | N | No
AB1-007 4735313 | TVA-PJM |  | N/A | N/A | Retracted |  | 58 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4735313_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2015 | 1/1/2018 | 1/1/2025 |  | 8/24/2015 |  |  |  |  | FF | No
AB1-008 4735314 | TVA-PJM |  | N/A | N/A | Retracted |  | 85 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4735314_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2015 | 1/1/2018 | 1/1/2025 |  | 8/24/2015 |  |  |  |  | FF | No
AB1-009 4735315 | TVA-PJM |  | N/A | N/A | Retracted |  | 95 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4735315_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/26/2015 | 1/1/2018 | 1/1/2025 |  | 8/24/2015 |  |  |  |  | FF | No
AB1-010 | Quakertown |  | NJ | Hunterdon | Withdrawn | JCPL | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2015 | N/A | N/A |  | 6/18/2015 | Customer Milestone Not Met | 4/1/2015 |  |  | N | No
AB1-011 | Bear Branch 13kV |  | MD | Prince George's | Withdrawn | BGE | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2015 | N/A | N/A |  | 6/18/2015 |  | 5/15/2015 |  |  | N | No
AB1-012 | Hackettstown |  | NJ | Warren | Withdrawn | JCPL | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2015 | N/A | N/A |  | 6/18/2015 | Customer Milestone Not Met | 4/1/2015 |  |  | N | No
AB1-013 | Riders Creek 115kV | Little Alligator Windfarm | NC | Tyrell | Withdrawn | Dominion | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1013_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1013_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_013_csa.pdf | Document Posted | N/A | N/A |  | 5/29/2015 | N/A | N/A |  | 5/22/2018 |  | 12/31/2020 | 12/31/2020 |  | N | No
AB1-014 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | In Service | DEOK | 125 | 125 | 47.5 | 125 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1014_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1014_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_014_csa.pdf | Document Posted | N/A | N/A | 8/19/2020 | 6/8/2015 | N/A | N/A | 11/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/18/2020 | N | No
AB1-015 | Evergreen 138kV | Warren Natural Gas Generation Faciility | OH | Trumbull | In Service | ATSI | 16.5 | 16.5 | 0 | 16.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_015_csa.pdf | Document Posted | N/A | N/A |  | 6/16/2015 | N/A | N/A | 10/10/2016 |  |  | 10/1/2017 | 10/1/2017 | 10/10/2016 | N | No
AB1-016 4740070 |  |  | N/A | N/A | Withdrawn |  |  | 90 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [6 empty] | 1/1/2016 | 1/1/2025 |  | 6/22/2015 |  |  |  |  | FF | No
AB1-017 | Highland-Sammis 345 kV & Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 940 | 140 | 64 | 140 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_017_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/18/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 8/11/2018 | N | No
AB1-018 4740256 | TVA-PJM |  | N/A | N/A | Retracted |  | 90 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4740256_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/18/2015 | 1/1/2016 | 1/1/2021 |  | 3/31/2016 |  |  |  |  | FF | No
AB1-019 | Newlinville 230 kV |  | PA | Chester | Withdrawn | PECO | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab1019_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/ab1019_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2015 | N/A | N/A |  | 4/12/2018 |  | 6/1/2018 |  |  | S | No
AB1-020 | Cold Spring 240v |  | MD | Baltimore City | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1020_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/29/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-021 | West Caldwell 13kV | West Caldwell Solar | NJ | Essex | In Service | PSEG | 2 | 2 | 0.3 | 0.3 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/29/2015 | N/A | N/A | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 6/1/2018 | N | No
AB1-022 | Columbia 115kV |  | VA | Louisa | Withdrawn | Dominion | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1022_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/6/2015 | N/A | N/A |  | 4/6/2020 |  | 3/31/2017 | 3/31/2017 |  | Y | No
AB1-023 4743994 | LGEE-PJM |  | N/A | N/A | Withdrawn |  | 120 | 120 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4743994_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/7/2015 | 6/1/2017 | 6/1/2022 |  | 8/18/2016 |  |  |  |  | FF | No
AB1-024 | Loretto-Wilton Ctr |  | IL | Livingston | Withdrawn | ComEd | 50 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2015 | N/A | N/A |  | 8/25/2016 |  | 6/1/2017 |  |  | S | No
AB1-025 | Lumberton 13kV | Lumberton Solar | NJ | Burlington | In Service | PSEG | 6.8 | 6.8 | 2.6 | 6.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/AB1025_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/21/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 8/22/2016 | N | No
AB1-026 | Westmoreland 34.5kV | Montross Solar | VA | Westmoreland | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1026_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1026_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_026_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 7/22/2015 | N/A | N/A |  | 5/25/2017 | Customer Milestone Not Met | 11/15/2020 | 11/15/2020 |  | N | No
AB1-027 | Old Church 34.5 KV | Mechanicsville Solar | VA | Hanover | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_027_csa.pdf | Document Posted | N/A | N/A |  | 7/22/2015 | N/A | N/A | 8/20/2020 |  |  | 12/1/2020 | 12/1/2020 | 9/23/2020 | N | No
AB1-028 | Boykins 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2015 | N/A | N/A |  | 8/14/2015 |  | 8/31/2016 |  |  | N | No
AB1-029 | Loretto-Pontiac |  | IL | Livingston | Withdrawn | ComEd | 35 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2015 | N/A | N/A |  | 3/10/2017 |  | 6/1/2017 |  |  | S | No
AB1-030 | Huron 69kV |  | NJ | Atlantic | Withdrawn | AEC | 23 | 7.5 | 3.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1030_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/28/2015 | N/A | N/A |  | 6/28/2016 | Customer Milestone Not Met | 12/1/2016 |  |  | N | No
AB1-031 | North Wales 34kV |  | PA | Montgomery | Withdrawn | PECO | 9 | 9 | 0 |  | Energy | Generation Interconnection | Diesel |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2015 | N/A | N/A |  | 7/29/2015 |  |  |  |  | N | No
AB1-031A | LAKEWOOD 18 KV OCEAN C1-ATLANTIC 230 KV REACTR |  | NJ | Unknown | Withdrawn | JCPL | 25 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ab1031a_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2015 | N/A | N/A |  | 3/3/2017 |  |  |  |  | EE | No
AB1-032 | Lee Station Southwest 12kV |  | OH | Athens | Withdrawn | AEP | 3.3 | 3.3 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1032_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2015 | N/A | N/A |  | 8/1/2017 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
AB1-033 | North Wales 34.5kV | Morris Road | PA | Montgomery | Deactivated | PECO | 6 | 4 | 4.1 | 4 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_033_csa.pdf | Document Posted | N/A | N/A |  | 8/12/2015 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 9/3/2020 | N | No
AB1-034 | Maintou 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 0.6 | 0.6 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1034_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2015 | N/A | N/A |  | 4/8/2016 | Customer Milestone Not Met | 9/1/2015 |  |  | N | No
AB1-035 | Mill Creek 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1035_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-036 | Howard 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1036_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-037 | Ridgeview 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1037_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-038 | Shadyside 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1038_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-039 | Lipins Corner 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1039_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-040 | Glendale 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1040_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-041 | Hunt Club 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1041_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-042 | Wall Cove 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1042_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-043 | Riva Road 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1043_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-044 | Highland 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1044_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-045 | East Towson 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1045_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-046 | Sudbrook Park 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1046_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 8/15/2015 |  |  | BB | No
AB1-047 | Highland 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1047_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-048 | Texas 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1048_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-049 | Friendship Manor 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1049_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-050 | High Ridge 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1050_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-051 | Lutherville 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1051_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-052 | Bengies 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1052_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-053 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 1/13/2017 | Customer Initiated Withdrawal | 11/15/2017 | 11/15/2017 |  | N | No
AB1-054 | Boykins 115kV |  | VA | Southampton | Withdrawn | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1054_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 12/13/2016 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
AB1-055 | Balls Gap 34.5kV | Balls Gap Battery Facility | WV | Cabell | Deactivated | AEP | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1055_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1055_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1055_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 3/1/2017 | N | No
AB1-056 | Indian River 230kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Suspended | DPL | 247.8 | 247.8 | 64.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1056_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1056_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_056_csa.pdf | Document Posted | N/A | N/A | 7/1/2029 | 8/31/2015 | N/A | N/A | 10/29/2029 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AB1-057 | Indian River 230kV II |  | DE | Sussex | Withdrawn | DPL | 251.8 | 251.8 | 65.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1057_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1057_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 8/16/2018 |  | 3/1/2020 |  |  | N | No
AB1-058 | Gavin Unit #1 765kV | Gavin #1 | OH | Gallia | In Service | AEP | 1331 | 11 | 11 | 11 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1058_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 12/31/2017 | N | No
AB1-059 | Old Church 34.5kV |  | VA | Hanover | Withdrawn | Dominion | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1059_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 3/31/2016 | Customer Initiated Withdrawal | 1/1/2017 |  |  | N | No
AB1-060 | Cloverdale-Jacksons Ferry 765kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-061 | Fieldale-Thornton-Franklin 138kV & Danville-East Danville 138kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-062 | Graceton-Safe Harbor |  | N/A | N/A | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-063 | Locust St. 13kV | Cooper Solar | NJ | Camden | In Service | PSEG; PSEG | 0.4 | 0.4 | 0 | 0.2 | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1063_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/1/2015 | N/A | N/A | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 2/15/2017 | N | No
AB1-064 | Monessen 25kV | Westmoreland Landfill Project | PA | Westmoreland | Withdrawn | APS | 11.2 | 4 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1064_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1064_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 2/21/2017 | Customer Initiated Withdrawal | 8/16/2017 | 8/16/2017 |  | N | No
AB1-065 | Jennings-Hoyes 34.5kV | CleanLight Power Solar Facility | MD | Garrett | Withdrawn | APS | 10.9 | 10.9 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1065_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1065_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 11/20/2020 |  | 10/31/2019 | 10/31/2019 |  | N | No
AB1-066 | Lime Kiln-Aqueduct 34.5kV |  | MD | Frederick | Withdrawn | APS | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 3/2/2016 | Customer Initiated Withdrawal | 12/15/2016 |  |  | N | No
AB1-067 | Unionville 12.5kV |  | VA | Orange | Withdrawn | Dominion | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1067_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 4/4/2016 | Customer Milestone Not Met | 9/26/2016 |  |  | N | No
AB1-068 | Eldred-Frackville 230kV |  | PA | Schuylkill | Withdrawn | PPL | 364 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1068_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2015 | N/A | N/A |  | 10/2/2017 |  | 5/1/2019 | 5/1/2019 |  | N | No
AB1-069 | Wylie Ridge 500kV | Beech Hollow Energy Center | PA | Washington | Withdrawn | APS | 1025 | 1025 | 950 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_069_csa.pdf | Document Posted | N/A | N/A |  | 9/9/2015 | N/A | N/A | 2/28/2023 | 3/25/2021 |  | 2/28/2023 | 2/28/2023 |  | N | No
AB1-070 | Emporia-Trego 115kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 80 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2015 | N/A | N/A |  | 9/28/2015 | Customer Initiated Withdrawal | 12/15/2017 |  |  | N | No
AB1-071 | Greenbury Point 240V |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/11/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-072 | Hancock-Marlowe 34.5kV |  | MD | Washington | Withdrawn | APS | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1072_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/14/2015 | N/A | N/A |  | 7/13/2016 | Customer Milestone Not Met | 7/1/2016 |  |  | N | No
AB1-073 | Eddystone 138kV |  | PA | Delaware | Withdrawn | PECO | 856 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1073_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 12/15/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-074 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 118 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 12/15/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-075 | Riverside 115kV |  | MD | Baltimore County | Withdrawn | BGE | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 12/16/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-076 | Fourmile Ridge 138kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1076_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 11/9/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-077 | Suffolk-WinFall 230kV |  | NC | Perquimans | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1077_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2015 | N/A | N/A |  | 11/21/2016 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AB1-078 | Wilson 34.5kV |  | PA | Washington | Withdrawn | APS | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1078_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/22/2015 | N/A | N/A |  | 5/18/2016 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AB1-079 | Zion 12kV |  | IL | Lake | Withdrawn | ComEd | 6.5 | 6.5 | 6.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1079_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2015 | N/A | N/A |  | 8/5/2016 | Customer Milestone Not Met | 12/29/2016 |  |  | N | No
AB1-080 | Dumont-Olive 345kV | St. Joseph's Energy Center, LLC | IN | St. Joseph | In Service | AEP | 715 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1080_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1080_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_080_csa.pdf | Document Posted | N/A | N/A | 7/1/2017 | 9/30/2015 | N/A | N/A | 12/28/2017 |  |  | 4/29/2018 | 4/29/2018 | 4/1/2018 | N | No
AB1-081 | Anaconda-Mayo Dunbar 115kV | Harts Mill Solar | NC | Edgecombe | In Service | Dominion | 80 | 80 | 56 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1081_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1081_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_081_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_081_csa.pdf | Document Posted | N/A | N/A | 11/23/2020 | 9/30/2015 | N/A | N/A | 12/21/2020 |  |  | 12/7/2020 | 12/7/2020 | 12/21/2020 | N | No
AB1-082 | Potter 46kV | IMG Generation Potter Facility | PA | Potter | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1082_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_082_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 9/18/2020 |  | 9/30/2019 | 9/30/2019 |  | N | No
AB1-083 | McDowell-Sharon 69kV |  | PA | Susquehanna | Withdrawn | ATSI | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1083_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 5/5/2016 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB1-084 | Greenfield-Elk Mountain 69kV |  | PA | Susquehanna | Withdrawn | PPL | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1084_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1084_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 6/14/2018 |  | 12/1/2017 |  |  | N | No
AB1-085 | North Aurora |  | IL | Kane | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 11/29/2016 | Customer Initiated Withdrawal | 9/1/2016 |  |  | N | No
AB1-086 | Pontiac Midpoint 345kV |  | IL | McLean | Withdrawn | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1086_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AB1-087 | Sullivan 345kV #1 | Sullivan Generating Station 1 | IN | Sullivan | Under Construction | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_087_csa.pdf | Document Posted | N/A | N/A | 4/22/2027 | 10/1/2015 | N/A | N/A | 5/22/2027 |  |  | 5/7/2027 | 5/7/2027 |  | N | No
AB1-088 | Sullivan 345kV #2 | Sullivan Generating Station 2 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_088_csa.pdf | Document Posted | N/A | N/A | 4/22/2027 | 10/1/2015 | N/A | N/A | 5/22/2027 |  |  | 5/7/2027 | 5/7/2027 |  | N | No
AB1-089 | Byron-Wayne 345kV #1 | Byron to Wayne Thermal #1 Project | IL | Lee | Withdrawn | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_089_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 6/9/2025 |  | 6/1/2026 | 6/1/2026 |  | N | No
AB1-090 | Byron-Wayne 345kV #2 |  | IL | Lee | Withdrawn | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 10/18/2018 |  | 6/1/2019 |  |  | N | No
AB1-091 | Davis Creek 345kV |  | IL | Kankakee | Withdrawn | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1091_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 4/11/2022 |  | 6/1/2019 |  |  | N | No
AB1-092 | Moshannon-East Towanda 230kV | Renovo Energy Center | PA | Clinton | Withdrawn | PENELEC | 504 | 41 | 17 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_092_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 4/20/2023 |  | 6/30/2025 | 6/30/2025 |  | N | No
AB1-093 | Oakland |  | NJ | Bergen | Withdrawn | RE | 0.85 | 0.85 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/5/2015 | N/A | N/A |  | 10/12/2015 |  | 12/1/2015 |  |  | N | No
AB1-094 | Rio Grande 12kV |  | NJ | Cape May | Withdrawn | AEC | 0.85 | 0.85 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/5/2015 | N/A | N/A |  | 10/12/2015 |  | 12/1/2015 |  |  | N | No
AB1-095 | Rona 12kV | Dovetail Biogas Facility | OH | Greene | In Service | ATSI | 0.85 | 0.85 | 0 | 0.85 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1095_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/6/2015 | N/A | N/A | 9/30/2016 |  |  | 12/31/2016 | 12/31/2016 | 9/30/2016 | Y | No
AB1-096 | Carroll-Mt. Airy 34.5kV | Union Bridge Solar Facility | MD | Carroll | In Service | APS | 8.166 | 8.166 | 3.134 | 8.166 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1096_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_096_csa.pdf | Document Posted | N/A | N/A |  | 10/7/2015 | N/A | N/A | 1/28/2022 |  |  | 2/28/2022 | 2/28/2022 | 4/21/2022 | N | No
AB1-097 | Harrisonburg-Stauton 115kV |  | VA | Rockingham | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1097_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/7/2015 | N/A | N/A |  | 4/26/2016 | Customer Initiated Withdrawal | 11/10/2017 |  |  | N | No
AB1-098 | Walkersville 12kV | Walkersville Solar Facility | MD | Frederick | Withdrawn | APS | 8.16 | 8.16 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1098_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1098_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1098_wmpa.pdf | Not Required | N/A | N/A |  | 10/8/2015 | N/A | N/A |  | 6/23/2017 | Customer Initiated Withdrawal | 1/1/2019 | 1/1/2019 |  | N | No
AB1-099 | Sunnymeade Road 13kV |  | NJ | Somerset | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/13/2015 | N/A | N/A |  | 6/16/2017 | Customer Initiated Withdrawal | 9/1/2016 | 9/1/2016 |  | Y | No
AB1-100 4764572 | NYIS-PJM |  | N/A | N/A | Withdrawn |  | 480 | 480 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4764572_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4764572_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/14/2015 | 6/1/2020 | 6/1/2025 |  | 1/29/2018 |  |  |  |  | FF | No
AB1-101 | Cloverdale-Jacksons Ferry 765kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab1101_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-102 | Graceton-Safe Harbor 230kV |  | N/A | N/A | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab1102_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-103 | Fieldale-Thornton & Danville-E. Danville 138kV | CMN | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab1103_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-104 | Camden 26kV |  | NJ | Camden | Withdrawn | PSEG | 9.9 | 9.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2015 | N/A | N/A |  | 2/22/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-105 | Highland-Hanna 345kV | Trumbull Energy Center | OH | Trumbull | Partially in Service - Under Construction | ATSI | 940 | 940 | 850 | 46 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_105_csa.pdf | Document Posted | N/A | N/A | 12/6/2024 | 10/22/2015 | N/A | N/A | 7/16/2025 |  |  | 1/29/2026 | 1/29/2026 |  | N | No
AB1-106 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 940 | 10 | 40 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1106_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1106_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_106_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/22/2015 | N/A | N/A |  |  |  | 3/1/2019 | 3/1/2019 | 11/18/2018 | N | No
AB1-107 | Bayshore-GM Powertrain 138 kV & Lallendorf 345kV | Cedar Point Energy Center | OH | Lucas | Withdrawn | ATSI | 955 | 955 | 860 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_107_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2015 | N/A | N/A | 11/30/2022 | 9/12/2023 |  | 11/30/2024 | 11/30/2024 |  | N | No
AB1-108 | Lackawanna 500 kV |  | PA | Lackawanna | Withdrawn | PPL | 485 | 485 | 485 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1108_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2015 | N/A | N/A |  | 5/15/2019 |  | 6/19/2019 |  |  | N | No
AB1-109 | Mountaineer | Mountaineer #1 | WV | Unknown | Partially in Service - Under Construction | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1109_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2015 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 | 12/31/2018 | N | No
AB1-110 | Cochranville-Peach Bottom 230kV |  | PA | Lancaster | Withdrawn | PECO | 620 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AB1-111 | Rock Springs-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PECO | 1235 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AB1-112 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 535 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1112_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1112_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_112_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2015 | N/A | N/A | 3/16/2021 |  |  | 5/9/2021 | 5/9/2021 | 4/1/2021 | N | No
AB1-113 | East New Market 12kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1113_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2015 | N/A | N/A |  | 3/24/2016 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AB1-114 | Masury-Maysvile 69kV |  | PA | Mercer | Withdrawn | ATSI | 12.5 | 12.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1114_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 3/2/2017 | Customer Milestone Not Met | 1/27/2017 |  |  | N | No
AB1-115 | Painesville 13kV | Lake County Generating Station | OH | Lake | Withdrawn | ATSI | 3.1 | 3.1 | 2.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1115_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1115_wmpa.pdf | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 2/8/2017 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
AB1-116 | Egg Harbor Road 12kV |  | NJ | Atlantic | In Service | AEC | 0.787 | 0.787 | 0 | 0.79 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1116_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 2/1/2018 | Y | No
AB1-117 | Cunningham 500kV |  | VA | Fluvanna | Withdrawn | Dominion | 920 | 17.3 | 17.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 11/4/2015 | Customer Initiated Withdrawal | 4/24/2016 |  |  | N | No
AB1-118 | Trenton 13kV |  | NJ | Mercer | Withdrawn | PSEG | 0.735 | 0.735 | 0.735 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 11/2/2015 | Customer Initiated Withdrawal | 1/31/2016 |  |  | N | No
AB1-119 | Tansboro Road 12kV | Tansboro Road | NJ | Camden | In Service | AEC | 0.735 | 0.735 | 0 | 0.735 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1119_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1119_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1119_wmpa.pdf | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  |  |  | 7/1/2017 | 7/1/2017 | 2/1/2018 | Y | No
AB1-120 | King of Prussia |  | PA | Montgomery | Withdrawn | PECO | 0.8 | 0.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 4/22/2016 | Customer Initiated Withdrawal | 3/14/2016 |  |  | Y | No
AB1-121 | Byron 345kV |  | IL | Ogle | Withdrawn | ComEd | 1927 |  |  |  | Energy | Merchant Transmission |  | DC | FTIR 989/NFTIR 938 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ab1121_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 6/30/2017 |  | 12/1/2021 |  |  | S | No
AB1-122 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | In Service | ComEd | 1160 | 1160 | 1150 | 1160 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1122_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1122_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_122_csa.pdf | Document Posted | N/A | N/A | 10/12/2022 | 10/30/2015 | N/A | N/A | 12/30/2022 |  |  | 6/20/2023 | 6/20/2023 | 6/16/2023 | N | No
AB1-123 | Showalter 34.5kV | Mason Dixon Solar Center Facility | MD | Washington | Withdrawn | APS | 18.4 | 18.4 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1123_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1123_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1123_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1123_wmpa.pdf | Not Required | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 5/4/2021 |  | 9/30/2018 | 9/30/2018 |  | N | No
AB1-124 | Carroll-Monocacy 34.5kV | Legore Bridge Solar Center Facility | MD | Frederick | Under Construction | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1124_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1124_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1124_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1124_wmpa.pdf | Not Required | N/A | N/A | 6/27/2025 | 10/29/2015 | N/A | N/A | 9/18/2025 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AB1-125 | Carroll-Monocacy 34.5kV | Biggs Ford Solar Facility | MD | Frederick | In Service | APS | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1125_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1125_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_125_csa.pdf | Not Required | N/A | N/A | 5/30/2025 | 10/30/2015 | N/A | N/A | 7/28/2025 |  |  | 9/1/2025 | 9/1/2025 | 8/6/2025 | N | No
AB1-126 | McConnellsburg-Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1126_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 7/12/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB1-127 | St. Thomas-Guilford 34.5kV | St. Thomas Township Solar Facility | PA | Franklin | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_127_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_127_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2015 | N/A | N/A | 7/24/2020 |  |  | 8/31/2020 | 8/31/2020 | 8/21/2020 | N | No
AB1-128 | St. Thomas-Mercersburg 34.5kV | St. Thomas Township Solar Facility II | PA | Franklin | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1128_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_128_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_128_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2015 | N/A | N/A | 8/5/2020 |  |  | 8/31/2020 | 8/31/2020 | 9/8/2020 | N | No
AB1-129 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1129_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 7/12/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB1-130 | Loretto 69kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 11/17/2015 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AB1-131 | South Joliet |  | IL | Will | Withdrawn | ComEd | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/3/2016 |  | 6/1/2016 |  |  | N | No
AB1-132 | Thelma 230kV | Oak Solar | NC | Northhampton | In Service | Dominion | 120 | 120 | 84 | 120 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1132_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1132_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_132_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 11/2/2015 | N/A | N/A | 12/21/2023 |  |  | 12/25/2023 | 12/25/2023 | 8/22/2024 | N | No
AB1-133 | Chestertown 69kV |  | MD | Somerset | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/16/2015 | Customer Milestone Not Met | 11/1/2016 |  |  | N | No
AB1-134 | Wye Mills-Centreville 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/16/2015 | Customer Milestone Not Met | 11/1/2016 |  |  | N | No
AB1-135 | Chickahominy 34.5kV | Charles City Solar | VA | Unknown | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1135_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1135_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_135_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_135_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 6/7/2017 | Customer Milestone Not Met | 11/15/2019 | 11/15/2019 |  | N | No
AB1-136 | Picway Solar 138kV |  | OH | Franklin | Withdrawn | AEP | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/17/2015 | Customer Milestone Not Met | 11/1/2016 |  |  | N | No
AB1-137 | Frankford 25kV | Millsboro Solar | DE | Sussex | Withdrawn | DPL | 6 | 6 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1137_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1137_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1137_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1137_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 10/1/2021 | 12/7/2020 |  | 3/26/2021 | 3/26/2021 |  | N | No
AB1-138 | Navy 34.5kV | Lakehurst Solar Farm | NJ | Ocean | In Service | JCPL | 9.6 | 9.6 | 3.6 | 9.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1138_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_138_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/24/2020 |  |  | 8/18/2020 | 8/18/2020 | 3/24/2020 | N | No
AB1-139 | Metuchen 26kV | Nixon Lane Solar | NJ | Middlesex | In Service | PSEG | 6.6 | 6.6 | 2.5 | 6.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1139_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 5/26/2017 | N | No
AB1-140 | George Washington 138kV I |  | WV | Marshall | Withdrawn | AEP | 575 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1140_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB1-141 | Church-Wye Mills 138 kV I | Pondtown Solar 1 | MD | Queen Anne's | In Service | DPL | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1141_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1141_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_141_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_141_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 9/28/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB1-142 | Church-Wye Mills 138 kV II | Pondtown Solar 1 | MD | Queen Anne's | In Service | DPL | 39.6 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1142_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1142_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_142_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 9/28/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB1-143 | George Washington 138kV II |  | WV | Marshall | Withdrawn | AEP | 585 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1143_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB1-144 | Shawville 230kV | Shawville Generating Station | PA | Clearfield | In Service | PENELEC | 590 | 590 | 590 | 532 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1144_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_144_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_144_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/21/2017 | 12/21/2017 | 10/24/2016 | N | No
AB1-145 | Winslow 12kV |  | NJ | Camden | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1145_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1145_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 12/11/2017 |  | 12/23/2016 |  |  | N | No
AB1-146 | Sabrooke 12kV |  | IL | Winnebago | Withdrawn | ComEd | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/21/2017 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AB1-147 | Hoytdale 138kV |  | PA | Beaver | Withdrawn | ATSI | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1147_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/25/2016 | Customer Initiated Withdrawal | 11/1/2016 |  |  | N | No
AB1-148 | Branchburg-Deans 500kV |  | NJ | Somerset | Withdrawn | PSEG | 1745 | 368 | 235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/2/2016 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AB1-149 | Baker 138kV |  | WV | Hardy | Withdrawn | APS | 121.6 | 121.6 | 15.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1149_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/28/2016 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AB1-150 | Grassy Falls 138kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 50.6 | 50.6 | 6.7 | 50.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1150_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_150_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_150_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/30/2020 |  |  | 4/30/2020 | 4/30/2020 | 3/14/2020 | N | No
AB1-151 | Paupack 230kV |  | PA | Wayne | Withdrawn | PPL | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1151_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/29/2016 | Customer Initiated Withdrawal | 6/1/2020 |  |  | N | No
AB1-152 | Culpeper 34.5kV | Stevensburg Solar | VA | Unknown | Withdrawn | Dominion | 15 | 15 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1152_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1152_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1152_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2019 | 10/31/2019 |  | N | No
AB1-153 | Hunterstown 500kV |  | PA | Adams | Withdrawn | ME | 1061.5 | 1061.5 | 985.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1153_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/10/2016 | Customer Initiated Withdrawal | 6/1/2020 |  |  | N | No
AB1-154 | Gilbert 230kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1092.2 | 1092.2 | 1028 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1154_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2154_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 8/16/2018 |  | 6/1/2020 |  |  | N | No
AB1-155 | Wakefield 34.5kV |  | VA | Surry | Withdrawn | Dominion | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/16/2015 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB1-156 | Sligo 34.5kV |  | NC | Camden | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1156_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 4/7/2016 | Customer Milestone Not Met | 10/31/2017 |  |  | N | No
AB1-157 | George Washington 138kV III |  | WV | Marshall | Withdrawn | AEP | 595 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1157_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB1-158 | Thornville 34.5kV |  | OH | Perry | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/12/2015 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB1-159 | Wakefield 34.5kV |  | VA | Surry | Withdrawn | Dominion | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1159_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/3/2016 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB1-160 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 90 | 20 | 3.8 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1160_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_160_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 8/22/2019 |  |  | 10/31/2019 | 10/31/2019 | 11/20/2019 | N | No
AB1-161 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 1.34 | 1.34 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1161_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/21/2016 | Customer Initiated Withdrawal | 8/31/2016 |  |  | Y | No
AB1-162 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 16.7 | 16.7 | 6.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1162_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1162_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 7/1/2019 |  | 7/1/2017 |  |  | N | No
AB1-163 | Glidden-Van Hiseville 34.5 kV | Legler Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 2.88 | 2.88 | 0 | 2.88 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1163_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1163_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1163_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 10/30/2021 |  |  | 10/30/2021 | 10/30/2021 | 11/6/2021 | N | No
AB1-164 | Whiteley 25kV | Whitely - Greene Battery Storage Facility | PA | Greene | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1164_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1164_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1164_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 4/14/2017 | Customer Initiated Withdrawal | 7/31/2019 | 7/31/2019 |  | N | No
AB1-165 | Tabernacle 12kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1165_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1165_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 12/11/2017 |  | 12/24/2016 |  |  | N | No
AB1-166 | Wilson 23kV | Wilson Battery Storage | PA | Allegheny | Withdrawn | DL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1166_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1166_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1166_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2015 | N/A | N/A |  | 5/30/2019 |  | 8/31/2019 | 8/31/2019 |  | N | No
AB1-167 | South Cumberland 69kV |  | OH | Noble | Withdrawn | AEP | 50 | 50 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1167_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/30/2017 |  | 8/31/2017 |  |  | N | No
AB1-168 | Berlin 12kV |  | NJ | Camden | Withdrawn | AEC | 4.5 | 4.5 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1168_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1168_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 12/11/2017 |  | 3/31/2017 |  |  | N | No
AB1-169 | Stuart 345kV | Mason Energy Center | KY | Mason | Withdrawn | Dayton | 1150 | 1150 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1169_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1169_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_169_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_169_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 6/30/2023 | 2/9/2022 |  | 6/30/2023 | 6/30/2023 |  | N | No
AB1-169A | Minotola 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1169a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1169a_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 7/20/2020 |  | 6/1/2020 |  |  | N | No
AB1-170 | LaSalle-Braidwood |  | IL | Grundy | Withdrawn | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 8/4/2016 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AB1-171 | Franklin 25kV | Franklin Generation Facility | PA | Greene | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1171_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1171_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1171_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 10/22/2018 |  | 10/31/2019 | 10/31/2019 |  | N | No
AB1-172 | Joliet-Wilmington |  | IL | Will | Withdrawn | ComEd | 6.4 | 6.2 | 6.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1172_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 6/29/2018 |  | 9/1/2017 |  |  | N | No
AB1-173 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1173_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1173_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_173_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2015 | N/A | N/A | 8/26/2022 |  |  | 4/1/2022 | 4/1/2022 | 9/29/2022 | N | No
AB1-173A | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 39.6 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1173a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1173a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1173a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_173a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_173a_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2015 | N/A | N/A | 8/26/2022 |  |  | 4/1/2022 | 4/1/2022 | 9/29/2022 | N | No
AB1-174 | Thornville12kV | Thornville 12kV | OH | Perry | Withdrawn | AEP | 10 | 10 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1174_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1174_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1174_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/7/2018 |  | 12/31/2018 | 12/31/2018 |  | N | No
AB1-175 | Homer City-Mainesburg 345kV |  | PA | Clearfield | Withdrawn | PENELEC | 1000 | 989 | 960 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/19/2015 | Customer Initiated Withdrawal | 1/1/2020 |  |  | N | No
AB1-176 | Price 25kV II | Cedar Lane Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1176_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1176_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1176_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1176_wmpa.pdf | Not Required | N/A | N/A | 3/1/2026 | 10/30/2015 | N/A | N/A | 3/1/2026 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AB1-177 | Ontario 23kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1177_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 4/4/2016 | Customer Initiated Withdrawal | 4/30/2016 |  |  | N | No
AB1-178 | Pidgeon 69kV |  | OH | Columbiana | Withdrawn | ATSI | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1178_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/9/2016 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB1-179 | Sabinsville-Wellsboro 34kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1179_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/9/2016 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB1-180 | Pine View 12kV | Seven Islands Environmental Solutions, LLC | WV | Unknown | In Service | AEP | 3.2 | 3.2 | 2.4 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1180_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1180_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1180_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 3/7/2017 | N | No
AB1-181 | Cunningham 500kV |  | VA | Fluvanna | In Service | Dominion | 1000 | 28 | 37.3 | 28 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1181_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 2/28/2017 | 2/28/2017 | 3/7/2017 | N | No
AB1-182 | Bear Creek | Bear Creek Energy Storage Facility | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1182_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1182_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_182_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_182_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 7/25/2024 |  | 12/1/2022 | 12/1/2022 |  | N | No
AB1-183 | Kennedyville-Massey 69kV |  | MD | Kent | Withdrawn | DPL | 99 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1183_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 1/20/2017 | Customer Initiated Withdrawal | 10/28/2016 |  |  | N | No
AB1-184 | Centreville 12kV II |  | MD | Queen Anne's | Withdrawn | DPL | 1.96 | 1.96 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1184_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/21/2016 | Customer Initiated Withdrawal | 11/11/2016 |  |  | Y | No
AB1-185 | 4 QUAD C18 KV QC-1-981 CRES 138KV PROVIDWF |  | N/A | N/A | Withdrawn | ComEd | 2 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ab1185_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2015 | N/A | N/A |  | 10/18/2018 |  | 6/1/2016 |  |  | EE | No
AB1-186 | REDLION 34.5 KV REDLINFC-KENT 13 KV DOVER2CT |  | N/A | N/A | Withdrawn | DPL | 3 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ab1186_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2015 | N/A | N/A |  | 11/26/2018 |  | 6/1/2016 |  |  | EE | No
AB2-001 | Ringoes-US Bronze 34kV | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 0 | 3.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2015 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 12/31/2016 | N | No
AB2-002 4768938 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 148 | 148 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/6/2015 | 1/1/2018 | 1/1/2028 |  | 12/1/2015 |  |  |  |  | FF | No
AB2-003 | Halfway-N=Milnor 34.5kV | Thornton Solar Facility | MD | Washington | Withdrawn | APS | 4.4 | 4.4 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_003_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 11/9/2015 | N/A | N/A |  | 12/19/2016 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
AB2-004 | Halfway-Milnor 34.5kV | Hagerstown Solar Facility | MD | Washington | Withdrawn | APS | 5.4 | 5.4 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_004_csa.pdf | Document Posted | N/A | N/A |  | 11/13/2015 | N/A | N/A |  | 10/23/2017 |  | 3/31/2018 | 3/31/2018 |  | N | No
AB2-005 4771489 | TVA-PJM |  | N/A | N/A | Withdrawn |  | 148 | 148 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4771489_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4771489_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/20/2015 | 1/1/2019 | 1/1/2030 |  | 4/28/2017 |  |  |  |  | FF | No
AB2-006 4771490 | TVA-PJM |  | N/A | N/A | Retracted |  | 350 | 350 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4771490_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/20/2015 | 1/1/2021 | 1/1/2030 |  | 2/11/2016 |  |  |  |  | FF | No
AB2-007 4772393 | NYISJK-PJM-NYISABC |  | N/A | N/A | Withdrawn |  | 1000 | 1000 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4772393_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4772393_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 11/24/2015 | 5/1/2017 | 5/1/2022 |  | 5/31/2017 |  |  |  |  | FF | No
AB2-008 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 105 | 105 | 96 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2008_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2015 | N/A | N/A |  | 10/10/2016 | Customer Initiated Withdrawal | 5/31/2020 |  |  | N | No
AB2-009 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 116 | 116 | 105 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2009_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2015 | N/A | N/A |  | 10/10/2016 | Customer Initiated Withdrawal | 5/31/2020 |  |  | N | No
AB2-010 | Saltville-Holston 34.5kV - Phase I | Saltville-Holston 34.5kV Solar Facility | VA | Smyth | Withdrawn | AEP | 5 | 5 | 2.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2010_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2010_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2010_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2015 | N/A | N/A |  | 2/5/2019 |  | 12/1/2017 | 12/1/2017 |  | N | No
AB2-011 | Saltville-Holstone 34.5kV - Phase II | Saltville-Holston 34.5kV Solar Facility | VA | Smyth | Withdrawn | AEP | 5 | 5 | 2.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2011_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2011_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2015 | N/A | N/A |  | 2/5/2019 |  | 12/1/2017 | 12/1/2017 |  | N | No
AB2-012 | Blooming Grove to West Damascus 69 kV |  | PA | Wayne | Withdrawn | PPL | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2012_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2012_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/9/2015 | N/A | N/A |  | 8/3/2018 |  | 6/1/2018 |  |  | N | No
AB2-013 4776359 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 150 | 150 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4776359_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4776359_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/15/2015 | 6/1/2020 | 6/1/2025 |  | 4/11/2019 |  |  |  |  | FF | No
AB2-014 | Lakewood 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 0 | 8.1 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/15/2015 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 11/16/2016 | N | No
AB2-015 | Franklin 115kV | Tidewater Solar Projects | VA | Southampton | Withdrawn | Dominion | 91 | 91 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2015_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_015_csa.pdf | Document Posted | N/A | N/A | 6/1/2023 | 12/21/2015 | N/A | N/A | 8/31/2023 | 1/3/2022 |  | 12/31/2022 | 12/31/2022 |  | N | No
AB2-016 | Maddox Creek 345kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2016_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2015 | N/A | N/A |  | 3/9/2018 |  | 12/31/2019 |  |  | N | No
AB2-017 |  |  | NJ | Atlantic | Withdrawn | JCPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/4/2016 | N/A | N/A |  | 1/27/2016 | Customer Milestone Not Met |  |  |  | Y | No
AB2-018 | Bethel-Carolina 12.kkV |  | NC | Unknown | Withdrawn | Dominion | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2016 | N/A | N/A |  | 2/9/2016 |  | 12/31/2016 |  |  | N | No
AB2-019 | Erie West 345kV |  | PA | N/A | Withdrawn | PENELEC | 28 |  |  |  | Energy | Merchant Transmission |  | DC | 28 NFTWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ab2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/ab2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/ab2_019_csa.pdf | Document Posted | N/A | N/A |  | 2/3/2016 | N/A | N/A |  | 8/6/2022 |  | 3/31/2024 | 3/31/2024 |  | S | No
AB2-020 | Roseland-Williams 230kV |  | N/A | N/A | In Service | PSEG | 40 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 62 | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab2020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/ab2020_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/ab2_020_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 11/22/2017 | S | No
AB2-021 | Keeney-Rock Springs 500kV |  | MD | Unknown | In Service | BGE | 100 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 705 | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab2021_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/ab2021_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/ab2_021_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 10/31/2018 | S | No
AB2-022 | Elizabeth City 34.5kV | Elizabeth City Solar | NC | Camden | In Service | Dominion | 20 | 20 | 13 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2022_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2022_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2022_wmpa.pdf | Not Required | N/A | N/A |  | 2/4/2016 | N/A | N/A | 8/1/2021 |  |  | 6/30/2021 | 6/30/2021 | 10/18/2021 | N | No
AB2-023 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2016 | N/A | N/A |  | 3/30/2016 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-024 | Correctional 34.5kV |  | VA | New Kent | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2024_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2024_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2024_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/27/2017 | N | Yes
AB2-025 | Sapony 34.5kV |  | VA | Sussex | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2025_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2025_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2025_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-026 | Powhatan 34.5kV |  | VA | Powhatan | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2026_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2026_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2026_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-027 | Maple Ave-Mount Lena 34.5kV | Funkstonw Solar Facility | MD | Washington | Withdrawn | APS | 8.8 | 8.8 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2027_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2027_wmpa.pdf | Not Required | N/A | N/A |  | 2/10/2016 | N/A | N/A |  | 10/26/2020 |  | 11/30/2017 | 11/30/2017 |  | N | No
AB2-028 | Fall Creek-Desoto 345kV |  | IN | Henry | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2028_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2016 | N/A | N/A |  | 6/17/2021 |  | 10/31/2018 |  |  | N | No
AB2-029 | Remington 34.5kV |  | VA | Fauquier | In Service | Dominion | 19.8 | 19.8 | 7.6 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2029_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2029_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2029_wmpa.pdf | Not Required | N/A | N/A |  | 2/11/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 10/1/2017 | N | No
AB2-030 | Tasley 25kV |  | VA | Accomack | Withdrawn | DPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2016 | N/A | N/A |  | 10/16/2017 |  | 12/1/2016 |  |  | N | No
AB2-031 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 59.6 | 20 | 13.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2031_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_031_csa.pdf | Document Posted | N/A | N/A |  | 2/13/2016 | N/A | N/A | 8/26/2022 |  |  | 4/1/2022 | 4/1/2022 | 9/29/2022 | N | No
AB2-032 | Church-Wye Mills 138 kV | Pondtown Solar 2 | MD | Queen Anne's | In Service | DPL | 20 | 20 | 13.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2032_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2032_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_032_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_032_csa.pdf | Document Posted | N/A | N/A |  | 2/11/2016 | N/A | N/A | 9/23/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB2-033 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 10 | 10 | 7.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2033_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2016 | N/A | N/A |  | 3/20/2018 |  | 5/1/2017 |  |  | N | No
AB2-034 4788768 |  |  | N/A | N/A | Withdrawn |  | 100 | 100 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/23/2016 | 6/1/2017 | 6/1/2022 |  | 2/23/2016 |  |  |  |  | FF | No
AB2-035 | Bethel-Carolina 12.5kV |  | NC | Pitt | Withdrawn | Dominion | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2035_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/23/2016 | N/A | N/A |  | 11/30/2018 |  | 12/31/2016 |  |  | N | No
AB2-036 | Church - Oil City 138kV | Waypost Solar Project | MD | Caroline | Suspended | DPL | 92 | 92 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2036_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_036_csa.pdf | Document Posted | N/A | N/A | 6/20/2026 | 2/26/2016 | N/A | N/A | 10/23/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AB2-037 | Keeney-Steele 230kV | Cherrywood Solar I | MD | Caroline | Under Construction | DPL | 202 | 202 | 76.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2037_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2037_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_037_csa.pdf | Document Posted | N/A | N/A | 5/8/2026 | 2/26/2016 | N/A | N/A | 5/18/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AB2-038 | Frostburg 138kV |  | MD | Allegany | In Service | APS | 139.4 | 0 | 2.9 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_038_csa.pdf | Document Posted | N/A | N/A |  | 3/1/2016 | N/A | N/A | 12/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 9/13/2017 | N | No
AB2-039 | Bakers Pond-Ivor 115kV |  | VA | Southampton | Withdrawn | Dominion | 85 | 85 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2039_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 7/7/2017 | Customer Milestone Not Met | 12/31/2018 | 12/31/2018 |  | N | No
AB2-040 | Brink 115kV | Brink Solar Project | VA | Greensville | In Service | Dominion | 80 | 80 | 44 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2040_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2040_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_040_csa.pdf | Document Posted | N/A | N/A | 10/10/2024 | 3/2/2016 | N/A | N/A | 11/11/2024 |  |  | 10/1/2024 | 10/1/2024 | 12/27/2024 | N | No
AB2-041 | Frostburg 138kV | Mason Dixon Wind Farm | PA | Somerset | Withdrawn | APS | 80 | 19.4 | 3.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_041_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/29/2016 | N/A | N/A | 12/15/2020 | 10/26/2020 |  | 12/15/2020 | 12/15/2020 |  | N | No
AB2-042 | Smithfield-Surry 230kV |  | VA | Isle of Wight | Withdrawn | Dominion | 160 | 160 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2042_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 10/11/2016 | Customer Milestone Not Met | 9/30/2018 |  |  | N | No
AB2-043 | Chase City 115kV | Bluestone Farm Solar | VA | Mecklenburg | In Service | Dominion | 49.9 | 49.9 | 18.9 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2043_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2043_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_043_csa.pdf | Document Posted | N/A | N/A | 3/2/2021 | 2/29/2016 | N/A | N/A | 3/28/2021 |  |  | 4/8/2021 | 4/8/2021 | 4/3/2021 | N | No
AB2-044 |  |  | NJ | Middlesex | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 3/17/2016 |  | 7/1/2017 |  |  | N | No
AB2-045 | Buckingham 34.5kV |  | VA | Buckingham | In Service | Dominion | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2045_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2045_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2045_wmpa.pdf | Not Required | N/A | N/A |  | 2/29/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-046 | Charleroi 12kV |  | PA | Washington | Withdrawn | APS | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 6/27/2016 | Customer Initiated Withdrawal | 12/1/2016 |  |  | Y | No
AB2-047 | Brokaw-Pontiac Midpoint | Blooming Grove WF | IL | McLean | In Service | ComEd | 250 | 250 | 32.5 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2047_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_047_csa.pdf | Document Posted | N/A | N/A | 10/20/2020 | 2/29/2016 | N/A | N/A | 10/30/2020 |  |  | 12/30/2020 | 12/30/2020 | 10/30/2020 | N | No
AB2-048 | Grandin 12kV | Clinton Energy Storage System | NJ | Hunterdon | Withdrawn | JCPL | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2048_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2048_wmpa.pdf | Not Required | N/A | N/A |  | 3/3/2016 | N/A | N/A |  | 7/31/2018 |  | 6/30/2019 | 6/30/2019 |  | Y | No
AB2-049 | Gloucester Township 12kV | GEMS Landfill Solar | NJ | Camden | In Service | AEC | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2049_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2049_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2049_wmpa.pdf | Not Required | N/A | N/A |  | 3/4/2016 | N/A | N/A | 3/18/2022 |  |  | 6/30/2022 | 6/30/2022 | 4/14/2022 | N | No
AB2-050 | Four Rivers 230kV | Doswell Complex 5 & 6 | VA | Hanover | In Service | Dominion | 746 | 20 | 20 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2050_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/4/2016 | N/A | N/A |  |  |  | 3/1/2020 | 3/1/2020 | 2/28/2018 | N | No
AB2-051 | Chesapeake 230kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 840 | 840 | 765.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2051_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2051_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/14/2016 | N/A | N/A |  | 10/3/2018 |  | 1/1/2021 |  |  | N | No
AB2-052 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-053 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-054 | JK Smith 345kV |  | KY | Clark | Withdrawn | EKPC | 614 | 614 | 504 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2054_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2016 | N/A | N/A |  | 5/8/2017 | Customer Initiated Withdrawal | 3/1/2023 |  |  | N | No
AB2-055 | Bayonne 345kV |  | NJ | Hudson | Withdrawn | PSEG | 1041.4 | 1041.4 | 1041.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2016 | N/A | N/A |  | 9/20/2019 |  | 6/1/2021 |  |  | N | No
AB2-056 | Colora 34.5kV |  | MD | Cecil | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2056_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2016 | N/A | N/A |  | 5/24/2017 | Customer Initiated Withdrawal | 10/1/2018 |  |  | N | No
AB2-057 | Brunswick 26kV | New Road Solar | NJ | Middlesex | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2057_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2057_wmpa.pdf | Not Required | N/A | N/A |  | 3/24/2016 | N/A | N/A |  |  |  | 3/30/2018 | 3/30/2018 | 6/22/2018 | N | No
AB2-058 | Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 0 | 3.6 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/25/2016 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 12/6/2016 | N | No
AB2-059 | Benson-Dunbar 115kV | Moccasin Creek Solar | NC | Edgecombe | In Service | Dominion | 100 | 100 | 66 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_059_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2016 | N/A | N/A | 6/30/2020 |  |  | 6/15/2020 | 6/15/2020 | 10/12/2020 | N | No
AB2-060 | Chase City-Lunenburg 115kV | Chase City Solar | VA | Mecklenburg | In Service | Dominion | 80 | 80 | 54.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_060_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2016 | N/A | N/A | 5/15/2020 |  |  | 5/15/2020 | 5/15/2020 | 7/21/2020 | N | No
AB2-061 | Meadow Road 13kV | Meadow Road Solar | NJ | Middlesex | Withdrawn | PSEG | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2061_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2061_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2061_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2016 | N/A | N/A |  | 5/12/2017 | Customer Initiated Withdrawal | 6/30/2018 | 6/30/2018 |  | N | No
AB2-062 | Unionville 115kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2062_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2062_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 8/24/2018 |  | 2/1/2018 |  |  | N | No
AB2-063 | Price 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2063_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2063_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 7/1/2019 |  | 12/31/2018 |  |  | N | No
AB2-064 | Southwest Lima 345kV |  | OH | Van Wert | Withdrawn | AEP | 40 | 40 | 15.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2064_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 9/22/2016 |  | 12/31/2018 |  |  | N | No
AB2-065 | Madison-Tanners Creek 138kV |  | IN | Rush | Withdrawn | AEP | 124.2 | 124.2 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2065_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 2/27/2018 |  | 12/31/2019 |  |  | N | No
AB2-066 | Crawfords Corner 23kV |  | NJ | Monmouth | Withdrawn | JCPL | 4.1 | 0.1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2066_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 11/18/2016 | Customer Milestone Not Met | 7/31/2016 |  |  | N | No
AB2-067 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1100 | 1100 | 1100 | 1100 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_067_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 3/31/2016 | N/A | N/A | 9/17/2022 |  |  | 12/31/2022 | 12/31/2022 | 4/7/2023 | N | No
AB2-068 | Chickahominy 500kV | C4GT | VA | Charles City | Withdrawn | Dominion | 1060 | 1060 | 1060 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_068_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2016 | N/A | N/A | 12/31/2023 | 1/11/2021 |  | 12/31/2023 | 12/31/2023 |  | N | No
AB2-069 | Chase City-Kerr Dam 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 49 | 49 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2069_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 10/11/2016 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AB2-070 | Mt. Pulaski-Brokaw | Alta Farms II | IL | DeWitt | In Service | ComEd | 197 | 197 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2070_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2070_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_070_csa.pdf | Document Posted | N/A | N/A | 4/1/2023 | 3/31/2016 | N/A | N/A | 5/1/2023 |  |  | 5/31/2023 | 5/31/2023 | 5/20/2023 | N | No
AB2-071 | Hunterstown-Lincoln 115kV |  | PA | Adams | Withdrawn | ME | 100 | 100 | 68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2071_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 5/31/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-072 | Arnold's Corner 34.5kV |  | VA | King George | Withdrawn | Dominion | 18 | 18 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2072_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 1/29/2019 |  | 9/15/2017 |  |  | N | No
AB2-073 | Earleys 230kV |  | NC | Hertford | Withdrawn | Dominion | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2016 | N/A | N/A |  | 5/27/2016 | Customer Milestone Not Met | 10/31/2016 |  |  | N | No
AB2-074 | Sunbury #2 500kV |  | PA | Snyder | Withdrawn | PPL | 1143 | 113 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2074_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2074_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/1/2016 | N/A | N/A |  | 5/4/2020 |  | 9/2/2019 |  |  | N | No
AB2-075 4796024 | DUK-PJM |  | N/A | N/A | Retracted |  | 42 | 42 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4796024_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4796024_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/5/2016 | 6/1/2020 | 6/1/2025 |  | 5/2/2017 |  |  |  |  | FF | No
AB2-076 4796025 | DUK-PJM |  | N/A | N/A | Retracted |  | 51 | 51 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4796025_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4796025_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/5/2016 | 6/1/2020 | 6/1/2025 |  | 5/2/2017 |  |  |  |  | FF | No
AB2-077 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2077_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_077_csa.pdf | Document Posted | N/A | N/A | 11/7/2023 | 4/14/2016 | N/A | N/A | 4/17/2024 |  |  | 5/31/2024 | 5/31/2024 | 6/18/2024 | N | No
AB2-078 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 40 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2078_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_078_csa.pdf | Document Posted | N/A | N/A | 11/7/2023 | 4/14/2016 | N/A | N/A | 4/17/2024 |  |  | 5/31/2024 | 5/31/2024 | 6/18/2024 | N | No
AB2-079 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 60 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_079_csa.pdf | Document Posted | N/A | N/A | 11/7/2023 | 4/14/2016 | N/A | N/A | 4/17/2024 |  |  | 5/31/2024 | 5/31/2024 | 6/18/2024 | N | No
AB2-080 | Marysville-Flatlick 765kV |  | OH | Pickaway | Withdrawn | AEP | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2080_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/12/2016 | N/A | N/A |  | 10/4/2016 | Customer Milestone Not Met | 6/1/2021 |  |  | N | No
AB2-081 | Sligo 34.5kV |  | NC | Camden | Withdrawn | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/13/2016 | N/A | N/A |  | 5/3/2016 |  | 10/31/2017 |  |  | N | No
AB2-082 | Metuchen 230kv |  | NJ | Middlesex | Withdrawn | PSEG | 675 | 675 | 671 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2082_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2016 | N/A | N/A |  | 4/30/2019 |  | 6/1/2019 |  |  | N | No
AB2-083 | Delano 138kV |  | OH | Ross | Withdrawn | AEP | 40 | 40 | 27.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2083_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2016 | N/A | N/A |  | 3/4/2021 |  | 10/31/2017 |  |  | N | No
AB2-084 | Costen 25kV | Costen Solar Energy Center | MD | Somerset | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2084_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2084_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2084_wmpa.pdf | Not Required | N/A | N/A |  | 4/15/2016 | N/A | N/A |  | 2/1/2019 |  | 10/20/2019 | 10/20/2019 |  | N | No
AB2-085 | Adams 138kV | Stone Branch Solar | OH | Adams | Withdrawn | AEP | 49.9 | 49.9 | 33.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2085_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2085_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_085_csa.pdf | Document Posted | N/A | N/A |  | 4/18/2016 | N/A | N/A |  | 3/26/2025 |  | 12/31/2023 | 12/31/2023 |  | N | No
AB2-086 | Grassfield 13.2kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2016 | N/A | N/A |  | 5/5/2016 | Customer Milestone Not Met | 10/31/2017 |  |  | N | No
AB2-087 | Earleys 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2016 | N/A | N/A |  | 11/27/2017 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB2-088 | Tarboro 12.5kV |  | NC | Edgecombe | Withdrawn | Dominion | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2088_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/22/2016 | N/A | N/A |  | 11/30/2018 |  | 12/31/2016 |  |  | N | No
AB2-089 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_089_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_089_csa.pdf | Document Posted | N/A | N/A |  | 4/25/2016 | N/A | N/A |  | 7/24/2019 |  | 6/1/2017 |  |  | N | No
AB2-090 | Chase City 34.5kV |  | VA | Mecklenburg | Withdrawn | Dominion | 36 | 36 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2090_imp.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2090_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/25/2016 | N/A | N/A |  | 8/31/2018 |  | 6/12/2018 | 6/12/2018 |  | N | No
AB2-091 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 105 | 105 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2091_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2016 | N/A | N/A |  | 4/21/2017 | Customer Initiated Withdrawal | 5/31/2020 |  |  | N | No
AB2-092 | Bergen 138kV | Bergen Generating Station | NJ | Bergen | Partially in Service - Under Construction | PSEG | 1371.1 | 51.1 | 51.1 | 26 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_092_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2016 | N/A | N/A |  |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AB2-093 | Ormet 138kV | Hannibal Port Power Project | OH | Monroe | In Service | AEP | 485 | 485 | 485 | 485 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_093_csa.pdf | Document Posted | N/A | N/A | 12/15/2020 | 4/26/2016 | N/A | N/A | 5/22/2021 |  |  | 9/13/2021 | 9/13/2021 | 6/1/2021 | N | No
AB2-094 | Warren Glen Switch Point 34kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/Combined with Feaas | Document Posted |  |  |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/26/2016 | N/A | N/A |  | 11/23/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AB2-095 | Ocean Pines-Walston Switch 69kV |  | MD | Wicomico | Withdrawn | DPL | 30 | 30 | 11.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2095_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2016 | N/A | N/A |  | 10/12/2016 | Customer Initiated Withdrawal | 10/31/2018 |  |  | N | No
AB2-096 | Silver Lake-Cherry Valley | Garden Prairie Energy Facility | IL | Boone | Withdrawn | ComEd | 450 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2096_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2096_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_096_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2016 | N/A | N/A |  | 5/5/2022 |  | 4/30/2024 | 4/30/2024 |  | N | No
AB2-097 | Antietam 34.5kV | Hagerstown Plant | MD | Washington | In Service | APS | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2097_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2097_wmpa.pdf | Not Required | N/A | N/A |  | 4/27/2016 | N/A | N/A | 12/31/2022 |  |  | 2/28/2020 | 2/28/2020 | 10/15/2020 | N | No
AB2-098 | Everetts 34.5kV |  | NC | Martin | Withdrawn | Dominion | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2016 | N/A | N/A |  | 9/18/2019 |  | 12/30/2016 |  |  | N | No
AB2-099 | Ahoskie 34.5kV | Colice Hall Solar | NC | Hertford | In Service | Dominion | 5 | 5 | 3.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2099_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_099_csa.pdf | Document Posted | N/A | N/A | 3/1/2023 | 4/28/2016 | N/A | N/A | 6/29/2023 |  |  | 7/23/2023 | 7/23/2023 | 7/6/2023 | N | No
AB2-100 | Clubhouse-Lakeview 230kV | Sadler Solar | VA | Greensville | In Service | Dominion | 100 | 100 | 67 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_100_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2016 | N/A | N/A | 1/18/2021 |  |  | 12/1/2021 | 12/1/2021 | 1/22/2021 | N | No
AB2-101 | George Washington 138kV |  | WV | Marshall | Withdrawn | AEP | 626 | 31 | 31 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2016 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 4/1/2019 |  |  | N | No
AB2-102 | Cumberland 230kV | Cumberland | NJ | Cumberland | Withdrawn | AEC | 230 | 230 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2102_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_102_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2016 | N/A | N/A | 12/1/2025 | 4/26/2024 |  | 12/1/2023 | 12/1/2023 |  | N | No
AB2-103 | Seaman 138kV |  | OH | Adams | Withdrawn | AEP | 40 | 40 | 27.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2103_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 3/26/2018 |  | 10/31/2017 |  |  | N | No
AB2-104 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I, LLC | WV | Brooke | Withdrawn | APS | 750 | 65 | 65 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2104_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_104_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_104_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2016 | N/A | N/A | 12/31/2021 | 10/10/2020 |  | 8/3/2021 | 8/3/2021 |  | N | No
AB2-105 | Mantua 12kV |  | NJ | Gloucester | Withdrawn | AEC | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2105_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 10/12/2016 | Customer Milestone Not Met | 12/31/2016 |  |  | Y | No
AB2-106 | Pierson Avenue 480V |  | NJ | Middlesex | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | Y | No
AB2-107 | Burlington 480V |  | NJ | Burlington | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/30/2016 | Customer Milestone Not Met | 12/31/2016 |  |  | Y | No
AB2-108 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | Y | No
AB2-109 | Reusens 34.5kV | Reusens Hydro Electric Generating Plant | VA | City of Lynchburg | In Service | AEP | 12.5 | 12.5 | 4 | 12.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 3/31/2018 | 3/31/2018 | 11/29/2017 | N | No
AB2-110 | Englishtown-Millhurst 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 11.1 | 11.1 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 4/19/2017 |  |  | N | No
AB2-111 | Millhurst-Rt 33 Switch Point 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 11.1 | 11.1 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 4/20/2017 |  |  | N | No
AB2-112 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 485 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 2/7/2019 | N | No
AB2-113 | Cecil County 1 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2113_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-114 | Cecil County 2 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2114_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-115 | Cecil County 3 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2115_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/21/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-116 | Cecil County 4 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2116_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-117 | Cecil County 5 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2117_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-118 | Cecil County 6 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2118_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-119 | Middle Township 12kV |  | NJ | Cape May | Withdrawn | AEC | 1.5 | 1.5 | 0.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2119_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 5/24/2017 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AB2-120 | Piney Grove-New Church 138kV |  | MD | Worcester | Withdrawn | DPL | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2120_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2120_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 2/23/2021 |  | 12/14/2018 |  |  | N | No
AB2-121 | Burlington 26kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2121_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 2/14/2017 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB2-122 | Egg Harbor 12kV | Winzinger Egg Harbor Solar Project | NJ | Atlantic | Withdrawn | AEC | 1.9 | 1.9 | 0.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2122_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2122_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2122_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2122_wmpa.pdf | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 5/5/2020 |  | 9/4/2021 | 9/4/2021 |  | N | No
AB2-123 | Whiterock 34kV |  | MD | Howard | Withdrawn | BGE | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2123_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-124 | Whiterock 34kV |  | MD | Howard | Withdrawn | BGE | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2124_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-125 | Marriott Hill 34kV |  | MD | Anne Arundel | Withdrawn | BGE | 3.3 | 3.3 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2125_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-126 | Finksburg 34kV |  | MD | Baltimore County | Withdrawn | BGE | 3.8 | 3.8 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2126_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-127 | Gilbert 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 16 | 16 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2127_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 12/2/2016 | Customer Initiated Withdrawal | 6/29/2018 |  |  | N | No
AB2-128 | Clubhouse-Lakeview 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 57.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2128_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/17/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-129 | Doubs 230kV | Potomac Solar, LLC | MD | Frederick | Withdrawn | APS | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2129_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2129_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_129_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_129_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/30/2021 |  | 4/30/2020 | 4/30/2020 | 5/30/2021 | N | No
AB2-130 | Laurel 69kV |  | DE | Sussex | Withdrawn | DPL | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2130_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/19/2021 |  | 6/1/2019 |  |  | N | No
AB2-131 | Galion-Roberts South 138kV |  | OH | Marion | Withdrawn | ATSI | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2131_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2131_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 8/29/2020 |  | 6/1/2019 |  |  | N | No
AB2-132 | Haumesser Road | Lee-DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 240 | 0 | 2.2 | 0 | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2132_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_132_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2016 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/1/2023 | N | No
AB2-133 | Chestertown 69kV | Morgnec Road Solar | MD | Kent | Under Construction | DPL | 55.8 | 55.8 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_133_csa.pdf | Document Posted | N/A | N/A | 1/18/2026 | 4/29/2016 | N/A | N/A | 1/26/2026 |  |  | 8/16/2025 | 8/16/2025 |  | N | No
AB2-134 | Hopewell-Surry 230kV | Colonial Trail West Solar | VA | Surry | In Service | Dominion | 142.4 | 142.4 | 71.8 | 142.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2134_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_134_csa.pdf | Document Posted | N/A | N/A | 10/3/2019 | 4/29/2016 | N/A | N/A | 11/7/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/7/2019 | N | No
AB2-135 | Church-Kent 69kV | Jones Farm Lane Solar | MD | Queen Anne's | In Service | DPL | 64 | 64 | 29.9 | 64 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2135_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2135_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_135_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_135_csa.pdf | Document Posted | N/A | N/A | 5/21/2025 | 4/30/2016 | N/A | N/A | 6/5/2025 |  |  | 4/30/2025 | 4/30/2025 | 6/8/2025 | N | No
AB2-136 | Cambridge-West Cambridge 69kV | Egypt Road Solar | MD | Dorchester | Under Construction | DPL | 51.1 | 51.1 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2136_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2136_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_136_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_136_csa.pdf | Document Posted | N/A | N/A | 12/19/2025 | 4/30/2016 | N/A | N/A | 12/22/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AB2-137 | St. Clair 13.2kV |  | OH | Franklin | Withdrawn | AEP | 4 | 4 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/30/2016 | Customer Initiated Withdrawal | 11/1/2017 |  |  | N | No
AB2-138 | Clybourn 12.5kV |  | IL | Cook | Withdrawn | ComEd | 0.1 | 0.1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met |  |  |  | Y | No
AB2-139 | Raceway Mall 34.5kV | Freemall Fuel Cell Facility | NJ | Monmouth | In Service | JCPL | 0.42 | 0.42 | 0 | 0.42 | Energy | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2139_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2139_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 2/1/2018 | Y | No
AB2-140 | Rock Ridge 13kV |  | MD | Harford | Withdrawn | BGE | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2140_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/27/2017 | Customer Initiated Withdrawal | 10/31/2017 | 10/31/2017 |  | N | No
AB2-141 | George Washington 138kV |  | WV | Marshall | Withdrawn | AEP | 394 | 394 | 388.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2141_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/27/2019 |  | 4/1/2019 |  |  | N | No
AB2-142 | Steele 25kV |  | MD | Caroline | Withdrawn | DPL | 13.4 | 13.4 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2142_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/24/2017 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AB2-143 | Lynch 25kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2143_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 10/14/2016 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AB2-144 | Emmitsburg–Taneytown 2 34.5 kV |  | MD | Frederick | Withdrawn | APS | 13.8 | 13.8 | 5.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2144_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 11/9/2016 | Customer Milestone Not Met | 3/1/2017 |  |  | N | No
AB2-145 | Axton 138kV |  | VA | Henry | Withdrawn | AEP | 572 | 572 | 572 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2145_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/23/2018 |  | 1/1/2021 |  |  | N | No
AB2-146 | Axton 138kV |  | VA | Henry | Withdrawn | AEP | 382 | 382 | 382 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 10/3/2016 | Customer Initiated Withdrawal | 1/1/2021 |  |  | N | No
AB2-147 | Clubhouse-Freeman 115kV |  | VA | Greensville | Withdrawn | Dominion | 40 | 40 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2147_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/11/2017 | Customer Initiated Withdrawal | 10/30/2017 |  |  | N | No
AB2-148 | Mapleton-Murphy 115kV |  | NC | Hertford | Withdrawn | Dominion | 19.9 | 19.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/18/2016 | Customer Milestone Not Met | 10/30/2017 |  |  | N | No
AB2-149 | Myrtle-Windsor 115kV |  | VA | Isle of Wight | Withdrawn | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2149_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/21/2017 | Customer Initiated Withdrawal | 10/30/2017 |  |  | N | No
AB2-150 | Clubhouse-Freeman 115kV |  | VA | Greensville | Withdrawn | Dominion | 40 | 40 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2150_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/11/2017 | Customer Initiated Withdrawal | 10/30/2017 |  |  | N | No
AB2-151 | Mapleton-Murphy 115kV |  | NC | Hertford | Withdrawn | Dominion | 19.9 | 19.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/18/2016 | Customer Milestone Not Met | 10/30/2017 |  |  | N | No
AB2-152 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 57.6 | 54 | 54 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2152_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/1/2017 | Customer Initiated Withdrawal | 6/30/2019 |  |  | N | No
AB2-153 | Church-Wye Mills 138 kV | Pondtown Solar 2 | MD | Queen Anne's | In Service | DPL | 40 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2153_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2153_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_153_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_153_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 9/23/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB2-154 | Kendall 345kV |  | IL | Kendall | Withdrawn | ComEd | 1283 | 65 | 65 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2154_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/27/2016 | Customer Initiated Withdrawal | 5/1/2017 |  |  | N | No
AB2-155 | Richland-Stryker |  | OH | Defiance | Withdrawn | ATSI | 379 | 25 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2155_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 11/4/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AB2-156 | W.H. Zimmer 345kV |  | OH | Clermont | Withdrawn | DEOK | 1350 | 50 | 50 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2156_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AB2-157 | Prince George's County 12kV | Rollins Avenue Phoenix | MD | Prince George's | In Service | PEPCO | 2.5 | 2.5 | 0.8 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2157_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2157_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2157_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/19/2019 |  |  | 7/12/2019 | 7/12/2019 | 12/23/2019 | N | No
AB2-158 | Louisa-South Anna 230kV | Belcher Solar | VA | Louisa | In Service | Dominion | 88.2 | 88.2 | 61 | 88.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2158_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2158_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_158_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 5/31/2021 |  |  | 12/1/2020 | 12/1/2020 | 6/30/2021 | N | No
AB2-159 | Lumberton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 8.1 | 1.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 12/11/2017 |  | 10/3/2016 |  |  | N | No
AB2-160 | Reams 115kV | Reams Solar | VA | Dinwiddie | Withdrawn | Dominion | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2160_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_160_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_160_csa.pdf | Document Posted | N/A | N/A | 5/31/2026 | 4/30/2016 | N/A | N/A | 10/30/2026 | 7/18/2024 |  | 12/31/2022 | 12/31/2022 |  | N | No
AB2-161 | Waverly #2 DP 115kV | Waverly Solar | VA | Sussex | In Service | Dominion | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2161_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_161_csa.pdf | Document Posted | N/A | N/A | 11/2/2023 | 5/2/2016 | N/A | N/A | 12/21/2023 |  |  | 12/29/2023 | 12/29/2023 | 3/14/2024 | N | No
AB2-162 | Camden 480V |  | NJ | Camden | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/30/2016 | Customer Milestone Not Met | 12/31/2016 |  |  | Y | No
AB2-163 | Sicklerville 12kV |  | NJ | Camden | Withdrawn | AEC | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | Y | No
AB2-164 | Wattsville-Wallops Island 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2164_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018 |  |  | N | No
AB2-165 | Tasley-Oak Hall 69kV I |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2165_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018 |  |  | N | No
AB2-166 | Edgewood 12kV | Aydelotte Solar Project | MD | Wicomico | Withdrawn | DPL | 5.5 | 5.5 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2166_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2166_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2166_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 1/10/2019 |  | 3/31/2019 | 3/31/2019 |  | N | No
AB2-167 | Stockton 69kV |  | MD | Worcester | Withdrawn | DPL | 14 | 14 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2167_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 8/11/2017 | Customer Initiated Withdrawal | 11/1/2017 |  |  | N | No
AB2-168 | Perch 34.5kV | Crouse Solar Project | MD | Cecil | Withdrawn | DPL | 9 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2168_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2168_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2168_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2168_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 3/9/2020 |  | 9/6/2022 | 9/6/2022 |  | N | No
AB2-169 | Pantago-Five Points 115kV | Wilkinson Solar Energy Center | NC | Hyde | In Service | Dominion | 74 | 74 | 39 | 74 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2169_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2169_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_169_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_169_csa.pdf | Document Posted | N/A | N/A | 10/10/2019 | 4/29/2016 | N/A | N/A | 11/18/2019 |  |  | 6/30/2021 | 6/30/2021 | 11/20/2019 | N | No
AB2-170 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | In Service | AEP | 150 | 130 | 49.4 | 130 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2170_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2170_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_170_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_170_csa.pdf | Document Posted | N/A | N/A | 8/7/2020 | 4/29/2016 | N/A | N/A | 10/13/2020 |  |  | 6/1/2021 | 6/1/2021 | 10/13/2020 | N | No
AB2-171 | Handsome 115kV |  | VA | Southampton | Withdrawn | Dominion | 75 | 75 | 28.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2171_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/18/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AB2-172 | Todd 69kV | Richfield Solar and Storage | MD | Dorchester | In Service | DPL | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2172_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2172_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_172_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_172_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2016 | N/A | N/A | 1/30/2024 |  |  | 1/10/2024 | 1/10/2024 | 2/9/2024 | N | No
AB2-173 | Nelson 345kV |  | IL | Lee | Withdrawn | ComEd | 206 | 16 | 28 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2173_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 12/24/2019 |  | 6/1/2018 |  |  | N | No
AB2-174 | Emporia-Trego 115kV | Greensville County Solar Project | VA | Greensville | In Service | Dominion | 80 | 80 | 42 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_174_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/1/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/1/2020 | N | No
AB2-175 | Peach Bottom 500kV | Peach Bottom Units #2 & #3 | PA | York | Partially in Service - Under Construction | PECO | 2709.8 | 44 | 44 | 44 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2175_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_175_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A | 3/26/2019 |  |  | 12/31/2018 | 12/31/2018 | 3/26/2019 | N | No
AB2-176 | Chase City 34.5kV |  | VA | Mecklenburg | Withdrawn | Dominion | 14 | 14 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2176_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/23/2018 |  | 6/1/2017 |  |  | N | No
AB2-177 | Kenney 25kV |  | MD | Worcester | Withdrawn | DPL | 6.6 | 6.6 | 2.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2177_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 6/9/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB2-178 | Beckjord 138kV | 138kV Bus 5 Beckjord Battery | OH | Clermont | Withdrawn | DEOK | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_178_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_178_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 12/10/2019 |  | 11/30/2018 | 11/30/2018 |  | N | No
AB2-179 | Townsend 138kV | New Castle Solar | DE | New Castle | In Service | DPL | 50 | 50 | 37.6 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2179_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2179_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_179_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_179_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 11/22/2022 |  |  | 12/16/2022 | 12/16/2022 | 12/30/2022 | N | No
AB2-180 | Rockawalkin 69kV | Hebron Solar | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2180_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2180_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2180_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2180_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 10/6/2022 |  | 2/29/2024 | 2/29/2024 |  | N | No
AB2-181 | Catoctin 138kV |  | MD | Frederick | Withdrawn | APS | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 6/2/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-182 | Townsend 25kV |  | MD | Cecil | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-183 | Massey 25kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-184 | Monkton |  | MD | Baltimore County | Withdrawn | BGE | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/19/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-185 | Wye Mills 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 8 | 8 | 5.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2185_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2185_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 4/14/2021 |  | 6/30/2017 |  |  | N | No
AB2-186 | South Hertford 34.5kV |  | NC | Perquimans | Withdrawn | Dominion | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2186_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 1/28/2019 |  | 6/30/2017 |  |  | N | No
AB2-187 | Indian River-Nelson 138kV |  | DE | Sussex | Withdrawn | DPL | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-188 | Creswell 34.5kV |  | NC | Washington | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2188_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/20/2019 |  | 6/30/2017 |  |  | N | No
AB2-189 | Mackeys 230kV |  | NC | Washington | Withdrawn | Dominion | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-190 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | In Service | Dominion | 150 | 150 | 105 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2190_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2190_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_190_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 8/6/2021 |  | Customer Milestone Not Met | 12/1/2021 | 12/1/2021 | 1/19/2022 | N | No
AB2-191 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 70.4 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2191_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_191_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 3/1/2019 | 3/1/2019 | 2/11/2019 | N | No
AB2-192 | Tasley-Oak Hall 69kV II |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2192_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018 |  |  | N | No
AC1-001 | Delano 138kV | Salt City Solar | OH | Ross | In Service | AEP | 49.9 | 49.9 | 33.93 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1001_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_001_csa.pdf | Document Posted | N/A | N/A | 6/29/2023 | 5/6/2016 | N/A | N/A | 6/29/2023 |  |  | 8/31/2023 | 8/31/2023 | 8/8/2023 | N | No
AC1-002 4804066 | AMIL-PJM |  | N/A | N/A | Withdrawn | ATSI | 550 | 550 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4804066_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4804066_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/5/2016 | 6/1/2017 | 6/1/2022 |  | 10/24/2017 |  |  |  |  | FF | No
AC1-003 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I | WV | Brooke | Withdrawn | APS | 830 | 80 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_003_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/9/2016 | N/A | N/A | 12/31/2021 | 10/10/2020 |  | 8/3/2021 | 8/3/2021 |  | N | No
AC1-004 4804766 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 300 | 300 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4804766_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/10/2016 | 6/1/2017 | 6/1/2022 |  | 8/5/2016 |  |  |  |  | FF | No
AC1-005 | Zion-Stateline |  | IL | Cook | Withdrawn | ComEd | 1000 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2016 | N/A | N/A |  | 6/6/2016 |  | 12/31/2021 |  |  | S | No
AC1-006 | Aydlett 34.5kV |  | NC | Currituck | Withdrawn | Dominion | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2016 | N/A | N/A |  | 9/21/2016 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AC1-007 | Crittenden 34.5kV |  | VA | Isle of Wight | Withdrawn | Dominion | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1007_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2016 | N/A | N/A |  | 4/11/2017 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AC1-008 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 1799.3 | 15 | 19.2 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1008_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_008_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 6/9/2016 | N/A | N/A |  |  |  | 1/13/2023 | 1/13/2023 | 2/7/2023 | N | No
AC1-009 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1009_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2016 | N/A | N/A |  | 3/29/2018 |  | 3/31/2019 |  |  | N | No
AC1-010 | Gloucester 26kV | National Park NJ | NJ | Gloucester | Under Construction | PSEG | 6 | 6 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_010_csa.pdf | Document Posted | N/A | N/A | 1/30/2026 | 6/22/2016 | N/A | N/A | 2/9/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AC1-011 | Emlenton 34.5kV |  | PA | Clarion | Withdrawn | PENELEC | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2016 | N/A | N/A |  | 4/21/2017 | Customer Milestone Not Met | 1/5/2018 |  |  | N | Yes
AC1-012 | Rupert 34.5kV | Tri-State Solar | WV | Greenbrier | Withdrawn | AEP | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1012_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1012_wmpa.pdf | Not Required | N/A | N/A |  | 6/23/2016 | N/A | N/A |  | 7/30/2018 |  | 10/31/2017 | 10/31/2017 |  | Y | No
AC1-013 | Clybourn 12.5kV | Western Avenue Battery | IL | Cook | Withdrawn | ComEd | 0.1 | 0.1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1013_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1013_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1013_wmpa.pdf | Not Required | N/A | N/A |  | 6/28/2016 | N/A | N/A |  | 5/7/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-014 | Farmingdale-Bennett I 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1014_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/8/2016 | N/A | N/A |  | 7/10/2017 | Customer Milestone Not Met | 5/30/2018 |  |  | N | Yes
AC1-015 | Farmingdale-Bennett II 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 0.4 | 0.4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1015_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/8/2016 | N/A | N/A |  | 7/10/2017 | Customer Milestone Not Met | 9/1/2017 |  |  | N | Yes
AC1-016 | Burlington 26 kV | Burlington 26 kV Solar | NJ | Burlington | Withdrawn | PSEG | 8.8 | 8.8 | 3.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1016_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1016_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1016_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A | 3/31/2021 |  |  | 3/31/2021 | 3/31/2021 |  | N | No
AC1-017 | Levittown 13 kV | Levittown 13 kV Solar | NJ | Burlington | In Service | PSEG | 3.7 | 3.7 | 1.4 | 3.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1017_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1017_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1017_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A | 4/17/2020 |  |  | 3/31/2020 | 3/31/2020 | 5/28/2020 | N | No
AC1-018 | Morris Park 12.47kV | Strykers Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 1.4 | 1.4 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_018_csa.pdf | Document Posted | N/A | N/A |  | 7/13/2016 | N/A | N/A |  | 8/4/2020 |  | 7/1/2019 | 7/1/2019 |  | N | Yes
AC1-019 | Lake Nelson 13 kV | Lake Nelson 13 kV Solar | NJ | Middlesex | Withdrawn | PSEG | 0.9 | 0.9 | 0.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1019_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1019_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1019_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A |  | 1/22/2018 |  | 11/30/2018 | 11/30/2018 |  | N | No
AC1-020 | Kittatinny-Newton 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 12.2 | 12.2 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1020_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/13/2016 | N/A | N/A |  | 5/31/2017 | Customer Milestone Not Met | 9/1/2016 |  |  | N | Yes
AC1-021 | Yukon Hatfield 500kV | Smithton Generation Station | PA | Westmoreland | In Service | APS | 1050 | 110 | 0 | 110 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1021_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_021_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/14/2016 | N/A | N/A |  |  |  | 3/1/2019 |  | 11/18/2018 | N | No
AC1-022 | N. Vienna 138kV |  | OH | Brown | Withdrawn | DEOK | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2016 | N/A | N/A |  | 8/3/2016 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AC1-023 | Southwest Lima-East Lima 345kV |  | OH | Allen | Withdrawn | AEP | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2016 | N/A | N/A |  | 8/2/2016 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AC1-024 | Frazeysburg 138kV |  | OH | Muskingum | Withdrawn | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1024_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2016 | N/A | N/A |  | 4/21/2017 | Customer Milestone Not Met | 12/1/2018 |  |  | N | No
AC1-025 | Dale Summit | State College Pumping Station Battery | PA | Centre | In Service | APS | 1.5 | 1.5 | 0 | 1.5 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1025_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1025_wmpa.pdf | Not Required | N/A | N/A |  | 7/18/2016 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 2/14/2019 | Y | Yes
AC1-026 | Sayreville |  | NJ | Atlantic | Withdrawn | JCPL | 1.3 | 1.3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/18/2016 | N/A | N/A |  | 8/9/2016 |  |  |  |  | Y | No
AC1-027 | Pendleton 34.5kV | Oceana Solar Facility | VA | City of Virginia Beach | In Service | Dominion | 17.6 | 17.6 | 11.2 | 17.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1027_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1027_wmpa.pdf | Not Required | N/A | N/A |  | 7/26/2016 | N/A | N/A |  |  |  | 1/1/2018 | 1/1/2018 | 12/1/2017 | N | No
AC1-028 | North Salisbury 25kV |  | MD | Wicomico | Withdrawn | DPL | 3.8 | 3.8 | 3.8 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1028_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2016 | N/A | N/A |  | 4/5/2017 | Customer Initiated Withdrawal | 6/30/2017 |  |  | N | No
AC1-029 | South River 230kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 480 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_029_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/29/2016 | N/A | N/A |  | 11/27/2019 |  | 5/16/2019 | 5/16/2019 |  | N | No
AC1-030 | Cinnaminson 13kV | Pennsauken Solar 3 | NJ | Camden | In Service | PSEG | 2.5 | 2.5 | 0.95 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1030_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1030_wmpa.pdf | Not Required | N/A | N/A |  | 8/1/2016 | N/A | N/A |  |  |  | 12/29/2017 | 12/29/2017 | 12/13/2017 | N | Yes
AC1-031 | Hampstead 13 kV |  | MD | Carroll | Withdrawn | BGE | 2 | 2 | 0.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1031_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/1/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AC1-032 | Wilmington |  | IL | Will | Withdrawn | ComEd | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2016 | N/A | N/A |  | 8/30/2017 | Customer Initiated Withdrawal | 6/30/2017 |  |  | Y | No
AC1-033 | Kewanee 138 kV | Midland Wind Farm | IL | Henry | In Service | ComEd | 100.8 | 100.8 | 13.1 | 100.8 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_033_csa.pdf | Document Posted | N/A | N/A | 11/17/2023 | 8/14/2016 | N/A | N/A | 11/21/2023 |  |  | 4/15/2024 | 4/15/2024 | 1/31/2024 | N | No
AC1-034 | Heartsease DP - Mayo Dunbar 115kV | Edgecome Solar Energy Center | NC | Edgecombe | Suspended | Dominion | 75 | 75 | 42.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1034_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1034_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_034_csa.pdf | Document Posted | N/A | N/A | 6/13/2025 | 8/11/2016 | N/A | N/A | 12/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AC1-035 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | ME | 750 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1035_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_035_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2016 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 3/30/2018 | N | No
AC1-036 | Twittys Creek 34.5kV | Twittys Creek Solar | VA | Charlotte | In Service | Dominion | 13.75 | 13.75 | 5.7 | 13.75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1036_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1036_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1036_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/8/2020 | N | No
AC1-037 | Doremus 13kV | Hillside Battery | NJ | Union | Withdrawn | PSEG | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1037_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1037_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2016 | N/A | N/A |  | 8/30/2017 | Customer Initiated Withdrawal | 12/29/2017 | 12/29/2017 |  | N | No
AC1-038 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 293 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1038_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/30/2016 | N/A | N/A |  |  |  | 10/1/2018 | 10/1/2018 | 5/30/2016 | N | No
AC1-039 | Catoctin 34kV | Catoctin Furnace Solar Facility | MD | Frederick | Withdrawn | APS | 20 | 20 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_039_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 2/25/2021 |  | 10/31/2018 | 10/31/2018 |  | N | No
AC1-040 | Rockport-Duff-Coleman 345 kV |  | IN | Spencer | Withdrawn | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 11/7/2018 |  | 12/31/2020 |  |  | N | No
AC1-041 | Mt. Olive 12kV |  | MD | Worcester | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1041_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 6/5/2018 |  | 5/1/2018 |  |  | N | No
AC1-042 | Altavista-Mt. Airy 69kV | Sycamore Solar I | VA | Pittsylvania | In Service | Dominion | 42 | 42 | 15.96 | 42 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1042_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_042_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_042_csa.pdf | Document Posted | N/A | N/A |  | 9/1/2016 | N/A | N/A | 3/23/2023 |  |  | 12/1/2022 | 12/1/2022 | 2/14/2023 | N | No
AC1-043 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1043_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1043_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_043_csa.pdf | Document Posted | N/A | N/A | 10/28/2026 | 8/31/2016 | N/A | N/A | 3/25/2027 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AC1-044 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1650 | 550 | 550 | 550 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_044_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 8/31/2016 | N/A | N/A | 9/17/2022 |  |  | 12/31/2022 | 12/31/2022 | 12/7/2022 | N | No
AC1-045 | King's Fork 34.5kV | TWE Myrtle Solar | VA | City of Suffolk | Withdrawn | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1045_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1045_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 6/22/2018 |  | 11/15/2018 | 11/15/2018 |  | N | No
AC1-046 | Fentress 34.5kV | Centerville Pike Solar | VA | City of Chesapeake | Withdrawn | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1046_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1046_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 10/20/2017 |  | 11/15/2018 | 11/15/2018 |  | N | No
AC1-047 | Hickory 34.5kV | TWE Chesapeake Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1047_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1047_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1047_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 10/20/2017 |  | 11/15/2018 | 11/15/2018 |  | N | Yes
AC1-048 | Germantown 115kV | Brookview Solar I | PA | Adams | Withdrawn | ME | 35 | 35 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_048_csa.pdf | Document Posted | N/A | N/A | 11/30/2033 | 8/31/2016 | N/A | N/A | 12/30/2033 | 12/11/2023 |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-049 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1049_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 12/6/2018 |  | 5/1/2018 |  |  | N | No
AC1-050 | Mardela 12kV | Mardela Springs | MD | Wicomico | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1050_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1050_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1050_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 8/27/2018 |  | 5/1/2018 |  |  | N | No
AC1-051 | Willard-S. Greenwich 69kV |  | OH | Huron | Withdrawn | AEP | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1051_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_051_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 1/12/2021 |  | 12/31/2017 |  |  | N | No
AC1-052 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 9 | 9 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 3/20/2018 |  | 5/1/2017 |  |  | N | No
AC1-053 | Lanesville-Brokaw | Top Hat Wind Energy Center | IL | Logan | Under Construction | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_053_csa.pdf | Document Posted | N/A | N/A | 8/31/2025 | 9/1/2016 | N/A | N/A | 8/20/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AC1-054 | Kerr Dam–Eatons Ferry 115 kV | Hawtree Creek | NC | Warren | In Service | Dominion | 65 | 65 | 44.5 | 65 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1054_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1054_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_054_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A | 12/1/2021 |  |  | 6/1/2021 | 6/1/2021 | 10/1/2021 | N | No
AC1-055 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 580 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1055_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_055_csa.pdf | Document Posted | N/A | N/A | 11/11/2027 | 9/10/2016 | N/A | N/A | 7/31/2028 |  |  | 1/31/2029 | 1/31/2029 |  | N | No
AC1-056 4831048 | PJM-AMIL |  | N/A | N/A | Confirmed |  | 100 | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4831048_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4831048_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/12/2016 | 6/1/2018 | 6/1/2025 | [6 empty] | FF | No
AC1-057 4831050 | PJM-MECS |  | N/A | N/A | Retracted | ATSI | 200 | 200 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4831050_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4831050_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/12/2016 | 6/1/2018 | 6/1/2025 |  | 10/30/2017 |  |  |  |  | FF | No
AC1-058 4831663 | PJM-AMIL |  | N/A | N/A | Retracted |  | 300 | 300 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4831663_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/13/2016 | 6/1/2018 | 6/1/2023 |  | 11/14/2016 |  |  |  |  | FF | No
AC1-059 | Desoto-Tanners Creek 345kV |  | IN | Fayette | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1059_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2016 | N/A | N/A |  | 6/5/2018 |  | 12/15/2018 |  |  | N | No
AC1-060 | Providence Forge 34.5kV | Charles City 1 | VA | Charles City | In Service | Dominion | 24 | 0 | 2.5 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_060_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 6/9/2017 | N | No
AC1-061 | Locks 34.5kV | Dinwiddie 2 | VA | Dinwiddie | In Service | Dominion | 3 | 0 | 0.2 | 0 | Capacity | Generation Interconnection | Diesel; Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_061_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 6/1/2017 | N | No
AC1-062 | Jetersville 34.5kV | Amelia 1 | VA | Amelia | In Service | Dominion | 16 | 0 | 1.9 | 0 | Capacity | Generation Interconnection | Diesel; Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_062_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/24/2018 | N | No
AC1-063 | Shackleford 34.5kV | King & Queen Landfill Facility | VA | King and Queen | In Service | Dominion | 14 | 0 | 2.2 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1063_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_063_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 5/9/2019 | N | No
AC1-064 | Route 16 34.5kV | Route 16 (Mountain View) 345kV (Upton 114) | PA | Franklin | In Service | APS | 15 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_064_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 6/22/2017 | N | No
AC1-065 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1065_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1065_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_065_csa.pdf | Document Posted | N/A | N/A | 10/7/2025 | 9/22/2016 | N/A | N/A | 6/6/2026 |  |  | 7/14/2026 | 7/14/2026 |  | N | No
AC1-066 | Linden 26 kV |  | NJ | Union | Withdrawn | PSEG | 5 | 5 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1066_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/21/2016 | N/A | N/A |  | 12/11/2017 |  | 9/1/2017 |  |  | N | No
AC1-067 | Davis Creek-Burnham |  | IL | Cook | Withdrawn | ComEd | 1254 | 1254 | 1092 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2016 | N/A | N/A |  | 3/27/2019 |  | 12/1/2021 |  |  | N | No
AC1-068 | Atlanta 69kV I | Pickaway County Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 34 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_068_csa.pdf | Document Posted | N/A | N/A | 10/10/2024 | 9/28/2016 | N/A | N/A | 10/11/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-069 | Atlanta 69kV II | Pickaway County II Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 34 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_069_csa.pdf | Document Posted | N/A | N/A | 10/10/2024 | 9/28/2016 | N/A | N/A | 10/11/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-070 | Stuarts Draft 23kV |  | VA | Augusta | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1070_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2016 | N/A | N/A |  | 12/15/2017 |  | 10/1/2018 |  |  | N | Yes
AC1-071 | Paupack-Lackawanna 230kV | Waymart Wind II | PA | Wayne | Withdrawn | PPL | 67.25 | 67.25 | 8.74 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1071_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_071_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2016 | N/A | N/A | 10/15/2024 | 9/8/2022 |  | 10/15/2021 | 10/15/2021 |  | N | No
AC1-072 | Segreto (Covert) 345kV | Covert Generating Facility | MI | Van Buren | In Service | ITCI | 1055 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1072_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2016 | N/A | N/A |  |  |  | 6/18/2018 | 6/18/2018 | 5/9/2018 | N | No
AC1-073 | Laurel Mountain 138 kV | Laurel Mountain Wind Farm & Energy Storage Facility | WV | Barbour | Canceled | APS | 141.3 | 16.3 | 5.8 | 0 | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1073_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_073_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2016 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 |  | N | No
AC1-074 | Jacksonville-Renaker 138kV I | Bluebird Solar | KY | Harrison | In Service | EKPC | 80 | 80 | 56 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1074_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1074_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_074_csa.pdf | Document Posted | N/A | N/A | 11/6/2024 | 9/30/2016 | N/A | N/A | 6/23/2025 |  |  | 5/28/2025 | 5/28/2025 | 9/3/2025 | N | No
AC1-075 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | In Service | Dominion | 60 | 60 | 38.3 | 60 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_075_csa.pdf | Document Posted | N/A | N/A | 3/3/2021 | 9/29/2016 | N/A | N/A | 3/30/2021 |  |  | 12/31/2021 | 12/31/2021 | 4/1/2021 | N | No
AC1-076 | Locust Grove-Paytes 115kV | Pine Glade Solar | VA | Orange | In Service | Dominion | 62.5 | 62.5 | 23.8 | 62.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_076_csa.pdf | Document Posted | N/A | N/A | 5/30/2024 | 10/2/2016 | N/A | N/A | 7/19/2024 |  |  | 7/15/2024 | 7/15/2024 | 9/13/2024 | N | No
AC1-077 | Sayreville Storage |  | NJ | Middlesex | Withdrawn | JCPL | 0.04 | 0.38 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 10/27/2016 |  |  |  |  | Y | No
AC1-078 | Beatty-London 138kV | Big Plain | OH | Madison | In Service | ATSI | 176 | 176 | 66 | 176 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1078_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_078_csa.pdf | Document Posted | N/A | N/A | 5/5/2023 | 10/1/2016 | N/A | N/A | 6/25/2023 |  |  | 8/31/2023 | 8/31/2023 | 7/25/2023 | N | No
AC1-079 | Broadwell Solar |  | KY | Harrison | Withdrawn | EKPC | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 10/21/2016 |  | 6/1/2019 |  |  | N | No
AC1-080 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | In Service | Dominion | 80 | 20 | 12.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1080_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1080_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_080_csa.pdf | Document Posted | N/A | N/A | 3/3/2021 | 9/30/2016 | N/A | N/A | 3/30/2021 |  |  | 12/31/2021 | 12/31/2021 | 4/1/2021 | N | No
AC1-081 | Susquehanna-Lackawanna 500kV |  | PA | Luzerne | Withdrawn | PPL | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1081_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 4/7/2017 | Customer Initiated Withdrawal | 9/28/2020 |  |  | N | No
AC1-082 | Ravenswood-Hemlock 69kV | Great Bend | OH | Meigs | Under Construction | AEP | 48 | 48 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1082_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_082_csa.pdf | Document Posted | N/A | N/A | 10/1/2025 | 10/1/2016 | N/A | N/A | 10/7/2025 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AC1-083 | Smith Mountain-Bearskin 138kV | Maplewood Solar | VA | Pittsylvania | In Service | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1083_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1083_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_083_csa.pdf | Document Posted | N/A | N/A | 12/15/2021 | 9/30/2016 | N/A | N/A | 9/2/2022 |  |  | 5/20/2022 | 5/20/2022 | 9/2/2022 | N | No
AC1-084 | Mt. Arlington Solar |  | NJ | Morris | Withdrawn | JCPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 10/17/2016 |  | 3/31/2018 |  |  | N | No
AC1-085 | Stuart-Clinton 345kV | Highland County Solar | OH | Highland | In Service | Dayton | 400 | 400 | 152 | 400 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1085_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1085_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_085_csa.pdf | Document Posted | N/A | N/A |  | 10/2/2016 | N/A | N/A | 10/27/2023 |  |  | 12/31/2023 | 12/31/2023 | 8/21/2024 | N | No
AC1-086 | Thelma 230kV | Cherry Solar | NC | Northhampton | Suspended | Dominion | 180 | 180 | 123.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_086_csa.pdf | Document Posted | N/A | N/A |  | 10/11/2016 | N/A | N/A | 12/15/2025 |  |  | 8/31/2025 | 8/31/2025 |  | N | No
AC1-087 | Siegfried-Hauto 69kV | PA Solar Park | PA | Carbon | In Service | PPL | 20 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1087_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_087_csa.pdf | Document Posted | N/A | N/A |  | 10/11/2016 | N/A | N/A | 12/1/2019 |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AC1-088 | Strawton 138kV |  | IN | Madison | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1088_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2016 | N/A | N/A |  | 5/8/2018 |  | 12/31/2017 |  |  | N | No
AC1-089 | Hillsboro-Wildcat 138kV | Willowbrook Solar | OH | Highland | In Service | AEP | 150 | 150 | 57 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_089_csa.pdf | Document Posted | N/A | N/A | 11/13/2023 | 10/15/2016 | N/A | N/A | 11/13/2023 |  |  | 1/19/2024 | 1/19/2024 | 9/27/2024 | N | No
AC1-090 | Hamilton Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1090_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2016 | N/A | N/A |  | 7/17/2017 | Customer Milestone Not Met | 10/1/2017 |  |  | N | Yes
AC1-091 | Cedar Creek 138kV I | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1091_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_091_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_091_csa.pdf | Document Posted | N/A | N/A | 9/1/2026 | 10/19/2016 | N/A | N/A | 9/15/2026 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-092 | Cedar Creek 138kV II | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 39.6 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_092_csa.pdf | Document Posted | N/A | N/A | 9/1/2026 | 10/20/2016 | N/A | N/A | 9/15/2026 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-093 | Cedar Creek 138kV III | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 58.4 | 18.8 | 7.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_093_csa.pdf | Document Posted | N/A | N/A | 9/1/2026 | 10/20/2016 | N/A | N/A | 9/15/2026 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-094 | Cedar Creek 138kV IV | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 74.3 | 15.9 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1094_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1094_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_094_csa.pdf | Document Posted | N/A | N/A | 9/1/2026 | 10/20/2016 | N/A | N/A | 9/15/2026 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-095 | Cedar Creek 25kV |  | DE | New Castle | Withdrawn | DPL | 9.9 | 9.9 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2016 | N/A | N/A |  | 3/9/2020 |  | 6/30/2018 |  |  | N | No
AC1-096 | Marysville-Flatlick 765kV |  | OH | Pickaway | Withdrawn | AEP | 1277 | 1277 | 1277 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2016 | N/A | N/A |  | 2/23/2017 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AC1-097 | Hatfield 500kV | Renaissance Energy Center | PA | Greene | Withdrawn | APS | 1140 | 1140 | 1040 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1097_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1097_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_097_csa.pdf | Document Posted | N/A | N/A |  | 10/21/2016 | N/A | N/A |  | 11/11/2019 |  | 6/1/2021 |  |  | N | No
AC1-098 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Under Construction | Dominion | 60 | 60 | 37.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1098_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1098_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_098_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_098_csa.pdf | Document Posted | N/A | N/A | 8/13/2025 | 10/22/2016 | N/A | N/A | 9/15/2025 |  |  | 11/15/2025 | 11/15/2025 |  | N | No
AC1-099 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Under Construction | Dominion | 80 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1099_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1099_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_099_csa.pdf | Document Posted | N/A | N/A | 8/13/2025 | 10/22/2016 | N/A | N/A | 9/15/2025 |  |  | 11/15/2025 | 11/15/2025 |  | N | No
AC1-100 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 678 | 98 | 43.4 | 98 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1100_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_100_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/10/2017 | N | No
AC1-101 | Johns Creek-Excel 138kV I | Pike County Solar | KY | Pike | Suspended | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_101_csa.pdf | Document Posted | N/A | N/A | 10/1/2028 | 10/26/2016 | N/A | N/A | 11/1/2028 |  |  | 12/1/2028 | 12/1/2028 |  | N | No
AC1-102 | Johns Creek-Excel 138kV II | Pike County Solar | KY | Pike | Suspended | AEP | 100 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1102_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_102_csa.pdf | Document Posted | N/A | N/A | 10/1/2028 | 10/25/2016 | N/A | N/A | 11/1/2028 |  |  | 12/1/2028 | 12/1/2028 |  | N | No
AC1-103 | Nottingham 138kV | Harrison Power Plant | OH | Harrison | Withdrawn | AEP | 1050 | 1050 | 1026 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_103_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2016 | N/A | N/A |  | 7/21/2022 |  | 6/11/2024 | 6/11/2024 |  | N | No
AC1-104 | Deepwater-Penns Grove 69kV |  | NJ | Salem | Withdrawn | AEC | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2016 | N/A | N/A |  | 11/6/2017 |  | 6/30/2018 |  |  | N | No
AC1-105 | Halifax-Mt. Laurel 115kV | Sunnybrook Farm Solar | VA | Halifax | In Service | Dominion | 51 | 51 | 34.5 | 51 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_105_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A | 12/20/2022 |  |  | 2/9/2023 | 2/9/2023 | 12/28/2022 | N | No
AC1-106 | Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 49.9 | 0 | 15.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1106_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2016 | N/A | N/A |  | 4/10/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC1-107 | Chickahominy 500kV | Chickahominy Power | VA | Charles City | Withdrawn | Dominion | 1600 | 1600 | 1600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_107_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A | 3/1/2024 | 2/13/2022 |  | 3/1/2024 | 3/1/2024 |  | N | No
AC1-108 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1100 | 50 | 100 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1108_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A | 9/13/2019 |  |  | 3/1/2021 | 3/1/2021 | 9/22/2019 | N | No
AC1-109 | Aurora 345kV | Aurora Generation | IL | Du Page | In Service | ComEd | 980 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 8/27/2020 | N | No
AC1-110 | Aurora 138kV | Aurora Generation | IL | Du Page | In Service | ComEd | 1046 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1110_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_110_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 8/28/2023 | 8/28/2023 | 4/30/2023 | N | No
AC1-111 | Aurora 138kV | Aurora Generation | IL | Du Page | In Service | ComEd | 1016 | 36 | 36 | 36 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 8/27/2020 | N | No
AC1-112 | Old Church 34.5kV | Hollyfield Solar Facility | VA | King William | In Service | Dominion | 17 | 17 | 10.9 | 17 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1112_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1112_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 8/8/2018 | N | No
AC1-113 | Rockford | Rockford I Energy Center | IL | Winnebago | In Service | ComEd | 320 | 20 | 20 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1113_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 | 6/5/2021 | N | No
AC1-114 | Rockford II | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 173 | 20 | 20 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1114_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 | 8/25/2021 | N | No
AC1-115 | St. Johns 115kV |  | VA | Caroline | Withdrawn | Dominion | 14.9 | 14.9 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1115_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 12/29/2017 |  | 4/30/2018 |  |  | N | No
AC1-116 | Mount Eagle 34.5kV | Rivanna Solar | VA | Albemarle | Withdrawn | Dominion | 12.5 | 12.5 | 4.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1116_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1116_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 6/5/2023 |  | 4/17/2023 | 4/17/2023 |  | N | Yes
AC1-117 | Stockton 34.5kV | Leatherwood | VA | Henry | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1117_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1117_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1117_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | Yes
AC1-118 | Westmoreland 34.5kV | Montross Solar Facility | VA | Westmoreland | In Service | Dominion | 20 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1118_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1118_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1118_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 12/12/2018 | N | No
AC1-119 | Deep Run |  | NJ | Middlesex | Withdrawn | JCPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 11/16/2016 |  | 4/30/2017 |  |  | N | No
AC1-120 | Mitchell-Mountain Run 115kV | Cricket Solar | VA | Culpeper | Engineering and Procurement | Dominion | 60 | 60 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1120_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1120_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_120_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_120_csa.pdf | Document Posted | N/A | N/A | 1/1/2027 | 10/29/2016 | N/A | N/A | 6/1/2027 |  |  | 2/28/2029 | 2/28/2029 |  | N | No
AC1-121 | Mitchell-Mountain Run 115kV | Cricket Solar | VA | Culpeper | Engineering and Procurement | Dominion | 80 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1121_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1121_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_121_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_121_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2016 | N/A | N/A | 6/1/2027 |  |  | 2/28/2029 | 2/28/2029 |  | N | No
AC1-122 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | In Service | AEP | 60 | 60 | 40.7 | 60 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1122_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1122_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_122_csa.pdf | Document Posted | N/A | N/A | 9/30/2020 | 10/27/2016 | N/A | N/A | 10/21/2020 |  |  | 6/1/2021 | 6/1/2021 | 10/21/2020 | N | No
AC1-123 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | In Service | AEP | 80 | 20 | 13.7 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1123_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1123_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_123_csa.pdf | Document Posted | N/A | N/A | 9/30/2020 | 10/27/2016 | N/A | N/A | 10/15/2020 |  |  | 6/1/2021 | 6/1/2021 | 10/21/2020 | N | No
AC1-124 | Harryette 12kV |  | OH | Guernsey | Withdrawn | AEP | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1124_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 7/20/2017 | Customer Initiated Withdrawal | 10/1/2017 |  |  | Y | No
AC1-125 | Harryette 12kV |  | OH | Guernsey | Withdrawn | AEP | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1125_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 7/20/2017 | Customer Initiated Withdrawal | 10/1/2017 |  |  | Y | No
AC1-126 4841985 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841985_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841985_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-127 4841988 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841988_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841988_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-128 4841989 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841989_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841989_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-129 4841990 | PJM-CPLE |  | N/A | N/A | Confirmed |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841990_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841990_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 | [6 empty] | FF | No
AC1-130 4841991 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 10/31/2016 |  |  |  |  | FF | No
AC1-131 4841992 | PJM-CPLE |  | N/A | N/A | Confirmed |  | 50 | 50 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841992_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841992_ltf2.pdf | Executed Agreement and/or Study |  | Not Required | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 | [6 empty] | FF | No
AC1-132 4841993 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 50 | 50 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841993_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841993_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-133 4841994 | PJM-CPLE |  | N/A | N/A | Withdrawn |  | 100 | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4841994_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4841994_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-134 | Four Rivers 230kV | Doswell Facility (Doswell Complex 5 & 6) | VA | Hanover | In Service | Dominion | 746 | 0 | 50 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1134_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_134_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 | 2/28/2018 | N | No
AC1-135 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 1274 | 0 | 62 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/16/2016 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AC1-136 | Keriton 12kV |  | KY | Keaton | Withdrawn | DEOK | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/4/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC1-137 | Erlanger 12kV |  | KY | Boone | Withdrawn | DEOK | 1.9 | 1.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/4/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC1-138 | Bend Station 12kV |  | KY | Boone | Withdrawn | DEOK | 2.5 | 2.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/28/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC1-139 | Doubs 230kV |  | MD | Frederick | Withdrawn | APS | 102 | 102 | 38.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1139_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 10/31/2017 |  | 6/1/2019 |  |  | N | No
AC1-140 | North Longview 500 kV | Longview Power | WV | Monongalia | In Service | APS | 710 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1140_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_140_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_140_csa.pdf | Document Posted | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 6/30/2018 | 6/30/2018 | 5/14/2018 | N | No
AC1-141 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | In Service | AEP | 1085 | 91 | 91 | 91 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1141_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/24/2021 | 10/28/2016 | N/A | N/A | 12/27/2021 |  |  | 3/15/2022 | 3/15/2022 | 12/27/2021 | N | No
AC1-142 | Garner-Lancaster 115kV |  | VA | Lancaster | Withdrawn | Dominion | 100 | 100 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 6/12/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC1-142A | Joliet | Joliet Units 7 and 8 | IL | Will | Deactivated | ComEd | 1100 | 64 | 64 | 64 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1142a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1142a_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_142A_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/8/2020 | N | No
AC1-143 | Brandy-Remington 115kV | Elkwood Solar | VA | Culpeper | Under Construction | Dominion | 60 | 60 | 41.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1143_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1143_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_143_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_143_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 12/16/2024 |  |  | 12/16/2023 | 12/16/2023 |  | N | No
AC1-144 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 85 | 85 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1144_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/18/2018 |  | 10/1/2019 |  |  | N | No
AC1-145 | Gretna DP 69 kV | Whitethorn Solar | VA | Pittsylvania | In Service | Dominion | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1145_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1145_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_145_csa.pdf | Document Posted | N/A | N/A | 7/1/2021 | 10/31/2016 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 10/13/2021 | N | No
AC1-146 | Chatham 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/8/2017 | Customer Initiated Withdrawal | 9/1/2018 |  |  | N | No
AC1-147 | Grassfield 34.5kV |  | VA | City of Chesapeake | In Service | Dominion | 20 | 20 | 12.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1147_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1147_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1147_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A | 9/30/2022 |  |  | 12/31/2021 | 12/31/2021 | 3/25/2022 | N | Yes
AC1-148 | Granger-Twin Branch 138kV |  | IN | St. Joseph | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1148_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 3/16/2018 |  | 11/1/2018 |  |  | N | No
AC1-149 | Buckskin 69kV |  | OH | Ross | Withdrawn | AEP | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-150 | Beaver 138kV |  | OH | Pike | Withdrawn | AEP | 200 | 200 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-151 | Harwood-Berwick 69kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1151_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1151_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 9/23/2019 |  | 2/28/2019 |  |  | N | No
AC1-152 | Lawrenceburg 345kV PB I | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 1270 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1152_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_152_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/13/2019 | N | No
AC1-153 | Kendall-Tazewell-Dresden-Mole Creek |  | IL | Grundy | Withdrawn | ComEd | 2460 | 1300 | 1250 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1153_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 8/10/2018 |  | 6/1/2021 |  |  | N | No
AC1-154 | I.B. Corners 12kV | Harris Project | MD | Queen Anne's | Withdrawn | DPL | 3.2 | 3.2 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1154_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1154_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1154_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/25/2018 |  | 11/8/2018 | 11/8/2018 |  | N | No
AC1-155 | Mt. Airy 34.5kV |  | VA | Wythe | Withdrawn | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-156 | Morgan's Cut 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-157 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/18/2016 | Customer Initiated Withdrawal | 10/1/2019 |  |  | N | No
AC1-158 | Spotsylvania 500kV | Spotsylvania Energy Center | VA | Spotsylvania | In Service | Dominion | 485 | 485 | 337 | 485 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1158_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1158_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_158_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 10/31/2016 | N/A | N/A | 12/31/2022 |  |  | 12/31/2022 | 12/31/2022 | 9/2/2020 | N | No
AC1-159 | Chesapeake 230kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 1250.1 | 250.1 | 369.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 10/3/2018 |  | 1/1/2021 |  |  | N | No
AC1-160 | Buckskin 69kV |  | OH | Ross | Withdrawn | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/18/2016 | Customer Initiated Withdrawal | 10/1/2019 |  |  | N | No
AC1-161 | Septa 500kV | Cavalier | VA | Isle of Wight | In Service | Dominion | 240 | 240 | 168.2 | 240 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1161_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_161_csa.pdf | Document Posted | N/A | N/A | 6/23/2023 | 11/2/2016 | N/A | N/A | 12/12/2023 |  |  | 1/1/2023 | 1/1/2023 | 12/10/2024 | N | No
AC1-162 | Briery-Clover 230kV |  | VA | Prince Edward | Withdrawn | Dominion | 240 | 240 | 168.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1162_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 2/26/2019 |  | 10/1/2019 |  |  | N | No
AC1-163 | Ahoskie 34.5KV |  | NC | Hertford | Withdrawn | Dominion | 16.94 | 16.94 | 11.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1163_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/1/2018 |  | 10/1/2019 |  |  | N | No
AC1-164 | Chickahominy 230kV | Chickahominy Solar 1 and 2 | VA | Charles City | Partially in Service - Under Construction | Dominion | 320 | 320 | 220.8 | 225 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1164_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1164_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_164_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_164_csa.pdf | Document Posted | N/A | N/A | 8/1/2025 | 10/31/2016 | N/A | N/A | 8/1/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AC1-165 | Atlanta 69kV III | Buckeye Plains II Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 33.6 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1165_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1165_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_165_csa.pdf | Document Posted | N/A | N/A | 9/19/2024 | 11/2/2016 | N/A | N/A | 10/2/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-166 | Atlanta 69kV IV | Buckeye Plains Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 33.6 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1166_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1166_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_166_csa.pdf | Document Posted | N/A | N/A | 9/19/2024 | 11/2/2016 | N/A | N/A | 10/2/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-167 | Mark Center 69kV | Mark Center Solar Project | OH | Defiance | Under Construction | AEP | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1167_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1167_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_167_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_167_csa.pdf | Document Posted | N/A | N/A | 3/31/2026 | 11/1/2016 | N/A | N/A | 4/30/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AC1-168 | Kewanee-Streator | Hickory Wind | IL | Putnam | Suspended | ComEd | 78.65 | 78.65 | 10.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1168_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1168_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_168_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_168_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AC1-169 | Chicago Heights |  | IL | Will | Withdrawn | ComEd | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/4/2018 |  | 9/30/2017 |  |  | Y | No
AC1-170 | New Canton 12.47V |  | NJ | Mercer | Withdrawn | JCPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1170_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 4/28/2017 | Customer Initiated Withdrawal | 10/1/2017 |  |  | Y | Yes
AC1-171 | Powerton | ZEP Valley Wind Farm | IL | Tazewell | Withdrawn | ComEd | 79.1 | 79.1 | 10.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1171_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1171_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_171_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_171_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 10/18/2022 |  | 12/15/2025 | 12/15/2025 |  | N | No
AC1-172 | Lawrenceburg 345kV PB II | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 1320 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1172_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_172_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/13/2019 | N | No
AC1-173 | Logtown 138kV | Timber Road IV Wind Farm (Southern Phase) | OH | Paulding | In Service | AEP | 75.9 | 75.9 | 9.9 | 75.9 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1173_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_173_csa.pdf | Document Posted | N/A | N/A | 2/5/2020 | 10/31/2016 | N/A | N/A | 2/15/2020 |  |  | 3/31/2020 | 3/31/2020 | 3/27/2020 | N | No
AC1-174 | Losantville 345kV | Riverstart Solar Park | IN | Randolph | In Service | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_174_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/24/2021 |  |  | 6/1/2022 | 6/1/2022 | 9/24/2021 | N | No
AC1-175 | Losantville 345kV | Riverstart Solar Park | IN | Randolph | In Service | AEP | 200 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1175_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1175_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_175_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/10/2021 |  |  | 6/1/2022 | 6/1/2022 | 9/24/2021 | N | No
AC1-176 | Timber Switch 138kV |  | OH | Paulding | Withdrawn | AEP | 58.7 | 58.7 | 7.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1176_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/9/2020 |  | 10/31/2019 |  |  | N | No
AC1-177 | Kings Creek 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1177_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/28/2019 |  | 1/1/2019 |  |  | N | No
AC1-178 | Millsboro 25kV |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/5/2016 |  | 1/1/2019 |  |  | N | No
AC1-179 | Millsboro 25kV II |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/5/2016 |  | 1/1/2019 |  |  | N | No
AC1-180 | Kings Creek 25kV |  | MD | Somerset | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1180_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 3/20/2017 | Customer Initiated Withdrawal | 1/1/2019 |  |  | N | No
AC1-181 | Richland 138kV | Richland Power Plant | OH | Defiance | In Service | ATSI | 428 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1181_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2019 |  | 8/8/2018 | N | No
AC1-182 | W.H. Zimmer Station 345kV | Zimmer Station | OH | Clermont | Deactivated | DEOK | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1182_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_182_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 1/13/2019 | N | No
AC1-183 | Ontelaunee 230kV |  | PA | Berks | Withdrawn | ME | 608.1 | 12 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1183_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/15/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC1-184 | Printz |  | PA | Delaware | Withdrawn | PECO | 676.5 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1184_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/25/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC1-185 | Lee County | Lee Energy Facility | IL | Lee | In Service | ComEd | 688 | 48 | 48 | 48 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1185_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1185_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2019 |  | 12/14/2018 | N | No
AC1-186 | Central City 115kV |  | PA | Somerset | Withdrawn | PENELEC | 138 | 138 | 17.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1186_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/11/2018 |  | 12/31/2019 |  |  | N | No
AC1-187 | Potter-Gold 115kV |  | PA | Potter | Withdrawn | APS | 117 | 117 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1187_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/20/2018 |  | 12/31/2019 |  |  | N | No
AC1-188 | Rio-Lick 138kV | Dixon Solar | OH | Jackson | Engineering and Procurement | AEP | 70 | 70 | 46.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1188_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1188_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ac1_188_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_188_csa.pdf | Document Posted | N/A | N/A | 12/21/2026 | 11/1/2016 | N/A | N/A | 1/4/2027 |  |  | 2/26/2027 | 2/26/2027 |  | N | No
AC1-189 | Chinquapin-Everetts 230kV | Pitt Solar | NC | Pitt | Engineering and Procurement | Dominion | 80 | 80 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1189_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1189_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_189_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_189_csa.pdf | Document Posted | N/A | N/A | 4/30/2026 | 10/31/2016 | N/A | N/A | 5/5/2026 |  |  | 11/17/2026 | 11/17/2026 |  | N | No
AC1-190 | East New Market 69kV | New Market Solar | MD | Dorchester | Suspended | DPL | 50 | 50 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1190_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1190_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_190_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 6/15/2026 |  |  | 7/1/2028 | 7/1/2028 |  | N | No
AC1-191 | Elmont 115kV | Springfield Solar | VA | Hanover | Engineering and Procurement | Dominion | 80 | 80 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1191_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1191_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_191_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_191_csa.pdf | Document Posted | N/A | N/A | 11/10/2026 | 10/31/2016 | N/A | N/A | 1/6/2027 |  |  | 3/31/2024 | 3/31/2024 |  | N | No
AC1-192 | Conastone-Peach Bottom |  | N/A | N/A | Withdrawn | BGE |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/2/2016 |  |  |  |  | EE | No
AC1-193 | Handsome DP-Southampton 115kV |  | VA | Southampton | Withdrawn | Dominion | 130 | 55 | 20.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1193_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/18/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC1-194 | Elk 138kV | Vinton Solar | OH | Vinton | Suspended | AEP | 125 | 125 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1194_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1194_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_194_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_194_csa.pdf | Document Posted | N/A | N/A | 5/31/2025 | 10/31/2016 | N/A | N/A | 6/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AC1-195 | Dunkirk-Ada 69kV |  | OH | Hardin | Withdrawn | AEP | 75 | 75 | 9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1195_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/30/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC1-196 | Mantua 12kV |  | NJ | Gloucester | Withdrawn | AEC | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Initiated Withdrawal | 6/30/2017 |  |  | Y | No
AC1-197 | Somerset 480v | Somerset 480v | NJ | Somerset | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1197_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1197_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1197_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1197_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-198 | Union 480v | Union 480v | NJ | Union | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1198_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1198_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1198_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1198_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-199 | Mercer 480v I | Mercer 480v I | NJ | Mercer | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1199_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1199_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1199_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1199_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 1/31/2018 | 1/31/2018 |  | Y | No
AC1-200 | Mercer 480v II | Mercer 480v II | NJ | Mercer | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1200_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1200_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1200_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1200_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 2/28/2018 | 2/28/2018 |  | Y | No
AC1-201 | Camden 480v II | Camden 480v II | NJ | Camden | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1201_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1201_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1201_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1201_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-202 | Cedar 12kV | The Home Depot Store #0951 | NJ | Ocean | Withdrawn | AEC | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1202_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1202_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1202_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1202_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/12/2018 |  | 12/31/2018 | 12/31/2018 |  | Y | No
AC1-203 | Camden 480v III | Camden 480v III | NJ | Camden | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1203_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1203_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1203_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1203_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-204 | Elwood | Jackson Generation | IL | Will | In Service | ComEd | 1200.9 | 1200.9 | 1115.9 | 1200.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1204_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1204_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1204_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_204_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_204_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 11/8/2021 |  |  | 4/1/2022 | 4/1/2022 | 5/3/2022 | N | No
AC1-205 | Madison Park |  | NJ | Middlesex | Withdrawn | JCPL | 10.3 | 10.3 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/17/2016 |  | 12/29/2017 |  |  | N | No
AC1-206 | Clubhouse 230kV |  | VA | Greensville | Withdrawn | Dominion | 85 | 85 | 57.72 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1206_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1206_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 1/18/2018 |  | 10/1/2019 |  |  | N | No
AC1-207 | Monroe 34.5kV | Hoffman Station Road Solar | NJ | Middlesex | In Service | JCPL | 13.1 | 13.1 | 4.9 | 13.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1207_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1207_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_207_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_207_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 6/16/2020 |  |  | 5/26/2020 | 5/26/2020 | 6/25/2020 | N | Yes
AC1-208 | Cox-Whitakers 115kV | Halifax County Solar | NC | Halifax | Under Construction | Dominion | 80 | 80 | 55.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1208_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1208_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1208_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_208_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_208_csa.pdf | Document Posted | N/A | N/A | 4/27/2026 | 11/1/2016 | N/A | N/A | 7/27/2026 |  |  | 8/9/2026 | 8/9/2026 |  | N | No
AC1-209 | Pine Grove Solar | Pine Grove Solar | PA | York | Withdrawn | PECO | 18 | 18 | 12.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1209_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1209_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1209_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1209_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 10/4/2019 |  | 9/30/2021 | 9/30/2021 |  | N | Yes
AC1-210 | Madison 69kV |  | OH | Madison | Withdrawn | AEP | 45 | 45 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1210_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/17/2018 |  | 6/30/2018 |  |  | N | No
AC1-211 | McConnellsburg 138kV |  | PA | Fulton | Withdrawn | APS | 70 | 70 | 48.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1211_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1211_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/6/2017 |  | 6/30/2018 |  |  | N | No
AC1-212 | Minster 69kV | Minster III ESS | OH | Auglaize | Withdrawn | Dayton | 19.9 | 19.9 | 1.9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1212_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1212_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1212_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1212_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A | 7/1/2020 | 12/16/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AC1-213 | North Salisbury 25kV |  | MD | Somerset | Withdrawn | DPL | 5.3 | 5.3 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1213_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1213_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/24/2021 |  | 9/30/2017 |  |  | N | No
AC1-214 | Crescent Ridge | Lone Tree Wind | IL | Bureau | In Service | ComEd | 79.4 | 79.4 | 19 | 79.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1214_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1214_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1214_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_214_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_214_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 11/27/2020 |  |  | 12/30/2020 | 12/30/2020 | 11/20/2020 | N | No
AC1-215 | Chase-City-Twittys Creek 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 100 | 100 | 68.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1215_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/21/2017 | Customer Initiated Withdrawal | 6/30/2018 |  |  | N | No
AC1-216 | Hopewell-Surry 230kV | Spring Grove I Solar | VA | Surry | In Service | Dominion | 97.9 | 97.9 | 54.8 | 97.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1216_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1216_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1216_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_216_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_216_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 9/14/2020 |  |  | 12/1/2020 | 12/1/2020 | 10/1/2020 | N | No
AC1-217 | McConnellsburg-Texas Eastern 6 138kV |  | PA | Franklin | Withdrawn | APS | 55 | 55 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1217_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1217_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/29/2017 |  | 6/30/2018 |  |  | N | No
AC1-218 |  |  | NJ | Morris | Withdrawn | JCPL | 0.25 | 0.25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/7/2016 |  | 1/31/2017 |  |  | Y | No
AC1-219 |  |  | NJ | Morris | Withdrawn | JCPL | 0.2 | 0.2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/7/2016 |  | 1/31/2017 |  |  | Y | No
AC1-220 | Price 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 26.5 | 26.5 | 15.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1220_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1220_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/8/2018 |  | 9/30/2018 |  |  | N | No
AC1-221 | Halifax-Person 230kV | Alton Post Office Solar | VA | Halifax | In Service | Dominion | 29.2 | 29.2 | 14.6 | 29.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1221_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1221_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_221_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_221_csa.pdf | Document Posted | N/A | N/A | 9/26/2024 | 11/2/2016 | N/A | N/A | 10/31/2024 |  |  | 12/31/2024 | 12/31/2024 | 1/9/2025 | N | No
AC1-222 | Crystal Hill-Halifax 115kV | Halifax County Solar | VA | Halifax | In Service | Dominion | 44.7 | 44.7 | 22.9 | 44.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1222_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1222_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1222_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_222_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_222_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 11/3/2016 | N/A | N/A | 12/7/2023 |  |  | 12/29/2023 | 12/29/2023 | 2/15/2024 | N | No
AC1-223 | E. Frankfort-University Park North |  | IL | Will | In Service | ComEd | 0 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ac1223_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ac1223_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/ac1223_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 |  | 12/12/2018 | EE | No
AC1-224 | Wye Mills 25kV |  | MD | Talbot | Withdrawn | DPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1224_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1224_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1224_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 4/4/2018 |  | 2/1/2017 |  |  | Y | No
AC1-225 | Sorenson-Marysville 765kV |  | OH | Van Wert | Withdrawn | AEP | 300.2 | 300.2 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1225_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1225_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/16/2018 |  | 12/31/2019 |  |  | N | No
AC1-226 | Wurno-Claytor 138kV |  | VA | Pulaski | Withdrawn | AEP | 200.1 | 200.1 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1226_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 4/3/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC1-227 | Low Moor-Lexington 230kV |  | VA | Botetourt | Withdrawn | Dominion | 96.6 | 96.6 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1227_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/13/2018 |  | 12/31/2019 |  |  | N | No
AC1-228 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1228_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1228_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 2/23/2018 |  | 3/31/2018 |  |  | N | No
AC1-229 | Omar 12kV |  | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1229_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1229_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/6/2018 |  | 3/31/2018 |  |  | N | No
AC2-001 |  |  | OH | Van Wert | Withdrawn | AEP | 300.2 | 300.2 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 12/6/2016 | Queue Not Required | 12/31/2019 |  |  | N | No
AC2-002 |  |  | VA | Pulaski | Withdrawn | AEP | 179.4 | 179.4 | 23 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 12/6/2016 | Queue Not Required | 12/31/2019 |  |  | N | No
AC2-003 |  |  | VA | Botetourt | Withdrawn | Dominion | 78.2 | 78 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 12/6/2016 | Queue Not Required | 10/12/2023 |  |  | N | No
AC2-004 | Meyersdale 115kV |  | PA | Somerset | Withdrawn | PENELEC | 98.75 | 50.75 | 6.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2004_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 7/12/2018 |  | 12/13/2019 |  |  | N | No
AC2-005 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 1/23/2017 |  | 3/31/2018 |  |  | N | No
AC2-006 | Oman 12kV |  | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 1/23/2017 |  | 3/31/2018 |  |  | N | No
AC2-007 | Belvidere |  | IL | Boone | Withdrawn | ComEd | 20 | 20 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2007_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 7/5/2018 |  | 12/31/2017 |  |  | N | No
AC2-008 | Wildcat 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2016 | N/A | N/A |  | 6/5/2017 | Customer Initiated Withdrawal | 6/3/2019 |  |  | N | No
AC2-009 | Pennington 13 kV | Pennington 13 kV Solar | NJ | Mercer | In Service | PSEG | 0.59 | 0.59 | 0.1 | 0.55 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2009_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2009_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2009_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2016 | N/A | N/A | 6/1/2023 |  |  | 3/2/2018 | 3/2/2018 | 10/19/2017 | N | Yes
AC2-010 | Millsboro 25kV |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2016 | N/A | N/A |  | 3/24/2017 | Customer Milestone Not Met | 4/30/2018 |  |  | N | No
AC2-011 | Millsboro 25kV II |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2016 | N/A | N/A |  | 3/24/2017 | Customer Milestone Not Met | 7/31/2018 |  |  | N | No
AC2-012 | Grassfield-Great Bridge 115kV | Shillelagh Solar | VA | City of Chesapeake | In Service | Dominion | 118 | 118 | 44.8 | 118 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2012_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2012_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_012_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2016 | N/A | N/A | 11/8/2023 |  |  | 12/31/2023 | 12/31/2023 | 12/20/2023 | N | No
AC2-013 | Ripley 69kV |  | MD | Charles | Withdrawn | PEPCO | 27.5 | 27.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2016 | N/A | N/A |  | 1/24/2017 | Customer Milestone Not Met | 11/30/2018 |  |  | N | No
AC2-014 | Ripley-Nanjemoy 69kV |  | MD | Charles | Withdrawn | PEPCO | 32.5 | 32.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2016 | N/A | N/A |  | 1/24/2017 | Customer Milestone Not Met | 11/30/2018 |  |  | N | No
AC2-015 | Chatfield-Howard 138kV | Sycamore Creek Solar | OH | Crawford | Under Construction | AEP | 117 | 117 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2015_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_015_csa.pdf | Document Posted | N/A | N/A | 6/13/2025 | 12/29/2016 | N/A | N/A | 9/22/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AC2-016 | Stemple 345kV | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 748 | 6 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2016_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_016_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/3/2017 | N/A | N/A |  |  |  | 9/1/2019 | 9/1/2019 | 2/14/2020 | N | No
AC2-017 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 1810.4 | 11.1 | 11.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2017_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_017_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 1/4/2017 | N/A | N/A |  |  |  | 1/13/2023 | 1/13/2023 | 2/7/2023 | N | No
AC2-018 | Rock Springs 500kV | Rock Springs Units #3 & #4 | MD | Cecil | In Service | Essential Power | 390 | 60 | 8 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2018_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/19/2017 | N/A | N/A |  |  |  | 6/1/2017 |  | 10/1/2017 | N | No
AC2-019 | Highland 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2017 | N/A | N/A |  | 7/13/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC2-020 | Greenfield-Buckskin 69kV |  | OH | Ross | Withdrawn | Dayton | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2020_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2017 | N/A | N/A |  | 8/3/2018 |  | 12/31/2019 |  |  | N | No
AC2-021 | Albright-Cross School 138 kV |  | MD | Garrett | Withdrawn | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2021_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2021_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 9/9/2020 |  | 1/15/2019 |  |  | N | No
AC2-022 | Gordonsville-Remington 230kV |  | VA | Culpeper | Withdrawn | Dominion | 100 | 100 | 70.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2022_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 11/1/2017 |  | 9/30/2019 |  |  | N | No
AC2-023 | Hebron 69kV | Porter Mill Solar | MD | Wicomico | Engineering and Procurement | DPL | 45.8 | 45.8 | 26.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2023_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_023_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_023_csa.pdf | Document Posted | N/A | N/A | 6/1/2026 | 1/25/2017 | N/A | N/A | 7/1/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AC2-024 | Edison 4kV |  | NJ | Middlesex | Withdrawn | PSEG | 1.2 | 1.2 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2024_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 1/29/2018 |  | 12/31/2017 |  |  | N | Yes
AC2-025 | Hatfield 500kV |  | PA | Greene | Withdrawn | APS | 1140 | 1140 | 1140 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 3/28/2017 | Customer Initiated Withdrawal | 6/1/2022 |  |  | N | No
AC2-026 | Wakefield 138kV |  | OH | Scioto | Withdrawn | AEP | 50 | 50 | 27.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2026_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2017 | N/A | N/A |  | 9/6/2017 | Customer Milestone Not Met | 6/30/2019 |  |  | N | No
AC2-027 | Highland 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2017 | N/A | N/A |  | 7/19/2017 | Customer Initiated Withdrawal | 11/30/2018 |  |  | N | No
AC2-028 | Highland 13.2kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2017 | N/A | N/A |  | 4/12/2017 | Customer Initiated Withdrawal | 10/31/2018 |  |  | N | No
AC2-029 | Circleville 138kV | Circleville Solar Energy | OH | Pickaway | Suspended | AEP | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2029_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2029_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_029_csa.pdf | Document Posted | N/A | N/A | 11/1/2026 | 2/2/2017 | N/A | N/A | 12/1/2026 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AC2-030 | East Beaver 69kV |  | OH | Pike | Withdrawn | AEP | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2030_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 12/6/2017 |  | 12/31/2018 |  |  | N | No
AC2-031 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2031_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/4/2017 |  | 10/1/2019 |  |  | N | No
AC2-032 | Graceton-Cooper 230kV |  | N/A | N/A | Withdrawn | BGE | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/3/2017 |  | 6/1/2018 |  |  | EE | No
AC2-033 | Graceton-Bagley 230kV |  | N/A | N/A | Withdrawn | BGE | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/24/2017 |  |  |  |  | EE | No
AC2-034 | Eugene-Dequine 345kV |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 3/24/2017 |  |  |  |  | EE | No
AC2-035 | Lick-Firebrick 69kV |  | OH | Jackson | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2035_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 2/25/2019 |  | 6/1/2019 |  |  | N | No
AC2-036 | Ravenswood-East Bashan Switch 69kV |  | OH | Meigs | Withdrawn | AEP | 0 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2036_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 3/12/2019 |  | 6/1/2020 |  |  | N | No
AC2-037 | Lick 69kV |  | OH | Jackson | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/5/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-038 | Lee 69kV |  | OH | Athens | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2038_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 9/27/2019 |  | 6/1/2019 |  |  | N | No
AC2-039 | Poston-Dexter 69kV |  | OH | Athens | Withdrawn | AEP | 43 | 43 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/5/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-040 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2040_imp.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/18/2017 |  | 6/1/2019 |  |  | N | No
AC2-041 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2041_fea,pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/18/2017 |  | 6/1/2019 |  |  | N | No
AC2-042 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2042_imp.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/18/2017 |  | 6/1/2019 |  |  | N | No
AC2-043 | W. Millersport-S. Baltimore 138kV |  | OH | Fairfield | Withdrawn | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2043_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2017 | N/A | N/A |  | 9/14/2018 |  | 12/15/2018 |  |  | N | No
AC2-044 | Maddox Creek 345kV | Blue Creek Wind Farm | OH | Van Wert | Suspended | AEP | 370 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_044_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2017 | N/A | N/A |  |  |  | 11/30/2024 | 11/30/2024 |  | N | No
AC2-045 | Clark 12kV | Solar Power and Light, LLC | OH | Athens | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2045_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2045_wmpa.pdf | Not Required | N/A | N/A |  | 2/7/2017 | N/A | N/A |  | 6/29/2020 |  | 12/31/2019 | 12/31/2019 |  | N | No
AC2-046 | EAst Beaver 138kV |  | OH | Jackson | Withdrawn | AEP | 63 | 63 | 39.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2046_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/8/2017 | N/A | N/A |  | 9/26/2017 |  | 12/31/2018 |  |  | N | No
AC2-047 | Ashley-Millbrook Park 69 kV |  | OH | Scioto | Withdrawn | AEP | 18.3 | 18.3 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2047_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/8/2017 | N/A | N/A |  | 10/23/2017 |  | 10/31/2018 |  |  | N | No
AC2-048 | Sporn 138kV |  | OH | Meigs | Withdrawn | AEP | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2048_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/10/2017 | N/A | N/A |  | 1/9/2023 |  | 12/31/2018 |  |  | N | No
AC2-049 | Hillsboro-Millbrook 138kV |  | OH | Highland | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2049_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2017 | N/A | N/A |  | 10/13/2017 |  | 6/1/2019 |  |  | N | No
AC2-050 | Tabernacle 12kV | Seneca Energy | NJ | Burlington | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2050_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2050_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2050_wmpa.pdf | Not Required | N/A | N/A |  | 2/10/2017 | N/A | N/A |  | 6/27/2022 |  | 11/30/2025 | 11/30/2025 |  | N | No
AC2-051 | Pickaway Solar |  | OH | Pickaway | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2017 | N/A | N/A |  | 3/24/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-052 4862612 | PJM-LINDENVFT |  | N/A | N/A | Confirmed |  | 300 | 330 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4862612_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 2/14/2017 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
AC2-053 | Germantown 115kV | Brookview Solar I | PA | Adams | Withdrawn | ME | 55 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_053_csa.pdf | Document Posted | N/A | N/A | 11/30/2033 | 2/15/2017 | N/A | N/A | 12/30/2033 | 12/11/2023 |  | 12/31/2023 | 12/31/2023 |  | N | No
AC2-054 | South Rultonham 69kV |  | OH | Muskingum | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2017 | N/A | N/A |  | 5/1/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-055 | Buckskin 69kV |  | OH | Highland | Withdrawn | AEP | 47.5 | 47.5 | 18.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2017 | N/A | N/A |  | 4/22/2021 |  | 7/1/2019 |  |  | N | No
AC2-056 | Killen 345kV |  | OH | Adams | Withdrawn | Dayton | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2017 | N/A | N/A |  | 5/5/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-057 | Ridgeway-Dan River 69kV |  | VA | Pittsylvania | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2057_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  | 10/4/2017 |  | 12/31/2018 |  |  | N | No
AC2-058 | Newcomerstown-N. Philly 69kV |  | OH | Tuscarawas | Withdrawn | AEP | 16.37 | 16.37 | 16.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  | 7/12/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-059 | Biers Run-Circleville 138kV | Yellowbud Solar | OH | Ross | In Service | AEP | 127 | 127 | 62.5 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_059_csa.pdf | Document Posted | N/A | N/A | 10/24/2022 | 2/16/2017 | N/A | N/A | 12/21/2022 |  |  | 12/15/2022 | 12/15/2022 | 12/21/2022 | N | No
AC2-060 | Buckskin 69kV | Ross County Solar | OH | Ross | In Service | AEP | 100 | 100 | 64 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_060_csa.pdf | Document Posted | N/A | N/A | 8/16/2024 | 2/18/2017 | N/A | N/A | 9/17/2024 |  |  | 6/1/2024 | 6/1/2024 | 2/19/2025 | N | No
AC2-061 | Hillsboro-Clinton 138kV | Dodson Creek Solar | OH | Ross | In Service | AEP | 117 | 117 | 58.1 | 117 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2061_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2061_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_061_csa.pdf | Document Posted | N/A | N/A | 3/14/2025 | 2/17/2017 | N/A | N/A | 3/30/2025 |  |  | 5/30/2025 | 5/30/2025 | 6/17/2025 | N | No
AC2-062 | Emerald-Kenton 138kV |  | OH | Brown | Withdrawn | AEP | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2062_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 10/4/2017 |  | 12/31/2019 |  |  | N | No
AC2-063 | Earleys 230kV |  | NC | Bertie | Withdrawn | Dominion | 100 | 100 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 3/17/2017 | Customer Milestone Not Met | 10/31/2019 |  |  | N | No
AC2-064 | Hillsboro-Millbrook 138kV |  | OH | Highland | Withdrawn | AEP | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 12/9/2019 |  | 6/1/2019 |  |  | N | No
AC2-065 | Delaware-Darby 138kV |  | N/A | N/A | Withdrawn | Dayton | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 5/24/2017 |  | 6/1/2018 |  |  | EE | No
AC2-066 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | In Service | DEOK | 200 | 75 | 28.5 | 75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2066_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_066_csa.pdf | Document Posted | N/A | N/A | 8/19/2020 | 2/24/2017 | N/A | N/A | 11/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/18/2020 | N | No
AC2-067 | Camden-Crystal I 69kV | Eaton OH Solar | OH | Preble | Engineering and Procurement | Dayton | 49.9 | 49.9 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_067_csa.pdf | Document Posted | N/A | N/A | 11/23/2026 | 2/27/2017 | N/A | N/A | 12/12/2026 |  |  | 1/28/2027 | 1/28/2027 |  | N | No
AC2-068 | Camden-Crystal II 69kV | Eaton OH Solar | OH | Preble | Engineering and Procurement | Dayton | 69.9 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_068_csa.pdf | Document Posted | N/A | N/A | 11/23/2026 | 2/27/2017 | N/A | N/A | 12/12/2026 |  |  | 1/28/2027 | 1/28/2027 |  | N | No
AC2-069 | Jacsonville-Renaker 138kV III |  | KY | Harrison | Withdrawn | EKPC | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2069_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2017 | N/A | N/A |  | 9/11/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-070 | Old Church 34.5kV | Hollyfield II | VA | King William | Withdrawn | Dominion | 13 | 13 | 9.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2070_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2070_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/30/2021 | 1/22/2021 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-071 | Buckingham 35kV | Buckingham IIK | VA | Buckingham | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2071_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2071_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 | 1/22/2021 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-072 | Nokesville 35kV | Nokesville | VA | Prince William | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2072_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2072_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 | 1/22/2021 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-073 | Harmony Village 35kV | Church View | VA | Middlesex | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2073_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2073_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 | 9/24/2019 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-074 | Mt. Jackson 35kV | Mt. Jackson I | VA | Shenandoah | Withdrawn | Dominion | 15.65 | 15.65 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2074_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2074_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 | 1/22/2021 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-075 | Jacksonville-Renaker 138 kV | Bluebird Solar | KY | Harrison | In Service | EKPC | 100 | 20 | 13.3 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_075_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 11/6/2024 | 2/28/2017 | N/A | N/A | 6/23/2025 |  |  | 5/28/2025 | 5/28/2025 | 9/3/2025 | N | No
AC2-076 | Kiski Valley–Vandergrift 25 kV | Kiski Valley | PA | Westmoreland | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2076_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2076_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 10/22/2018 |  | 4/30/2020 | 4/30/2020 |  | N | No
AC2-077 | Sabinsville 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 8/1/2019 |  | 5/31/2018 |  |  | N | No
AC2-078 | Disputanta-Waverly 115kV | Warwick PVI | VA | Prince George | Withdrawn | Dominion | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2078_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_078_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 2/9/2021 |  | 12/1/2022 | 12/1/2022 |  | N | No
AC2-079 | Ivor-Oak Ridge 115kV | Windsor PVI | VA | Isle of Wight | Suspended | Dominion | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_079_csa.pdf | Document Posted | N/A | N/A | 10/29/2024 | 3/3/2017 | N/A | N/A | 11/29/2025 |  |  | 6/1/2023 | 6/1/2023 |  | N | No
AC2-080 | Olive-Reynolds 345kV |  | IN | Jasper | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2080_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 4/21/2021 |  | 12/31/2019 |  |  | N | No
AC2-081 | Battle Town 115kV |  | VA | Clarke | Withdrawn | APS | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 3/24/2017 | Customer Milestone Not Met | 12/31/2019 |  |  | N | No
AC2-082 | Remington-Gainesville 230kV |  | VA | Fauquier | Withdrawn | Dominion | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2082_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 6/5/2018 |  | 12/31/2019 |  |  | N | No
AC2-083 | Dawson-South Justice 115kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 10/3/2020 |  | 6/1/2019 |  |  | N | No
AC2-084 | Dawson-South Justice 115kV | American Beech Solar | NC | Halifax | Under Construction | Dominion | 140 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_084_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_084_csa.pdf | Document Posted | N/A | N/A | 8/13/2025 | 3/2/2017 | N/A | N/A | 9/15/2025 |  |  | 11/15/2025 | 11/15/2025 |  | N | No
AC2-085 | Eastwood 34kV |  | OH | Clermont | Withdrawn | DEOK | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2085_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 7/2/2018 |  | 5/31/2019 |  |  | N | No
AC2-086 | Eastwood 34.5kV |  | OH | Clermont | Withdrawn | DEOK | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 4/10/2017 | Customer Initiated Withdrawal | 5/30/2019 |  |  | N | No
AC2-087 | Buckskin 69kV |  | OH | Ross | Withdrawn | AEP | 85 | 85 | 47.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2087_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 1/15/2020 |  | 5/31/2019 |  |  | N | No
AC2-088 | S. Bethel-Brown 69kV | Nestlewood Solar | OH | Clermont | In Service | DEOK | 70 | 70 | 38.4 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_088_csa.pdf | Document Posted | N/A | N/A | 12/7/2023 | 3/1/2017 | N/A | N/A | 12/20/2023 |  |  | 3/31/2024 | 3/31/2024 | 12/27/2023 | N | No
AC2-089 | Klockner 34.5 kV | Silverside Solar | VA | Wythe | Withdrawn | AEP | 18.2 | 18.2 | 8.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2089_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2089_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2089_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 3/22/2019 |  | 12/31/2019 | 12/31/2019 |  | N | No
AC2-090 | Losantville 345kV | Riverstart Solar Park III | IN | Randolph | In Service | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_090_csa.pdf | Document Posted | N/A | N/A | 3/26/2024 | 3/7/2017 | N/A | N/A | 8/21/2024 |  | Customer Milestone Not Met | 12/31/2024 | 12/31/2024 | 12/18/2024 | N | No
AC2-091 | Modoc (Riverstart Solar IV) 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-092 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1105 | 55 | 65 | 55 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2092_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_092_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/1/2017 | N/A | N/A | 6/1/2023 |  |  | 6/1/2022 | 6/1/2022 | 1/26/2023 | N | No
AC2-093 | Brunswick-Wake 500 kV |  | NC | Northhampton | Withdrawn | Dominion | 675 | 675 | 429.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2093_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2017 | N/A | N/A |  | 7/6/2018 |  | 12/1/2021 |  |  | N | No
AC2-094 | Louisa-North Anna 230kV |  | VA | Louisa | Withdrawn | Dominion | 99.9 | 99.9 | 63.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2094_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2017 | N/A | N/A |  | 10/30/2017 |  | 10/1/2019 |  |  | N | No
AC2-095 | Eastwood 138kV |  | OH | Clermont | Withdrawn | DEOK | 10 | 10 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2017 | N/A | N/A |  | 4/11/2017 | Customer Initiated Withdrawal | 5/30/2019 |  |  | N | No
AC2-096 | Wurno I 34.5KV |  | VA | Pulaski | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 1/10/2018 |  | 6/1/2018 |  |  | N | No
AC2-097 | Wurno II 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 1/10/2018 |  | 6/1/2018 |  |  | N | No
AC2-098 | Buckhorn-Lonesome Pine 138kV |  | VA | Tazewell | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2098_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 8/30/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AC2-099 | Nursery 36kV |  | OH | Lake | Withdrawn | ATSI | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2099_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 9/8/2017 | Customer Initiated Withdrawal | 6/30/2018 |  |  | N | Yes
AC2-100 | Halifax-Person 230kV | Powells Creek Solar | VA | Halifax | In Service | Dominion | 50 | 50 | 33.6 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_100_csa.pdf | Document Posted | N/A | N/A | 7/26/2023 | 3/12/2017 | N/A | N/A | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 | 8/23/2023 | N | No
AC2-101 | Ripley-Nanjemoy 69kV | Shugart Solar | MD | Charles | Withdrawn | SMECO | 32.5 | 32.5 | 12.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2101_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2101_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2101_wmpa.pdf | Not Required | N/A | N/A |  | 3/10/2017 | N/A | N/A | 12/31/2020 | 12/3/2020 |  | 3/15/2021 | 3/15/2021 |  | N | No
AC2-102 | Mitchell DP 115kV |  | VA | Culpeper | Withdrawn | Dominion | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2102_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2017 | N/A | N/A |  | 4/15/2020 |  | 6/30/2019 |  |  | N | No
AC2-103 | Beaver-Davis Besse 345 kV I | Firelands Wind | OH | Erie | Engineering and Procurement | ATSI | 297.66 | 297.66 | 38.69 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_103_csa.pdf | Document Posted | N/A | N/A | 12/18/2026 | 3/10/2017 | N/A | N/A | 11/23/2026 |  |  | 6/7/2025 | 6/7/2025 |  | N | No
AC2-104 | Marysville-Sorenson 765kv |  | OH | Van Wert | Withdrawn | AEP | 500.25 | 500.25 | 65.03 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2017 | N/A | N/A |  | 11/7/2019 |  | 12/31/2020 |  |  | N | No
AC2-105 | Saddler 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 100 | 73.51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 3/29/2017 | Customer Initiated Withdrawal | 10/1/2019 |  |  | N | No
AC2-106 | Biers Run 138kV |  | OH | Ross | Withdrawn | AEP | 100 | 100 | 68.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2106_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 12/13/2017 |  | 10/1/2019 |  |  | N | No
AC2-107 | Perth 115kV |  | VA | Halifax | Withdrawn | Dominion | 100 | 100 | 68.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 3/27/2019 |  | 10/1/2019 |  |  | N | No
AC2-108 | Wharton 115kV |  | NC | Beaufort | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 9/30/2019 |  |  | N | No
AC2-110 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 70 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2110_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_110_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2017 | N/A | N/A | 6/6/2026 |  |  | 7/14/2026 | 7/14/2026 |  | N | No
AC2-111 | College Corner 138kV | Angelina Solar I | OH | Preble | Engineering and Procurement | AEP | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2111_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2111_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ac2_111_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_111_csa.pdf | Document Posted | N/A | N/A | 1/5/2027 | 3/16/2017 | N/A | N/A | 1/30/2027 |  |  | 4/1/2027 | 4/1/2027 |  | N | No
AC2-112 | Stuarts Draft-Waynesboro 115kV | Augusta Solar | VA | Augusta | Withdrawn | Dominion | 150 | 150 | 103.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2112_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2112_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_112_csa.pdf | Document Posted | N/A | N/A |  | 3/17/2017 | N/A | N/A | 12/31/2024 | 9/27/2024 |  | 12/15/2023 | 12/15/2023 |  | N | No
AC2-113 | Culpeper 35kV | Culpeper North | VA | Culpeper | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2113_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2113_wmpa.pdf | Not Required | N/A | N/A |  | 3/17/2017 | N/A | N/A |  | 10/8/2018 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-114 | Magnolia-Summersville 69kV |  | KY | Campbell | Withdrawn | EKPC | 49.9 | 49.9 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2114_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2017 | N/A | N/A |  | 9/13/2017 | Customer Initiated Withdrawal | 7/1/2019 |  |  | N | No
AC2-115 | Rockford | Rockford I Energy Center | IL | Winnebago | In Service | ComEd | 360 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2115_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_115_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 | 8/27/2021 | N | No
AC2-116 | Rockford II | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 180 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2116_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_116_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 | 8/25/2021 | N | No
AC2-117 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 606 | 46 | 46 | 46 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2117_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_117_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 5/31/2021 | 5/31/2021 | 11/6/2023 | N | No
AC2-118 | Cabot-Keystone 500kV |  | PA | Armstrong | Withdrawn | APS | 1200 | 1200 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2118_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2017 | N/A | N/A |  | 8/22/2017 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AC2-119 | Grandview 138kV |  | WV | Raliegh | Withdrawn | AEP | 25 | 25 | 17.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2119_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2017 | N/A | N/A |  | 9/6/2017 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AC2-120 | Ripley 69kV | Ripley Solar | MD | Charles | In Service | SMECO | 27.5 | 27.5 | 10.45 | 10.45 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2120_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2120_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2120_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2120_wmpa.pdf | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 2/28/2023 |  |  | 7/13/2022 | 7/13/2022 | 6/23/2023 | N | No
AC2-121 | Gordonsville-Remington 230kV |  | VA | Culpeper | Withdrawn | Dominion | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2121_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2017 | N/A | N/A |  | 11/2/2017 |  | 9/15/2019 |  |  | N | No
AC2-122 | Lick Run 115kV |  | PA | Somerset | Withdrawn | PENELEC | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2122_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2017 | N/A | N/A |  | 12/10/2018 |  | 12/15/2019 |  |  | N | No
AC2-123 | Jacksons Ferry 138kV | Wythe County Solar Project | VA | Wythe | In Service | AEP | 75 | 75 | 44.6 | 75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2123_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2123_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ac2_123_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_123_csa.pdf | Document Posted | N/A | N/A | 5/16/2024 | 3/25/2017 | N/A | N/A | 2/28/2025 |  |  | 3/30/2025 | 3/30/2025 | 4/3/2025 | N | No
AC2-124 | Gunn Road 345kV |  | OH | Hardin | Withdrawn | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2124_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 11/19/2018 |  | 12/15/2019 |  |  | N | No
AC2-125 | Ladysmith 230 kV I | Ladysmith Combustion Turbines Unit 1 | VA | Caroline | In Service | Dominion | 209 | 19 | 14.9 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2125_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_125_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 6/1/2021 |  |  | 6/1/2020 | 6/1/2020 | 5/17/2019 | N | No
AC2-126 | Ladysmith 230 kV II | Ladysmith Combustion Turbines Unit 2 | VA | Caroline | In Service | Dominion | 209 | 19 | 15 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2126_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_126_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 6/1/2021 |  |  | 6/1/2020 | 6/1/2020 | 5/17/2019 | N | No
AC2-127 | Ladysmith CT Unit 3 |  | VA | Caroline | Withdrawn | Dominion | 209 | 19 | 8.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2127_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 4/12/2019 |  | 6/1/2017 |  |  | N | No
AC2-128 | Ladysmith CT Unit 4 |  | VA | Caroline | Withdrawn | Dominion | 209 | 19 | 7.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2128_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 4/12/2019 |  | 6/1/2017 |  |  | N | No
AC2-129 | Ladysmith CT Unit 5 |  | VA | Caroline | Withdrawn | Dominion | 209 | 19 | 7.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2129_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 4/12/2019 |  | 6/1/2017 |  |  | N | No
AC2-130 | Chesterfield 230kV 5 | Chesterfield Unit 5 | VA | Chesterfield | Deactivated | Dominion | 370 | 14 | 13.2 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2130_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_130_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
AC2-131 | Chesterfield 230kV 7 |  | VA | Chesterfield | Withdrawn | Dominion | 246 | 14 | 14.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2131_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 12/17/2018 |  | 6/1/2017 |  |  | N | No
AC2-132 | Chesterfield 230kV 8 |  | VA | Chesterfield | Withdrawn | Dominion | 246 | 11 | 8.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2132_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 12/17/2018 |  | 6/1/2017 |  |  | N | No
AC2-133 | Warren County 500kV | Warren County Power Station | VA | Warren | In Service | Dominion | 1484 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2133_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_133_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 | 9/4/2018 | N | No
AC2-134 | Hamburg 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 9 | 9 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2134_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2017 | N/A | N/A |  | 10/24/2017 |  | 12/31/2018 |  |  | N | Yes
AC2-135 | Double Toll Gate 34.5kV |  | VA | Clarke | Withdrawn | APS | 20 | 20 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2017 | N/A | N/A |  | 6/20/2017 | Customer Initiated Withdrawal | 6/30/2018 |  |  | N | No
AC2-136 | East Hagerstown 12kV | East Hagerstown Solar | MD | Washington | Under Construction | APS | 11.8 | 11.8 | 5.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2136_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2136_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2136_wmpa.pdf | Not Required | N/A | N/A | 11/14/2025 | 3/29/2017 | N/A | N/A | 12/15/2025 |  |  | 5/1/2026 | 5/1/2026 |  | N | No
AC2-137 | Elko 34.5kV | Briel Farm Solar | VA | Henrico | In Service | Dominion | 18.8 | 18.8 | 11.4 | 18.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2137_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2137_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2137_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 | 12/30/2020 | 12/21/2020 | N | No
AC2-138 | Northern Neck 34.5kV | Gardy's Mill Solar | VA | Westmoreland | In Service | Dominion | 10.8 | 10.8 | 4.8 | 10.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2138_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2138_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2138_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 | 12/30/2020 | 12/21/2020 | N | No
AC2-139 | Mantua 12kV | The Home Depot Store # 0974 | NJ | Gloucester | Withdrawn | AEC | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2139_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2139_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A |  | 11/12/2018 |  | 12/30/2018 | 12/30/2018 |  | Y | No
AC2-140 | DC Cook Unit 2 | DC Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 1220 | 28 | 38 | 28 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2140_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_140_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 1/14/2017 | N | No
AC2-141 | Septa 500kV | Sycamore Cross Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 240 | 240 | 168.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 1/1/2027 | 3/30/2017 | N/A | N/A | 3/26/2027 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AC2-142 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 664.7 | 129.7 | 129.7 | 129.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2142_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_142_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A | 3/16/2021 |  |  | 5/9/2021 | 5/9/2021 | 4/1/2021 | N | No
AC2-143 | Cranbury 34.5kV |  | NJ | Middlesex | Withdrawn | JCPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2143_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 11/13/2017 | Customer Initiated Withdrawal | 3/31/2019 |  |  | Y | Yes
AC2-144 | Newburgh 12.47kV | 59 Newburgh | NJ | Warren | Withdrawn | JCPL | 0.25 | 0.25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2144_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2144_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 3/17/2021 |  | 6/1/2018 | 6/1/2018 |  | Y | Yes
AC2-145 | Beach Glen 4.8kV | 94-98 Ford | NJ | Morris | Withdrawn | JCPL | 0.2 | 0.2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2145_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2145_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2145_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 3/17/2021 |  | 6/1/2018 | 6/1/2018 |  | Y | Yes
AC2-146 | Modoc 138kV |  | IN | Randolph | Withdrawn | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-147 | Maryland |  | IL | Ogle | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2147_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 2/18/2020 |  | 5/1/2019 |  |  | N | No
AC2-148 | South Dixon |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 2/6/2018 |  | 5/1/2019 |  |  | N | No
AC2-149 | Glidden |  | IL | DeKalb | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2149_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 7/5/2018 |  | 5/1/2019 |  |  | N | No
AC2-150 | Dixon |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 2/6/2018 |  | 5/1/2019 |  |  | N | No
AC2-151 | Mazon |  | IL | Grundy | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 5/30/2018 |  | 5/1/2019 |  |  | N | No
AC2-152 | Pontiac Midpoint |  | IL | Livingston | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 4/10/2018 |  | 5/1/2019 |  |  | N | No
AC2-153 | Steward |  | IL | DeKalb | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 4/10/2018 |  | 5/1/2019 |  |  | N | No
AC2-154 | Davis Creek 138kV | Staley Solar | IL | Kankakee | Engineering and Procurement | ComEd | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2154_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2154_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_154_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_154_csa.pdf | Document Posted | N/A | N/A | 6/15/2027 | 3/29/2017 | N/A | N/A | 6/1/2027 |  |  | 6/28/2024 | 6/28/2024 |  | N | No
AC2-155 | North Franklin 138kV |  | WV | Pendleton | Withdrawn | APS | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2155_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 8/16/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC2-156 | Sandwich 34.5kV |  | IL | DeKalb | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2156_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 5/5/2021 |  | 3/31/2019 |  |  | N | No
AC2-157 | Sullivan 345 kV | Trade Post Solar Energy Center | IN | Sullivan | Under Construction | AEP | 200 | 200 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2157_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_157_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_157_csa.pdf | Document Posted | N/A | N/A | 11/17/2025 | 3/29/2017 | N/A | N/A | 1/5/2026 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
AC2-158 | Cashie-Earleys 230kV |  | NC | Bertie | Withdrawn | Dominion | 65 | 65 | 32.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2158_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 11/2/2017 |  | 5/1/2019 |  |  | N | No
AC2-159 | Jackson-Woodland 115kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2159_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 11/2/2017 |  | 5/1/2019 |  |  | N | No
AC2-160 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL |  | 1.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2160_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 9/8/2017 | Customer Initiated Withdrawal | 12/1/2017 |  |  | Y | No
AC2-161 | Smithfield 34.5kV | Solidago | VA | Isle of Wight | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2161_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2161_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2161_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 9/5/2018 |  | 12/31/2020 | 12/31/2020 |  | N | No
AC2-162 | Old Church 34.5kV | Sweetspire | VA | Hanover | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2162_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2162_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2162_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 9/10/2018 |  | 12/31/2020 | 12/31/2020 |  | N | No
AC2-163 | Harmony Village-Dunnsville 34.5kV |  | VA | Middlesex | Withdrawn | Dominion | 17.5 | 17.5 | 12.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 3/30/2017 | Customer Initiated Withdrawal | 6/3/2019 |  |  | N | No
AC2-164 | Darby-Urbana 138kV |  | OH | Champaign | Withdrawn | Dayton | 200 | 0 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2164_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 2/22/2018 |  | 12/15/2019 |  |  | N | No
AC2-165 | Bremo-Powhatan 230kV | Cartersville Solar | VA | Powhatan | Suspended | Dominion | 99.9 | 99.9 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2165_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2165_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_165_csa.pdf | Document Posted | N/A | N/A | 10/30/2026 | 3/30/2017 | N/A | N/A | 2/1/2027 |  |  | 5/17/2026 | 5/17/2026 |  | N | No
AC2-166 | Waterman 34 kV |  | IL | DeKalb | Withdrawn | ComEd | 40 | 40 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2166_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 9/25/2018 |  | 12/1/2019 |  |  | N | No
AC2-167 | Boykins-Murphy 115kV |  | VA | Southampton | Withdrawn | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 6/20/2017 | Customer Initiated Withdrawal | 6/30/2019 |  |  | N | No
AC2-168 | Clinton 23kV | Gaucho Solar | PA | Washington | In Service | DL | 11.7 | 11.7 | 4.4 | 11.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2168_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2168_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2168_wmpa.pdf | Not Required | N/A | N/A | 3/21/2023 | 3/30/2017 | N/A | N/A | 3/21/2023 |  |  | 6/1/2023 | 6/1/2023 | 6/29/2023 | N | Yes
AC2-169 | Nortonville 12kV |  | NJ | Gloucester | Withdrawn | AEC | 4.14 | 4.14 | 2.07 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 5/1/2017 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC2-170 | Quarryville | Keystone Solar | PA | Lancaster | Withdrawn | PPL | 5 | 0 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2170_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_170_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A | 12/31/2022 | 10/2/2023 |  | 11/1/2021 | 11/1/2021 |  | N | No
AC2-171 | Jeffersonville 69kV |  | OH | Ross | Withdrawn | Dayton | 29 | 29 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2171_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 8/23/2017 | Customer Initiated Withdrawal | 5/31/2019 |  |  | N | No
AC2-172 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 310 | 17 | 12 | 17 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2172_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_172_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A |  |  |  | 10/1/2018 | 10/1/2018 | 5/30/2016 | N | No
AC2-173 | Wempleton-Belvidere |  | IL | Winnebago | Withdrawn | ComEd | 90 | 90 | 60.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2173_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 10/13/2017 |  | 11/1/2018 | 11/1/2018 |  | N | No
AC2-174 | Double Tollgate 34.5kV | Double Tollgate Solar Project | VA | Clarke | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2174_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2174_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2174_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2017 | N/A | N/A |  | 2/28/2024 |  | 3/31/2023 | 3/31/2023 |  | N | No
AC2-175 | Berkshire Solar 12 kV | Berkshire Solar | NJ | Morris | In Service | JCPL | 1.6 | 1.6 | 0 | 1.6 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2175_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2175_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A | 9/30/2021 |  |  | 9/30/2021 | 9/30/2021 | 11/6/2021 | N | Yes
AC2-176 | Jay 138 kV | Bitter Ridge Wind Farm | IN | Jay | In Service | AEP | 130 | 130 | 16.9 | 130 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2176_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2176_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ac2_176_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_176_csa.pdf | Document Posted | N/A | N/A | 9/2/2020 | 3/31/2017 | N/A | N/A | 9/5/2020 |  |  | 10/31/2020 | 10/31/2020 | 9/5/2020 | N | No
AC2-177 | Desoto-Tanners Creek 345kV |  | IN | Henry | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2177_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 6/17/2021 |  | 12/31/2019 |  |  | N | No
AC2-178 | Ortanna 138kV |  | MD | Frederick | Withdrawn | APS | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 5/31/2019 |  |  | N | No
AC2-179 | Natrium 138kV |  | WV | Marshall | Withdrawn | AEP | 57 | 57 | 48.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2179_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 7/12/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-180 | Babcock & Wilcox 69kV |  | VA | Campbell | Withdrawn | AEP | 12 | 12 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2180_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 11/20/2019 |  | 10/1/2018 |  |  | N | No
AC2-181 | Payne 69kV |  | IN | Randolph | Withdrawn | AEP | 49.9 | 49.9 | 18.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-182 | McConnelsburg-Texas Eastern |  | PA | Franklin | Withdrawn | PENELEC | 80 | 80 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 6/30/2018 |  |  | N | No
AC2-183 | Pepper 69kV |  | DE | Sussex | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 5/1/2017 | Customer Initiated Withdrawal | 12/15/2018 |  |  | N | No
AC2-184 | Cedar Creek 138kV I | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 94.3 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_184_csa.pdf | Document Posted | N/A | N/A | 9/1/2026 | 4/1/2017 | N/A | N/A | 9/15/2026 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC2-185 | Cedar Creek 138kV II | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 114.3 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_185_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_185_csa.pdf | Document Posted | N/A | N/A | 9/1/2026 | 4/1/2017 | N/A | N/A | 9/15/2026 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC2-186 | Harrington 25kV | Raceway Solar | DE | Kent | Under Construction | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2186_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2186_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_186_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_186_csa.pdf | Document Posted | N/A | N/A | 4/1/2026 | 4/1/2017 | N/A | N/A | 4/15/2026 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AC2-187 | Harrington 69kV | Raceway Solar | DE | Kent | Under Construction | DPL | 30 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2187_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2187_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_187_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_187_csa.pdf | Document Posted | N/A | N/A | 4/1/2026 | 3/31/2017 | N/A | N/A | 4/15/2026 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AC2-188 | Harrington 69 kV | Raceway Solar | DE | Kent | Under Construction | DPL | 50 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2188_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2188_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_188_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_188_csa.pdf | Document Posted | N/A | N/A | 4/1/2026 | 3/31/2017 | N/A | N/A | 4/15/2026 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AC2-189 | Crisfield-Kings Creek 69kV |  | MD | Somerset | Withdrawn | DPL | 11.6 | 11.6 | 10.3 |  | Capacity | Generation Interconnection | Methane; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2189_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 4/17/2018 |  | 12/31/2018 |  |  | N | No
AC2-190 | Sussex-Harbeson 69kV |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | 9.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2190_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 9/15/2017 |  | 12/31/2018 |  |  | N | No
AC2-191 | Sussex-Harbeson 69kV II |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | 9.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2191_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 9/15/2017 |  | 9/28/2018 |  |  | N | No
AC2-192 | Greene-Clark 138kV |  | OH | Fayette | Withdrawn | ATSI | 56 | 56 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2192_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 8/29/2017 | Customer Initiated Withdrawal | 5/31/2019 |  |  | N | No
AC2-193 | Camden 26kV |  | NJ | Camden | Withdrawn | PSEG | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AC2-194 | WinFall 34.5kV |  | NC | Perquimans | Withdrawn | Dominion | 16.2 | 16.2 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2194_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 11/8/2017 |  | 12/22/2017 |  |  | N | No
AC2-195 | Galion-Roberts South 138 kV | Marion County Solar Project | OH | Marion | Under Construction | ATSI | 99.96 | 99.96 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2195_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2195_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2195_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_195_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_195_csa.pdf | Document Posted | N/A | N/A | 8/2/2025 | 4/1/2017 | N/A | N/A | 11/17/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AC2-196 | Fentress 34.5kV | Centerville Pike Solar | VA | City of Chesapeake | Withdrawn | Dominion | 16.66 | 16.7 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2196_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2196_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2196_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A | 11/15/2021 | 2/8/2021 |  | 12/15/2021 | 12/15/2021 |  | N | No
AD1-001 | Kilmer 480 v | Kilmer 480V | NJ | Union | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1001_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-002 | North Bergen I 480 v | North Bergen I 480V | NJ | Hudson | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1002_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-003 | North Bergen II 480 v | North Bergen II 480V | NJ | Bergen | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1003_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/1/2020 | 1/1/2020 |  | Y | No
AD1-004 | Paramus 480 v | Paramus 480V | NJ | Bergen | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1004_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-005 | Jackson Rd 480 v | Jackson Road 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1005_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-006 | Secaucus 480 v |  | NJ | Hudson | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 10/26/2017 |  | 12/31/2017 |  |  | Y | No
AD1-007 | Bergenfield 480 v | Bergenfield 480V | NJ | Bergen | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-008 | Sand Hills 480 v | Sand Hills 480V | NJ | Middlesex | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1008_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/21/2020 | 1/21/2020 |  | Y | No
AD1-009 | Saddle Brook 480 v | Saddle Brook 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1009_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-010 | McLean 480 v | McLean 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1010_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-011 | Athenia 480 v | Atheina 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1011_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-012 | Cheesequake 12.5 kV |  | NJ | Middlesex | Withdrawn | JCPL | 0.21 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/1/2017 | Customer Milestone Not Met | 3/31/2018 |  |  | Y | No
AD1-013 | Twombly Road 138kV | Rochelle Solar | IL | Ogle | Engineering and Procurement | ComEd | 40 | 40 | 15.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1013_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1013_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad1_013_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_013_csa.pdf | Document Posted | N/A | N/A | 12/31/2026 | 4/6/2017 | N/A | N/A | 1/1/2027 |  |  | 5/27/2028 | 5/27/2028 |  | N | No
AD1-014 | Hutching-Sugar Creek 138kV |  | N/A | N/A | Withdrawn | Dayton | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 4/17/2017 | N/A | N/A |  | 5/24/2017 |  | 6/1/2018 |  |  | EE | No
AD1-015 | Frazeysburg 138 kV | Muskingum Solar | OH | Muskingum | Withdrawn | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1015_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1015_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_015_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2017 | N/A | N/A |  | 2/14/2022 |  | 12/31/2023 | 12/31/2023 |  | N | No
AD1-016 | Marengo | Marengo Solar, LLC | IL | McHenry | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1016_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1016_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1016_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2017 | N/A | N/A | 3/31/2026 | 8/26/2024 |  | 8/31/2026 | 8/31/2026 |  | N | No
AD1-017 | Smith Mountain-Bearskin 138 kV | Maplewood Solar | VA | Pittsylvania | In Service | AEP | 120 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_017_csa.pdf | Document Posted | N/A | N/A | 12/17/2021 | 5/11/2017 | N/A | N/A | 12/28/2021 |  |  | 12/1/2022 | 12/1/2022 | 9/2/2022 | N | No
AD1-018 | Carlos Jct - Plaza 34 kV | Pigtoe Bobcat Solar | MD | Allegany | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1018_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1018_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1018_wmpa.pdf | Not Required | N/A | N/A |  | 5/12/2017 | N/A | N/A | 1/1/2021 | 10/6/2022 |  | 1/1/2021 | 1/1/2021 |  | N | No
AD1-019 | Ontario 23 kV |  | NJ | Atlantic | Withdrawn | AEC | 13.1 | 7.6 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1019_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2017 | N/A | N/A |  | 3/8/2022 |  | 6/3/2019 |  |  | N | No
AD1-020 | Hunterstown-Lincoln 115 kV | Adams Solar LLC | PA | Adams | In Service | ME | 80 | 80 | 53.6 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1020_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_020_csa.pdf | Document Posted | N/A | N/A | 12/22/2023 | 6/9/2017 | N/A | N/A | 12/27/2023 |  |  | 2/25/2024 | 2/25/2024 | 3/21/2024 | N | No
AD1-021 4885734 | PJM-LindenVFT |  | N/A | N/A | Confirmed | PSEG | 330 | 330 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4885734_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4885734_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/13/2017 | 1/15/2018 | 6/1/2019 | [6 empty] | FF | No
AD1-022 | Cashie-Trowbridge 230 kV | Sumac Solar | NC | Bertie | Engineering and Procurement | Dominion | 80 | 80 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1022_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_022_csa.pdf | Document Posted | N/A | N/A |  | 6/19/2017 | N/A | N/A | 5/1/2028 |  |  | 7/1/2028 | 7/1/2028 |  | N | No
AD1-023 | Cashie-Trowbridge 230 kV |  | NC | Bertie | Withdrawn | Dominion | 40 | 40 | 25.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/19/2017 | N/A | N/A |  | 4/21/2022 |  | 6/1/2019 |  |  | N | No
AD1-024 | Davis Creek-Wilmington |  | IL | Kankakee | Withdrawn | ComEd | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1024_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/19/2017 | N/A | N/A |  | 3/1/2018 |  | 5/1/2019 |  |  | N | No
AD1-025 | Hopewell-Surry 230 kV | Spring Grove Solar II | VA | Surry | Under Construction | Dominion | 150 | 150 | 94.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_025_csa.pdf | Document Posted | N/A | N/A | 6/24/2025 | 6/28/2017 | N/A | N/A | 11/3/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AD1-026 | Shenango-Hoytdale 345 kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 1000 | 0 | 130 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1026_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/22/2019 | 6/28/2017 | N/A | N/A |  |  |  | 3/30/2020 | 3/30/2020 | 4/28/2020 | N | No
AD1-027 | Camden 26 kV |  | NJ | Camden | Withdrawn | PSEG | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2017 | N/A | N/A |  | 8/9/2017 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AD1-028 | Home DepotNJ #957 - Old Bridge | Old Bridge Fuel Cell | NJ | Middlesex | Withdrawn | JCPL | 0.2 | 0.2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1028_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1028_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1028_wmpa.pdf | Not Required | N/A | N/A |  | 7/11/2017 | N/A | N/A |  | 12/18/2018 |  | 3/31/2020 | 3/31/2020 |  | N | Yes
AD1-029 | Scotland Neck-South Justice 115 kV |  | NC | Halifax | Withdrawn | Dominion | 110 | 110 | 66.3 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1029_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2017 | N/A | N/A |  | 3/6/2018 |  | 12/1/2019 |  |  | N | No
AD1-030 | Camden 26 kV II |  | NJ | Burlington | Withdrawn | PSEG | 7 | 7 | 2.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2017 | N/A | N/A |  | 8/9/2017 | Customer Milestone Not Met | 5/31/2018 |  |  | N | No
AD1-031 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Withdrawn | ComEd | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1031_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1031_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_031_csa.pdf | Document Posted | N/A | N/A | 4/15/2027 | 7/24/2017 | N/A | N/A | 4/15/2027 | 6/3/2025 |  | 6/15/2027 | 6/15/2027 |  | N | No
AD1-032 4893040 | PJM-OVEC |  | N/A | N/A | Retracted |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 7/25/2017 | 11/1/2017 | 11/1/2018 | [6 empty] | FF | No
AD1-033 | Fentress-Landstown 230 kV | Bedford Solar Center | VA | City of Chesapeake | In Service | Dominion | 70 | 70 | 42 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_033_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2017 | N/A | N/A | 12/31/2021 |  |  | 12/1/2021 | 12/1/2021 | 11/23/2021 | N | No
AD1-034 | Sapony 230 kV |  | VA | Sussex | Withdrawn | Dominion | 74.9 | 74.9 | 44.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1034_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2017 | N/A | N/A |  | 3/16/2018 |  | 12/31/2020 |  |  | N | No
AD1-035 | Darby-East Liberty 69 kV |  | OH | Union | Withdrawn | Dayton | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1035_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2017 | N/A | N/A |  | 2/20/2018 |  | 10/1/2019 |  |  | N | No
AD1-036 | Chatfield 138 kV |  | OH | Crawford | Withdrawn | AEP | 35 | 35 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2017 | N/A | N/A |  | 9/15/2017 |  | 12/31/2020 |  |  | N | No
AD1-037 | Martins Creek 230 kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 651.6 | 51.6 | 86.6 | 51.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1037_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/28/2017 | N/A | N/A | 8/16/2022 |  |  | 9/29/2019 | 9/29/2019 | 7/10/2019 | N | No
AD1-038 | Oliver Solar |  | NJ | Burlington | Withdrawn | PSEG | 0.3 | 0.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2017 | N/A | N/A |  | 8/25/2017 | Customer Milestone Not Met | 10/31/2019 |  |  | Y | No
AD1-039 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | Partially in Service - Under Construction | ComEd | 1262.7 | 102.7 | 93 | 102.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1039_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/12/2022 | 7/29/2017 | N/A | N/A | 12/30/2022 |  |  | 2/28/2025 | 2/28/2025 | 6/16/2023 | N | No | This project slid to the next queue
AD1-040 | Mount Eagle 34.5 kV |  | VA | Albemarle | Withdrawn | Dominion | 11 | 11 | 4.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 8/10/2017 | Customer Initiated Withdrawal | 4/30/2018 |  |  | N | No
AD1-041 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | In Service | Dominion | 50 | 50 | 30 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1041_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1041_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_041_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 8/3/2017 | N/A | N/A | 7/17/2024 |  |  | 6/28/2024 | 6/28/2024 | 8/22/2024 | N | No
AD1-042 | Stuarts Draft-Waynesboro 115 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 0 | 12.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1042_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 4/10/2018 |  | 10/31/2018 |  |  | N | No
AD1-043 | Makahoy 138 kV | Lone Oak Solar | IN | Madison | Withdrawn | AEP | 120 | 120 | 45.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1043_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1043_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_043_csa.pdf | Document Posted | N/A | N/A | 6/1/2028 | 8/1/2017 | N/A | N/A |  | 6/20/2025 |  | 7/1/2028 | 7/1/2028 |  | N | No
AD1-044 | Oak Grove 34.5 kV I | Oak Grove I | VA | Westmoreland | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1044_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1044_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2017 | N/A | N/A | 6/30/2021 | 8/14/2020 |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-045 | Oak Grove 34.5 kV II | Oak Grove II | VA | Westmoreland | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1045_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1045_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2017 | N/A | N/A | 6/30/2021 | 8/14/2020 |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-046 | Oak Grove 34.5 kV III | Oak Grove III | VA | Westmoreland | Withdrawn | Dominion | 11.2 | 11.2 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1046_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1046_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2017 | N/A | N/A | 6/30/2021 | 8/14/2020 |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-047 | Brink 115 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1047_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 1/30/2020 |  | 12/1/2018 |  |  | N | No
AD1-048 | Turner 34.5 kV | Turner I Solar | VA | Henrico | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1048_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1048_wmpa.pdf | Not Required | N/A | N/A |  | 8/3/2017 | N/A | N/A | 12/31/2022 | 9/5/2019 |  | 12/31/2022 | 12/31/2022 |  | N | No
AD1-049 | Culpeper 34.5 kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 20 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/3/2017 | N/A | N/A |  | 9/11/2018 |  | 12/1/2019 |  |  | N | No
AD1-050 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 45 | 45 | 29.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2017 | N/A | N/A |  | 10/15/2019 |  | 12/1/2019 |  |  | N | No
AD1-051 | Sporn South 138 kV |  | WV | Mason | Withdrawn | AEP | 30 | 30 | 18.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1051_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2017 | N/A | N/A |  | 6/4/2018 |  | 12/31/2018 |  |  | N | No
AD1-052 | Freemont Energy Center | Freemont Energy Center | OH | Sandusky | In Service | ATSI | 745 | 38 | 26.3 | 38 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_052_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/10/2017 | N/A | N/A | 10/1/2020 |  |  | 10/1/2020 | 10/1/2020 | 2/24/2021 | N | No
AD1-053 | Plainsboro 13 kV | Plainsboro 13kV | NJ | Middlesex | Withdrawn | PSEG | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1053_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1053_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1053_wmpa.pdf | Not Required | N/A | N/A |  | 8/11/2017 | N/A | N/A |  | 3/6/2019 |  | 12/31/2018 | 12/31/2018 |  | Y | Yes
AD1-054 | Bergen 13 kV | Bergen 13kV | NJ | Bergen | In Service | PSEG | 1.5 | 1.5 | 0 | 1.5 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1054_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1054_wmpa.pdf | Not Required | N/A | N/A |  | 8/11/2017 | N/A | N/A | 12/20/2019 |  |  | 10/15/2019 | 10/15/2019 | 12/31/2019 | Y | Yes
AD1-055 | Crystal Hill-Halifax 115 kV | Halifax County Solar | VA | Halifax | In Service | Dominion | 64.7 | 20 | 15.9 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1055_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1055_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_055_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 8/16/2017 | N/A | N/A | 12/7/2023 |  |  | 12/29/2023 | 12/29/2023 | 2/15/2024 | N | No
AD1-056 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 60 | 60 | 38.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1056_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1056_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_056_csa.pdf | Document Posted | N/A | N/A |  | 8/14/2017 | N/A | N/A | 12/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-057 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 93 | 33 | 21.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1057_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1057_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_057_csa.pdf | Document Posted | N/A | N/A |  | 8/14/2017 | N/A | N/A | 12/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-058 | Halifax-Person 230 kV | Alton Post Office Solar | VA | Halifax | In Service | Dominion | 75.1 | 45.9 | 36.6 | 45.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1058_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_058_csa.pdf | Document Posted | N/A | N/A | 9/26/2024 | 8/16/2017 | N/A | N/A | 10/31/2024 |  |  | 12/31/2024 | 12/31/2024 | 1/9/2025 | N | No
AD1-059 | Lakewood 230 kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 0 | 14.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1059_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_059_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/17/2017 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 | 5/7/2018 | N | No
AD1-060 | Mercersburg-Milnor 34.5 kV | Upton Solar | PA | Franklin | In Service | APS | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_060_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2017 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 12/17/2020 | N | No
AD1-061 | McConnelsburg-Mercersburg 34 kV |  | PA | Franklin | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1061_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1061_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_061_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2017 | N/A | N/A |  |  |  | 3/31/2022 | 3/31/2022 | 5/6/2022 | N | No
AD1-062 | Itasca 12.5 kV | 0 | IL | Du Page | Withdrawn | ComEd | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1062_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1062_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1062_wmpa.pdf | Not Required | N/A | N/A |  | 8/18/2017 | N/A | N/A |  |  |  | 12/1/2018 | 12/1/2018 | 9/5/2018 | Y | No
AD1-063 | Harmony Village 34.5 kV | Puller Solar | VA | Middlesex | In Service | Dominion | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1063_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1063_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2017 | N/A | N/A | 10/8/2018 |  |  | 12/1/2018 | 12/1/2018 | 10/8/2018 | N | No
AD1-064 | White Rock-Wayne 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2017 | N/A | N/A |  | 9/19/2019 |  | 12/15/2019 |  |  | N | No
AD1-065 | Eldred-Frackville 230kV |  | PA | Schuylkill | Withdrawn | PPL | 175.8 | 175.8 | 25.84 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1065_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 10/15/2018 |  | 12/31/2020 |  |  | N | No
AD1-066 | Crescent Ridge |  | IL | Bureau | Withdrawn | ComEd | 79.4 | 0 | 9.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1066_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 7/1/2018 |  | 10/31/2019 |  |  | N | No
AD1-067 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 76.13 | 5.725 | 1.1 | 5.725 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 11/30/2018 |  | 10/19/2020 | N | No
AD1-068 | Albright-Garrett 138 kV |  | WV | Preston | Withdrawn | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1068_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 7/19/2021 |  | 12/15/2020 |  |  | N | No
AD1-069 | Iron Bridge-Donegal 138 kV |  | PA | Fayette | Withdrawn | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1069_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 4/14/2020 |  | 12/15/2020 |  |  | N | No
AD1-070 | Fostoria Central 138 kV | South Branch Solar | OH | Hancock | Suspended | AEP | 205 | 205 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1070_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1070_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_070_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD1-071 | Levittown 13kV | Levittown 13kV | NJ | Burlington | Withdrawn | PSEG | 2.6 | 2.6 | 0.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1071_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1071_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 11/8/2018 |  | 3/31/2019 | 3/31/2019 |  | N | Yes
AD1-072 | Biers Run-Circleville 138 kV | Yellowbud Solar | OH | Ross | In Service | AEP | 147 | 20 | 13.7 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_072_csa.pdf | Document Posted | N/A | N/A | 10/24/2022 | 8/31/2017 | N/A | N/A | 12/21/2022 |  |  | 12/15/2022 | 12/15/2022 | 12/21/2022 | N | No
AD1-073 | Buckskin 69 kV | Ross County Solar | OH | Ross | In Service | AEP | 120 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1073_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_073_csa.pdf | Document Posted | N/A | N/A | 8/16/2024 | 9/2/2017 | N/A | N/A | 9/17/2024 |  |  | 6/1/2024 | 6/1/2024 | 2/19/2025 | N | No
AD1-074 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 300 | 300 | 198.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1074_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1074_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_074_csa.pdf | Document Posted | N/A | N/A | 12/27/2027 | 9/1/2017 | N/A | N/A | 1/27/2028 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD1-075 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 375 | 75 | 49.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_075_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2017 | N/A | N/A | 12/27/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD1-076 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 484 | 109 | 72.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_076_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2017 | N/A | N/A | 12/27/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD1-077 | Standardsville-Pratts 34.5 kV |  | VA | Greene | Withdrawn | APS | 17 | 17 | 10.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1077_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2017 | N/A | N/A |  | 4/25/2018 |  | 1/31/2019 |  |  | N | No
AD1-078 | Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1078_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2017 | N/A | N/A |  | 6/14/2019 |  | 1/31/2019 |  |  | N | No
AD1-079 4899239 | PJM-CPLE |  | N/A | N/A | Withdrawn |  |  | 130 |  |  | Energy | Long-Term Firm Transmission | [10 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/1/2017 | 1/1/2021 | 1/1/2026 |  | 9/28/2017 |  |  |  |  | FF | No
AD1-080 | Endless Caverns 34.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 20 | 20 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1080_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2017 | N/A | N/A |  | 4/24/2018 |  | 1/31/2019 |  |  | N | No
AD1-081 | Beatty-London 138 kV | Big Plain 2 | OH | Madison | In Service | ATSI | 196 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1081_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1081_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_081_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/22/2023 | 9/6/2017 | N/A | N/A | 6/25/2023 |  |  | 8/31/2023 | 8/31/2023 | 7/25/2023 | N | No
AD1-082 | Bakers Pond-Ivor 115kV | Waverly Solar | VA | Sussex | In Service | Dominion | 68 | 68 | 43.3 | 68 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1082_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_082_csa.pdf | Document Posted | N/A | N/A | 10/26/2023 | 9/8/2017 | N/A | N/A | 12/28/2023 |  |  | 2/16/2024 | 2/16/2024 | 3/14/2024 | N | No
AD1-083 | Page-Bethel 138 kV | Cape Solar | VA | Page | Withdrawn | APS | 100 | 100 | 60.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1083_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1083_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_083_csa.pdf | Document Posted | N/A | N/A |  | 9/11/2017 | N/A | N/A |  | 7/21/2023 |  | 12/31/2023 | 12/31/2023 |  | N | No
AD1-084 | Cushaw 115 kV | Cushaw Hydropower Station | VA | Bedford | In Service | Dominion | 7.5 | 5.5 | 5.5 | 5.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1084_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1084_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/12/2017 | N/A | N/A |  |  |  | 1/15/2019 | 1/15/2019 | 11/12/2018 | N | No
AD1-085 | North Shenandoah-Stanley 34.5 kV | North Shenandoah-Stanley 34.5kV | VA | Page | Withdrawn | APS | 20 | 20 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1085_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1085_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1085_wmpa.pdf | Not Required | N/A | N/A |  | 9/15/2017 | N/A | N/A | 7/31/2026 | 8/5/2024 |  | 9/8/2026 | 9/8/2026 |  | N | No
AD1-086 | E. Frankfort-Goodings Grove |  | N/A | N/A | Withdrawn | ComEd | 23.9 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ad1086_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ad1086_arr-fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2017 | N/A | N/A |  | 8/23/2021 |  | 6/20/2021 | 6/20/2021 |  | EE | No
AD1-087 | Clover-Sedge Hill 230 kV | Foxhound Solar | VA | Halifax | In Service | Dominion | 64.2 | 64.2 | 43.7 | 64.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_087_csa.pdf | Document Posted | N/A | N/A | 2/1/2024 | 9/16/2017 | N/A | N/A | 2/15/2024 |  |  | 5/31/2024 | 5/31/2024 | 4/24/2024 | N | No
AD1-088 | Briery-Clover 230 kV | Seven Bridges Solar | VA | Mecklenburg | Suspended | Dominion | 80 | 80 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_088_csa.pdf | Document Posted | N/A | N/A | 1/1/2026 | 9/15/2017 | N/A | N/A | 5/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-089 | Birdneck 34.5 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 16 | 4 | 1.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2017 | N/A | N/A |  | 11/1/2017 |  | 12/1/2020 |  |  | N | No
AD1-090 | Muskingum River 345 kV Phase I |  | OH | Washington | Withdrawn | AEP | 1260 | 1260 | 1180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1090_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2017 | N/A | N/A |  | 8/30/2019 |  | 1/1/2022 |  |  | N | No
AD1-091 | Muskingum River 345 kV Phase II |  | OH | Washington | Withdrawn | AEP | 630 | 630 | 590 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2017 | N/A | N/A |  | 11/7/2017 |  | 1/1/2022 |  |  | N | No
AD1-092 4902076 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 105 | 105 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4902076_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4902076_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2017 | 6/1/2019 | 6/1/2024 |  | 10/30/2018 |  |  |  |  | FF | No
AD1-093 4902084 | AMIL-PJM |  | N/A | N/A | Withdrawn | AEP | 180 | 180 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4902084_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4902084_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2017 | 6/1/2019 | 6/1/2024 |  | 10/30/2018 |  |  |  |  | FF | No
AD1-094 4902085 | AMIL-PJM |  | N/A | N/A | Withdrawn | AEP | 34 | 34 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4902085_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4902085_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/18/2017 | 6/1/2019 | 6/1/2024 |  | 10/30/2018 |  |  |  |  | FF | No
AD1-095 | North Salisbury 25 kV |  | MD | Wicomico | Withdrawn | DPL | 8 | 2 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1095_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2017 | N/A | N/A |  | 2/6/2018 |  | 6/1/2019 |  |  | N | No
AD1-096 | Stillman Valley 34 kV |  | IL | Ogle | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2017 | N/A | N/A |  | 7/22/2020 |  | 12/15/2018 |  |  | N | No
AD1-097 | Linwood 230 kV II | Phillips Island CT1, CT2, CT3, and ST4 | PA | Delaware | In Service | PECO | 919 | 67 | 34.8 | 67 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_097_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2017 | N/A | N/A |  |  |  | 7/30/2021 | 7/30/2021 | 6/9/2020 | N | No
AD1-098 | Dixon - McGirr 138 kV |  | IL | Lee | Withdrawn | ComEd | 100 | 100 | 57.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1098_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1098_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/21/2017 | N/A | N/A |  | 3/20/2023 |  | 12/1/2020 |  |  | N | No
AD1-099 | South Bend 500 kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 720 | 0 | 70 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1099_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_099_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2017 | N/A | N/A |  |  |  | 9/1/2019 | 9/1/2019 | 9/20/2018 | N | No
AD1-100 | Loretto-Wilton 345 kV & Braidwood-Davis Creek 345 kV | Heritage Prairie Wind | IL | Kankakee | Under Construction | ComEd | 850 | 850 | 150 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1100_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_100_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 9/22/2017 | N/A | N/A | 11/2/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AD1-101 | Continental 69 kV | Blue Harvest Solar Park | OH | Putnam | In Service | AEP | 49.9 | 49.9 | 18.96 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_101_csa.pdf | Document Posted | N/A | N/A | 12/17/2022 | 9/21/2017 | N/A | N/A | 8/22/2023 |  |  | 6/30/2023 | 6/30/2023 | 11/22/2023 | N | No
AD1-102 | Wurno-Claytor Lake 138 KV |  | VA | Pulaski | Withdrawn | AEP | 180.01 | 180.01 | 23.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1102_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/21/2017 | N/A | N/A |  | 5/17/2023 |  | 12/18/2020 |  |  | N | No
AD1-103 | Beaver-Davis Besse 345 kV II |  | OH | Huron | Withdrawn | ATSI | 500.4 | 500.4 | 65.052 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1103_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  | 7/13/2022 |  | 12/18/2020 |  |  | N | No
AD1-104 | Marysville-Sorenson 765 kV II |  | OH | Van Wert | Withdrawn | AEP | 403.2 | 403.2 | 52.42 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  | 3/27/2020 |  | 12/17/2021 |  |  | N | No
AD1-105 | Kings Dominion DP 115 kV | Sweet Sue Solar | VA | King William | Under Construction | Dominion | 74 | 74 | 44.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1105_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1105_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1105_wmpa.pdf | Not Required | N/A | N/A | 4/6/2026 | 9/23/2017 | N/A | N/A | 5/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-106 | North Waldo-Wild Creek 138 kV | Chestnut Solar | OH | Marion | Suspended | AEP | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1106_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1106_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_106_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_106_csa.pdf | Document Posted | N/A | N/A | 6/1/2026 | 9/23/2017 | N/A | N/A |  |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-107 | McGuire Battery Storage |  | NJ | Burlington | Withdrawn | JCPL | 1.25 | 1.25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  | 10/2/2017 |  | 8/1/2018 | 8/1/2018 |  | Y | No
AD1-108 | Grover 34 kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 9/17/2018 | 9/17/2018 | 7/16/2018 | N | No
AD1-109 | Canton 34.5 kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 21 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 7/9/2018 | 7/9/2018 | 5/10/2018 | N | No
AD1-110 | North Meshoppen 34.5 kV | Roundtop Energy Projects | PA | Susquehanna | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 8/9/2018 | 8/9/2018 | 6/22/2018 | N | No
AD1-111 | Woolrich 12.47 kV |  | PA | Clinton | Withdrawn | PPL | 4.13 | 4.125 | 4.125 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2017 | N/A | N/A |  | 1/3/2018 |  | 12/31/2018 |  |  | N | Yes
AD1-112 | Davis Creek 138 kV |  | IL | Kankakee | Withdrawn | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2017 | N/A | N/A |  | 10/2/2017 |  | 9/30/2020 |  |  | N | No
AD1-113 | Raritan River 230 kV | Woodbridge Energy Center | NJ | Middlesex | Withdrawn | JCPL | 820 | 35 | 75 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_113_csa.pdf | Document Posted | N/A | N/A |  | 9/25/2017 | N/A | N/A |  | 2/16/2022 |  | 6/1/2021 | 6/1/2021 |  | N | No
AD1-114 | Kelson Ridge 230kV | CPV Maryland | MD | Charles | In Service | PEPCO | 820 | 75 | 75 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1114_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2017 | N/A | N/A |  |  |  | 5/31/2021 | 5/31/2021 | 3/28/2019 | N | No
AD1-115 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 150 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1115_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_115_csa.pdf | Document Posted | N/A | N/A | 10/28/2026 | 9/27/2017 | N/A | N/A | 3/25/2027 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AD1-116 | Nevada 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1116_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/26/2017 | N/A | N/A |  | 9/21/2022 |  | 12/31/2020 |  |  | N | No
AD1-117 | Maryland 138 kV |  | IL | Ogle | Withdrawn | ComEd | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1117_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2017 | N/A | N/A |  | 12/11/2018 |  | 7/1/2020 |  |  | N | No
AD1-118 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 700 | 60 | 60 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1118_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_118_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/27/2017 | N/A | N/A |  |  |  | 8/1/2022 | 8/1/2022 | 8/17/2022 | N | No
AD1-119 | Payne 69 kV | Timber Road Solar Park | OH | Paulding | In Service | AEP | 49.9 | 49.9 | 18.96 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1119_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1119_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_119_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_119_csa.pdf | Document Posted | N/A | N/A | 12/15/2022 | 9/28/2017 | N/A | N/A | 6/29/2023 |  |  | 11/30/2023 | 11/30/2023 | 9/12/2024 | N | No
AD1-120 4904819 | DUK-PJM |  | N/A | N/A | Withdrawn |  | 109 | 109 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4904819_ltf1.pdf |  |  |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/28/2017 | 6/1/2019 | 6/1/2024 |  | 10/3/2018 |  |  |  |  | FF | No
AD1-121 4904949 | CPLE-PJM |  | N/A | N/A | Withdrawn |  | 109 | 109 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4904949_ltf1.pdf |  | Withdrawn |  | Withdrawn |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/28/2017 | 6/1/2019 | 6/1/2024 |  | 10/3/2018 |  |  |  |  | FF | No
AD1-122 4904950 | PJM-DUK |  | N/A | N/A | Withdrawn | Dominion | 130 | 130 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4904950_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4904950_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/28/2017 | 1/1/2021 | 1/1/2026 |  | 10/26/2018 |  |  |  |  | FF | No
AD1-123 | Welco 34.5 kV |  | VA | Halifax | Withdrawn | Dominion | 10 | 10 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 6/6/2018 |  | 12/31/2018 |  |  | N | Yes
AD1-124 | Lynbrook 12 kV |  | VA | Campbell | Withdrawn | AEP | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 9/10/2019 |  | 12/31/2019 |  |  | N | No
AD1-125 | Baker 138 kV | Short Mountain Wind Energy | WV | Hardy | Suspended | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1125_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1125_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_125_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_125_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2017 | N/A | N/A |  |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AD1-126 | W. DeKalb-Waterman |  | IL | DeKalb | Withdrawn | ComEd | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1126_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 7/5/2018 |  | 12/31/2020 |  |  | N | No
AD1-127 | Cambria Slope 115 kV |  | PA | Cambria | Withdrawn | PENELEC | 325 | 235 | 235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1127_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 5/8/2018 |  | 9/1/2020 |  |  | N | No
AD1-128 | Modoc-Delaware 138 kV | Riverstart Solar Park IV | IN | Randolph | Under Construction | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1128_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1128_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_128_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_128_csa.pdf | Document Posted | N/A | N/A | 3/3/2025 | 9/29/2017 | N/A | N/A | 9/24/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD1-129 | Belvidere 34 kV | Cherry Valley Solar Project, LLC | IL | Boone | Withdrawn | ComEd | 12.5 | 12.5 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1129_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1129_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1129_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 8/26/2024 |  | 9/30/2026 | 9/30/2026 |  | N | Yes
AD1-130 | Hardin Switch 345 kV | Hardin Energy Center – Phase 2 | OH | Hardin | In Service | AEP | 150 | 150 | 101.47 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1130_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_130_csa.pdf | Document Posted | N/A | N/A | 5/22/2024 | 10/2/2017 | N/A | N/A | 8/7/2024 |  |  | 12/31/2024 | 12/31/2024 | 12/3/2024 | N | No
AD1-131 | Sedge Hill-Person 230 kV | Powells Creek Solar | VA | Halifax | In Service | Dominion | 70 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1131_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1131_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_131_csa.pdf | Document Posted | N/A | N/A | 7/26/2023 | 9/30/2017 | N/A | N/A | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 | 8/23/2023 | N | No
AD1-132 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 10/2/2017 |  | 12/15/2019 |  |  | N | No
AD1-133 | Pontiac MidPoint-Dresden |  | IL | Grundy | Withdrawn | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1133_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1133_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 5/31/2023 |  | 12/31/2019 |  |  | N | No
AD1-134 | JK Smith 138 kV |  | KY | Unknown | Withdrawn | EKPC | 73 | 73 | 72.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1134_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 4/22/2019 |  | 7/1/2020 |  |  | N | No
AD1-135 | Clinton 23 kV II | Gaucho Solar | PA | Washington | In Service | DL | 20 | 8.3 | 3.15 | 8.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1135_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1135_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1135_wmpa.pdf | Not Required | N/A | N/A | 3/21/2023 | 9/29/2017 | N/A | N/A | 3/21/2023 |  |  | 6/1/2023 | 6/1/2023 | 6/29/2023 | N | No
AD1-136 | South Bethel-Brown 69 kV | Nestlewood Solar | OH | Clermont | In Service | DEOK | 80 | 10 | 5.4 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1136_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1136_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_136_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_136_csa.pdf | Document Posted | N/A | N/A | 12/7/2023 | 9/30/2017 | N/A | N/A | 12/20/2023 |  |  | 3/31/2024 | 3/31/2024 | 12/27/2023 | N | No
AD1-137 | Dequine 345 kV |  | IN | Benton | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1137_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 1/16/2020 |  | 12/18/2020 |  |  | N | No
AD1-138 | Valley 138 kV |  | MI | Van Buren | Withdrawn | AEP | 100 | 100 | 65.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 10/2/2017 |  | 12/1/2020 |  |  | N | No
AD1-139 | Mullin-Grant Tap 138 kV |  | IN | Madison | Withdrawn | AEP | 100 | 99.9968 | 68.9978 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 10/2/2017 |  | 12/1/2020 |  |  | N | No
AD1-140 | Greene-Clark 138 kV | Kingwood Solar | OH | Greene | Engineering and Procurement | ATSI | 175 | 175 | 95.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1140_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1140_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_140_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_140_csa.pdf | Document Posted | N/A | N/A | 5/29/2026 | 9/29/2017 | N/A | N/A | 7/22/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AD1-141 | S. Lucasville-Wakefield 138 kV |  | OH | Scioto | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1141_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 3/27/2020 |  | 12/1/2019 |  |  | N | No
AD1-142 | Milan 34.5 kV | Milan Energy | PA | Bradford | In Service | PENELEC | 21 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_142_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 7/9/2018 | 7/9/2018 | 4/24/2018 | N | No
AD1-143 | Hauto-Siegfried 69 kV | Broad Mountain | PA | Carbon | Withdrawn | PPL | 90 | 90 | 11.84 |  | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1143_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1143_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_143_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_143_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2017 | N/A | N/A | 6/30/2024 | 3/31/2023 |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-144 | Kings Fork 34.5 kV | TWE Myrtle Solar Project | VA | City of Suffolk | In Service | Dominion | 15 | 15 | 9.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1144_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1144_wmpa.pdf | Not Required | N/A | N/A | 4/15/2020 | 9/30/2017 | N/A | N/A | 5/5/2020 |  |  | 6/1/2020 | 6/1/2020 | 6/29/2020 | N | No
AD1-145 | Laurel-Dupont Seaford 69 kV |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | 9.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1145_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 11/14/2018 |  | 7/31/2019 |  |  | N | No
AD1-146 | Millsboro 25 kV |  | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1146_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/16/2018 |  | 6/30/2019 |  |  | N | No
AD1-147 | Martinsville-Wilmington 69 kV |  | OH | Clinton | Withdrawn | Dayton | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/3/2017 |  | 9/1/2020 |  |  | N | No
AD1-148 | Brokaw-Lanesville | HillTopper Wind Farm | IL | Logan | In Service | ComEd | 185 | 0 | 36.3 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1148_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_148_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/1/2017 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 9/1/2022 | N | No
AD1-149 | Carbondale 69 kV |  | WV | Kanawha | Withdrawn | AEP | 19.9 | 19.9 | 8.33 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1149_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 6/18/2018 |  | 6/30/2019 |  |  | N | No
AD1-150 | Kankakee 34.5 kV |  | IL | Kankakee | Withdrawn | ComEd | 19.9 | 19.9 | 3.98 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/5/2017 |  | 7/31/2019 |  |  | N | No
AD1-151 | Hopewell-Surry 230 kV | Wild Indigo Solar | VA | Surry | Suspended | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1151_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1151_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_151_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_151_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2017 | N/A | N/A | 6/1/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AD1-152 | Clover-Sedge Hill 230 kV | Piney Creek Solar | VA | Halifax | In Service | Dominion | 80 | 80 | 48 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1152_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1152_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_152_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_152_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2017 | N/A | N/A | 6/19/2023 |  |  | 12/1/2023 | 12/1/2023 | 8/15/2023 | N | No
AD1-153 | Walker Mill 12 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2.76 | 2.76 | 1.0488 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1153_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 12/24/2018 |  | 9/1/2018 |  |  | N | Yes
AD1-154 | Timblin 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1154_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 2/4/2021 |  | 6/1/2020 |  |  | N | No
AD1-155 | Meadow Brook-Strasburg 138 kV | Foxglove Solar | VA | Frederick | In Service | APS | 75 | 75 | 37.2 | 75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1155_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1155_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_155_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_155_csa.pdf | Document Posted | N/A | N/A | 9/11/2024 | 10/2/2017 | N/A | N/A | 9/23/2024 |  |  | 6/30/2024 | 6/30/2024 | 10/19/2024 | N | No
AD1-156 | Poe 34.5 kV | Rives Road Solar | VA | Prince George | Withdrawn | Dominion | 19.7 | 19.7 | 11.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1156_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1156_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1156_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2017 | N/A | N/A | 6/1/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AD1-157 | South Creek 34.5 kV | Spout Springs Solar | VA | Appomattox | Withdrawn | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1157_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1157_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1157_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2017 | N/A | N/A | 10/1/2021 | 1/26/2021 |  | 12/15/2021 | 12/15/2021 |  | N | No
AD1-158 | Old Chapel-Millville 138kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/6/2017 |  | 6/30/2019 |  |  | N | No
AD1-159 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/6/2017 |  | 6/30/2019 |  |  | N | No
AD1-160 | Pamplin 34.5 kV | Pamplin Solar | VA | Appomattox | Withdrawn | Dominion | 15.7 | 15.7 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1160_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1160_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1160_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2017 | N/A | N/A | 6/15/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AD1-161 | Stonewall-Long Mountain 69 kV |  | VA | Appomattox | Withdrawn | AEP | 55 | 55 | 30.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1161_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 5/31/2023 |  | 12/31/2020 |  |  | N | No
AD2-001 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 318 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/2/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 10/2/2020 | N | No
AD2-002 | Franklin-Emerald 25 kV | Evergreene Energy | PA | Greene | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2002_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2002_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2002_wmpa.pdf | Not Required | N/A | N/A |  | 10/17/2017 | N/A | N/A | 12/31/2022 | 12/30/2020 |  | 12/31/2022 | 12/31/2022 |  | N | No
AD2-003 4907750 | PJM-OVEC |  | N/A | N/A | Withdrawn |  | 41 | 41 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4907750_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 10/24/2017 | 2/1/2018 | 2/1/2019 |  | 12/27/2017 |  |  |  |  | FF | No
AD2-004 | Steel-Vienna 230 kV |  | MD | Caroline | Withdrawn | DPL | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2004_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2017 | N/A | N/A |  | 9/19/2018 |  | 12/1/2022 |  |  | N | No
AD2-005 | Nottingham 138kV | Harrison Power Plant | OH | Harrison | Withdrawn | AEP | 1085 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2005_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_005_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2017 | N/A | N/A |  | 7/21/2022 |  | 6/11/2024 | 6/11/2024 |  | N | No
AD2-006 | Gilbert-Morris Park 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 7.5 | 7.5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2017 | N/A | N/A |  | 11/29/2017 |  | 11/30/2018 |  |  | N | No
AD2-007 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 7.6 | 7.6 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/4/2017 | N/A | N/A |  | 4/26/2023 |  | 11/1/2019 |  |  | N | No
AD2-008 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 52.1 | 52.1 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2008_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2008_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/4/2017 | N/A | N/A |  | 4/26/2023 |  | 9/30/2019 |  |  | N | No
AD2-009 | McConnellsburg 138 kV | Great Cover Solar LLC | PA | Fulton | In Service | APS | 70 | 70 | 48.1 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2009_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_009_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_009_csa.pdf | Document Posted | N/A | N/A | 11/21/2023 | 11/7/2017 | N/A | N/A | 12/8/2023 |  |  | 3/31/2024 | 3/31/2024 | 4/16/2024 | N | No
AD2-010 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2010_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  | 11/9/2018 |  | 6/1/2019 |  |  | N | No
AD2-011 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  | 11/9/2018 |  | 6/1/2019 |  |  | N | No
AD2-012 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2012_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  | 11/9/2018 |  | 6/1/2019 |  |  | N | No
AD2-013 | Earleys 115 kV |  | NC | Hertford | Withdrawn | Dominion | 74.9 | 74.9 | 52.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2017 | N/A | N/A |  | 11/30/2017 |  | 12/31/2020 |  |  | N | No
AD2-014 | Steubenville 69 kV | Steubenville Solar | OH | Jefferson | Suspended | AEP | 49.5 | 49.5 | 20.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2014_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2014_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_014_csa.pdf | Document Posted | N/A | N/A | 10/31/2027 | 11/10/2017 | N/A | N/A | 11/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AD2-015 | Dequine 345 kV |  | IN | Benton | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2017 | N/A | N/A |  | 1/16/2018 |  | 12/18/2020 |  |  | N | No
AD2-016 | Biers Run-Circleville 138 kV | Yellowbud Solar | OH | Ross | In Service | AEP | 274 | 127 | 62.5 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2016_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2016_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_016_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_016_csa.pdf | Document Posted | N/A | N/A | 10/24/2022 | 11/16/2017 | N/A | N/A | 12/21/2022 |  |  | 12/15/2022 | 12/15/2022 | 12/21/2022 | N | No
AD2-017 | Buckskin 69 kV |  | OH | Ross | Withdrawn | AEP | 120 | 100 | 65.59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2017 | N/A | N/A |  | 1/18/2018 |  | 12/31/2020 |  |  | N | No
AD2-018 | Roseland-Cedar Grove 230kV |  | NJ | Unknown | In Service | PSEG | 0 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ad2018_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ad2018_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/ad2_018_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 | 3/12/2021 | EE | No
AD2-019 | Williams-Cedar Grove 230kV |  | NJ | Unknown | In Service | PSEG | 0 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ad2019_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ad2019_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/ad2_019_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 | 3/12/2021 | EE | No
AD2-020 | Valley 138 kV | Southwest Michigan Energy Center | MI | Van Buren | Engineering and Procurement | AEP | 100 | 100 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2020_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_020_csa.pdf | Document Posted | N/A | N/A | 1/31/2027 | 12/1/2017 | N/A | N/A | 2/15/2027 |  |  | 4/30/2027 | 4/30/2027 |  | N | No
AD2-021 | Elko 34.5 kV | Briel Farm Solar | VA | Henrico | In Service | Dominion | 20 | 1.2 | 1.3 | 1.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2021_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2021_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2021_wmpa.pdf | Not Required | N/A | N/A |  | 11/29/2017 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 | 12/30/2020 | 12/21/2020 | N | No
AD2-022 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 96 | 96 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2022_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_022_csa.pdf | Document Posted | N/A | N/A | 7/1/2027 | 12/2/2017 | N/A | N/A | 7/12/2027 |  |  | 1/30/2026 | 1/30/2026 |  | N | No
AD2-023 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 54 | 95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2023_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2023_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_023_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_023_csa.pdf | Document Posted | N/A | N/A | 7/1/2027 | 12/2/2017 | N/A | N/A | 7/12/2027 |  |  | 1/30/2026 | 1/30/2026 |  | N | No
AD2-024 | Marengo 34 kV |  | IL | McHenry | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2024_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2017 | N/A | N/A |  | 9/17/2018 |  | 6/1/2019 |  |  | N | No
AD2-025 | Hillsborough 13 kV | Hillsborough Storage | NJ | Somerset | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2025_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2025_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2025_wmpa.pdf | Not Required | N/A | N/A |  | 12/5/2017 | N/A | N/A | 12/31/2023 | 12/19/2023 |  | 12/31/2023 | 12/31/2023 |  | Y | No
AD2-026 | East Flemington-Frenchtown 34.5 kV II | Quakertown Solar Farm | NJ | Hunterdon | In Service | JCPL | 8.8 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2026_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_026_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 5/3/2019 | N | No
AD2-027 | Camden Switch 26 kV | Taylors Lane Solar | NJ | Burlington | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2027_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2027_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2027_wmpa.pdf | Not Required | N/A | N/A |  | 12/7/2017 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 3/22/2019 | N | No
AD2-028 | McConnellsburg-Texas Eastern |  | PA | Franklin | Withdrawn | APS | 150 | 150 | 76.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2028_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/12/2017 | N/A | N/A |  | 8/20/2018 |  | 6/30/2019 |  |  | N | No
AD2-029 | Dorchester County 12kV |  | MD | Dorchester | Withdrawn | DPL | 19.5 | 19.5 | 7.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2029_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/13/2017 | N/A | N/A |  | 9/20/2018 |  | 12/31/2019 |  |  | N | No
AD2-030 | Wan 34.5 kV | Gloucester Solar | VA | Gloucester | In Service | Dominion | 19.8 | 19.8 | 13.1 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2030_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2030_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2030_wmpa.pdf | Not Required | N/A | N/A |  | 12/13/2017 | N/A | N/A |  |  |  | 5/21/2019 | 5/21/2019 | 3/22/2019 | N | No
AD2-031 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | In Service | Dayton | 49.9 | 49.9 | 19 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2031_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_031_csa.pdf | Document Posted | N/A | N/A | 6/6/2025 | 12/16/2017 | N/A | N/A | 6/16/2025 |  |  | 6/25/2025 | 6/25/2025 | 6/27/2025 | N | No
AD2-032 | Morrisville 230 kV |  | VA | Accomack | Withdrawn | Dominion | 150 | 150 | 83.8495 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/15/2017 | N/A | N/A |  | 1/5/2018 |  | 12/31/2020 |  |  | N | No
AD2-033 | Chase City-Lunenburg 115 kV | Red Brick Solar | VA | Lunenburg | Engineering and Procurement | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_033_csa.pdf | Document Posted | N/A | N/A | 9/1/2027 | 12/23/2017 | N/A | N/A | 9/1/2027 |  |  | 7/12/2026 | 7/12/2026 |  | N | No
AD2-035 | Ontelaunee 230 kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 630 | 38.9 | 14 | 38.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2035_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad2_035_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/2018 | N/A | N/A |  |  |  | 12/1/2019 |  | 12/1/2019 | N | No
AD2-036 | Jacksonville-Renaker 138kV IV |  | KY | Harrison | Withdrawn | EKPC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2036_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2018 | N/A | N/A |  | 8/19/2019 |  | 6/1/2020 |  |  | N | No
AD2-037 | Gilbert-Morris Park 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 7.5 | 7.5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2018 | N/A | N/A |  |  |  | 6/30/2019 |  |  | N | No
AD2-038 | Powerton-Nevada 345 kV | Osagrove Flats Wind | IL | Lasalle | Under Construction | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2038_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_038_csa.pdf | Document Posted | N/A | N/A | 5/6/2026 | 1/22/2018 | N/A | N/A | 9/1/2026 |  |  | 10/30/2026 | 10/30/2026 |  | N | No
AD2-039 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 90 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2039_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2039_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_039_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2018 | N/A | N/A | 6/6/2026 |  |  | 7/14/2026 | 7/14/2026 |  | N | No
AD2-040 | Showalter 34.5 kV |  | MD | Washington | Withdrawn | APS | 18.4 | 0 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2040_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2018 | N/A | N/A |  | 8/20/2018 |  | 12/31/2018 |  |  | N | No
AD2-041 | Normandy |  | IL | Whiteside | Withdrawn | ComEd | 17 | 17 | 11.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2018 | N/A | N/A |  | 2/20/2018 |  | 12/31/2019 |  |  | N | No
AD2-042 | Camden Switch 26 kV II | Pennsauken Solar II | NJ | Camden | In Service | PSEG | 13.2 | 13.2 | 5 | 13.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2042_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2042_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2042_wmpa.pdf | Not Required | N/A | N/A |  | 1/29/2018 | N/A | N/A | 10/4/2019 |  |  | 9/10/2019 | 9/10/2019 | 10/4/2019 | N | No
AD2-043 | Crystal Hill 115 kV |  | VA | Halifax | Withdrawn | Dominion | 65.5 | 65.5 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2018 | N/A | N/A |  | 12/20/2019 |  | 1/31/2019 |  |  | N | No
AD2-044 | Northern Neck 34.5 kV | Gardy's Mill Solar | VA | Westmoreland | In Service | Dominion | 14 | 3.2 | 1.5 | 3.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2044_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2044_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2044_wmpa.pdf | Not Required | N/A | N/A |  | 1/29/2018 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 |  | 12/21/2020 | N | No
AD2-045 | Price Solar |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2045_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2018 | N/A | N/A |  | 3/29/2019 |  | 10/1/2019 |  |  | N | No
AD2-046 | Boydton DP-Kerr Dam 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 80 | 80 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2046_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2018 | N/A | N/A |  | 3/15/2023 |  | 6/1/2021 |  |  | N | No
AD2-047 | Davis Creek 138 kV | Lower Crossing Wind | IL | Kankakee | Suspended | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2047_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_047_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 1/31/2018 | N/A | N/A | 10/31/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AD2-048 | Cynthia-Headquarters 69 kV | Blue Moon Solar | KY | Harrison | Under Construction | EKPC | 70 | 70 | 46.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_048_csa.pdf | Document Posted | N/A | N/A | 12/5/2025 | 2/1/2018 | N/A | N/A | 12/12/2025 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
AD2-049 | Newport News 23kV | Newport News Battery Storage | VA | City of Newport News | Withdrawn | Dominion | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2049_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2049_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2049_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2018 | N/A | N/A | 4/30/2021 | 10/21/2019 |  | 4/30/2021 | 4/30/2021 |  | N | No
AD2-050 | Buxmont 69kV |  | PA | Bucks | Withdrawn | PPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  | 3/2/2018 |  | 12/31/2019 |  |  | N | No
AD2-051 | Earleys – Northampton 230kV |  | NC | Hertford | Withdrawn | Dominion | 74.9 | 74.9 | 52.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  | 8/30/2022 |  | 12/31/2020 |  |  | N | No
AD2-052 | Laurel Lake Solar |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2052_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  | 5/1/2019 |  | 6/30/2019 |  |  | N | No
AD2-053 | South Canton-Harmon 345kV |  | OH | Adams | Withdrawn | AEP | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2018 | N/A | N/A |  | 9/19/2018 |  | 6/1/2019 |  |  | EE | No
AD2-054 | Dumont-Stillwell 345kV |  | IN | St. Joseph | Withdrawn | AEP | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2018 | N/A | N/A |  | 5/2/2019 |  |  |  |  | EE | No
AD2-055 | Moshannon-East Towanda 230 kV | Renovo Energy Center | PA | Clinton | Withdrawn | PENELEC | 548 | 44 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2055_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2055_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_055_csa.pdf | Document Posted | N/A | N/A |  | 2/9/2018 | N/A | N/A |  | 4/20/2023 |  | 6/30/2025 | 6/30/2025 |  | N | No
AD2-056 | Charles City |  | VA | Henrico | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2018 | N/A | N/A |  | 3/7/2018 |  | 12/31/2020 |  |  | N | No
AD2-057 | Highland-Hanna 345kV |  | OH | Trumbull | Withdrawn | ATSI | 940 | 940 | 850 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2057_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/20/2018 | N/A | N/A |  | 9/26/2018 |  | 10/16/2020 |  |  | N | No
AD2-058 | St. Barnabas 13 kV | Spectrum Solar | MD | Prince George's | In Service | PEPCO | 5.6 | 5.6 | 2.38 | 5.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2058_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2058_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2058_wmpa.pdf | Not Required | N/A | N/A |  | 2/21/2018 | N/A | N/A | 12/30/2023 |  |  | 6/3/2022 | 6/3/2022 | 1/2/2024 | N | No
AD2-059 | Chapel Street 138 kV | UD Motor Pool | DE | New Castle | Withdrawn | DPL | 0.77 | 0.77 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2059_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2059_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2059_wmpa.pdf | Not Required | N/A | N/A |  | 2/21/2018 | N/A | N/A | 4/1/2023 | 9/22/2023 |  | 11/1/2022 | 11/1/2022 |  | N | No
AD2-060 | Davis Creek 138kV | Staley Solar | IL | Kankakee | Engineering and Procurement | ComEd | 70 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_060_csa.pdf | Document Posted | N/A | N/A | 5/15/2027 | 2/21/2018 | N/A | N/A | 6/1/2027 |  |  | 6/28/2024 | 6/28/2024 |  | N | No
AD2-061 | Spring Run 23 kV |  | PA | Adams | Withdrawn | PENELEC | 7.4 | 7.4 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2018 | N/A | N/A |  | 4/25/2018 |  | 6/1/2020 |  |  | N | No
AD2-062 | Roxbury-Greene 138 kV | Beaver Creek Solar | PA | Franklin | Suspended | PENELEC | 80.3 | 80.3 | 53.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2062_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2062_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_062_csa.pdf | Document Posted | N/A | N/A |  | 2/24/2018 | N/A | N/A | 9/1/2024 |  |  | 12/3/2024 | 12/3/2024 |  | N | No
AD2-063 | Central-Chase City 115kV |  | VA | Charlotte | Withdrawn | Dominion | 149.5 | 149.5 | 89.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2063_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2063_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/26/2018 | N/A | N/A |  | 5/24/2023 |  | 3/31/2021 |  |  | N | No
AD2-064 | Tansboro 12kV |  | NJ | Camden | Withdrawn | AEC | 1.26 | 1.26 | 0.53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2064_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2064_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/27/2018 | N/A | N/A |  | 6/16/2020 |  | 12/1/2019 |  |  | N | No
AD2-065 | Atco 12 kV | Kettle Run | NJ | Burlington | In Service | AEC | 2.57 | 2.57 | 1.08 | 2.57 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2065_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2065_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2065_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2065_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2018 | N/A | N/A | 9/30/2022 |  |  | 5/20/2022 | 5/20/2022 | 3/24/2023 | N | No
AD2-066 | Mazon-Crescent Ridge 138 kV | Buffalo Solar | IL | Grundy | Engineering and Procurement | ComEd | 116 | 116 | 69.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2066_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2066_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_066_csa.pdf | Document Posted | N/A | N/A | 3/31/2027 | 3/1/2018 | N/A | N/A | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AD2-067 | Centerburg 138kV | Harvey Solar I | OH | Licking | Engineering and Procurement | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad2_067_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_067_csa.pdf | Document Posted | N/A | N/A | 10/15/2027 | 3/2/2018 | N/A | N/A | 10/29/2027 |  |  | 1/15/2028 | 1/15/2028 |  | N | No
AD2-068 | Everetts-Greenville 230kV |  | NC | Pitt | Withdrawn | Dominion | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2068_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-069 | Cox's Corner 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 3 | 3 | 2.01 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2069_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2018 | N/A | N/A |  | 6/21/2019 |  | 9/30/2019 |  |  | N | No
AD2-070 | Gilbert-Morris Park 34.5kV | Milford Solar Farm | NJ | Hunterdon | In Service | JCPL | 7.5 | 7.5 | 3.2 | 7.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2070_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_070_csa.pdf | Document Posted | N/A | N/A |  | 3/12/2018 | N/A | N/A | 9/18/2019 |  |  | 6/1/2020 | 6/1/2020 | 9/18/2019 | N | No
AD2-071 | Strawton-Deer Creek 138 kV | Madison County Solar | IN | Madison | Suspended | AEP | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2071_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_071_csa.pdf | Document Posted | N/A | N/A | 9/30/2025 | 3/15/2018 | N/A | N/A | 9/30/2025 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
AD2-072 | Van Arsdell-Mercer Industrial 69kV | Mercer County Solar Project | KY | Mercer | Withdrawn | EKPC | 95 | 95 | 63.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_072_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2018 | N/A | N/A | 6/30/2026 | 11/18/2024 |  | 6/30/2023 | 6/30/2023 |  | N | No
AD2-073 | Sanders DP 230 kV | Woodbine Road Solar | VA | Westmoreland | In Service | Dominion | 19.92 | 19.92 | 13.32 | 19.92 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2073_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2073_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2073_wmpa.pdf | Not Required | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 9/2/2021 | N | No
AD2-074 | Garner DP-Lancaster 115 kV | Waller Solar I | VA | Lancaster | Engineering and Procurement | Dominion | 86 | 86 | 32.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2074_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2074_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad2_074_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_074_csa.pdf | Document Posted | N/A | N/A | 3/31/2027 | 3/15/2018 | N/A | N/A | 9/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AD2-075 | Segreto 345kV | Covert Generating Facility | MI | Van Buren | Withdrawn | AEP | 1340 | 285 | 145 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2075_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_075_csa.pdf | Document Posted | N/A | N/A |  | 3/15/2018 | N/A | N/A |  | 6/1/2023 |  | 8/31/2023 | 8/31/2023 |  | N | No
AD2-076 | Carville 138 kV | Concho Solar I | MD | Queen Anne's | Suspended | DPL | 49 | 49 | 18.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_076_csa.pdf | Document Posted | N/A | N/A |  | 3/15/2018 | N/A | N/A | 6/3/2027 |  |  | 6/3/2024 | 6/3/2024 |  | N | No
AD2-077 | Buxmont 69 kV | Energy Mountain | PA | Bucks | Suspended | PPL | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2077_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2077_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_077_csa.pdf | Document Posted | N/A | N/A | 3/31/2029 | 3/16/2018 | N/A | N/A |  |  |  | 7/31/2029 | 7/31/2029 |  | N | No
AD2-078 | N. Haverhill 69kV |  | OH | Scioto | Withdrawn | AEP | 95 | 20 | 40 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2078_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2018 | N/A | N/A |  | 10/15/2020 |  | 9/1/2020 |  |  | N | No
AD2-079 | Capitol Ave 34.5kV | St. Joseph County, Indiana | IN | St. Joseph | In Service | AEP | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_079_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2018 | N/A | N/A |  |  |  | 3/31/2021 | 3/31/2021 | 3/16/2021 | N | No
AD2-080 | Dumont-Stillwell 345kV |  | IN | St. Joseph | Withdrawn | AEP | 309 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ad2080_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2018 | N/A | N/A |  | 6/25/2020 |  | 6/1/2020 |  |  | EE | No
AD2-081 | Banister 34.5kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | 13.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2081_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 9/13/2018 |  | 9/30/2019 |  |  | N | No
AD2-082 | Pamplin 34.5kV |  | VA | Prince Edward | Withdrawn | Dominion | 15 | 15 | 10.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2082_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 4/5/2019 |  | 9/30/2019 |  |  | N | No
AD2-083 | Larrabee 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 1100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ad2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ad2083_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 2/2/2022 |  |  |  |  | S | No
AD2-084 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 1100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ad2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ad2084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 2/2/2022 |  | 12/31/2025 |  |  | S | No
AD2-085 | Myrtle-Windsor DP 115kV | Knoxville Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 51 | 51 | 19.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2085_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2085_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_085_csa.pdf | Document Posted | N/A | N/A | 6/15/2027 | 3/21/2018 | N/A | N/A | 6/22/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
AD2-086 | Hardin Switch 345 kV | Hardin Energy Center – Phase 3 | OH | Hardin | In Service | AEP | 230 | 230 | 138 | 230 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_086_csa.pdf | Document Posted | N/A | N/A | 10/25/2024 | 3/21/2018 | N/A | N/A | 12/7/2024 |  |  | 12/31/2025 | 12/31/2025 | 2/21/2025 | N | No
AD2-087 | Randolf 138kV |  | OH | Darke | Withdrawn | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 12/9/2019 |  | 12/31/2020 |  |  | N | No
AD2-088 | Laurel 69kV |  | DE | Sussex | Withdrawn | DPL | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2088_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 2/6/2020 |  | 12/31/2020 |  |  | N | No
AD2-089 | Anaconda-Tar River 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/Delay email sent 2/82/19; 3/31/19 | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 12/9/2019 |  | 12/31/2020 |  |  | N | No
AD2-090 | Handsom - Southampton 115kV |  | VA | Southampton | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2020 |  |  | N | No
AD2-091 | Hardin Tap 345kV | Hardin Energy Center – Storage I | OH | Hardin | Suspended | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2091_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_091_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_091_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 3/20/2018 | N/A | N/A | 10/22/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD2-092 | Marysville 345kV | Cadence Solar II Energy Center | OH | Union | Under Construction | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_092_csa.pdf | Document Posted | N/A | N/A | 2/28/2025 | 3/22/2018 | N/A | N/A | 10/6/2025 |  |  | 3/20/2026 | 3/20/2026 |  | N | No
AD2-093 | Marysville 345kV | Cadence Solar Energy Center | OH | Union | Under Construction | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_093_csa.pdf | Document Posted | N/A | N/A | 2/28/2025 | 3/21/2018 | N/A | N/A | 10/6/2025 |  |  | 3/20/2026 | 3/20/2026 |  | N | No
AD2-094 | Pantego-Five Points 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 4/2/2018 |  | 12/31/2020 |  |  | N | No
AD2-095 | Todd 69 kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 4/2/2018 |  | 12/31/2021 |  |  | N | No
AD2-096 | Marysville 345kV | Cadence Energy Storage | OH | Union | Suspended | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2096_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2096_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_096_csa.pdf | Document Posted | N/A | N/A | 9/30/2025 | 3/21/2018 | N/A | N/A | 9/30/2025 |  |  | 3/20/2026 | 3/20/2026 |  | N | No
AD2-097 | Spruance NUG 230kV | Spruance Operating Services LLC | VA | Henrico | In Service | Dominion | 66 | 66 | 11 | 66 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2097_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_097_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2018 | N/A | N/A | 8/1/2019 |  |  | 5/1/2019 | 5/1/2019 | 10/1/2019 | N | No
AD2-098 4934836 | PJM-WEC |  | N/A | N/A | Confirmed |  |  | 4 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4934836_ltf1.pdf |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-2/4934836_ltf2.pdf | Executed Agreement and/or Study |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/21/2018 | 9/1/2018 | 6/1/2037 | [6 empty] | FF | No
AD2-099 4934920 |  |  | N/A | N/A | Withdrawn |  |  | 75 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ltf-phase-1/4934920_ltf1.pdf | [6 empty] | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 3/21/2018 | 6/1/2021 | 6/1/2026 |  | 6/15/2018 |  |  |  |  | FF | No
AD2-100 | Kincaid-Pana 345 kV | Broomstick Solar Energy Centergy Center | IL | Christian | Suspended | ComEd | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2100_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_100_csa.pdf | Document Posted | N/A | N/A | 10/7/2028 | 3/23/2018 | N/A | N/A | 11/7/2028 |  |  | 12/7/2028 | 12/7/2028 |  | N | No
AD2-101 | Bloom-Davis Creek |  | IL | Will | Withdrawn | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2101_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 5/1/2019 |  | 12/31/2021 |  |  | N | No
AD2-102 | Wempletown 345 kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2102_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/5/2023 |  | 12/31/2021 |  |  | N | No
AD2-103 | Crane CT 1 115kV |  | MD | Baltimore County | Withdrawn | BGE | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2103_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 10/27/2021 |  | 10/31/2019 |  |  | N | No
AD2-104 | Crane CT 2-3-4 115kV |  | MD | Baltimore County | Withdrawn | BGE | 144.6 | 144.6 | 144.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2104_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2104_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 10/27/2021 |  | 10/31/2019 |  |  | N | No
AD2-105 | Leslie-Stinnett 161KV |  | KY | Leslie | Withdrawn | AEP | 100 | 100 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2105_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2021 |  |  | N | No
AD2-106 | Bulan 69kV |  | KY | Perry | Withdrawn | AEP | 80 | 80 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2106_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2021 |  |  | N | No
AD2-107 | Chavies-Bonnyman 69kV |  | KY | Perry | Withdrawn | AEP | 55 | 55 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/16/2020 |  | 12/31/2021 |  |  | N | No
AD2-108 | Springdale CT II 138kV | Springdale | PA | Allegheny | In Service | APS | 96 | 0 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2108_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad2_108_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_108_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 7/10/2019 | N | No
AD2-109 | Gans 138kV |  | PA | Fayette | Withdrawn | APS | 100 | 4 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2109_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 7/12/2019 |  | 5/31/2022 |  |  | N | No
AD2-110 | Guilford 138kV | Chambersburg Energy, LLC | PA | Franklin | In Service | APS | 100 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 9/30/2022 | 9/30/2022 | 9/14/2020 | N | No
AD2-111 | Hunlock 69 kV |  | PA | Luzerne | Withdrawn | AEP | 50 | 6 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 3/28/2018 |  | 5/31/2022 |  |  | N | No
AD2-112 | Springdale CC II 138kV | Springdale | PA | Allegheny | In Service | APS | 610 | 20 | 50.4 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2112_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 11/21/2023 | N | No
AD2-113 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 788.1 | 68.1 | 60.6 | 70 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2113_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_113_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A | 6/1/2023 |  |  | 6/1/2023 | 6/1/2023 | 4/27/2022 | N | No
AD2-114 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | Withdrawn | APS | 1200 | 410 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2114_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_114_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_114_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A | 6/1/2023 | 10/20/2021 |  | 6/1/2023 | 6/1/2023 |  | N | No
AD2-115 | Lyons-Moselem 69kV | Lyons Solar | PA | Berks | In Service | ME | 20 | 20 | 13 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2115_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2115_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_115_csa.pdf | Document Posted | N/A | N/A | 8/25/2023 | 3/24/2018 | N/A | N/A | 11/29/2023 |  |  | 8/31/2023 | 8/31/2023 | 12/1/2023 | N | No
AD2-116 | Hokes-Grantley 69 kV | Cottontail Solar 2 | PA | York | In Service | ME | 20 | 20 | 13 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2116_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2116_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_116_csa.pdf | Document Posted | N/A | N/A | 3/23/2023 | 3/24/2018 | N/A | N/A | 12/1/2023 |  |  | 12/31/2023 | 12/31/2023 | 3/1/2024 | N | No
AD2-117 | Bernville 69kV |  | PA | Berks | Withdrawn | ME | 15 | 15 | 7.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2117_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 5/8/2019 |  | 4/1/2020 |  |  | N | No
AD2-118 | Laurel 12 kV |  | DE | Sussex | Withdrawn | DPL | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 3/28/2018 |  | 4/1/2020 |  |  | N | No
AD2-119 | Milesburg-Dale Summit 230kV |  | PA | Centre | Withdrawn | APS | 75 | 75 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2119_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 9/11/2018 |  | 12/15/2021 |  |  | N | No
AD2-120 | Shenango-McDowell 138kV |  | PA | Mercer | Withdrawn | ATSI | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2120_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 6/19/2019 |  | 12/15/2020 |  |  | N | No
AD2-121 | Oyster Creek 230 kV I |  | NJ | Ocean | Withdrawn | JCPL | 530 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/11/2018 |  | 6/1/2024 |  |  | S | No
AD2-122 | Oyster Creek 230 kV II |  | NJ | Ocean | Withdrawn | JCPL | 635 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/11/2018 |  | 6/1/2024 |  |  | S | No
AD2-123 | East Danville-Roxborough 230 kV |  | NC | Person | Withdrawn | AEP | 94 | 94 | 68.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/16/2018 |  | 6/1/2021 |  |  | N | No
AD2-124 | East Danville-Roxborough 230 kV |  | NC | Person | Withdrawn | AEP | 20 | 20 | 14.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/16/2018 |  | 6/1/2021 |  |  | N | No
AD2-125 | Myersdale Storage |  | PA | Somerset | Withdrawn | PENELEC | 68 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2020 |  |  | N | No
AD2-126 | Backbone Mountain 138 kV |  | WV | Tucker | Withdrawn | APS | 90 | 90 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/27/2018 |  | 12/31/2020 |  |  | N | No
AD2-127 | East Carbondale-Lackawanna 69 kV |  | PA | Wayne | Withdrawn | PPL | 89 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2020 |  |  | N | No
AD2-128 | Mill Run 25 kV |  | PA | Fayette | Withdrawn | APS | 15 | 15 | 3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/27/2018 |  | 12/31/2020 |  |  | N | No
AD2-129 | Somerset Storage |  | PA | Somerset | Withdrawn | PENELEC | 18 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2020 |  |  | N | No
AD2-130 | ESS-J338 |  | IL | Will | Withdrawn | ComEd | 13.6 | 0 | 4.3 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2130_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 12/14/2018 |  | 9/14/2018 |  |  | N | No
AD2-131 | Kincaid-Pana 345kV | Broomstick Solar Energy Centergy Center | IL | Christian | Suspended | ComEd | 260 | 50 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2131_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2131_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_131_csa.pdf | Document Posted | N/A | N/A | 9/24/2026 | 3/24/2018 | N/A | N/A | 9/24/2026 |  |  | 12/7/2028 | 12/7/2028 |  | N | No
AD2-132 | Olive-Reynolds 345kV |  | IN | Pulaski | Withdrawn | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2132_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 1/10/2019 |  | 12/31/2020 |  |  | N | No
AD2-133 | Eagle Valley 115kV | Sandy Ridge | PA | Centre | In Service | PENELEC | 135.4 | 85.4 | 15.3 | 135.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_133_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2018 | N/A | N/A | 7/1/2023 |  |  | 7/31/2023 | 7/31/2023 | 9/16/2023 | N | No
AD2-134 | Shady Oaks | Shady Oaks Wind Power Project | IL | Lee | Partially in Service - Under Construction | ComEd | 215.4 | 105.9 | 21.2 | 105.9 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2134_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_134_csa.pdf | Document Posted | N/A | N/A | 9/7/2023 | 3/25/2018 | N/A | N/A | 9/16/2023 |  |  | 12/7/2027 | 12/7/2027 |  | N | No
AD2-135 | Williamstown 12kV | Monroe-Sicklerville Road LF Solar | NJ | Gloucester | Partially in Service - Under Construction | AEC | 1.62 | 1.62 | 0.6 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2135_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2135_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2135_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2135_wmpa.pdf | Not Required | N/A | N/A | 5/1/2025 | 3/23/2018 | N/A | N/A | 5/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AD2-136 | Melmore Tap 138kV |  | OH | Seneca | Withdrawn | AEP | 360 | 360 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2136_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2136_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 11/22/2022 |  | 10/31/2021 |  |  | N | No
AD2-137 | Loretto-Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2137_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-138 | Olive-Reynolds #1 345kV |  | IN | Warren | Withdrawn | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2138_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/20/2021 |  | 12/31/2020 |  |  | N | No
AD2-139 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 200 | 200 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/31/2018 |  | 12/31/2020 |  |  | N | No
AD2-140 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2140_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-141 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 26.25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2141_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-142 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-143 | Richland Jct-East Leipsic 138kV |  | IN | Randolph | Withdrawn | AEP | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2143_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 1/7/2019 |  | 12/31/2020 |  |  | N | No
AD2-144 | Marysville 345kV |  | IN | Randolph | Withdrawn | AEP | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2144_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 1/7/2019 |  | 12/31/2020 |  |  | N | No
AD2-145 | Star 345kV |  | IN | Randolph | Withdrawn | ATSI | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2145_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 9/4/2018 |  | 12/31/2020 |  |  | N | No
AD2-146 | Wiley 138 kV |  | OH | Butler | Withdrawn | DEOK | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/31/2018 |  | 12/31/2020 |  |  | N | No
AD2-147 | South Charleston 345kV |  | OH | Butler | Withdrawn | Dayton | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2147_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 9/24/2019 |  | 12/31/2020 |  |  | N | No
AD2-148 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2148_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-149 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2149_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-150 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2150_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-151 | Hillcrest 345kV |  | OH | Muskingum | Withdrawn | DEOK | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2151_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 7/26/2019 |  | 12/31/2020 |  |  | N | No
AD2-152 | Pocono 230 kV |  | PA | Wayne | Withdrawn | PPL | 150 | 150 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/5/2018 |  | 12/31/2020 |  |  | N | No
AD2-153 | Brokaw-Pontiac Midpoint |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2153_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/19/2019 |  | 12/31/2020 |  |  | N | No
AD2-154 | Brokaw-Pontiac Midpoint |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2154_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/17/2019 |  | 12/31/2020 |  |  | N | No
AD2-155 | Brokaw-Pontiac Midpoint |  | IL | Kankakee | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2155_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/17/2019 |  | 12/31/2020 |  |  | N | No
AD2-156 | Avery 138 kV |  | OH | Erie | Withdrawn | ATSI | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/2/2018 |  | 12/31/2020 |  |  | N | No
AD2-157 | Hampshire-Gore 138kV |  | WV | Hampshire | Withdrawn | APS | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2157_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 10/10/2022 |  | 12/21/2021 |  |  | N | No
AD2-158 | Old Chapel-Millville 138kV | Wild Hill Solar | WV | Jefferson | Withdrawn | APS | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2158_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2158_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_158_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 3/24/2018 | N/A | N/A | 12/15/2025 | 10/16/2024 |  | 9/1/2024 | 9/1/2024 |  | N | No
AD2-159 | Chestnut 345kV |  | IL | Macon | Withdrawn | ComEd | 187.5 | 187.5 | 33 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  | 3/4/2022 |  |  |  |  | N | No
AD2-160 | Hickory-Moyock 230kV | Oak Trail Solar | NC | Currituck | In Service | Dominion | 50 | 50 | 32.8 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2160_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_160_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_160_csa.pdf | Document Posted | N/A | N/A |  | 3/26/2018 | N/A | N/A | 6/9/2023 |  |  | 7/1/2023 | 7/1/2023 | 7/5/2023 | N | No
AD2-161 | Hunlock 69kV |  | PA | Luzerne | Withdrawn | PPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  | 3/28/2018 |  | 5/22/2022 |  |  | N | No
AD2-162 | Biers Run-Circleville 138kV | Scioto Farms Solar Project | OH | Pickaway | Withdrawn | AEP | 110 | 110 | 73.81 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2162_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2162_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_162_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_162_csa.pdf | Document Posted | N/A | N/A |  | 3/27/2018 | N/A | N/A |  | 6/21/2023 |  | 5/31/2025 | 5/31/2025 |  | N | No
AD2-163 | Broadview-Tangy 138 kV | Madison Fields Solar Project | OH | Madison | In Service | ATSI | 180 | 180 | 120.7 | 180 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2163_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2163_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_163_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_163_csa.pdf | Document Posted | N/A | N/A | 10/26/2023 | 3/27/2018 | N/A | N/A | 10/30/2023 |  |  | 12/31/2023 | 12/31/2023 | 1/23/2024 | N | No
AD2-164 | Peninsula 34.5kV | Langley AFB Generation | VA | City of Hampton | Withdrawn | Dominion | 26.7 | 26.7 | 26.7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2164_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2164_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2164_wmpa.pdf | Not Required | N/A | N/A |  | 3/26/2018 | N/A | N/A | 6/1/2022 | 6/30/2020 |  | 6/1/2022 | 6/1/2022 |  | N | No
AD2-165 | South River II 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 565 | 105 | 40 |  | Capacity | Generation Interconnection | Natural Gas; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2165_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  | 2/10/2020 |  | 5/1/2021 |  |  | N | No
AD2-166 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | ME | 825 | 75 | 89.8 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2166_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_166_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2018 | N/A | N/A |  |  |  | 4/30/2022 | 4/30/2022 | 4/28/2022 | N | No
AD2-167 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 1090 | 90 | 52 | 90 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2167_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_167_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2018 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 | 7/27/2017 | N | No
AD2-168 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2020 |  |  | N | No
AD2-169 | Pleasant Hill-Trego 115kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2169_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 1/28/2020 |  | 9/30/2020 |  |  | N | No
AD2-170 | Carll's Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 9/20/2018 |  | 1/1/2019 |  |  | N | No
AD2-171 | Branchburg-Alburtis 500kV |  | NJ | Hunterdon | Withdrawn | PSEG | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2171_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 11/25/2020 |  | 6/1/2023 |  |  | N | No
AD2-172 | Lena 138kV | High Point Solar | IL | Stephenson | In Service | ComEd | 50 | 50 | 21 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2172_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2172_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_172_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_172_csa.pdf | Document Posted | N/A | N/A | 5/1/2022 | 3/29/2018 | N/A | N/A |  |  |  | 2/28/2024 | 2/28/2024 | 11/30/2023 | N | No
AD2-173 | Bremo-Kidds Store 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 75 | 75 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 4/2/2018 |  | 5/1/2020 |  |  | N | No
AD2-174 | Oakville-St. Andrews 69kV |  | MD | St. Mary's | Withdrawn | SMECO | 52.5 | 52.5 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 1/24/2019 |  | 9/30/2020 |  |  | N | No
AD2-175 | Davis Creek 345 kV |  | IL | Kankakee | Withdrawn | ComEd | 205 | 205 | 123 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2175_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 12/10/2019 |  | 12/31/2021 |  |  | N | No
AD2-176 | Marengo 138kV |  | IL | McHenry | Withdrawn | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2176_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 6/27/2019 |  | 12/31/2021 |  |  | N | No
AD2-177 | Pontiac MidPoint 345 kV |  | IL | Livingston | Withdrawn | ComEd | 205 | 205 | 123 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 3/23/2018 |  | 12/31/2021 |  |  | N | No
AD2-178 | Wurno 138kV | Blackbird Solar | VA | Pulaski | Withdrawn | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2178_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2178_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 4/5/2023 |  | 6/1/2021 |  |  | N | No
AD2-179 | Morgans Cut-Glen Lyn 138kV | Blue Jay Solar | VA | Pulaski | Suspended | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2179_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2179_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_179_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_179_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 3/29/2018 | N/A | N/A | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD2-180 | Elk Garden-Parr Run 138kV | Black Rock Wind | WV | Mineral | In Service | APS | 110 | 110 | 15.08 | 110 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2180_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2180_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_180_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_180_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2018 | N/A | N/A |  |  |  | 12/15/2021 | 12/15/2021 | 10/25/2021 | N | No
AD2-181 | Shawboro-Sligo 230 kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2018 |  |  | N | No
AD2-182 | George Washington 138 kV |  | WV | Marshall | Withdrawn | AEP | 481.5 | 481.5 | 380 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 4/1/2022 |  |  | N | No
AD2-183 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 31.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2020 |  |  | N | No
AD2-184 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 31.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2020 |  |  | N | No
AD2-185 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 31.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2021 |  |  | N | No
AD2-186 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 9/30/2019 |  |  | N | No
AD2-187 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 12 | 8.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 9/30/2019 |  |  | N | No
AD2-188 | Nelson-Electric Junc |  | IL | Lee | Withdrawn | ComEd | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 6/30/2021 |  |  | N | No
AD2-189 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1875 | 225 | 186 | 225 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2189_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_189_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_189_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 3/30/2018 | N/A | N/A | 9/17/2022 |  |  | 12/31/2022 | 12/31/2022 | 2/27/2023 | N | No
AD2-190 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | 111.7933 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 11/1/2020 |  |  | N | No
AD2-191 | Melmore 138kV |  | OH | Seneca | Withdrawn | AEP | 370 | 170 | 22.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2191_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 6/3/2020 |  | 11/2/2020 |  |  | N | No
AD2-192 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 625 | 45 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2192_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2192_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_192_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_192_csa.pdf | Document Posted | N/A | N/A | 11/11/2027 | 3/31/2018 | N/A | N/A | 7/31/2028 |  |  | 1/31/2029 | 1/31/2029 |  | N | No
AD2-193 | Spotsylvania 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 556 | 208.5 | 208.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 11/1/2020 |  |  | N | No
AD2-194 | Elwood 345 kV | Jackson Generation | IL | Will | Partially in Service - Under Construction | ComEd | 1260.9 | 60 | 120 | 19.49 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2194_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_194_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2018 | N/A | N/A | 6/1/2024 |  |  | 1/1/2027 | 1/1/2027 |  | N | No
AD2-195 | Trowbridge-Pantero 115 kV |  | NC | Washington | Withdrawn | Dominion | 80 | 80 | 55.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2195_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 9/25/2018 |  | 6/1/2021 |  |  | N | No
AD2-196 | Acahela 230 kV |  | PA | Luzerne | Withdrawn | PPL | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/5/2018 |  | 12/31/2020 |  |  | N | No
AD2-197 | Carson-Rodgers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 500 | 500 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn | [5 empty] | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/9/2018 |  | 5/3/2021 |  |  | N | No
AD2-198 | Ellwood |  | IL | Will | Withdrawn | ComEd | 1745 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 3/1/2020 |  |  | N | No
AD2-199 | St. Barnabas 13kV II | Spectrum Solar II | MD | Prince George's | Withdrawn | PEPCO | 3 | 3 | 1.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2199_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2199_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2199_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2199_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2199_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2018 | N/A | N/A | 12/30/2023 | 4/27/2024 |  | 6/3/2022 | 6/3/2022 |  | N | No
AD2-200 | Briery-Clover 230 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 144 | 14 | 9.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2200_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 10/16/2018 |  | 9/2/2019 |  |  | N | No
AD2-201 | South Creek 115 kV |  | VA | Appomattox | Withdrawn | Dominion | 62 | 62 | 40.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 3/31/2020 |  |  | N | No
AD2-201A | Hickman-Riverbend 69kV |  | VA | Pulaski | Withdrawn | AEP | 50 | 50 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2201a_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 1/22/2019 |  | 5/3/2021 |  |  | N | No
AD2-202 | Clover-Sedge Hill 230kV | Foxhound Solar | VA | Halifax | In Service | Dominion | 83 | 18.8 | 12.8 | 18.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2202_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2202_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2202_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_202_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_202_csa.pdf | Document Posted | N/A | N/A | 2/1/2024 | 3/31/2018 | N/A | N/A | 2/15/2024 |  |  | 5/31/2024 | 5/31/2024 | 4/24/2024 | N | No
AD2-203 | Clubhouse-Lakeville 230 kV |  | VA | Greensville | Withdrawn | Dominion | 72.3 | 72.3 | 49.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 9/4/2020 |  |  | N | No
AD2-204 | Burlington 26 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/2/2018 |  | 5/31/2019 |  |  | N | No
AD2-205 | Byllesby 69 kV | Buck & Byllesby Hydro Project | VA | Carroll | In Service | AEP | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2205_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_205_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/13/2018 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 1/31/2019 | N | No
AD2-206 | Clubhouse-Freeman DP 115 kV |  | VA | Greensville | Withdrawn | Dominion | 250 | 250 | 150.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/4/2018 |  | 6/1/2020 |  |  | N | No
AD2-207 | Suffolk-Poe 115 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/4/2018 |  | 6/1/2020 |  |  | N | No
AD2-208 | Boykins 115 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/5/2018 |  |  |  |  | N | No
AD2-209 | Cherryville 12.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2209_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 10/9/2018 |  | 11/30/2018 |  |  | N | No
AD2-210 | Cedar Knolls 12.5 kV | South Jefferson Road Storage | NJ | Morris | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2210_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2210_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2210_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2018 | N/A | N/A | 11/30/2023 | 11/1/2023 |  | 12/31/2020 | 12/31/2020 |  | N | No
AD2-211 | Great Adventure 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 3/31/2018 |  | 10/1/2018 |  |  | N | No
AD2-212 | Ocean Bay 128 kV |  | MD | Worcester | Withdrawn | DPL | 160 | 160 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/10/2018 |  | 6/1/2022 |  |  | N | No
AD2-213 | East Flemington-Lebanon 34.5 kV | Justin Court Energy Storage | NJ | Hunterdon | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2213_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2213_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2213_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_213_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_213_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 4/1/2018 | N/A | N/A | 12/18/2023 |  |  | 7/14/2023 | 7/14/2023 | 2/15/2024 | N | No
AD2-214 | Rock Falls-Garden Plains |  | IL | Whiteside | Withdrawn | ComEd | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2214_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2214_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2214_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 5/2/2023 |  | 5/3/2021 |  |  | N | No
AD2-215 | Kings Fork 34.5 kV | Godwin Blvd Solar | VA | City of Suffolk | Withdrawn | Dominion | 15 | 15 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2215_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2215_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2215_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2215_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2018 | N/A | N/A | 12/1/2021 | 1/14/2021 |  | 12/1/2021 | 12/1/2021 |  | N | No
AD2-216 | Axton 138 kV |  | VA | Henry | Withdrawn | AEP | 68 | 68 | 43.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/3/2018 |  | 3/31/2020 |  |  | N | No
AD2-217 | Crossland 13 kV |  | PA | Mercer | Withdrawn | ATSI | 8.8 | 8.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/4/2018 |  | 3/1/2019 |  |  | N | No
AE1-001 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 1820.8 | 28.1 | 7.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_001_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 4/2/2018 | N/A | N/A |  |  |  | 1/13/2023 | 1/13/2023 | 2/7/2023 | N | No
AE1-002 | Wilton Center-Loretto |  | IN | Benton | Withdrawn | ComEd | 100 | 100 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/4/2018 | N/A | N/A |  | 7/29/2019 |  | 12/31/2020 |  |  | N | No
AE1-003 | Williams 138 kV |  | WV | Grant | Withdrawn | APS | 209 | 59 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1003_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/4/2018 | N/A | N/A |  | 9/25/2020 |  | 12/31/2020 |  |  | N | No | This project slid two queues
AE1-004 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 110 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_004_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2018 | N/A | N/A | 6/6/2026 |  |  | 7/14/2026 | 7/14/2026 |  | N | No
AE1-005 | Pantego-Five Points 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2018 | N/A | N/A | 10/28/2025 |  |  | 12/31/2020 |  |  | N | No
AE1-006 | Germantown 115 kV | Brookview Solar I | PA | Adams | Withdrawn | ME | 75 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1006_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_006_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 11/30/2033 | 4/23/2018 | N/A | N/A | 12/30/2033 | 12/11/2023 |  | 12/15/2025 | 12/15/2025 |  | N | No
AE1-007 | Camden-Crystal III 69 kV |  | OH | Preble | Withdrawn | Dayton | 89.9 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1007_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1007_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/23/2018 | N/A | N/A |  | 8/16/2021 |  | 7/1/2019 |  |  | N | No
AE1-008 | College Corner 138 kV |  | OH | Preble | Withdrawn | AEP | 100 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1008_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/23/2018 | N/A | N/A |  | 8/1/2019 |  | 7/1/2019 |  |  | N | No
AE1-009 | Bremo-Cunningham DP 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1009_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/25/2018 | N/A | N/A |  | 3/11/2019 |  | 3/31/2020 |  |  | N | No
AE1-010 | Locust Grove-Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 95.5 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1131_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2018 | N/A | N/A |  | 3/11/2019 |  | 9/30/2021 |  |  | N | No
AE1-011 | Livingston Road 13 kV |  | MD | N/A | Withdrawn | PEPCO | 1.48 | 1.48 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2018 | N/A | N/A |  | 9/24/2018 |  | 3/31/2019 |  |  | Y | No
AE1-012 | 64th St. 13 kV | 1724 64th Street | MD | Prince George's | Withdrawn | PEPCO | 0.54 | 0.54 | 0.22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1012_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1012_wmpa.pdf | Not Required | N/A | N/A |  | 10/2/2018 | N/A | N/A |  | 11/11/2022 |  | 12/30/2022 | 12/30/2022 |  | N | No
AE1-013 | Suitland Road 13 kV | 4179 Suitland Road | MD | Prince George's | Withdrawn | PEPCO | 0.9 | 0.9 | 0.378 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1013_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1013_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1013_wmpa.pdf | Not Required | N/A | N/A |  | 5/3/2018 | N/A | N/A | 6/30/2024 | 4/27/2024 |  | 12/31/2022 | 12/31/2022 |  | N | No
AE1-014 | Canada Street 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 0.54 | 0.54 | 0.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2018 | N/A | N/A |  | 9/24/2018 |  | 9/30/2019 |  |  | Y | No
AE1-015 | St. Barnabas Road 13 kV | 5203 Saint Barnabas Road | MD | Prince George's | Withdrawn | PEPCO | 1.4 | 1.4 | 0.567 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1015_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1015_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1015_wmpa.pdf | Not Required | N/A | N/A |  | 5/2/2018 | N/A | N/A |  | 11/11/2022 |  | 12/31/2022 | 12/31/2022 |  | N | No
AE1-016 | Livingston Road 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 1.08 | 1.08 | 0.4536 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1016_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/3/2018 | N/A | N/A |  | 12/16/2019 |  | 9/30/2019 |  |  | N | No
AE1-017 | Peak Creek-Draper 34.5 kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 20 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1017_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/14/2018 | N/A | N/A |  | 7/15/2020 |  | 6/1/2020 |  |  | N | No
AE1-018 | Peak Creek-Memoria Drive 12 kV | Pulaski Community Solar | VA | Pulaski | Withdrawn | AEP | 5 | 5 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1018_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 5/14/2018 | N/A | N/A |  | 2/21/2020 |  | 6/1/2020 |  |  | N | No
AE1-019 | Earleys-Scotland Neck 115 kV |  | NC | Hertford | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/15/2018 | N/A | N/A |  | 10/31/2018 |  | 6/30/2021 |  |  | N | No
AE1-020 | Oyster Creek 230 kV | Ocean Wind | NJ | Ocean | Suspended | JCPL | 816 | 816 | 229.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1020_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_020_csa.pdf | Document Posted | N/A | N/A |  | 5/23/2018 | N/A | N/A | 2/28/2026 |  |  | 2/28/2026 | 2/28/2026 |  | N | No | This project slid to the next queue
AE1-021 | Gavin #2 765 kV | Gavin Unit No. 2 | OH | Gallia | In Service | AEP | 1367 | 11 | 11 | 11 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1021_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_021_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/24/2018 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 | 6/19/2021 | N | No
AE1-022 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | 111.7933 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 6/21/2018 |  | 11/2/2020 |  |  | N | No
AE1-023 | Wempletown |  | IL | Winnebago | Withdrawn | ComEd | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 6/25/2018 |  | 12/15/2021 |  |  | N | No
AE1-024 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 63.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1024_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 10/3/2020 |  | 12/15/2021 |  |  | N | No
AE1-025 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 63.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1025_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 10/3/2020 |  | 12/15/2021 |  |  | N | No
AE1-026 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 63.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 10/3/2020 |  | 12/15/2022 |  |  | N | No
AE1-027 | Hickory 34.5 kV | Hickory Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1027_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1027_wmpa.pdf | Not Required | N/A | N/A |  | 5/29/2018 | N/A | N/A | 8/15/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-028 | Hickory 34.5 kV | Hickory Solar | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 12 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1028_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1028_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1028_wmpa.pdf | Not Required | N/A | N/A |  | 5/29/2018 | N/A | N/A | 8/15/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-029 | Wheatland 12 kV |  | PA | Mercer | Withdrawn | ATSI | 8.8 | 8.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1029_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/30/2018 | N/A | N/A |  | 6/19/2019 |  | 3/1/2019 |  |  | N | No
AE1-030 | Stuart-Clinton 345 kV II |  | OH | Montgomery | Withdrawn | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2018 | N/A | N/A |  | 6/29/2018 |  | 6/1/2021 |  |  | N | No
AE1-031 | Stuart-Clinton 345 kV III |  | OH | Montgomery | Withdrawn | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2018 | N/A | N/A |  | 6/29/2018 |  | 6/1/2020 |  |  | N | No
AE1-032 4948568 | AMIL-PJM |  | N/A | N/A | Withdrawn |  |  | 180 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-is/4954950_ltf1.pdf |  | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 5/24/2018 | 6/1/2021 | 6/1/2026 |  | 10/4/2018 |  |  |  |  | PP | No
AE1-033 4950965 | ALTE-PJM |  | N/A | N/A | Withdrawn |  |  | 165 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/4/2018 | 6/1/2022 | 6/1/2027 |  | 12/21/2018 |  |  |  |  | PP | No
AE1-034 | Larrabee 230 kV |  | NJ | Atlantic | Withdrawn | JCPL | 1104 | 1104 | 310.224 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1034_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/7/2018 | N/A | N/A |  | 4/19/2019 |  | 6/1/2024 |  |  | N | No
AE1-035 | Earleys 230 kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 99.9 | 19.9 | 13.4 | 19.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_035_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/8/2018 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 2/24/2020 | N | No
AE1-036 | Red Oak 230 kV | Red Oak | NJ | Middlesex | In Service | JCPL | 776 | 0 | 9 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_036_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/13/2018 | N/A | N/A |  |  |  | 7/1/2018 |  | 2/8/2019 | N | No
AE1-037 | Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1200 | 1200 | 1200 |  | Capacity | Merchant Transmission | Wind | AC | 0 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ae1037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/18/2018 | N/A | N/A |  | 1/24/2020 |  | 12/31/2025 |  |  | S | No
AE1-038 | Cartanza 69 kV |  | DE | Kent | Withdrawn | DPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1038_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2018 | N/A | N/A |  | 9/30/2019 |  | 10/31/2020 |  |  | N | No
AE1-039 | West Street (Orchard Hills) 12.47 kV | Orchard Hills Sanitary Landfill | MI | Berrien | In Service | AEP | 4 | 0.8 | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/22/2018 | N/A | N/A |  |  |  | 9/30/2020 | 9/30/2020 | 10/1/2019 | N | No
AE1-040 | Greenfield 69 kV | Fayette Solar | OH | Fayette | In Service | Dayton | 48 | 48 | 31.6 | 48 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1040_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1040_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_040_csa.pdf | Document Posted | N/A | N/A | 10/18/2024 | 6/26/2018 | N/A | N/A | 11/23/2024 |  |  | 5/31/2024 | 5/31/2024 | 1/2/2025 | N | No
AE1-041 | Edison 4kV | Highland Park | NJ | Middlesex | In Service | PSEG | 1.1 | 1.1 | 0.2 | 0.6 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1041_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1041_wmpa.pdf | Not Required | N/A | N/A |  | 6/25/2018 | N/A | N/A | 12/19/2019 |  |  | 1/31/2020 | 1/31/2020 | 12/30/2019 | N | No
AE1-042 4954950 | TVA-PJM |  | N/A | N/A | Withdrawn |  |  | 180 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1042_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 6/26/2018 | 6/1/2021 | 6/1/2026 |  | 2/1/2019 |  |  |  |  | PP | No
AE1-043 | Clayton-Woodstown 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2018 | N/A | N/A |  | 7/25/2018 |  | 11/1/2018 |  |  | Y | No
AE1-044 | Morrisville 230 kV | Fitch Solar | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | 111.7933 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_044_csa.pdf | Document Posted | N/A | N/A |  | 7/6/2018 | N/A | N/A |  | 1/8/2025 |  | 12/30/2025 | 12/30/2025 |  | N | No
AE1-045 | Minotola 12 kV I |  | NJ | Atlantic | Withdrawn | AEC | 3 | 3 | 2.01 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1045_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2018 | N/A | N/A |  | 3/4/2019 |  | 12/31/2019 |  |  | N | No
AE1-046 | Minotola 12 kV II |  | NJ | Atlantic | Withdrawn | AEC | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1046_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2018 | N/A | N/A |  | 9/20/2019 |  | 12/31/2019 |  |  | N | No
AE1-047 | Spotsylvania 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 800 | 300 | 208.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2018 | N/A | N/A |  | 10/12/2018 |  | 11/1/2021 |  |  | N | No
AE1-048 | Wye Mills 25 kV |  | MD | Queen Anne's | Withdrawn | DPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2018 | N/A | N/A |  | 8/9/2018 |  |  |  |  | Y | No
AE1-049 | Tanners Creek - Miami Fort Upgrade Acceleration (b2828; b2831; b2968) |  | OH | Adams | Withdrawn | DEOK |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2018 | N/A | N/A |  | 10/31/2018 |  |  |  |  | EE | No
AE1-050 | Gavin Unit 1 765 kV | Gavin Unit No. 1 | OH | Gallia | In Service | AEP | 1349 | 18 | 18 | 18 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/20/2018 | N/A | N/A | 5/20/2025 |  |  | 5/31/2025 | 5/31/2025 | 5/21/2025 | N | No
AE1-051 | East Carbondale-Lackawanna 69kV |  | PA | Wayne | Withdrawn | PPL | 74.5 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2018 | N/A | N/A |  | 1/25/2023 |  | 9/1/2020 |  |  | N | No
AE1-052 | William 138 kV | Backbone Mountain Windpower | WV | Tucker | Withdrawn | APS | 66 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1052_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_052_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/21/2018 | N/A | N/A |  | 11/28/2022 |  | 9/1/2024 | 9/1/2024 |  | N | No
AE1-053 | Meyersdale North |  | PA | Somerset | Withdrawn | PENELEC | 30 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2018 | N/A | N/A |  | 12/1/2022 |  | 9/1/2020 |  |  | N | No
AE1-054 | Mill Run 25kV |  | PA | Fayette | Withdrawn | APS | 15 | 0 | 7.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1054_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2018 | N/A | N/A |  | 3/19/2021 |  | 9/1/2020 |  |  | N | No
AE1-055 | Mason 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 134 | 134 | 134 |  | Capacity | Generation Interconnection | Natural Gas; Other; Storage; Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2018 | N/A | N/A |  | 8/14/2018 |  | 12/31/2021 |  |  | N | No
AE1-056 | Red House-South Creek 115 kV | Caden Energix Spout Spring | VA | Appomattox | Suspended | Dominion | 60 | 60 | 38.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1056_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1056_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_056_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2018 | N/A | N/A |  |  |  | 1/31/2025 | 1/31/2025 |  | N | No
AE1-057 | Brandy DP 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2018 | N/A | N/A |  | 11/7/2018 |  | 12/1/2019 |  |  | N | No
AE1-058 | Frackville-Siegfried 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 500 | 500 | 250 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1158_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/26/2018 | N/A | N/A |  | 10/13/2023 |  | 12/15/2022 |  |  | N | No
AE1-059 | Stanton-Summit 230 kV | AREW Old Forge | PA | Luzerne | Withdrawn | PPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_059_csa.pdf | Document Posted | N/A | N/A | 7/30/2027 | 7/27/2018 | N/A | N/A | 8/30/2027 | 3/7/2024 |  | 9/30/2027 | 9/30/2027 |  | N | No
AE1-060 | Kittatinny-Newton 34.5 kV | VESI – Andover Energy Storage | NJ | Sussex | In Service | JCPL | 19.8 | 19.8 | 0 | 19.8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_060_csa.pdf | Document Posted | N/A | N/A | 9/16/2022 | 7/26/2018 | N/A | N/A | 10/3/2022 |  |  | 9/30/2022 | 9/30/2022 | 6/17/2023 | N | No
AE1-061 | Minotola 12 kV | Panther Branch Storage | NJ | Atlantic | Withdrawn | AEC | 5.5 | 5.5 | 2.75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1061_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1061_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1061_wmpa.pdf | Not Required | N/A | N/A |  | 7/30/2018 | N/A | N/A |  | 4/28/2023 |  | 4/1/2025 | 4/1/2025 |  | N | No
AE1-062 | Silver Lake 69 kV |  | NJ | Camden | Withdrawn | AEC | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1062_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1062_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2018 | N/A | N/A |  | 3/22/2022 |  | 10/30/2020 |  |  | N | No
AE1-063 | Buckeye-Ringoes 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 3 | 3 | 1.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1063_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2018 | N/A | N/A |  | 3/27/2019 |  | 11/29/2019 |  |  | N | No
AE1-064 | Whitehouse-Lone Gum 138 kV |  | VA | Bedford | Withdrawn | AEP | 102.1 | 102.1 | 67.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1064_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 4/12/2024 |  | 5/3/2021 |  |  | N | No
AE1-065 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 158.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1065_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/5/2019 |  | 12/31/2025 |  |  | N | No
AE1-066 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 163.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1066_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/5/2019 |  | 12/31/2027 |  |  | N | No
AE1-067 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 148.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1067_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/5/2019 |  | 12/31/2029 |  |  | N | No
AE1-068 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Withdrawn | Dominion | 500 | 500 | 322.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1068_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1068_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 9/8/2023 |  | 12/1/2021 |  |  | N | No
AE1-069 | Carson-Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 400 | 400 | 254.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1069_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1069_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 9/8/2023 |  | 12/1/2021 |  |  | N | No
AE1-070 - moved to TC1 | Elwood 345 kV |  | IL | Will | Withdrawn | ComEd | 1610 | 0 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1070_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 1/22/2025 |  | 12/31/2020 |  |  | N | No
AE1-071 | Shade Gap-Roxbury 115 kV | Aspen Road Solar | PA | Franklin | In Service | PENELEC | 100.1 | 100.1 | 62.1 | 100.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_071_csa.pdf | Document Posted | N/A | N/A | 12/20/2024 | 7/31/2018 | N/A | N/A | 2/18/2025 |  |  | 3/8/2025 | 3/8/2025 | 2/28/2025 | N | No
AE1-072 | Shawboro-Sligo 230 kV | Shawboro Solar | NC | Currituck | Engineering and Procurement | Dominion | 150 | 150 | 98.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_072_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2018 | N/A | N/A | 11/1/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
AE1-073 | Bremo-Kidds Store 115 kV |  | VA | Accomack | Withdrawn | Dominion | 75 | 75 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1073_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/13/2019 |  | 12/1/2021 |  |  | N | No
AE1-074 | Winterpock 34.5 kV | Winterpock I | VA | Chesterfield | Under Construction | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1074_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1074_wmpa.pdf | Not Required | N/A | N/A | 11/1/2025 | 8/1/2018 | N/A | N/A | 11/1/2025 |  |  | 2/4/2025 | 2/4/2025 |  | N | No
AE1-075 | Powhatan 34.5 kV | Powhatan Solar I, LLC | VA | Powhatan | In Service | Dominion | 18 | 18 | 12 | 18 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1075_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1075_wmpa.pdf | Not Required | N/A | N/A | 1/19/2024 | 8/2/2018 | N/A | N/A | 12/4/2024 |  |  | 10/31/2024 | 10/31/2024 | 1/31/2025 | N | No
AE1-076 | Twombley Road 138 kV |  | IL | Ogle | Withdrawn | ComEd | 35.4 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  | 9/10/2018 |  | 12/31/2019 |  |  | N | No
AE1-077 | Sandy Springs-High Ridge 230 kV |  | MD | Allegany | Withdrawn | BGE | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ae1077_imp-arr.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ae1077_arr-fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  | 7/20/2022 |  | 6/1/2020 |  |  | EE | No
AE1-078 | Greendale-Miami Fort 138kV Upgrades |  | OH | Adams | Withdrawn | DEOK | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ae1078_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  | 9/23/2019 |  | 6/1/2020 |  |  | EE | No
AE1-079 | Maysville-Sharon 69 kV | Welcome Solar, LLC | PA | Mercer | Under Construction | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_079_csa.pdf | Document Posted | N/A | N/A | 11/24/2026 | 8/11/2018 | N/A | N/A | 6/25/2026 |  |  | 2/24/2027 | 2/24/2027 |  | N | No
AE1-080 | Wylie Ridge 500 kV |  | PA | Washington | Withdrawn | APS | 1075 | 50 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1080_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/21/2018 | N/A | N/A |  | 3/26/2021 |  | 2/1/2022 |  |  | N | No
AE1-080A 4964319 | PJM-MECS |  | N/A | N/A | Withdrawn |  |  | 300 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/16/2018 | 6/1/2020 | 6/1/2025 |  | 12/20/2018 |  |  |  |  | PP | No
AE1-081 | Landing 12.47 kV | Durban Ave Solar | NJ | Sussex | In Service | JCPL | 1.25 | 1.25 | 0.52 | 1.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1081_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1081_wmpa.pdf | Not Required | N/A | N/A |  | 8/27/2018 | N/A | N/A | 6/30/2020 |  |  | 6/30/2021 | 6/30/2021 | 9/25/2020 | N | No
AE1-082 | Charles County 13 kV |  | MD | Charles | Withdrawn | SMECO | 1.25 | 1.25 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2018 | N/A | N/A |  | 9/13/2018 |  | 11/30/2018 |  |  | Y | No
AE1-083 | Busselton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1083_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2018 | N/A | N/A |  | 6/19/2019 |  | 5/31/2019 |  |  | N | No
AE1-084 | Barterbrook-Stuarts Draft 115 kV | Round Hill Solar | VA | Augusta | Withdrawn | Dominion | 83 | 83 | 49.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1084_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1084_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_084_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_084_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2018 | N/A | N/A |  | 7/11/2024 |  | 10/31/2023 | 10/31/2023 |  | N | No
AE1-085 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Withdrawn | Dominion | 75 | 75 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2018 | N/A | N/A |  | 8/31/2022 |  | 6/1/2022 |  |  | N | No
AE1-086 | Grassy Falls 138 kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 55.6 | 5 | 0.6 | 5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1086_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_086_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 5/31/2020 |  |  | 5/31/2020 | 5/31/2020 | 3/14/2020 | N | No
AE1-087 | Todd 69 kV | Richfield Solar and Storage | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_087_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2018 | N/A | N/A |  | 4/27/2024 |  | 4/1/2024 | 4/1/2024 |  | N | No
AE1-088 | Five Points-Pantego 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  | 4/17/2020 |  | 12/31/2020 |  |  | N | No
AE1-089 | Elderberry-Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 310 | 310 | 130.65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1089_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2021 |  |  | N | No
AE1-090 | Hardin Switch 345 kV | Hardin Energy Center - Phase 3 | OH | Hardin | In Service | AEP | 250 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_090_csa.pdf | Document Posted | N/A | N/A | 10/25/2024 | 9/1/2018 | N/A | N/A | 12/7/2024 |  |  | 12/31/2025 | 12/31/2025 | 2/21/2025 | N | No
AE1-091 | West Newton-Lynn 138 kV | Strawhat Solar Energy Center | OH | Hardin | Suspended | AEP | 110 | 110 | 46.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1091_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_091_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_091_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 1/14/2026 | 1/14/2026 |  | N | No
AE1-092 - moved to TC1 | Blue Jacket-Kirby 138 kV | Fountain Point Solar | OH | Union | Active | Dayton | 206.55 | 206.6 | 96.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1092_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-093 | Elk 138 kV | Vinton Energy Storage | OH | Vinton | Suspended | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1093_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_093_csa.pdf | Document Posted | N/A | N/A | 10/30/2026 | 8/31/2018 | N/A | N/A | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-094 4966856 | PJM-HUDSON |  | N/A | N/A | Withdrawn |  |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1094_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2019 | 6/1/2020 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-095 4966859 | PJM-HUDSON |  | N/A | N/A | Withdrawn |  |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1095_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2020 | 6/1/2021 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-096 4966862 | PJM-HUDSON |  | N/A | N/A | Withdrawn |  |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1096_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2021 | 6/1/2022 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-097 4966877 | PJM-HUDSON |  | N/A | N/A | Withdrawn |  |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1097_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2022 | 6/1/2027 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-098 | Endless Caverns 34.5 kV | Endless Caverns Solar | VA | Rockingham | Withdrawn | Dominion | 15.7 | 15.7 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1098_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1098_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1098_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 5/1/2023 | 3/6/2023 |  | 6/26/2023 | 6/26/2023 |  | N | No
AE1-099 | Endless Caverns 34.kV | Endless Caverns Solar | VA | Rockingham | Withdrawn | Dominion | 15.7 | 15.7 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1099_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1099_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 5/1/2023 | 3/6/2023 |  | 6/26/2023 | 6/26/2023 |  | N | No
AE1-100 | Axton 138 kV | Caden Energix Axton | VA | Henry | In Service | AEP | 66 | 66 | 41.9 | 66 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_100_csa.pdf | Document Posted | N/A | N/A | 7/1/2023 | 9/3/2018 | N/A | N/A | 12/26/2023 |  |  | 12/31/2023 | 12/31/2023 | 2/22/2024 | N | No
AE1-101 | McConnellsburg-Texas Eastern 138 kV | Great Cove Solar II | PA | Franklin | In Service | APS | 150 | 150 | 100.5 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_101_csa.pdf | Document Posted | N/A | N/A | 12/10/2023 | 9/2/2018 | N/A | N/A | 12/13/2023 |  |  | 3/31/2024 | 3/31/2024 | 6/6/2024 | N | No
AE1-102 | Maddox Creek 345 kV | Blue Creek Wind Farm | OH | Van Wert | Suspended | AEP | 396 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1102_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_102_csa.pdf | Document Posted | N/A | N/A |  | 9/1/2018 | N/A | N/A |  |  |  | 11/30/2024 | 11/30/2024 |  | N | No
AE1-103 | Holland-Union Camp 115 kV | Ho-Fel Solar | VA | Isle of Wight | Under Construction | Dominion | 40 | 40 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_103_csa.pdf | Document Posted | N/A | N/A | 7/16/2026 | 9/1/2018 | N/A | N/A | 8/10/2026 |  |  | 10/19/2026 | 10/19/2026 |  | N | No
AE1-104 | BL England 138 kV | Ocean Wind LLC | NJ | Cape May | Suspended | AEC | 432 | 432 | 121.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1104_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1104_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_104_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_104_csa.pdf | Document Posted | N/A | N/A |  | 9/6/2018 | N/A | N/A | 2/28/2026 |  |  | 2/28/2026 | 2/28/2026 |  | N | No
AE1-105 | North Longview 500 kV | Maidsville CCGT | WV | Preston | Suspended | APS | 1270 | 1270 | 1235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_105_csa.pdf | Document Posted | N/A | N/A |  | 9/6/2018 | N/A | N/A |  |  |  | 7/1/2026 | 7/1/2026 |  | N | No
AE1-106 | Lake Lynn-Hazelton 138 kV | Brandonville Solar | WV | Preston | Suspended | APS | 99.6 | 99.6 | 59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1106_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1106_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_106_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_106_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 9/11/2018 | N/A | N/A | 10/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-107 | Mt. Pleasant-Lums Pond 138 kV |  | DE | New Castle | Withdrawn | DPL | 53.1 | 53.1 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1107_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1107_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/10/2018 | N/A | N/A |  | 4/5/2023 |  | 9/30/2021 |  |  | N | No
AE1-108 | Bremo-Scottsville 138 kV | Riverstone Solar | VA | Buckingham | Engineering and Procurement | AEP | 149.5 | 149.5 | 89.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1108_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1108_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_108_csa.pdf | Document Posted | N/A | N/A | 10/15/2026 | 9/13/2018 | N/A | N/A | 11/15/2026 |  |  | 11/30/2027 | 11/30/2027 |  | N | No
AE1-109 | Frenchs Mill 34 kV | Capon Bridge Solar | WV | Hampshire | In Service | APS | 20 | 20 | 8.7 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1109_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1109_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1109_wmpa.pdf | Not Required | N/A | N/A | 6/20/2024 | 9/15/2018 | N/A | N/A | 7/10/2024 |  |  | 7/31/2024 | 7/31/2024 | 7/25/2024 | N | No
AE1-109A | Baker Pont-Ivor 115 kV |  | VA | Southampton | Withdrawn | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1109a_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2018 | N/A | N/A |  | 3/6/2019 |  | 12/1/2022 |  |  | N | No
AE1-110 4966477 | PJM-DUK |  | N/A | N/A | Withdrawn |  |  | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-is/4966477_ltf1.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1110_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/28/2018 | 1/1/2025 | 1/1/2030 |  | 2/28/2019 |  |  |  |  | PP | No
AE1-111 4966479 | PJM-DUK |  | N/A | N/A | Withdrawn |  |  | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-is/4966479_ltf1.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1111_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/28/2018 | 1/1/2025 | 1/1/2031 |  | 2/28/2019 |  |  |  |  | PP | No
AE1-112 4966484 | PJM-DUK |  | N/A | N/A | Withdrawn |  |  | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-is/4966484_ltf1.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ae1112_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/28/2018 | 1/1/2025 | 1/1/2032 |  | 2/28/2019 |  |  |  |  | PP | No
AE1-113 | Mole Creek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 300 | 300 | 66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1113_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1113_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_113_csa.pdf | Document Posted | N/A | N/A | 9/21/2026 | 9/14/2018 | N/A | N/A | 10/1/2026 |  |  | 1/18/2027 | 1/18/2027 |  | N | No
AE1-114 - moved to TC1 | Maryland-Lancaster 138 kV | Leaf River Wind | IL | Ogle | Active | ComEd | 150 | 150 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1114_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-115 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1115_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1115_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/14/2018 | N/A | N/A |  | 4/29/2022 |  | 6/1/2021 |  |  | N | No
AE1-116 | Somerset 22.86kV |  | PA | Somerset | Withdrawn | PENELEC | 9 | 0 | 4.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1116_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/14/2018 | N/A | N/A |  | 3/19/2021 |  | 10/1/2020 |  |  | N | No
AE1-117 | Bethany 138 kV |  | DE | Sussex | Withdrawn | DPL | 152 | 152 | 41.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1117_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  | 7/15/2022 |  | 6/1/2022 |  |  | N | No
AE1-118 | Bethany-138th Street 138 kV |  | DE | Sussex | Withdrawn | DPL | 152 | 152 | 41.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1118_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  | 7/10/2020 |  | 6/1/2022 |  |  | N | No
AE1-119 | Lemoyne 345 kV |  | OH | Wood | Withdrawn | ATSI | 1260 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1119_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2018 | N/A | N/A |  | 10/27/2021 |  | 6/1/2022 |  |  | N | No
AE1-120 | Hillcrest 138 kV | Hillcrest Solar I | OH | Brown | In Service | DEOK | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1120_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_120_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/19/2020 | 9/17/2018 | N/A | N/A | 11/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/18/2020 | N | No
AE1-121 | Axton 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 529.5 | 529.5 | 483 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1121_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  | 1/8/2021 |  | 6/1/2022 |  |  | N | No
AE1-122 | Axton 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 529.5 | 529.5 | 483 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1122_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  | 7/18/2019 |  | 6/1/2023 |  |  | N | No
AE1-123 | Emlenton 34.5 kV | Clarion Boards | PA | Clarion | In Service | PENELEC | 18 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1123_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1123_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1123_wmpa.pdf | Not Required | N/A | N/A |  | 9/20/2018 | N/A | N/A | 10/2/2023 |  |  | 11/10/2023 | 11/10/2023 | 11/3/2023 | N | No
AE1-124 | Oak Grove 34.5 kV | VSF Solar I | VA | Westmoreland | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1124_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1124_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1124_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 4/30/2021 |  | 3/27/2024 | 3/27/2024 |  | N | No
AE1-125 | Mt. Jackson 34.5 kV |  | VA | Shenandoah | Withdrawn | Dominion | 18.9 | 18.9 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1125_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 3/11/2019 |  | 11/20/2020 |  |  | N | No
AE1-126 | Kingsland 26 kV |  | NJ | Bergen | Withdrawn | PSEG | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 10/1/2018 |  | 11/29/2019 |  |  | N | No
AE1-127 | Eldred-Sunbury 69 kV |  | PA | Northumberland | Withdrawn | PPL | 50 | 50 | 32.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1127_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 10/18/2019 |  | 6/7/2021 |  |  | N | No
AE1-128 | Bedford North-Wills Mounain 115 kV |  | PA | Bedford | Withdrawn | PENELEC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1128_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 2/8/2023 |  | 12/31/2021 |  |  | N | No
AE1-129 | Zion View - Middletown 115 kV | Strinestown Solar Project | PA | York | Engineering and Procurement | ME | 79.6 | 79.6 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1129_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1129_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_129_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_129_csa.pdf | Document Posted | N/A | N/A | 11/9/2026 | 9/7/2018 | N/A | N/A | 12/7/2026 |  |  | 1/7/2027 | 1/7/2027 |  | N | No
AE1-130 | Meads Store 138 kV |  | VA | Bedford | Withdrawn | AEP | 83 | 83 | 55.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1130_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2018 | N/A | N/A |  | 8/6/2021 |  | 11/30/2020 |  |  | N | No
AE1-131 | Gardners-Hunterstown 115 kV |  | PA | Adams | Withdrawn | ME | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1131_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2018 | N/A | N/A |  | 6/11/2021 |  | 12/31/2021 |  |  | N | No
AE1-132 | McConnellsburg 138 kV |  | PA | Fulton | Withdrawn | APS | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1132_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1132_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/20/2018 | N/A | N/A |  | 2/23/2022 |  | 12/31/2021 |  |  | N | No
AE1-133 | Elizabeth City-Tanglewood 230 kV |  | NC | Alamance | Withdrawn | Dominion | 300 | 300 | 201 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1133_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/11/2019 |  | 9/1/2022 |  |  | N | No
AE1-134 | Nelson 345 kV | Nelson Energy Center | IL | Lee | In Service | ComEd | 609 | 9 | 24.4 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_134_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/30/2023 | 6/30/2023 | 5/12/2023 | N | No
AE1-135 | Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1135_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/19/2019 |  | 6/30/2019 |  |  | N | No
AE1-136 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Withdrawn | APS | 53.32 | 53.32 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1136_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/26/2019 |  | 12/31/2021 |  |  | N | No
AE1-137 | Bluff Point-Randolph |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/3/2018 |  | 10/31/2021 |  |  | N | No
AE1-138 | Hamilton 115 kV |  | PA | Adams | Withdrawn | ME | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1138_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/30/2022 |  |  |  |  | N | No
AE1-139 | Hunterstown 115 kV |  | PA | Adams | Withdrawn | ME | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1139_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/29/2022 |  | 12/15/2022 | 12/15/2022 |  | N | No
AE1-140 | Fayetteville-West Waynesboro 138 kV |  | PA | Franklin | Withdrawn | APS | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1140_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 4/30/2019 |  | 12/31/2021 |  |  | N | No
AE1-141 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2021 |  |  | N | No
AE1-142 | Manitou-Pleasant Plains 34.5 kV | Toms River Solar | NJ | Ocean | In Service | JCPL | 20 | 20 | 8.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_142_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A | 2/15/2021 |  |  | 2/28/2021 | 2/28/2021 | 3/12/2021 | N | No
AE1-143 | Marion County 161 kV | Northern Bobwhite Solar | KY | Marion | Engineering and Procurement | EKPC | 96 | 96 | 64.163 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1143_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1143_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_143_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_143_csa.pdf | Document Posted | N/A | N/A | 12/15/2026 | 9/25/2018 | N/A | N/A | 1/15/2027 |  |  | 3/15/2027 | 3/15/2027 |  | N | No
AE1-145 | Wallops Island 69 kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1145_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 4/20/2022 |  | 12/1/2020 |  |  | N | No
AE1-146 | Ebersole #2-Fostoria Central 138 kV | Border Basin | OH | Hancock | Under Construction | AEP | 120 | 120 | 81.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1146_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1146_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_146_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_146_csa.pdf | Document Posted | N/A | N/A | 10/3/2025 | 9/25/2018 | N/A | N/A | 11/3/2025 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-147 | Bellefonte 46 kV | Nittany Solar | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1147_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1147_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1147_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A | 12/15/2022 | 3/12/2022 |  | 12/15/2022 | 12/15/2022 |  | N | No
AE1-148 - moved to TC1 | Kerr Dam-Ridge Rd 115 kV | Antlers Road Solar | VA | Mecklenburg | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-149 | Disputanta-Poe 115 kV | Bakers Pond Solar | VA | Prince George | Suspended | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1149_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1149_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_149_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_149_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A | 3/1/2026 |  |  | 7/1/2026 | 7/1/2026 |  | N | No
AE1-150 | Curdsville-Willis Mountain 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1150_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/15/2019 |  | 12/1/2021 |  |  | N | No
AE1-151 | PACA Street 13.8kV |  | MD | Baltimore City | Withdrawn | BGE | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1151_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/8/2019 |  | 3/2/2020 |  |  | N | No
AE1-152 | Gosport 34.5 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 21.5 | 21.5 | 20.2 |  | Capacity | Generation Interconnection | Natural Gas; Diesel; Other; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/16/2018 |  | 10/16/2020 |  |  | N | No
AE1-153 | Remington-Gordonsville 230 kV | Maroon Solar | VA | Culpeper | Suspended | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1153_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1153_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_153_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_153_csa.pdf | Document Posted | N/A | N/A |  | 9/25/2018 | N/A | N/A | 12/25/2025 |  |  | 5/30/2027 | 5/30/2027 |  | N | No
AE1-154 | Louisa-South Anna 230 kV | Belcher Solar | VA | Louisa | Withdrawn | Dominion | 105.2 | 17 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1154_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_154_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_154_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A | 6/1/2023 | 7/5/2023 |  | 12/1/2021 | 12/1/2021 |  | N | No
AE1-155 | Garner-Northern Neck 115 kV | Bookers Mill Solar | VA | City of Richmond | In Service | Dominion | 127 | 127 | 76.2 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1155_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1155_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_155_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_155_csa.pdf | Document Posted | N/A | N/A | 10/6/2023 | 9/26/2018 | N/A | N/A | 3/12/2024 |  |  | 5/14/2024 | 5/14/2024 | 12/18/2024 | N | No
AE1-156 | Quakertown Solar II 34.5 kV | Quakertown Solar Farm | NJ | Hunterdon | Partially in Service - Under Construction | JCPL | 17.6 | 8.8 | 4.1 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1156_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_156_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_156_csa.pdf | Document Posted | N/A | N/A |  | 9/25/2018 | N/A | N/A | 8/15/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE1-157 | Ladysmith CT-St. Johns 230 kV | CC Solar I | VA | Caroline | Suspended | Dominion | 120 | 120 | 77.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1157_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_157_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_157_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AE1-158 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 120 | 120 | 79.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1158_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 7/28/2023 |  | 12/1/2021 |  |  | N | No
AE1-159 | Fredericksburg-Pinewood 115 kV |  | VA | Caroline | Withdrawn | Dominion | 120 | 120 | 75.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 12/20/2019 |  | 12/1/2021 |  |  | N | No
AE1-160 | Venango 34.5 kV | Titusville Solar | PA | Venango | Withdrawn | PENELEC | 20 | 20 | 12.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/Delay email sent 11/27/19 | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1160_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1160_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 4/2/2024 |  | 12/31/2024 | 12/31/2024 |  | N | No
AE1-161 | Landis 138 kV |  | NJ | Cumberland | Withdrawn | AEC | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1161_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 8/7/2023 |  | 10/1/2021 |  |  | N | No
AE1-162 | Smithfield 34.5 kV | Solidago Solar | VA | Isle of Wight | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1162_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1162_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1162_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A | 6/20/2023 |  |  | 12/31/2023 | 12/31/2023 | 8/1/2023 | N | No
AE1-163 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 350 | 350 | 49 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1163_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1163_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_163_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_163_csa.pdf | Document Posted | N/A | N/A | 11/1/2026 | 9/24/2018 | N/A | N/A | 11/1/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
AE1-164 | Old Chapel 138 kV |  | VA | Accomack | Withdrawn | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1164_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 2/19/2019 |  | 12/30/2021 |  |  | N | No
AE1-165 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1165_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 4/8/2019 |  | 12/30/2021 |  |  | N | No
AE1-166 | Loretto-Wilton 345 kV & Braidwood-Davis Creek 345 kV | Heritage Prairie Solar | IL | Kankakee | Engineering and Procurement | ComEd | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1166_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1166_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae1_166_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 9/24/2018 | N/A | N/A | 8/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AE1-167 | Wattsville 12 kV |  | VA | Accomack | Withdrawn | DPL | 11.09 | 11.09 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1167_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 4/22/2020 |  | 6/25/2021 |  |  | N | No
AE1-168 | Victoria-Martin 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1168_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/8/2020 |  | 9/1/2021 |  |  | N | No
AE1-169 | Titusville 115 kV |  | PA | Venango | Withdrawn | PENELEC | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1169_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/23/2020 |  | 7/1/2021 |  |  | N | No
AE1-170 | Kenzie Creek-Colby 138 kV | Wingstem Solar Energy Farm | MI | Cass | Suspended | AEP | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1170_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1170_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_170_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_170_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 9/25/2018 | N/A | N/A | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE1-171 | Reynolds-Olive 345 kV |  | IN | White | Withdrawn | AEP | 280 | 280 | 118 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-172 - moved to TC1 | Loretto-Wilton Center | Livingston Wind | IL | Livingston | Active | ComEd | 255 | 255 | 44.88 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1172_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE1-173 | Carson-Suffolk 500 kV | Blackwater Solar | VA | Sussex | Under Construction | Dominion | 800 | 800 | 480 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1173_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1173_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae1_173_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2029 | 9/25/2018 | N/A | N/A | 7/1/2029 |  |  | 10/1/2029 | 10/1/2029 |  | N | No
AE1-174 | Light Foot 34.5 kV |  | VA | James City | Withdrawn | Dominion | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1174_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 6/16/2020 |  | 10/23/2020 |  |  | N | No
AE1-175 | Light Foot 34.5 kV | Lightfoot 34.5 kV II | VA | James City | In Service | Dominion | 19.9 | 19.9 | 13.3 | 19.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1175_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1175_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 11/15/2021 | 11/15/2021 | 5/10/2022 | N | No
AE1-176 | Roanoke-Vinton 12 kV (Niagara Hydro) | Niagara Power Plant Dam | VA | Roanoke | In Service | AEP | 2.4 | 2.4 | 2.4 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1176_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_176_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 5/23/2020 | N | No
AE1-177 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 80 | 19 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 10/1/2018 |  | 10/31/2020 |  |  | N | No
AE1-178 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 294 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_178_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 12/21/2021 | 12/21/2021 | 5/25/2021 | N | No
AE1-179 | South Millville-Newport 69 kV | Buckshutem Solar I | NJ | Cumberland | Withdrawn | AEC | 59.7 | 59.7 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1179_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1179_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_179_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_179_csa.pdf | Document Posted | N/A | N/A | 1/31/2027 | 9/25/2018 | N/A | N/A | 1/31/2027 | 3/13/2025 |  | 1/31/2027 | 1/31/2027 |  | N | No
AE1-180 | Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1180_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 8/7/2019 |  | 9/30/2020 |  |  | N | No
AE1-181 | St. Johns-Freeland 69 kV |  | PA | Luzerne | Withdrawn | PPL | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1181_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1181_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 11/1/2022 |  | 10/27/2020 |  |  | N | No
AE1-182 | Newville-West Carlise 69 kV |  | PA | Cumberland | Withdrawn | PPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1182_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 8/14/2020 |  |  |  |  | N | No
AE1-183 | Maysville-McDowell 69 kV | Jackson Center Solar Facility | PA | Mercer | Engineering and Procurement | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1183_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1183_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_183_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_183_csa.pdf | Document Posted | N/A | N/A | 5/31/2026 | 9/26/2018 | N/A | N/A | 6/29/2026 |  |  | 7/31/2026 | 7/31/2026 |  | N | No
AE1-184 | Pontiac Midpoint-Dresden |  | IL | Livingston | Withdrawn | ComEd | 82.7 | 82.7 |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ae1184_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 2/2/2022 |  | 6/1/2022 |  |  | EE | No
AE1-185 | Hokes-Jackson 69 kV | Cottontail Solar 1 | PA | York | In Service | ME | 20 | 20 | 12.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1185_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1185_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_185_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_185_csa.pdf | Document Posted | N/A | N/A | 3/9/2023 | 9/30/2018 | N/A | N/A | 7/22/2024 |  |  | 7/31/2024 | 7/31/2024 | 8/12/2024 | N | No
AE1-186 | Moselem-Lyons 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1186_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 3/25/2019 |  | 4/1/2021 |  |  | N | No
AE1-187 | North Lebanon- Cleona 69 kV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1187_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 11/26/2019 |  | 4/1/2021 |  |  | N | No
AE1-188 | Fayetteville 34.5 kV | Fayetteville Solar | PA | Franklin | Withdrawn | APS | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1188_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1188_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1188_wmpa.pdf | Not Required | N/A | N/A |  | 9/26/2018 | N/A | N/A | 9/30/2023 | 10/10/2023 |  | 3/1/2022 | 3/1/2022 |  | N | No
AE1-189 | Penville-Adams 138 kV |  | IN | Jay | Withdrawn | AEP | 245 | 245 | 103 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-190 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Partially in Service - Under Construction | Dominion | 70 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1190_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_190_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 9/28/2018 | N/A | N/A | 7/17/2024 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
AE1-191 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Partially in Service - Under Construction | Dominion | 150 | 80 | 48 | 52 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1191_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_191_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_191_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 9/28/2018 | N/A | N/A | 7/17/2024 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
AE1-192 | Belle Haven-Tasley 69 kV |  | VA | Accomack | Withdrawn | ODEC | 70 | 70 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1192_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1192_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/29/2020 |  | 11/30/2021 |  |  | N | No
AE1-193 | Crete 345 kV |  | IL | Henry | Withdrawn | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1193_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1193_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/7/2023 |  | 9/1/2021 |  |  | N | No
AE1-194 | Crete 345 kV |  | IL | Will | Withdrawn | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1194_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/7/2023 |  | 9/1/2021 |  |  | N | No
AE1-195 | Crete 345 kV |  | IL | Will | Withdrawn | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1195_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1195_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/7/2023 |  | 9/1/2021 |  |  | N | No
AE1-196 | Hokes-Jackson 69 kV II | Cottontail Solar 8 | PA | York | In Service | ME | 20 | 20 | 12.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1196_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1196_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_196_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_196_csa.pdf | Document Posted | N/A | N/A | 3/9/2023 | 9/28/2018 | N/A | N/A | 2/29/2024 |  |  | 12/31/2023 | 12/31/2023 | 4/24/2024 | N | No
AE1-197 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 9/1/2021 |  |  | N | No
AE1-198 | Crete 345 kV |  | IL | McHenry | Withdrawn | ComEd | 357 | 357 | 193 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1198_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1198_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/14/2022 |  | 9/1/2021 |  |  | N | No
AE1-199 | Twombly Road 138 kV |  | IL | Ogle | Withdrawn | ComEd | 40 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1199_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 8/14/2019 |  | 12/31/2019 |  |  | N | No
AE1-200 | College Corner-Randolph 138 kV |  | IN | Randolph | Withdrawn | AEP | 235 | 235 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-201 | Marengo 34 kV |  | IL | McHenry | Withdrawn | ComEd | 40 | 20 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1201_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 8/14/2019 |  | 9/15/2019 |  |  | N | No
AE1-202 | Effort Mountain 12.47 kV |  | PA | Monroe | Withdrawn | PPL | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1202_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1202_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 11/4/2019 |  | 9/30/2020 |  |  | N | No
AE1-203 | Iliff 12.47 kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1203_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1203_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/30/2019 |  | 9/30/2019 |  |  | N | No
AE1-204 | Waukegan 13 kV |  | IL | Lake | Withdrawn | ComEd | 4.4 | 4.4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1204_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 11/18/2019 |  | 9/30/2020 | 9/30/2020 |  | N | No
AE1-205 | McLean 345 kV | Blooming Grove Solar Energy Center | IL | Livingston | Engineering and Procurement | ComEd | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1205_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1205_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae1_205_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 12/29/2028 | 12/29/2028 |  | N | No
AE1-206 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Withdrawn | Dominion | 285 | 285 | 171 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1206_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1206_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/12/2023 |  | 12/31/2022 |  |  | N | No
AE1-207 | Mississinewa-Gaston 138 kV | Golden Aster Solar Energy Center | IN | Grant | Suspended | AEP | 160 | 160 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1207_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1207_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1207_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_207_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_207_csa.pdf | Document Posted | N/A | N/A | 3/30/2026 | 9/27/2018 | N/A | N/A | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE1-208 | Delaware-Van Buren 138 kV | Meadow Forge Solar Energy Center | IN | Delaware | Suspended | AEP | 130 | 130 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1208_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1208_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1208_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_208_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_208_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 9/27/2018 | N/A | N/A | 11/15/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AE1-209 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Suspended | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1209_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1209_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1209_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_209_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_209_csa.pdf | Document Posted | N/A | N/A | 2/26/2027 | 9/27/2018 | N/A | N/A | 3/12/2027 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE1-210 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Suspended | AEP | 200 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1210_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1210_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_210_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_210_csa.pdf | Document Posted | N/A | N/A | 2/26/2026 | 9/27/2018 | N/A | N/A | 12/1/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE1-211 | Reynolds 345 kV |  | IN | Jasper | Withdrawn | AEP | 302.4 | 302.4 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/1/2018 |  | 10/31/2020 |  |  | N | No
AE1-212 | Grandview-Clifftop 138 kV | Raleigh Solar Project | WV | Raliegh | Suspended | AEP | 90 | 90 | 53.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1212_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1212_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1212_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_212_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_212_csa.pdf | Document Posted | N/A | N/A | 5/25/2025 | 9/10/2018 | N/A | N/A |  |  |  | 6/25/2025 | 6/25/2025 |  | N | No
AE1-213 | Highland-Lordstown 1 & 2 345 kV |  | OH | Trumbull | Withdrawn | ATSI | 1170 | 1170 | 1025 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 11/1/2023 |  |  | N | No
AE1-214 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 800 | 625 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  | 12/1/2023 |  |  | N | No
AE1-215 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 500 | 395 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/1/2018 |  | 12/1/2023 |  |  | N | No
AE1-216 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 500 | 395 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  | 12/1/2023 |  |  | N | No
AE1-217 | Gaston 138kV |  | IN | Delaware | Withdrawn | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1217_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1217_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE1-218 | Glassboro 12 kV | Glassboro LF Solar | NJ | Gloucester | Withdrawn | AEC | 2 | 2 | 0.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1218_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1218_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1218_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1218_wmpa.pdf | Not Required | N/A | N/A | 12/30/2024 | 9/28/2018 | N/A | N/A | 6/15/2025 | 4/30/2025 |  | 7/31/2024 | 7/31/2024 |  | N | No
AE1-219 | Glassboro 12 kV II | Glassboro RE Solar | NJ | Gloucester | Withdrawn | AEC | 4.4 | 4.4 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1219_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1219_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1219_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1219_wmpa.pdf | Not Required | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 8/17/2020 |  | 7/17/2022 | 7/17/2022 |  | N | No
AE1-220 | Coleen-Clifford 138 kV |  | VA | Nelson | Withdrawn | AEP | 100 | 100 | 66.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 6/17/2019 |  | 6/1/2022 |  |  | N | No
AE1-221 | North Wales 34.5 kV | West Point Cogeneration Facility | PA | Montgomery | In Service | PECO | 38 | 0 | 14 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1221_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_221_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 4/21/2020 | N | No
AE1-222 | Dresden Tazewell Mole Creek |  | IL | Grundy | Withdrawn | ComEd | 2562.7 | 2562.7 | 1270 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1222_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 8/7/2019 |  | 6/1/2022 |  |  | N | No
AE1-223 | Allentown Booster 138 kV |  | NJ | Burlington | Withdrawn | PSEG | 1.86 | 1.86 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 6/3/2019 |  | 11/16/2018 |  |  | N | No
AE1-224 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 9/30/2018 |  | 9/30/2020 |  |  | N | No
AE1-225 | Columbia-Sunbury 69 kV | Sunbury Solar | PA | Snyder | Withdrawn | PPL | 19.8 | 19.8 | 9.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1225_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1225_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1225_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_225_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_225_csa.pdf | Document Posted | N/A | N/A | 6/30/2024 | 9/29/2018 | N/A | N/A |  | 6/24/2025 |  | 6/30/2027 | 6/30/2027 |  | N | No
AE1-226 | Face Rock-Kinzer #13 69 kV | Holtwood Solar | PA | Lancaster | Withdrawn | PPL | 19.8 | 19.8 | 9.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1226_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1226_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1226_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_226_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_226_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2018 | N/A | N/A | 3/1/2026 | 7/17/2025 |  | 4/1/2026 | 4/1/2026 |  | N | No
AE1-227 | South Cumberland 69 kV | Recreation Solar | OH | Guernsey | Suspended | AEP | 49.5 | 49.5 | 30.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1227_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1227_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_227_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_227_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 9/28/2018 | N/A | N/A | 11/15/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AE1-228 | Steward 138 kV |  | IL | Lee | Withdrawn | ComEd | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1228_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 8/12/2019 |  | 6/1/2021 |  |  | N | No
AE1-229 | Deepwater-Upper Pittsgrove 138 kV | Pilesgrove Solar Project | NJ | Salem | Suspended | AEC | 149.3 | 149.3 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1229_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1229_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1229_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_229_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_229_csa.pdf | Document Posted | N/A | N/A | 12/31/2026 | 9/18/2018 | N/A | N/A | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-230 | Shockoe 69 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | 7.2 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1230_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1230_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 9/1/2021 |  | 7/31/2020 |  |  | N | No
AE1-231 | Hughesville 69 kV |  | MD | Charles | Withdrawn | SMECO | 20 | 20 | 9.4 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1231_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1231_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 9/3/2021 |  | 7/31/2020 |  |  | N | No
AE1-232 | Harrowgate-Locks 115 kV |  | VA | Chesterfield | Withdrawn | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2021 |  |  | N | No
AE1-233 | West Dekalb 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 97.5 | 97.5 | 24.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 1/3/2019 |  | 12/31/2021 |  |  | N | No
AE1-234 | Nottingham 230kV Reactor Bypass |  | PA | Chester | Withdrawn | PECO | 578 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Issued |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  |  |  |  | EE | No
AE1-235 | Carson-Clover 500 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 180 | 180 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-236 | Corson-Septa 500 kV |  | NC | Edgecombe | Withdrawn | Dominion | 290 | 290 | 122 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-237 | Andover (Maysville) 69kV I | Welcome Solar II | PA | Crawford | Under Construction | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1237_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1237_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1237_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_237_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_237_csa.pdf | Document Posted | N/A | N/A | 5/29/2026 | 9/29/2018 | N/A | N/A | 6/25/2026 |  |  | 8/29/2026 | 8/29/2026 |  | N | No
AE1-238 | Oceanview Wind 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 816 | 816 | 225 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1238_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1238_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1238_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 8/28/2023 |  | 6/1/2024 |  |  | N | No
AE1-239 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 38.2 | 38.2 | 22.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1239_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 3/28/2019 |  | 12/31/2021 |  |  | N | No
AE1-240 | Carlls Corner-Sherman Avenue 69 kV | Nabb Solar Project | NJ | Cumberland | Withdrawn | AEC | 49.7 | 49.7 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1240_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1240_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1240_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_240_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_240_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2018 | N/A | N/A | 9/6/2027 | 4/23/2025 |  | 10/15/2024 | 10/15/2024 |  | N | No
AE1-241 | Wilmington-Davis Creek |  | IL | Will | Withdrawn | ComEd | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 5/31/2021 |  |  | N | No
AE1-242 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/5/2018 |  | 12/31/2022 |  |  | N | No
AE1-243 | Warren Glen Storage 34.5 kV | Warren Glen Storage | NJ | Warren | Partially in Service - Under Construction | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1243_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1243_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1243_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_243_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_243_csa.pdf | Document Posted | N/A | N/A | 1/14/2025 | 9/29/2018 | N/A | N/A | 4/17/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE1-244 | Gilbert Storage 34.5 kV |  | NJ | Atlantic | Withdrawn | JCPL | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1244_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1244_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 12/19/2019 |  | 9/30/2020 |  |  | N | No
AE1-245 | Haviland 138 kV | Grover Hill Wind Project | OH | Paulding | Under Construction | AEP | 140.3 | 140.3 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1245_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1245_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1245_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_245_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_245_csa.pdf | Document Posted | N/A | N/A | 12/4/2025 | 9/18/2018 | N/A | N/A | 12/8/2025 |  |  | 2/5/2026 | 2/5/2026 |  | N | No
AE1-246 | Barren County-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 85 | 85 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1246_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1246_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1246_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 1/21/2025 |  | 6/1/2022 |  |  | N | No | This project slid to the next queue
AE1-247 | Barren County-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 205 | 205 | 137.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1247_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1247_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 2/11/2020 |  | 6/1/2022 |  |  | N | No
AE1-248 | Bell Avenue 115 kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1248_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1248_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  | 4/22/2021 |  | 9/30/2021 |  |  | N | No | This project slid to the next queue
AE1-249 | Reams 115 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 70 | 70 | 40.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1249_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1249_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/10/2020 |  | 12/31/2021 |  |  | N | No
AE1-250 | Smith Mountain-E. Danville 138 kV | Blue Ridge Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1250_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1250_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1250_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_250_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_250_csa.pdf | Document Posted | N/A | N/A | 11/9/2026 | 8/31/2018 | N/A | N/A | 12/21/2026 |  |  | 1/21/2028 | 1/21/2028 |  | N | No
AE1-251 | Penn-Lees Lick 69 kV |  | KY | Scott | Withdrawn | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  | 3/27/2019 |  | 9/30/2021 |  |  | N | No
AE1-252 | Loretto-Wilton Center |  | IL | Livingston | Withdrawn | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1252_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1252_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  | 9/12/2023 |  | 10/1/2021 |  |  | N | No
AE1-253 | Tidd-Collier 345kV |  | PA | Adams | Withdrawn | APS | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 11/1/2018 |  | 5/31/2020 |  |  | EE | No
AE2-001 | Nittany-Zion 46 kV | Confer Solar I | PA | Centre | Suspended | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2001_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_001_csa.pdf | Document Posted | N/A | N/A | 3/20/2026 | 10/2/2018 | N/A | N/A | 4/3/2026 |  |  | 5/30/2026 | 5/30/2026 |  | N | No
AE2-002 | 64th Street 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 3.8 | 3.6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2018 | N/A | N/A |  | 9/6/2019 |  | 12/31/2019 |  |  | N | No
AE2-003 | Walker Mill Road 13 kV |  | MD | Prince George's | Withdrawn | DPL | 3 | 3 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2003_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2018 | N/A | N/A |  | 9/6/2019 |  | 10/1/2019 |  |  | N | No
AE2-004 | Poolesville 230 kV |  | VA | Surry | Withdrawn | Dominion | 60 | 60 | 40.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2018 | N/A | N/A |  | 11/28/2018 |  | 6/30/2021 |  |  | N | No
AE2-005 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 130 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2005_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_005_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2018 | N/A | N/A | 6/6/2026 |  |  | 7/14/2026 | 7/14/2026 |  | N | No
AE2-006 | Twittys Creek 34.5 kV | Twittys Creek Solar | VA | Charlotte | In Service | Dominion | 13.75 | 0 | 2.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2006_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2006_wmpa.pdf | Not Required | N/A | N/A |  | 10/8/2018 | N/A | N/A | 12/8/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/8/2020 | N | No
AE2-007 | Chesapeake 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 1205.6 | 967.6 | 967.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2007_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2018 | N/A | N/A |  | 12/11/2020 |  | 6/1/2022 |  |  | N | No
AE2-008 | Elderberry-Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 390 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE2-009 | Nottingham-Peach Bottom Tap 230 kV line |  | PA | Adams | Withdrawn | PECO | 11 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ae2009_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2018 | N/A | N/A |  | 3/20/2020 |  | 6/1/2020 |  |  | EE | No
AE2-010 | Paper Tap 69 kV | Jericho | PA | Delaware | In Service | PECO | 29 | 29 | 3 | 29 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2018 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 8/12/2020 | N | No
AE2-011 | Tansboro 12 kV |  | NJ | Camden | Withdrawn | AEC | 3.1 | 3.1 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2018 | N/A | N/A |  | 8/12/2019 |  | 11/30/2020 |  |  | N | No
AE2-012 | Red Oak-South River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 570 | 570 | 540 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2018 | N/A | N/A |  | 3/29/2019 |  | 6/1/2023 |  |  | N | No
AE2-013 | Highland-Lordstown 345 kV |  | OH | Trumbull | Withdrawn | ATSI | 1170 | 1170 | 1025 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2013_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2018 | N/A | N/A |  | 8/27/2019 |  | 11/1/2023 |  |  | N | No
AE2-014 | Sewaren 230 kV |  | NJ | Middlesex | Withdrawn | PSEG | 1200 | 1200 | 1200 |  | Capacity | Merchant Transmission | Wind | DC | 1200 F/NF TIR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ae2014_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2018 | N/A | N/A |  | 1/24/2020 |  | 1/1/2024 |  |  | S | No
AE2-015 | Cookstown-New Lisbon 34.5 kV |  | NJ | Burlington | Withdrawn | JCPL | 5 | 5 | 3.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2015_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/26/2018 | N/A | N/A |  | 8/15/2019 |  | 6/30/2020 |  |  | N | No
AE2-016 | Bustleton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.5 | 3.5 | 2.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/26/2018 | N/A | N/A |  | 5/15/2019 |  | 6/30/2020 |  |  | N | No
AE2-017 | Lexington Park 69 kV | Whitetail VI | MD | St. Mary's | Withdrawn | SMECO | 20 | 20 | 10.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2017_wmpa.pdf | Withdrawn | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2017_wmpa.pdf | Not Required | N/A | N/A |  | 11/28/2018 | N/A | N/A |  | 3/16/2021 |  | 3/31/2023 | 3/31/2023 |  | N | No
AE2-018 | Laurence 13.2 kV |  | NJ | Mercer | Withdrawn | PSEG | 3.5 | 3.5 | 2.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2018_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2018 | N/A | N/A |  | 8/15/2019 |  | 6/30/2020 |  |  | N | No
AE2-019 | New Road 230 kV | New Road Storage | VA | Loudoun | Engineering and Procurement | Dominion | 120 | 120 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2019_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2019_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_019_csa.pdf | Document Posted | N/A | N/A | 2/1/2027 | 12/12/2018 | N/A | N/A | 3/1/2027 |  |  | 9/27/2027 | 9/27/2027 |  | N | No
AE2-020 | Cardiff 230 kV I | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Withdrawn | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2020_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2020_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_020_csa.pdf | Document Posted | N/A | N/A |  | 12/16/2018 | N/A | N/A | 8/31/2029 | 3/3/2025 |  | 8/31/2029 | 8/31/2029 |  | N | No
AE2-021 | Cardiff 230 kV II | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Withdrawn | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2021_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2021_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_021_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_021_csa.pdf | Document Posted | N/A | N/A |  | 12/15/2018 | N/A | N/A | 8/31/2029 | 3/3/2025 |  | 8/31/2029 | 8/31/2029 |  | N | No
AE2-022 | Cardiff 230 kV III | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Withdrawn | AEC | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2022_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_022_csa.pdf | Document Posted | N/A | N/A |  | 12/15/2018 | N/A | N/A | 8/31/2029 | 3/3/2025 |  | 8/31/2029 | 8/31/2029 |  | N | No
AE2-023 | BL England 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 445.2 | 445.2 | 78.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2023_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  | 4/15/2020 |  | 12/1/2024 |  |  | N | No
AE2-024 | Larrabee 230 kV I |  | NJ | Ocean | Withdrawn | JCPL | 882 | 882 | 155.23 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2024_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2024_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/14/2018 | N/A | N/A |  | 9/1/2023 |  | 12/1/2025 |  |  | N | No
AE2-025 | Larrabee 230 kV II |  | NJ | Ocean | Withdrawn | JCPL | 445.2 | 445.2 | 78.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2025_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  | 9/12/2023 |  | 12/1/2026 |  |  | N | No
AE2-026 | Louisa-South Anna 230kV |  | VA | Louisa | Withdrawn | Dominion | 150 | 44.8 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2026_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2018 | N/A | N/A |  | 8/14/2019 |  | 10/30/2020 |  |  | N | No
AE2-027 | Harrowgate-Locks 115kV | Chester Solar | VA | Chesterfield | Suspended | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_027_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2018 | N/A | N/A | 11/1/2026 |  |  | 3/24/2026 | 3/24/2026 |  | N | No
AE2-028 | Broadway 12.47 kV | State Route 57 Solar | NJ | Warren | Withdrawn | JCPL | 0.75 | 0.75 | 0.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2028_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2028_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2028_wmpa.pdf | Not Required | N/A | N/A |  | 12/24/2018 | N/A | N/A |  | 6/7/2023 |  | 6/15/2021 | 6/15/2021 |  | N | No
AE2-029 | Grottoes-Merck 115kV | Sunridge Solar | VA | Rockingham | Under Construction | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2029_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2029_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_029_csa.pdf | Document Posted | N/A | N/A | 12/17/2025 | 12/29/2018 | N/A | N/A | 12/24/2025 |  |  | 3/14/2026 | 3/14/2026 |  | N | No
AE2-030 | Frostburg 138kV |  | MD | Allegany | Withdrawn | APS | 18 | 18 | 7.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2030_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/31/2018 | N/A | N/A |  | 3/7/2023 |  | 8/24/2020 |  |  | N | No
AE2-031 | Carson-Rawlings 500 kV |  | VA | Sussex | Withdrawn | Dominion | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2031_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2019 | N/A | N/A |  | 5/23/2022 |  | 12/31/2021 |  |  | N | No
AE2-032 | Pnode 1369011078-Pnode 51299 |  | PA | Lackawanna | Withdrawn | PPL | 811 | 811 |  |  | Energy | Upgrade Request |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-feas_docs/ae2032_arr-fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2019 | N/A | N/A |  | 9/5/2019 |  |  |  |  | EE | No
AE2-033 | Clubhouse-Sapony 230 kV | Enclave Solar Energy Center | VA | Sussex | Suspended | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_033_csa.pdf | Document Posted | N/A | N/A |  | 1/8/2019 | N/A | N/A | 12/30/2026 |  |  | 2/4/2027 | 2/4/2027 |  | N | No
AE2-034 | Mackeys 230 kV | Albemarle Beach Solar | NC | Washington | Partially in Service - Under Construction | Dominion | 140 | 60 | 42 | 40 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2034_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/16/2019 | N/A | N/A | 10/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-035 | Lena 138 kV | High Point II Solar | IL | Stephenson | In Service | ComEd | 100 | 50 | 21 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2035_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_035_csa.pdf | Document Posted | N/A | N/A | 5/1/2022 | 1/16/2019 | N/A | N/A |  |  |  | 2/28/2024 | 2/28/2024 | 11/30/2023 | N | No
AE2-036 | Masury-Maysville 138 kV |  | PA | Mercer | Withdrawn | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2036_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2019 | N/A | N/A |  | 8/12/2019 |  | 6/1/2019 |  |  | N | No
AE2-037 | Earleys-Everetts 230 kV |  | NC | Bertie | Withdrawn | Dominion | 71.5 | 71.5 | 48.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2037_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2019 | N/A | N/A |  | 4/13/2020 |  | 9/17/2021 |  |  | N | No
AE2-039 | Clayton-Williamstown 69 kV |  | NJ | Gloucester | Withdrawn | AEC | 44 | 44 | 28.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  | 2/20/2019 |  | 6/30/2022 |  |  | N | No
AE2-040 | Sapony 34.5 kV | Shands Energy Center | VA | Sussex | Under Construction | Dominion | 15.7 | 15.7 | 15.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2040_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2040_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2040_wmpa.pdf | Not Required | N/A | N/A | 8/29/2025 | 1/23/2019 | N/A | N/A | 9/23/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-041 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Engineering and Procurement | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2041_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2041_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_041_csa.pdf | Document Posted | N/A | N/A | 2/28/2027 | 1/24/2019 | N/A | N/A | 12/31/2027 |  |  | 3/1/2026 | 3/1/2026 |  | N | No
AE2-042 | Milton 69 kV | Northumberland Solar | PA | Northumberland | In Service | PPL | 65 | 65 | 43.5 | 65 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2042_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_042_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_042_csa.pdf | Document Posted | N/A | N/A | 6/19/2025 | 1/25/2019 | N/A | N/A | 7/14/2025 |  |  | 7/31/2025 | 7/31/2025 | 8/18/2025 | N | No
AE2-043 | Franklinville 138 kV |  | NJ | Gloucester | Withdrawn | AEC | 4 | 4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2019 | N/A | N/A |  | 4/1/2019 |  | 5/1/2020 |  |  | N | No
AE2-044 | Anaconda-Dunbar 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 120 | 40 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2044_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2019 | N/A | N/A |  | 4/23/2024 |  | 12/31/2019 |  |  | N | No
AE2-045 | Olive-Reynolds 345 kV | Bottlebrush Solar | IN | Lake | Engineering and Procurement | AEP | 200 | 200 | 84.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2045_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_045_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_045_csa.pdf | Document Posted | N/A | N/A | 12/31/2027 | 1/29/2019 | N/A | N/A | 1/30/2028 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AE2-046 | Harwood-East Hazelton 69 kV | McAdoo Solar | PA | Schuylkill | Withdrawn | PPL | 50 | 50 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_046_csa.pdf | Document Posted | N/A | N/A | 2/12/2025 | 2/2/2019 | N/A | N/A | 3/12/2025 | 10/21/2024 |  | 3/16/2025 | 3/16/2025 |  | N | No
AE2-047 | Ridgeway-Solite 69 kV | Henry County Solar Facility | VA | Henry | Engineering and Procurement | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2047_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_047_csa.pdf | Document Posted | N/A | N/A | 6/30/2026 | 1/31/2019 | N/A | N/A | 8/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-048 | Muskingum-W. Millersport 345 kV | Eastern Cottontail Solar | OH | Fairfield | Engineering and Procurement | AEP | 220 | 220 | 147.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2048_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_048_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_048_csa.pdf | Document Posted | N/A | N/A | 10/16/2028 | 1/31/2019 | N/A | N/A | 11/1/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AE2-049 | Wilmington-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 115 | 115 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2049_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-050 | Braidwood-E. Frankfort |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2050_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-051 | Carson-Septa 500 kV | Big Pine Solar | VA | Sussex | Engineering and Procurement | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2051_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2051_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_051_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 8/2/2028 | 2/1/2019 | N/A | N/A | 10/1/2028 |  |  | 8/1/2031 | 8/1/2031 |  | N | No
AE2-052 | Disputanta-Poe 115 kV |  | VA | Prince George | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2052_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  | 5/31/2024 |  | 9/15/2021 |  |  | N | No
AE2-053 - moved to TC1 | Kerr Dam-Ridge Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 110 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2019 | N/A | N/A |  | 6/24/2024 |  | 9/15/2021 |  |  | N | No
AE2-054 | Warfordsburg 34 kV | Blairs Valley | PA | Franklin | In Service | APS | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2054_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2054_wmpa.pdf | Not Required | N/A | N/A | 10/21/2024 | 2/2/2019 | N/A | N/A | 12/12/2024 |  |  | 11/30/2024 | 11/30/2024 | 1/30/2025 | N | No
AE2-055 | Shingletown-Boalsburg 46 kV | Windmill Road | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2055_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2055_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2055_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2023 | 8/27/2024 |  | 12/31/2023 | 12/31/2023 |  | N | No
AE2-056 | Howell 12.47 kV Solar I | Willow Brook Road Solar I | NJ | Monmouth | Withdrawn | JCPL | 3 | 3 | 1.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2056_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2056_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2056_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 | 8/8/2022 |  | 5/1/2022 | 5/1/2022 |  | N | No
AE2-057 | Jerseyville 12.47 kV Solar | Willow Brook Road Solar II | NJ | Monmouth | Withdrawn | JCPL | 1 | 1 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2057_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2057_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 | 3/11/2021 |  | 5/1/2022 | 5/1/2022 |  | N | No
AE2-058 | Cherokee-Milton 69 kV |  | PA | Northumberland | Withdrawn | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2058_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2019 | N/A | N/A |  | 9/4/2019 |  | 3/5/2021 |  |  | N | No
AE2-059 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 4 aka East Chilli Solar | PA | Northumberland | In Service | PPL | 20 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_059_csa.pdf | Document Posted | N/A | N/A | 2/2/2024 | 2/7/2019 | N/A | N/A | 8/11/2024 |  |  | 5/31/2024 | 5/31/2024 | 8/20/2024 | N | No
AE2-060 | Mifflintown Bus-Mifflintown Tap 69 kV | Cottontail Solar 5 aka Walker Solar | PA | Juniata | In Service | PPL | 20 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_060_csa.pdf | Document Posted | N/A | N/A | 10/26/2023 | 2/7/2019 | N/A | N/A | 12/8/2023 |  |  | 12/1/2023 | 12/1/2023 | 12/12/2023 | N | No
AE2-061 | Rock Springs 500 kV | Rock Springs Unit #1 and Unit #2 | MD | Cecil | In Service | Essential Power | 394 | 0 | 7 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_061_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/4/2019 | N/A | N/A |  |  |  | 8/23/2019 | 8/23/2019 | 8/12/2019 | N | No
AE2-062 | Romeoville 12 kV | Magid Glove & Safety Mfg. Co | IL | Will | In Service | ComEd | 0.98 | 0.98 | 0 | 0.98 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2062_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2062_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2062_wmpa.pdf | Not Required | N/A | N/A |  | 2/5/2019 | N/A | N/A | 3/31/2021 |  |  | 3/31/2021 | 3/31/2021 | 4/8/2021 | Y | No
AE2-063 | Normantown |  | IL | Will | Withdrawn | ComEd | 0.98 | 0.98 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2063_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2019 | N/A | N/A |  | 1/14/2020 |  | 9/2/2019 |  |  | Y | No
AE2-064 | Beaverbrook 13 kV | Kinsley 2 Beaverbrook Solar | NJ | Gloucester | In Service | PSEG | 5.8 | 2 | 0.85 | 5.13 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_064_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2019 | N/A | N/A | 1/30/2024 |  |  | 8/31/2020 | 8/31/2020 | 12/11/2023 | N | No
AE2-065 | Romeoville 12 kV | Kinsley 2 Deptford Solar | NJ | Gloucester | In Service | PSEG | 6.8 | 1.8 | 0.76 | 1.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_065_csa.pdf | Document Posted | N/A | N/A |  | 2/6/2019 | N/A | N/A | 6/1/2023 |  |  | 8/31/2020 | 8/31/2020 | 9/19/2020 | N | No
AE2-066 | Gloucester 13 kV |  | NJ | Gloucester | Withdrawn | PSEG | 4.5 | 4.5 | 1.89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2019 | N/A | N/A |  | 5/15/2019 |  | 12/10/2019 |  |  | N | No
AE2-067 | N. Meshoppen 34 kV |  | PA | Wyoming | Withdrawn | PENELEC | 20 | 20 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2067_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2019 | N/A | N/A |  | 9/4/2019 |  | 1/1/2021 |  |  | N | No
AE2-068 | Second Street12 kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2019 | N/A | N/A |  | 4/30/2019 |  | 6/1/2020 |  |  | N | No
AE2-069 | Burlington 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2019 | N/A | N/A |  | 4/10/2019 |  | 6/1/2020 |  |  | N | No
AE2-070 | White Rock 34 kV |  | MD | Howard | Withdrawn | BGE | 4 | 4 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2070_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-071 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | In Service | EKPC | 35 | 35 | 21 | 35 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2071_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_071_csa.pdf | Document Posted | N/A | N/A | 4/1/2024 | 2/19/2019 | N/A | N/A | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 | 6/7/2024 | N | No
AE2-072 | East Leipsic-Richland 138 kV | Powell Creek Solar | OH | Putnam | In Service | AEP | 150 | 150 | 90 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2072_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_072_csa.pdf | Document Posted | N/A | N/A | 1/23/2025 | 2/15/2019 | N/A | N/A | 3/17/2025 |  |  | 6/2/2025 | 6/2/2025 | 4/30/2025 | N | No
AE2-073 | Centerburg 138kV |  | OH | Licking | Withdrawn | AEP | 200 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2073_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2019 | N/A | N/A |  | 10/2/2024 |  | 11/1/2021 |  |  | N | No
AE2-074 | Potter 46 kV | Potter Solar | PA | Potter | Engineering and Procurement | APS | 35 | 35 | 15.11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2074_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2074_wmpa.pdf | Not Required | N/A | N/A | 5/31/2026 | 2/20/2019 | N/A | N/A | 6/17/2026 |  |  | 7/31/2026 | 7/31/2026 |  | N | No
AE2-075 | Second Street 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.4 | 4.4 | 2.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2019 | N/A | N/A |  | 4/30/2019 |  | 6/1/2020 |  |  | N | No
AE2-076 | Southampton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2019 | N/A | N/A |  | 4/10/2019 |  | 6/1/2020 |  |  | N | No
AE2-077 | Pierpoint-Freeport |  | IL | Winnebago | Withdrawn | ComEd | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2077_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2019 | N/A | N/A |  | 9/3/2019 |  | 12/31/2021 |  |  | N | No
AE2-078 | Poolesville 34.5 kV | Mantura | VA | Surry | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2078_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2078_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2078_wmpa.pdf | Not Required | N/A | N/A |  | 2/21/2019 | N/A | N/A |  | 6/6/2022 |  | 6/1/2022 | 6/1/2022 |  | N | No
AE2-079 | Poolesville 34.5 kV | Mantura II | VA | Surry | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2079_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2079_wmpa.pdf | Not Required | N/A | N/A |  | 2/21/2019 | N/A | N/A |  | 4/22/2022 |  | 6/1/2022 | 6/1/2022 |  | N | No
AE2-080 | Poolesville 34.5 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2080_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2019 | N/A | N/A |  | 4/28/2020 |  | 6/18/2021 |  |  | N | No
AE2-081 | Howell 12.47 kV Solar II | Casino Drive Solar | NJ | Monmouth | Withdrawn | JCPL | 3.2 | 3.2 | 1.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2081_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2081_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 | 8/8/2022 |  | 5/1/2022 | 5/1/2022 |  | N | No
AE2-082 | Englishtown-Wyckoff 34.5 kV Solar |  | NJ | Monmouth | Withdrawn | JCPL | 7 | 7 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2082_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2019 | N/A | N/A |  | 7/13/2021 |  | 9/30/2019 |  |  | N | No
AE2-083 | Forrester Solar 34.5 kV |  | NJ | Mercer | Withdrawn | JCPL | 1.63 | 1.625 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 3/5/2019 |  | 3/2/2020 |  |  | N | No
AE2-084 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 3 | PA | Montour | Suspended | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2084_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2084_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_084_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_084_csa.pdf | Document Posted | N/A | N/A | 10/1/2025 | 2/3/2019 | N/A | N/A | 10/1/2025 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AE2-085 | Southampton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 5.04 | 5.04 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2085_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-086 | Reeder Road Solar 12.47 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 4/3/2019 |  | 3/2/2020 |  |  | N | No
AE2-087 | Carlls Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.54 | 4.54 | 1.47 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2087_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 8/22/2019 |  | 3/2/2020 |  |  | N | No
AE2-088 | Clayton 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 2.53 | 2.53 | 0.735 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2088_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 8/22/2019 |  | 3/2/2020 |  |  | N | No
AE2-089 | Pennville-Adams 138 kV | Skycrest Solar Energy Center | IN | Jay | Engineering and Procurement | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2089_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_089_csa.pdf | Document Posted | N/A | N/A | 4/15/2026 | 2/22/2019 | N/A | N/A | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-090 | Randolph-Hodgin 138 kV |  | IN | Randolph | Withdrawn | AEP | 144 | 144 | 86.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 10/15/2020 |  | 12/31/2022 |  |  | N | No
AE2-091 | Newport 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 35 | 35 | 23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2091_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2019 | N/A | N/A |  | 3/31/2020 |  | 6/30/2022 |  |  | N | No
AE2-092 | Kidds Store-Sherwood 115 kV | Woodridge Solar | VA | Albemarle | Engineering and Procurement | Dominion | 138 | 138 | 82.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_092_csa.pdf | Document Posted | N/A | N/A | 11/12/2026 | 2/26/2019 | N/A | N/A | 12/1/2026 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AE2-093 | Easton-Steele 138 kV | Crockett Solar Project | MD | Talbot | Withdrawn | DPL | 44 | 44 | 16.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_093_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2019 | N/A | N/A | 3/31/2026 | 6/25/2025 |  | 3/31/2026 | 3/31/2026 |  | N | No
AE2-094 | Carson-Rogers Road 500 kV | Cassius Blue Solar | VA | Sussex | Engineering and Procurement | Dominion | 300 | 300 | 207.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2094_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2094_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_094_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2028 | 2/26/2019 | N/A | N/A | 8/1/2028 |  |  | 8/1/2031 | 8/1/2031 |  | N | No
AE2-095 | Hopewell 26 kV |  | NJ | Mercer | Withdrawn | PSEG | 2.15 | 2.145 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-096 | East Flemington-Frenchtown Solar 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2.75 | 2.75 | 1.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2096_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 9/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-097 | Levittown 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2097_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-098 | Belvidere Solar 12 kV |  | NJ | Warren | Withdrawn | JCPL | 1.88 | 1.875 | 0.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/3/2019 |  | 3/2/2020 |  |  | N | No
AE2-099 | Burlington 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2.77 | 2.77 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-100 | Carlstadt 13.2 kV |  | NJ | Bergen | Withdrawn | PSEG | 2.3 | 2.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2100_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-101 | Nortonville 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2101_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/21/2019 |  | 3/2/2020 |  |  | N | No
AE2-102 | Columbus 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 5.04 | 5.04 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-103 | Cookstown-Van Hiseville Solar 34.5 kV |  | NJ | Ocean | Withdrawn | JCPL | 3 | 3 | 1.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 5/23/2019 |  | 3/2/2020 |  |  | N | No
AE2-104 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Suspended | Dominion | 49 | 49 | 18.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2104_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2104_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_104_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_104_csa.pdf | Document Posted | N/A | N/A | 5/7/2026 | 3/2/2019 | N/A | N/A | 5/29/2026 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AE2-105 | Kittatinny-Newton Solar 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 3.5 | 3.5 | 1.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2105_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 9/6/2019 |  | 3/2/2020 |  |  | N | No
AE2-106 | Carlls Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.92 | 4.915 | 1.63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2106_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/22/2019 |  | 3/2/2020 |  |  | N | No
AE2-107 - moved to TC1 | Haumesser Road 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 6/21/2024 |  | 12/31/2022 |  |  | N | No
AE2-108 | Kings Dominion DP 115 kV |  | VA | Hanover | Withdrawn | Dominion | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2108_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/8/2020 |  | 3/31/2020 |  |  | N | No
AE2-109 | Kings Dominion DP 115 kV |  | VA | Hanover | Withdrawn | Dominion | 7 | 7 | 2.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2109_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/8/2020 |  | 3/31/2021 |  |  | N | No
AE2-110 | Columbia-West Bloomsburg 69 kV | Montour 1 | PA | Columbia | Suspended | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2110_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_110_csa.pdf | Document Posted | N/A | N/A | 11/30/2027 | 3/3/2019 | N/A | N/A | 12/6/2027 |  |  | 2/28/2025 | 2/28/2025 |  | N | No
AE2-111 | Beavertown Tap-Beavertown Weaving Tap 69kV | Thomas Ridge Solar | PA | Snyder | Withdrawn | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2111_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2111_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_111_csa.pdf | Document Posted | N/A | N/A |  | 3/1/2019 | N/A | N/A |  | 1/18/2023 |  | 12/31/2024 | 12/31/2024 |  | N | No
AE2-112 | Carville 138 kV II | Concho Solar I | MD | Queen Anne's | Suspended | DPL | 66 | 17 | 6.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ ae2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_112_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2019 | N/A | N/A | 6/3/2027 |  |  | 6/3/2024 | 6/3/2024 |  | N | No
AE2-113 | Farmers Valley-Ridgeway 115 kV | Ridgeway Solar | PA | McKean | Under Construction | PENELEC | 120 | 120 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2113_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2113_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_113_csa.pdf | Document Posted | N/A | N/A | 6/8/2026 | 3/1/2019 | N/A | N/A | 6/22/2026 |  |  | 8/10/2026 | 8/10/2026 |  | N | No
AE2-114 | Midland 23 kV I | BE-PINE 1 Cain Road | PA | Beaver | In Service | DL | 17.1 | 17.1 | 10.26 | 17.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2114_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2114_wmpa.pdf | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 | 11/20/2023 | N | No
AE2-115 | Midland 23 kV II | BE-PINE 2 Dam Road | PA | Beaver | In Service | DL | 17.1 | 17.1 | 10.26 | 17.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2115_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2115_wmpa.pdf | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 | 11/5/2023 | N | No
AE2-116 | Midland 23 kV III |  | PA | Adams | Withdrawn | DL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2116_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 12/3/2019 |  | 9/1/2021 |  |  | N | No
AE2-117 | ABW Tap-Alexandria 46 kV | HU-Pauls | PA | Huntingdon | Suspended | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2117_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2117_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_117_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_117_csa.pdf | Document Posted | N/A | N/A | 3/15/2027 | 3/1/2019 | N/A | N/A | 3/16/2027 |  |  | 3/31/2027 | 3/31/2027 |  | N | No
AE2-118 | ABW Tap-Williamsburg 46 kV | HU-Logging | PA | Huntingdon | Suspended | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2118_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2118_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_118_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_118_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 8/31/2024 | 8/31/2024 |  | N | No
AE2-119 | Shawville-Phillipsburg 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2119_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 12/16/2019 |  | 9/1/2021 |  |  | N | No
AE2-120 | Graymont-Zion 46 kV | CE-Shady Farm LLC | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2120_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2120_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_120_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_120_csa.pdf | Document Posted | N/A | N/A |  | 3/1/2019 | N/A | N/A |  | 6/7/2023 |  | 12/30/2025 | 12/30/2025 |  | N | No
AE2-121 | Milesburg-Tanney Junction 46 kV | CE-JACKSONVILLE | PA | Centre | Withdrawn | APS | 10.64 | 10.64 | 6.384 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2121_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2121_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_121_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_121_csa.pdf | Document Posted | N/A | N/A |  | 3/1/2019 | N/A | N/A | 4/30/2024 | 7/22/2024 |  | 12/31/2023 | 12/31/2023 |  | N | No
AE2-122 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 158.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2122_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2122_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/8/2025 |  | 12/31/2025 |  |  | N | No
AE2-123 - moved to TC1 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 163.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2123_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 6/24/2024 |  | 12/31/2027 |  |  | N | No
AE2-124 - moved to TC1 | Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 148.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2124_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 6/24/2024 |  | 12/31/2029 |  |  | N | No
AE2-125 | Stahlstown-Ligonier 25 kV | Stahlstown-Ligonier 25 kV | PA | Westmoreland | In Service | APS | 13.8 | 13.8 | 8.28 | 13.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2125_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2125_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2125_wmpa.pdf | Not Required | N/A | N/A | 10/15/2024 | 3/2/2019 | N/A | N/A | 11/21/2024 |  |  | 11/15/2024 | 11/15/2024 | 12/4/2024 | N | No
AE2-126 | Dubois-Curwensville 34.5 kV | CL-Viaduct | PA | Clearfield | In Service | PENELEC | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_126_csa.pdf | Document Posted | N/A | N/A | 9/1/2022 | 3/1/2019 | N/A | N/A | 3/1/2023 |  |  | 5/31/2023 | 5/31/2023 | 3/23/2023 | N | No
AE2-127 | Milesburg-Moshannon 230 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/12/2019 |  | 11/1/2021 |  |  | N | No
AE2-128 | Milesburg-Moshannon 230 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/12/2019 |  | 10/1/2021 |  |  | N | No
AE2-129 | Philipsburg-Clarence 34.5 kV | Philipsburg-Clarence 34.5 kV | PA | Clearfield | In Service | PENELEC | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2129_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2129_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2129_wmpa.pdf | Not Required | N/A | N/A | 11/1/2022 | 3/1/2019 | N/A | N/A | 3/1/2023 |  |  | 11/1/2022 | 11/1/2022 | 1/28/2023 | N | No
AE2-130 - moved to TC1 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 800 | 480 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2130_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 6/21/2024 |  | 12/1/2022 |  |  | N | No
AE2-131 | Philipsburg-Karthaus 34.5 | UN-Kylertown | PA | Westmoreland | Under Construction | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2131_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_131_csa.pdf | Document Posted | N/A | N/A | 11/30/2026 | 2/28/2019 | N/A | N/A | 1/11/2027 |  |  | 3/1/2027 | 3/1/2027 |  | N | No
AE2-132 | Remington CT 230 kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 190 | 0 | 17.7 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2132_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_132_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 5/31/2020 |  | 10/17/2019 | N | No
AE2-133 | Penns Tap-Richfield Tie 69 kV | Penn Solar (Cottontail 6) | PA | Snyder | In Service | PPL | 20 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_133_csa.pdf | Document Posted | N/A | N/A | 1/26/2024 | 3/6/2019 | N/A | N/A | 3/22/2024 |  |  | 12/1/2023 | 12/1/2023 | 5/8/2024 | N | No
AE2-134 | Locust Grove-Paytes 115 kV | Pine Glade Solar | VA | Orange | In Service | Dominion | 62.5 | 0 | 16.5 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_134_csa.pdf | Document Posted | N/A | N/A | 5/30/2024 | 3/6/2019 | N/A | N/A | 7/19/2024 |  |  | 7/15/2024 | 7/15/2024 | 9/13/2024 | N | No
AE2-135 | Frackville-Siegfried 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 500 | 500 | 250 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2019 | N/A | N/A |  | 4/5/2019 |  | 12/15/2022 |  |  | N | No
AE2-136 | Muskingum River-W. Millersport 345 kV | Appalachian Cottontail Solar | OH | Fairfield | Engineering and Procurement | AEP | 114 | 114 | 83.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2136_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2136_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_136_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/16/2028 | 3/6/2019 | N/A | N/A | 11/1/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AE2-137 | Yukon-Robbins 138 kV II | Allegheny Energy Center LLC | PA | Westmoreland | Withdrawn | APS | 625 | 84 | 87 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2137_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_137_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_137_csa.pdf | Document Posted | N/A | N/A |  | 3/7/2019 | N/A | N/A |  | 10/17/2023 |  | 9/1/2027 | 9/1/2027 |  | N | No
AE2-138 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 260 | 260 | 20.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2138_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2019 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AE2-139 | East Towanda-Grover 230 kV | Bradford Solar | PA | McKean | Engineering and Procurement | PENELEC | 100.5 | 100.5 | 60.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2139_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2139_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_139_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/1/2027 | 3/9/2019 | N/A | N/A | 11/16/2027 |  |  | 12/15/2027 | 12/15/2027 |  | N | No
AE2-140 | Axton-Danville 138 kV | Axton Solar | VA | Henry | Suspended | AEP | 201.1 | 201.1 | 120.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2140_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2140_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_140_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_140_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 3/11/2019 | N/A | N/A | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-141 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2141_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 9/4/2019 |  | 6/1/2021 |  |  | N | No
AE2-142 | Glen Gardner-Washington Solar 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 9/6/2019 |  | 3/2/2020 |  |  | N | No
AE2-143 | Yardville 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.91 | 3.905 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2143_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-144 | Deptford 13.2 kV |  | NJ | Gloucester | Withdrawn | PSEG | 4.03 | 4.03 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2144_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-145 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 2.52 | 2.52 | 0.84 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 4/3/2019 |  | 3/2/2020 |  |  | N | No
AE2-146 | Gold 115 kV |  | PA | Potter | Withdrawn | PENELEC | 183 | 183 | 75.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 9/4/2019 |  | 3/5/2021 |  |  | N | No
AE2-147 - moved to TC1 | Swamp 230 kV |  | NC | Perquimans | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2147_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  | 1/22/2025 |  | 12/1/2022 |  |  | N | No
AE2-148 | Beatty-Greene 345 kV | Fox Squirrel Solar | OH | Madison | Partially in Service - Under Construction | AEP | 577 | 577 | 397.3 | 577 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2148_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2148_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_148_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_148_csa.pdf | Document Posted | N/A | N/A |  | 2/22/2019 | N/A | N/A | 11/14/2023 |  |  | 11/1/2023 | 11/1/2023 | 11/1/2024 | N | No
AE2-149 | Biers Run-Bixby 345 kV |  | OH | Pickaway | Withdrawn | AEP | 400 | 400 | 291.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2149_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 2/14/2023 |  | 6/1/2022 |  |  | N | No
AE2-150 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Withdrawn | Dominion | 75 | 0 | 0 |  | Energy | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2150_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 8/31/2022 |  | 6/1/2022 |  |  | N | No
AE2-151 | Earleys 34.5kV | Kruger Energy Hertford | NC | Hertford | Withdrawn | Dominion | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2151_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2151_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2151_wmpa.pdf | Not Required | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 1/8/2021 |  | 12/8/2020 | 12/8/2020 |  | N | No
AE2-152 | Loretto-Wilton 345 kV & Braidwood-Davis Creek 345 kV | Heritage Prairie Solar | IL | Kankakee | Engineering and Procurement | ComEd | 300 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2152_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2152_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_152_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 3/4/2019 | N/A | N/A | 8/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AE2-153 | Braidwood-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2153_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 9/12/2023 |  | 3/31/2021 |  |  | N | No
AE2-154 | Meadow Lake 345 kV (MLV VIII) |  | IN | White | Withdrawn | AEP | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2154_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 6/29/2023 |  | 10/31/2021 |  |  | N | No
AE2-155 | Old Church 34.5 kV | Hanover Solar | VA | Hanover | In Service | Dominion | 25 | 5 | 3.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2155_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_155_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/15/2019 | N/A | N/A | 8/20/2020 |  |  | 12/1/2020 | 12/1/2020 | 9/23/2020 | N | No
AE2-156 - moved to TC1 | Yadkin 115 kV | Yadkins Energy Center | VA | City of Chesapeake | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2156_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-157 | Wakefield–Waverly 115 kV |  | VA | Sussex | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2157_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 3/9/2020 |  | 12/31/2021 |  |  | N | No
AE2-158 | Kanawha River 138 kV |  | WV | Fayette | Withdrawn | AEP | 48 |  |  |  | Energy | Merchant Transmission | Hydro | AC | 48 NFTIR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 4/1/2019 |  | 10/1/2021 |  |  | S | No
AE2-159 | Kanawha River 138 kV |  | WV | Fayette | Withdrawn | AEP | 48 | 48 | 0 |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2159_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 11/21/2019 |  | 10/1/2021 |  |  | N | No
AE2-160 | Kanawha River 138 kV | Hawks Nest Hydro | WV | Fayette | Engineering and Procurement | AEP | 105.159 | 51 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2160_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2160_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_160_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 2/29/2028 | 3/15/2019 | N/A | N/A | 3/13/2028 |  |  | 9/30/2028 | 9/30/2028 |  | N | No
AE2-161 | Morris Park-Washington 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 4/2/2019 |  | 3/2/2020 |  |  | N | No
AE2-162 | Lumberton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.78 | 3.78 | 1.26 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 5/6/2019 |  | 3/2/2020 |  |  | N | No
AE2-163 | West Caldwell 13.2 kV |  | NJ | Essex | Withdrawn | PSEG | 1 | 1 | 0.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2163_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-164 | Saddle Brook 13.2 kV |  | NJ | Bergen | Withdrawn | PSEG | 1.4 | 1.4 | 0.588 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2164_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-165 | Cedar Grove 13.2 kV |  | NJ | Passaic | Withdrawn | PSEG | 2.6 | 2.6 | 1.092 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2165_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-166 | Stockton 138 kV | Rocky Ford Solar Energy Center | VA | Henry | Suspended | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2166_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2166_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_166_csa.pdf | Document Posted | N/A | N/A | 3/30/2026 | 3/16/2019 | N/A | N/A | 5/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-167 | Belmont-Harrison 500 kV |  | WV | Doddridge | Withdrawn | APS | 1335 | 1335 | 1315 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2167_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 9/6/2019 |  | 7/1/2023 |  |  | N | No
AE2-168 | Belmont-Harrison 500 kV II |  | WV | Doddridge | Withdrawn | APS | 665 | 665 | 660 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2168_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 9/6/2019 |  | 7/1/2023 |  |  | N | No
AE2-169 | Delaware-Van Buren 138 kV | Meadow Forge Solar Energy Center | IN | Delaware | Suspended | AEP | 163 | 33 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2169_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2169_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_169_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_169_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 3/16/2019 | N/A | N/A | 11/15/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AE2-170 | Gaston-Desoto 138 kV |  | IN | Delaware | Withdrawn | AEP | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE2-171 | Makahoy 138 kV |  | IN | Madison | Withdrawn | AEP | 150 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2171_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 3/24/2021 |  | 12/31/2022 |  |  | N | No
AE2-172 | Mississinewa-Gaston 138 kV | Golden Aster Solar Energy Center | IN | Grant | Suspended | AEP | 200 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2172_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2172_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_172_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_172_csa.pdf | Document Posted | N/A | N/A | 3/30/2026 | 3/16/2019 | N/A | N/A | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE2-173 - moved to TC1 | McLean 345 kV | Blooming Grove Solar Energy Center | IL | McLean | Active | ComEd | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-174 | Fremont Center-Tiffin Center 138 kV circuit #1 |  | OH | Seneca | Withdrawn | AEP | 198 | 198 | 34.85 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2174_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 2/13/2023 |  | 10/31/2021 |  |  | N | No
AE2-175 | Jackson-Long Pond 69 kV | Swiftwater Solar | PA | Monroe | Partially in Service - Under Construction | PPL | 80 | 80 | 48 | 13.82 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2175_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2175_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_175_csa.pdf | Document Posted | N/A | N/A | 2/14/2025 | 3/19/2019 | N/A | N/A | 4/18/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-176 | Groton 138 kV Solar | Wheatsborough Solar | OH | Erie | In Service | ATSI | 125 | 125 | 75 | 125 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2176_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2176_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_176_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_176_csa.pdf | Document Posted | N/A | N/A | 5/16/2025 | 3/19/2019 | N/A | N/A | 7/28/2025 |  |  | 4/30/2025 | 4/30/2025 | 8/12/2025 | N | No
AE2-177 | Squabb SVC 230 kV |  | PA | Elk | Withdrawn | APS | 165 | 165 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/8/2019 |  | 10/31/2021 |  |  | N | No
AE2-178 | Wayne 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/8/2019 |  | 10/31/2021 |  |  | N | No
AE2-179 | Lick-Waverly 115kV |  | OH | Pike | Withdrawn | OVEC | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/1/2019 |  | 10/31/2021 |  |  | N | No
AE2-180 | Beatty-London 138 kV III |  | OH | Madison | Withdrawn | ATSI | 79 | 79 | 47.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2180_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 9/3/2019 |  | 10/31/2021 |  |  | N | No
AE2-181 | Snyder 69kV | Montpelier Solar | OH | Williams | Under Construction | ATSI | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2181_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2181_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_181_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_181_csa.pdf | Document Posted | N/A | N/A | 9/30/2025 | 3/18/2019 | N/A | N/A | 10/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-182 | Briery-Clover 230 kV | Seven Bridges Solar | VA | Mecklenburg | Withdrawn | Dominion | 122 | 17 | 11.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2182_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2182_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_182_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_182_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2019 | N/A | N/A | 11/1/2025 | 6/24/2024 |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-183 | Rogers Road 500 kV | Greensville Power Station | VA | Greensville | In Service | Dominion | 1756 | 75 | 0 | 75 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2183_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_183_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 8/15/2023 | 8/15/2023 | 8/30/2023 | N | No
AE2-184 | Warren County 500 kV | Warren County Power Station | VA | Warren | In Service | Dominion | 1499 | 15 | 0 | 15 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_184_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 4/30/2021 | 4/30/2021 | 8/11/2020 | N | No
AE2-185 - moved to TC1 | Gladys DP-Stonemill Switching Station 69 kV | Pigeon Run Solar and Storage | VA | Campbell | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2185_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-186 | Brandy DP-Remington 115 kV |  | VA | Fauquier | Withdrawn | Dominion | 60 | 60 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/29/2019 |  | 9/1/2020 |  |  | N | No
AE2-187 - moved to TC1 | Shockoe DP-Chatham 69 kV | Shockoe Solar Farm | VA | Pittsylvania | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2187_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-188 | Mitchell DP-Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2188_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2020 |  |  | N | No
AE2-189 | Housenville 138 kV |  | PA | Butler | Withdrawn | APS | 42 | 42 | 17.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2189_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 8/12/2019 |  | 12/31/2022 |  |  | N | No
AE2-190 | Elk Run D.P.-Gainesville 230 kV | Alameda Solar | VA | Fauquier | Withdrawn | Dominion | 70 | 70 | 27.02 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2190_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2190_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_190_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_190_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2019 | N/A | N/A | 12/1/2026 | 3/18/2025 |  | 12/31/2027 | 12/31/2027 |  | N | No
AE2-191 | Saxonburg 138 kV |  | PA | Butler | Withdrawn | APS | 52 | 52 | 21.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2191_Imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2191_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 3/2/2022 |  | 12/31/2022 |  |  | N | No
AE2-192 | Orrtanna 115 kV |  | PA | Adams | Withdrawn | ME | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2192_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2192_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2192_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 1/28/2022 |  | 12/31/2022 |  |  | N | No
AE2-193 | Shenango 138 kV |  | PA | Mercer | Withdrawn | ATSI | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2193_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2193_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 3/29/2022 |  | 12/31/2022 |  |  | N | No
AE2-194 | Congress-Toronto 138 kV | Kensington Solar | OH | Columbiana | Suspended | ATSI | 145 | 145 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2194_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2194_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_194_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_194_csa.pdf | Document Posted | N/A | N/A | 12/2/2025 | 3/18/2019 | N/A | N/A | 12/2/2025 |  |  | 1/2/2026 | 1/2/2026 |  | N | No
AE2-195 | East Canton-Robertsville 69 kV | Robertsville PV I | OH | Stark | Withdrawn | AEP | 19.7 | 19.7 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2195_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2195_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2195_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_195_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_195_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 11/14/2024 |  | 1/14/2026 | 1/14/2026 |  | N | No
AE2-196 | Mt. Airy-Wythe 138 kV |  | VA | Wythe | Withdrawn | AEP | 94.6 | 94.6 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2196_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2022 |  |  | N | No
AE2-197 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  | 10/1/2020 |  |  | Y | No
AE2-198 |  |  | NJ | Mercer | Withdrawn | PSEG | 2.75 | 2.75 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  |  |  |  | Y | No
AE2-199 |  |  | NJ | Camden | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  |  |  |  | Y | No
AE2-200 |  |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  |  |  |  | Y | No
AE2-201 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2019 |  |  |  |  | Y | No
AE2-202 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 3.88 | 3.88 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2019 |  |  |  |  | Y | No
AE2-203 |  |  | NJ | Warren | Withdrawn | JCPL | 4.38 | 4.38 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2019 |  |  |  |  | Y | No
AE2-204 | Bolivar 34.5 kV | Bolivar Solar | OH | Stark | Withdrawn | AEP | 19.3 | 19.3 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2204_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2204_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2204_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2204_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2204_wmpa.pdf | Not Required | N/A | N/A | 10/30/2026 | 3/19/2019 | N/A | N/A | 11/30/2026 | 6/23/2025 |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-205 | Cumberland 230 kV |  | NJ | Cumberland | Withdrawn | AEC | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2205_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2020 |  | 6/30/2022 |  |  | N | No
AE2-206 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | In Service | Dayton | 99 | 99 | 41.58 | 99 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2206_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_206_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_206_csa.pdf | Document Posted | N/A | N/A | 10/28/2024 | 3/20/2019 | N/A | N/A | 12/19/2024 |  |  | 1/31/2025 | 1/31/2025 | 2/5/2025 | N | No
AE2-207 | Heartsease DP-Mayo Dunbar 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2207_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 8/21/2019 |  | 12/31/2020 |  |  | N | No
AE2-208 | Chavies-Bonnyman 69 kV |  | KY | Perry | Withdrawn | AEP | 80 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2208_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2208_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2021 |  |  | N | No
AE2-209 | Airey 69 kV |  | MD | Dorchester | Withdrawn | DPL | 56 | 56 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2209_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2209_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 3/31/2020 |  | 12/31/2021 |  |  | N | No
AE2-210 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 90 | 90 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2210_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AE2-211 | Jackson-Three Mile Island 230 kV | Dover Solar | PA | York | Suspended | ME | 55 | 55 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2211_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2211_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2211_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_211_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_211_csa.pdf | Document Posted | N/A | N/A |  | 3/20/2019 | N/A | N/A | 9/14/2026 |  |  | 10/14/2026 | 10/14/2026 |  | N | No
AE2-212 | Harrowgate 34 kV | Harrowgate 1 | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2212_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2212_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2212_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2212_wmpa.pdf | Not Required | N/A | N/A |  | 3/20/2019 | N/A | N/A | 7/30/2027 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AE2-213 | Thorofare 13.2 kV |  | NJ | Gloucester | Withdrawn | PSEG | 3.15 | 3.145 | 1.1025 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2213_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2213_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-214 | Cole 345 kV | Pleasant Prairie Solar Energy Center | OH | Franklin | Engineering and Procurement | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2214_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2214_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2214_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_214_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_214_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 3/23/2019 | N/A | N/A | 6/1/2026 |  |  | 3/30/2027 | 3/30/2027 |  | N | No
AE2-215 | Blain 115 kV |  | PA | Perry | Withdrawn | PENELEC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2215_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2215_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2021 |  |  | N | No
AE2-216 | Hardin Switch 345 kV | Hardin Energy Center – Storage II | OH | Hardin | Engineering and Procurement | AEP | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2216_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2216_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2216_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_216_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_216_csa.pdf | Document Posted | N/A | N/A | 10/15/2026 | 3/21/2019 | N/A | N/A | 11/15/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-217 | East Springfield-London 138 kV | Sloopy Solar Energy Center | OH | Clark | Engineering and Procurement | ATSI | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2217_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2217_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2217_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_217_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_217_csa.pdf | Document Posted | N/A | N/A | 6/1/2028 | 3/21/2019 | N/A | N/A | 6/15/2028 |  |  | 9/30/2028 | 9/30/2028 |  | N | No
AE2-218 | Eldean 138 kV | Eldean Solar | OH | Miami | Withdrawn | Dayton | 178 | 178 | 106 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2218_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2218_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2218_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_218_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_218_csa.pdf | Document Posted | N/A | N/A | 3/9/2026 | 3/21/2019 | N/A | N/A | 3/31/2026 | 6/3/2025 |  | 12/31/2024 | 12/31/2024 |  | N | No
AE2-219 | Bluff Point-Randolph 138 kV | Riverstart Solar Park V | IN | Randolph | Suspended | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2219_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2219_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2219_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_219_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_219_csa.pdf | Document Posted | N/A | N/A | 3/31/2026 | 3/21/2019 | N/A | N/A | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE2-220 | Losantville 345 kV | Riverstart Solar Park II | IN | Randolph | Engineering and Procurement | AEP | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2220_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2220_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2220_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_220_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/15/2027 | 3/21/2019 | N/A | N/A | 6/15/2027 |  |  | 11/15/2027 | 11/15/2027 |  | N | No
AE2-221 | Clinton-Stuart 345 kV | Yellow Wood Solar Energy Center | OH | Clinton | Engineering and Procurement | Dayton | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2221_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2221_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_221_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_221_csa.pdf | Document Posted | N/A | N/A | 3/25/2026 | 3/21/2019 | N/A | N/A | 8/24/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AE2-222 | Higbee 69 kV |  | NJ | Atlantic | Withdrawn | AEC | 300 | 300 | 84.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2222_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2222_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 11/9/2022 |  | 6/1/2023 |  |  | N | No
AE2-223 - moved to TC1 | McLean 345 kV | Bright Stalk Generating Facility | IL | McLean | Active | ComEd | 350 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2223_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2223_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-224 | Bear Rock-Johnstown 230 kV | CPV Maple Hill Solar | PA | Cambria | In Service | PENELEC | 100 | 100 | 60 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2224_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2224_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2224_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_224_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_224_csa.pdf | Document Posted | N/A | N/A | 3/24/2023 | 3/23/2019 | N/A | N/A | 10/12/2023 |  |  | 11/17/2023 | 11/17/2023 | 11/28/2023 | N | No
AE2-225 | Suffolk 34 kV | Hosier Road Solar | VA | City of Suffolk | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2225_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2225_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2225_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2225_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 4/23/2021 |  | 11/30/2022 |  |  | N | No
AE2-226 | Millville-Old Chapel 138 kV | Rippon | WV | Jefferson | Engineering and Procurement | APS | 99 | 99 | 59.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2226_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2226_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2226_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_226_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_226_csa.pdf | Document Posted | N/A | N/A | 10/15/2026 | 3/22/2019 | N/A | N/A | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-227 | Iron Bridge 34 kV | Bradley Ridge Solar | VA | Chesterfield | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2227_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2227_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2227_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 7/11/2024 |  | 3/30/2025 | 3/30/2025 |  | N | No
AE2-228 | Tyler 34 kv | Bradley BridgeSolar | VA | Chesterfield | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2228_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2228_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2228_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2228_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 7/11/2024 |  | 3/30/2025 | 3/30/2025 |  | N | No
AE2-229 | Suffolk 34 kV | Hosier Road Solar II | VA | City of Suffolk | Withdrawn | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2229_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2229_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2229_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2229_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 4/23/2021 |  | 11/30/2022 |  |  | N | No
AE2-230 | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 70 | 70 | 42 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2230_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2230_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2230_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_230_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_230_csa.pdf | Document Posted | N/A | N/A | 10/20/2024 | 3/24/2019 | N/A | N/A | 11/17/2024 |  |  | 7/1/2024 | 7/1/2024 | 12/27/2024 | N | No
AE2-231 | St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2231_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2231_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2231_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 3/28/2025 |  | 12/1/2022 |  |  | N | No
AE2-232 | Oyster Creek 230 kV II |  | NJ | Atlantic | Withdrawn | JCPL | 400 | 400 | 112.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2232_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2232_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 3/26/2020 |  | 6/1/2023 |  |  | N | No
AE2-233 | Carson-Rogers Rd 500 kV |  | VA | Accomack | Withdrawn | Dominion | 94 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2233_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 10/2/2019 |  | 6/1/2022 |  |  | N | No
AE2-234 | Liberty Center-Buckeye Tap 69 kV | Maple Solar | IN | Huntington | Engineering and Procurement | AEP | 35 | 35 | 24.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2234_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2234_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2234_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_234_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_234_csa.pdf | Document Posted | N/A | N/A | 5/15/2027 | 3/22/2019 | N/A | N/A | 5/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AE2-235 | Murphysville-Plumville 69 kV |  | KY | Mason | Withdrawn | EKPC | 60 | 60 | 41.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2235_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 8/13/2019 |  | 7/31/2021 |  |  | N | No
AE2-236 | Columbia-Northeast 138 kV | Dover Solar Facility | IN | Whitley | Suspended | AEP | 55 | 55 | 38.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2236_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2236_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2236_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_236_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_236_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 7/29/2026 | 7/29/2026 |  | N | No
AE2-237 | Vernon-Sugar Loaf #2 115 kV |  | NJ | Sussex | Withdrawn | JCPL | 107 | 107 | 21.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2237_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2237_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 7/27/2022 |  | 3/1/2022 |  |  | N | No
AE2-238 | Reybold 12 kV |  | DE | New Castle | Withdrawn | DPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2238_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  | 9/17/2019 |  | 5/14/2021 |  |  | N | No
AE2-239 | Tanners Creek-East Bend & Miami Fort-Terminal 345 kV |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 4/1/2019 |  | 3/1/2023 |  |  | S | No
AE2-240 | Olive-Reynolds 1 & 2 345 kV |  | IN | Starke | Withdrawn | AEP | 3170 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ae2240_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 2/19/2021 |  | 6/1/2019 |  |  | S | No
AE2-241 | Bloomsburg-Columbia 69 kV | Mountain Holly | PA | Columbia | Suspended | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2241_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2241_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2241_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_241_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_241_csa.pdf | Document Posted | N/A | N/A | 2/1/2027 | 3/23/2019 | N/A | N/A | 2/9/2027 |  |  | 6/1/2027 | 6/1/2027 |  | N | No
AE2-242 | Bowmanns Mill-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 85 | 85 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2242_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 9/24/2019 |  | 3/5/2021 |  |  | N | No
AE2-243 | East Carbondale 12.47 kV I |  | PA | Wayne | Withdrawn | PPL | 16.5 | 16.5 | 2.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2243_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 9/6/2019 |  | 3/31/2021 |  |  | N | No
AE2-244 | East Carbondale 12.47 kV II |  | PA | Wayne | Withdrawn | PPL | 16.5 | 16.5 | 2.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2244_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 9/6/2019 |  | 3/31/2021 |  |  | N | No
AE2-245 | Stockton 34.5 kV |  | VA | Henry | Withdrawn | AEP | 20 | 0 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2245_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2245_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  | 10/23/2020 |  | 12/30/2020 |  |  | N | No
AE2-246 | Gretna DP 69 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 0 | 13.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2246_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  | 9/10/2019 |  | 12/15/2020 |  |  | N | No
AE2-247 | Myrtle-Windsor 115 kV | Knoxville Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 71 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2247_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2247_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_247_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_247_csa.pdf | Document Posted | N/A | N/A | 6/15/2027 | 3/25/2019 | N/A | N/A | 6/22/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
AE2-248 | Fillmore-Thompson Farm 46 kV | CE-FILMORE | PA | Centre | Suspended | APS | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2248_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2248_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2248_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2248_wmpa.pdf | Not Required | N/A | N/A |  | 3/25/2019 | N/A | N/A | 10/29/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AE2-249 | Bedford North-Pennsylvania Hollow 23 kV | BE-ASTOR | PA | Bedford | Withdrawn | PENELEC | 16.6 | 16.6 | 9.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2249_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2249_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_249_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_249_csa.pdf | Document Posted | N/A | N/A | 6/30/2025 | 3/25/2019 | N/A | N/A | 6/30/2025 | 6/22/2024 |  | 7/1/2021 | 7/1/2021 |  | N | No
AE2-250 - moved to TC1 | Purdy Sw.-Reams 115 kV |  | VA | Greensville | Withdrawn | Dominion | 82.5 | 82.5 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2250_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2250_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  | 1/22/2025 |  | 9/30/2021 |  |  | N | No
AE2-251 | Cardiff 230 kV |  | NJ | Monmouth | Withdrawn | AEC | 1200 | 1200 | 337.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2251_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2251_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  | 9/12/2023 |  | 6/1/2024 |  |  | N | No
AE2-252 | Gardners-Mountain 115 kV |  | PA | Cumberland | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2252_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2252_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  | 3/25/2020 |  | 11/9/2021 |  |  | N | No
AE2-253 | Hickory-Moyock 230 kV | Oak Trail Solar | NC | Currituck | In Service | Dominion | 100 | 50 | 34.5 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2253_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2253_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2253_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_253_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_253_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2019 | N/A | N/A | 6/9/2023 |  |  | 7/15/2023 | 7/15/2023 | 7/5/2023 | N | No
AE2-254 | Garrard County-Tommy-Gooch 69 kV | Turkey Creek Solar | KY | Garrard | In Service | EKPC | 50 | 50 | 30 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2254_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2254_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2254_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_254_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_254_csa.pdf | Document Posted | N/A | N/A | 9/22/2020 | 3/26/2019 | N/A | N/A | 9/23/2022 |  |  | 12/31/2022 |  | 10/28/2022 | N | No
AE2-255 | Molecreek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 400 | 100 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2255_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2255_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2255_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_255_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_255_csa.pdf | Document Posted | N/A | N/A | 9/21/2026 | 3/26/2019 | N/A | N/A | 10/1/2026 |  |  | 1/18/2027 | 1/18/2027 |  | N | No
AE2-256 | Copperstone-North Lebanon 230 kV | Lebanon Solar | PA | Lebanon | Withdrawn | ME | 70 | 70 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2256_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2256_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2256_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_256_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_256_csa.pdf | Document Posted | N/A | N/A | 6/1/2026 | 3/28/2019 | N/A | N/A | 7/1/2026 | 7/1/2025 |  | 8/1/2026 | 8/1/2026 |  | N | No
AE2-257 | Cedar Neck 69 kV |  | DE | Sussex | Withdrawn | DPL | 120 | 120 | 33 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2257_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2257_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2019 | N/A | N/A |  | 8/1/2022 |  | 6/1/2022 |  |  | N | No
AE2-258 | Chase City 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 49.9 | 0 | 14.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2258_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2258_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2019 | N/A | N/A |  | 9/12/2023 |  | 6/1/2020 |  |  | N | No
AE2-259 | Curdsville-Willis Mtn 115 kV | Blue Rock Solar | VA | Buckingham | Engineering and Procurement | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2259_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2259_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2259_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_259_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/14/2026 | 3/28/2019 | N/A | N/A | 10/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-260 | Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 200 | 82.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2260_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2260_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 9/12/2023 |  | 6/30/2020 |  |  | N | No
AE2-261 - moved to TC1 | Kincaid-Pana 345 kV | Black Diamond Solar | IL | Christian | Active | ComEd | 299 | 299 | 179.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2261_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2261_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-262 | Moshannon-Milesburg 230 kV | MPG Solar | PA | Centre | Engineering and Procurement | APS | 83.6 | 83.6 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2262_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2262_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2262_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_262_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_262_csa.pdf | Document Posted | N/A | N/A | 5/31/2028 | 3/29/2019 | N/A | N/A | 6/7/2028 |  |  | 7/31/2028 | 7/31/2028 |  | N | No
AE2-263 | Moshannon-Milesburg 230 kV II | MPG Solar | PA | Centre | Engineering and Procurement | APS | 161.98 | 78.38 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2263_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2263_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2263_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_263_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_263_csa.pdf | Document Posted | N/A | N/A | 5/31/2028 | 3/29/2019 | N/A | N/A | 6/7/2028 |  |  | 7/31/2028 | 7/31/2028 |  | N | No
AE2-264 | Altoona-Raystown 230 kV |  | PA | Blair | Withdrawn | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2264_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2264_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2264_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 6/6/2023 |  | 6/30/2022 |  |  | N | No
AE2-265 | Corey 138 kV |  | MI | St. Joseph | Withdrawn | AEP | 150 | 150 | 47.78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 4/1/2019 |  | 9/1/2021 |  |  | N | No
AE2-266 | Corey 138kV |  | MI | St. Joseph | Withdrawn | AEP | 198.9 | 198.9 | 64.19 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 4/1/2019 |  | 9/1/2021 |  |  | N | No
AE2-267 | Woodsdale 345 kV | Woodsdale Renewable Energy Center | OH | Butler | Engineering and Procurement | DEOK | 49 | 49 | 28.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2267_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2267_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2267_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_267_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_267_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 3/29/2019 | N/A | N/A | 5/1/2026 |  |  | 6/1/2026 | 6/1/2026 |  | N | No
AE2-268 | Harmony Village 34 kV |  | VA | Middlesex | Withdrawn | Dominion | 15 | 15 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2268_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2268_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 9/12/2019 |  | 12/31/2021 |  |  | N | No
AE2-269 | Fayetteville 138 kV |  | PA | Franklin | Withdrawn | APS | 22 | 22 | 9.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2269_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 8/12/2019 |  | 12/31/2021 |  |  | N | No
AE2-270 - moved to TC1 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2270_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2270_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 6/24/2024 |  | 9/29/2021 |  |  | N | No
AE2-271 | Montour 230 kV | Montour Solar One | PA | Montour | Withdrawn | PPL | 101.6 | 101.6 | 61 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2271_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2271_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2271_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_271_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_271_csa.pdf | Document Posted | N/A | N/A | 7/31/2026 | 3/14/2019 | N/A | N/A | 8/31/2026 | 7/25/2025 |  | 9/26/2026 | 9/26/2026 |  | N | No
AE2-272 | Woodstown 12 kV | Pilesgrove Solar | NJ | Salem | In Service | AEC | 19.9 |  | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2272_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2272_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_272_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 | 9/17/2019 | N | No
AE2-273 | Siegfried-Hauto 69KV | PA Solar Park | PA | Carbon | In Service | PPL | 20 | 0 | 0.4 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2273_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2273_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_273_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_273_csa.pdf | Document Posted | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AE2-274 | Siegfried-Hauto 69 kV | PA Solar Park | PA | Carbon | In Service | PPL | 20 | 0 | 0.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2274_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2274_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_274_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_274_csa.pdf | Document Posted | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AE2-275 - moved to TC1 | J.K. Smith-Fawkes 138 kV |  | KY | Madison | Withdrawn | EKPC | 90 | 90 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2275_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2275_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AE2-276 | Sullivan 345kV | Trade Post Energy Storage | IN | Sullivan | Engineering and Procurement | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2276_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2276_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2276_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_276_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2028 | 3/28/2019 | N/A | N/A | 10/30/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AE2-277 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 38.2 | 38.2 | 16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2277_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2277_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2277_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 3/30/2022 |  |  |  |  | N | No
AE2-278 | Urbana 138 kV | Urbana Solar | OH | Champaign | Withdrawn | Dayton | 150.7 | 150.7 | 90.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2278_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2278_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2278_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_278_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_278_csa.pdf | Document Posted | N/A | N/A |  | 3/26/2019 | N/A | N/A |  | 1/20/2022 |  | 6/30/2023 | 6/30/2023 |  | N | No
AE2-279 | Oxford 115 kV |  | PA | Adams | Withdrawn | ME | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2279_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  | 9/6/2019 |  | 10/1/2021 |  |  | N | No
AE2-280 | Claytor Lake-Edgemont 138 kV |  | VA | Montgomery | Withdrawn | AEP | 126.65 | 126.65 | 75.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2280_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2280_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 3/15/2024 |  | 12/31/2022 |  |  | N | No
AE2-281 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 400 | 50 | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2281_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2281_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2281_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_281_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_281_csa.pdf | Document Posted | N/A | N/A | 5/8/2026 | 3/29/2019 | N/A | N/A | 6/1/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
AE2-282 | East Fayette 138 kV | Arche Energy Project | OH | Fulton | In Service | ATSI | 67 | 67 | 43.9 | 67 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2282_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2282_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2282_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_282_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_282_csa.pdf | Document Posted | N/A | N/A | 9/7/2023 | 3/31/2019 | N/A | N/A | 10/11/2023 |  |  | 12/31/2023 | 12/31/2023 | 1/17/2024 | N | No
AE2-283 - moved to TC1 | Gladys-Stone Mill 69 kV | Gladys Solar | VA | Campbell | Active | Dominion | 53 | 53 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2283_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2283_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE2-284 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Withdrawn | AEP | 225 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2284_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE2-285 | Maysville 69 kV | MC Solar I | PA | Mercer | Engineering and Procurement | ATSI | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2285_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2285_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2285_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_285_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_285_csa.pdf | Document Posted | N/A | N/A | 11/20/2026 | 3/30/2019 | N/A | N/A | 12/3/2026 |  |  | 1/29/2027 | 1/29/2027 |  | N | No
AE2-286 | Airey 12 kV |  | MD | Dorchester | Withdrawn | DPL | 19.5 | 19.5 | 7.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2286_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 8/1/2019 |  | 12/31/2019 |  |  | N | No
AE2-287 | Brunswick 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2287_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 8/22/2019 |  | 6/30/2022 |  |  | N | No
AE2-288 | Sunbury 500 kV |  | PA | Snyder | Withdrawn | PPL | 1233 | 90 | 206 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2288_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2288_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/7/2020 |  | 5/1/2023 |  |  | N | No
AE2-289 | Frostburg 138 kV |  | MD | Allegany | Pending | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2289_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2289_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2289_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_289_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_289_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-290 | Nottingham 138 kV | Nottingham Solar | OH | Harrison | Suspended | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2290_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2290_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2290_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_290_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_290_csa.pdf | Document Posted | N/A | N/A | 9/15/2023 | 3/29/2019 | N/A | N/A | 9/15/2023 |  |  | 12/15/2023 | 12/15/2023 |  | N | No
AE2-291 - moved to TC1 | Grit DP-Perth 115 kV | Hillandale Solar | VA | Pittsylvania | Active | Dominion | 102 | 102 | 61.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2291_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2291_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE2-292 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Campbell | Withdrawn | Dominion | 127 | 127 | 76.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2292_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2292_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 6/24/2024 |  | 4/1/2021 |  |  | N | No
AE2-293 | Dauphin-Pine Grove 69kV |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/4/2019 |  | 6/1/2020 |  |  | N | No
AE2-294 | Dauphin-Pine Grove 69 kV |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/4/2019 |  | 3/31/2020 |  |  | N | No
AE2-295 | Eldred 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 174.8 | 174.8 | 25.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2295_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2295_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 7/7/2022 |  | 5/31/2022 |  |  | N | No
AE2-296 | Hutchings West 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 104 | 104 | 104 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2296_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 8/20/2019 |  | 5/1/2020 |  |  | N | No
AE2-297 | Madison-Tanners Creek 138 kV | Bellflower Solar 1 | IN | Henry | In Service | AEP | 152.5 | 152.5 | 91.5 | 152.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2297_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2297_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2297_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_297_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_297_csa.pdf | Document Posted | N/A | N/A | 11/18/2022 | 3/22/2019 | N/A | N/A | 12/2/2023 |  |  | 12/31/2024 | 12/31/2024 | 12/6/2022 | N | No
AE2-298 | Cavett Switch - West Van Wert 69 kV | White Trillium | OH | Van Wert | Engineering and Procurement | AEP | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2298_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2298_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2298_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_298_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_298_csa.pdf | Document Posted | N/A | N/A | 11/30/2026 | 3/22/2019 | N/A | N/A | 11/30/2026 |  |  | 12/30/2026 | 12/30/2026 |  | N | No
AE2-299 | Erie East 230 kV | Erie East Energy | PA | Erie | Suspended | PENELEC | 160 | 160 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2299_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2299_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2299_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_299_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_299_csa.pdf | Document Posted | N/A | N/A | 1/1/2026 | 3/22/2019 | N/A | N/A | 3/30/2026 |  |  | 6/1/2026 | 6/1/2026 |  | N | No
AE2-300 |  |  | OH | Licking | Withdrawn | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/1/2019 |  | 9/22/2022 |  |  | N | No
AE2-301 | Crisfield 25 kV |  | MD | Somerset | Withdrawn | DPL | 5.5 | 5.5 | 2.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2301_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2301_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 3/26/2020 |  | 9/22/2021 |  |  | N | No
AE2-302 | East Beaver-Lick 138 kV |  | OH | Jackson | Withdrawn | AEP | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2302_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2302_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2302_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 10/2/2023 |  | 7/1/2022 |  |  | N | No
AE2-303 | Honda Marysville Tap | Cardinal Solar | OH | Union | Withdrawn | Dayton | 49.9 | 49.9 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2303_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2303_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2303_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_303_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_303_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 3/7/2024 |  | 12/1/2023 | 12/1/2023 |  | N | No
AE2-304 | South Hertford 34 kV | South Hertford Solar | NC | Perquimans | Withdrawn | Dominion | 5 | 5 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2304_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2304_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2304_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2304_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 10/26/2020 |  | 6/1/2022 | 6/1/2022 |  | N | No
AE2-305 | Givens-Mechanicsburg 138 kV | Hillclimber Solar | OH | Champaign | Engineering and Procurement | Dayton | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2305_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2305_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2305_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_305_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2029 | 3/29/2019 | N/A | N/A | 8/30/2029 |  |  | 9/30/2029 | 9/30/2029 |  | N | No
AE2-306 | Gunn Road 345 kV | Scioto Solar | OH | Hardin | Under Construction | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2306_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2306_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2306_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_306_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_306_csa.pdf | Document Posted | N/A | N/A | 4/1/2026 | 3/30/2019 | N/A | N/A | 5/1/2026 |  |  | 12/28/2026 | 12/28/2026 |  | N | No
AE2-307 | Braidwood-East Frankfort |  | IL | Will | Withdrawn | ComEd | 225 | 225 | 165 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2307_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-308 - moved to TC1 | Three Forks-Dale 138 kV | Madison Solar 1 | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2308_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2308_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_308_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A | 1/31/2026 |  |  | 5/31/2021 |  |  | N | No
AE2-309 | Carlos Junction-Lonaconing 34.5 kV | Jade Meadow | MD | Allegany | In Service | APS | 19.84 | 19.84 | 11.9 | 19.84 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2309_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2309_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2309_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2309_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2019 | N/A | N/A | 1/16/2024 |  |  | 3/22/2024 | 3/22/2024 | 3/26/2024 | N | No
AE2-310 | Wilmington-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 85 | 85 | 67 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2310_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-311 | Carson-Septa 500 kV |  | VA | Sussex | Withdrawn | Dominion | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 6/19/2019 |  | 12/31/2021 |  |  | N | No
AE2-312 | Rocky Road |  | IL | Kane | Withdrawn | ComEd | 411.7 | 7 | 7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/4/2019 |  | 6/1/2019 |  |  | N | No
AE2-313 - moved to TC1 | Carson-Rawlings 500 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 314 | 314 | 188.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2313_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2313_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 1/22/2025 |  | 9/15/2022 |  |  | N | No
AE2-314 | Cardiff 230 kV |  | NJ | Atlantic | Withdrawn | AEC | 72 | 72 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2314_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 12/16/2019 |  | 6/30/2022 |  |  | N | No
AE2-315 | Yankee Tap 69 kV | Yankee 1-7 | OH | Montgomery | In Service | Dayton | 124 | 23.5 | 23.5 | 23.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2315_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2315_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2315_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_315_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_315_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 11/30/2022 | 11/30/2022 | 4/19/2022 | N | No
AE2-316 | Brookville-Squab Hollow 138 kV | Squab Solar | PA | Jefferson | Under Construction | PENELEC | 90 | 90 | 41.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2316_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2316_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2316_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_316_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_316_csa.pdf | Document Posted | N/A | N/A | 2/28/2026 | 3/30/2019 | N/A | N/A | 5/10/2026 |  |  | 7/10/2026 | 7/10/2026 |  | N | No
AE2-317 | Pequest River 115 kV |  | NJ | Atlantic | Withdrawn | JCPL | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2317_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2317_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/7/2020 |  | 6/30/2022 |  |  | N | No
AE2-318 | Ford-Cedarville 138 kV | Clermont County Solar Project | OH | Clermont | Suspended | DEOK | 100 | 100 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2318_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2318_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2318_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_318_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_318_csa.pdf | Document Posted | N/A | N/A | 9/1/2024 | 3/31/2019 | N/A | N/A | 10/1/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-319 | Atlanta 69kV I | Mustang County Solar Project | OH | Pickaway | Withdrawn | Dayton | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2319_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2319_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2319_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_319_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_319_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 2/9/2024 |  | 10/1/2028 | 10/1/2028 |  | N | No
AE2-320 | Atlanta 69 kV II |  | OH | Pickaway | Withdrawn | Dayton | 50 | 50 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2320_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2320_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 2/9/2024 |  | 12/1/2022 |  |  | N | No | This project slid to the next queue
AE2-321 - moved to TC1 | Belvidere-Marengo 138 kV | McHenry County Solar Project | IL | McHenry | Active | ComEd | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2321_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2321_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-322 | Mark Center 69 kV | Mark Center Solar Project | OH | Defiance | Under Construction | AEP | 109.9 | 60 | 40.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2322_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2322_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2322_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_322_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_322_csa.pdf | Document Posted | N/A | N/A | 3/31/2026 | 3/30/2019 | N/A | N/A | 4/30/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AE2-323 | Twin Branch-Guardian 138 kV | Elkhart County Solar Project | IN | Elkhart | Under Construction | AEP | 100 | 100 | 67.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2323_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2323_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2323_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_323_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_323_csa.pdf | Document Posted | N/A | N/A | 10/22/2025 | 3/30/2019 | N/A | N/A | 10/27/2025 |  |  | 5/1/2026 | 5/1/2026 |  | N | No
AE2-324 | Galion-Roberts South II 138 kV |  | OH | Marion | Withdrawn | ATSI | 120.3 | 20.3 | 20.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2324_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2324_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 6/24/2022 |  | 12/1/2022 |  |  | N | No
AE2-325 - moved to TC1 | Valley 138 kV | Southwest Michigan Energy Center | MI | Van Buren | Active | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2325_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2325_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-326 | Jacksons Ferry 138 kV | Wythe County Solar Project | VA | Wythe | Engineering and Procurement | AEP | 127.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2326_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2326_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2326_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_326_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A | 6/1/2027 |  |  | 6/15/2027 | 6/15/2027 |  | N | No
AE2-327 | Biers Run-Circleville 138 kV |  | OH | Pickaway | Withdrawn | AEP | 162.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2327_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 3/6/2020 |  | 12/1/2021 |  |  | N | No
AE2-328 | Briery DP-Clover 230 kV |  | VA | Accomack | Withdrawn | Dominion | 100 | 100 | 68.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2328_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 9/23/2019 |  | 4/1/2022 |  |  | N | No
AE2-329 | Cedarville-Ford 138 kV |  | OH | Clermont | Withdrawn | DEOK | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2022 |  |  | N | No
AE2-330 | Belvidere-Marengo |  | IL | McHenry | Withdrawn | ComEd | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2021 |  |  | N | No
AE2-331 | Mark Center 69 kV |  | OH | Defiance | Withdrawn | AEP | 34.8 | 34.8 | 139.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2021 |  |  | N | No
AE2-332 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2021 |  |  | N | No
AE2-333 | Bedington 138 kV | Bedington Energy Facility | MD | Frederick | Suspended | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2333_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2333_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2333_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_333_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_333_csa.pdf | Document Posted | N/A | N/A | 6/15/2025 | 4/1/2019 | N/A | N/A | 6/15/2025 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AE2-334 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Withdrawn | AEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2334_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2334_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2334_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_334_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_334_csa.pdf | Document Posted | N/A | N/A |  | 4/1/2019 | N/A | N/A | 12/31/2026 | 3/18/2025 |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-335 | Gloucester Solar II |  | NJ | Gloucester | Withdrawn | AEC | 60 | 60 | 41.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2335_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2335_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 3/31/2020 |  | 6/30/2022 |  |  | N | No
AE2-336 | St. Barnabas 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 4.6 | 4.6 | 1.932 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2336_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 9/6/2019 |  | 12/31/2020 |  |  | N | No
AE2-337 | St. Barnabas 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2.4 | 2.4 | 1.008 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2337_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 9/6/2019 |  | 12/31/2020 |  |  | N | No
AE2-338 | Avon 138 kV |  | KY | Fayette | Withdrawn | EKPC | 20.3 | 20.3 | 81.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/22/2019 |  | 12/1/2022 |  |  | N | No
AE2-339 | Avon 138 kV | Grassy Plains | KY | Fayette | Engineering and Procurement | EKPC | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2339_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2339_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2339_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ae2_339_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/1/2027 | 3/31/2019 | N/A | N/A | 5/17/2027 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AE2-340 | Sandwich-Plano |  | IL | Kendall | Withdrawn | ComEd | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2022 |  |  | N | No
AE2-341 - moved to TC1 | Sandwich-Plano 138 kV | Plano Skies Energy Center | IL | Kendall | Active | ComEd | 150 | 150 | 100.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2341_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2341_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-342 | Woodstock 69 kV | Woodstock Solar | OH | Champaign | Engineering and Procurement | Dayton | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2342_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2342_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2342_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_342_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_342_csa.pdf | Document Posted | N/A | N/A | 4/24/2026 | 3/31/2019 | N/A | N/A | 4/27/2026 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
AE2-343 | Andover (Maysville) 69 kV II | Welcome Solar III, LLC | PA | Crawford | Under Construction | ATSI | 17.9 | 17.9 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2343_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2343_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2343_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_343_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_343_csa.pdf | Document Posted | N/A | N/A | 5/29/2026 | 4/1/2019 | N/A | N/A | 7/30/2026 |  |  | 6/5/2024 | 6/5/2024 | 8/29/2026 | N | No
AE2-344 | Edinboro South-Venango Junction 115 kV | Shorebird Solar | PA | Crawford | Suspended | PENELEC | 116.5 | 116.5 | 69.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2344_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2344_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2344_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_344_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_344_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 3/14/2019 | N/A | N/A | 10/31/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-345 | Hunterstown-Texas Eastern Tap 115 kV | Granite Hill Solar | PA | Adams | Suspended | ME | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2345_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2345_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2345_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_345_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_345_csa.pdf | Document Posted | N/A | N/A | 1/2/2026 | 3/13/2019 | N/A | N/A | 1/12/2026 |  |  | 2/1/2026 | 2/1/2026 |  | N | No
AE2-346 | Ahoskie 34.5 kV | Colice Hall Solar | NC | Hertford | In Service | Dominion | 17 | 12 | 8.4 | 12 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2346_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2346_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_346_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_346_csa.pdf | Document Posted | N/A | N/A | 6/29/2023 | 3/29/2019 | N/A | N/A | 3/1/2023 |  |  | 9/15/2023 | 9/15/2023 | 7/6/2023 | N | No
AF1-001 | Thayerville 34.5 kV | Sand Flat Road Solar Project | MD | Garrett | Withdrawn | APS | 13.75 | 13.75 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1001_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1001_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2019 | N/A | N/A |  | 8/6/2024 |  | 2/28/2023 | 2/28/2023 |  | N | No
AF1-002 | Berwick 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 5 | 5 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  | 3/4/2020 |  | 3/31/2020 |  |  | N | No
AF1-003 | Hawkins Gate-Billingsley Rd 69 kV | Charles County Solar II | MD | Charles | Suspended | SMECO | 20 | 20 | 9.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1003_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1003_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1003_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1003_wmpa.pdf | Not Required | N/A | N/A | 4/1/2027 | 4/2/2019 | N/A | N/A | 4/1/2027 |  |  | 9/30/2027 | 9/30/2027 |  | N | No
AF1-004 | Hwy 228-Bennsville 69 kV |  | MD | Charles | Withdrawn | SMECO | 16.82 | 16.82 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1004_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  | 10/8/2020 |  | 4/30/2021 |  |  | N | No
AF1-005 | Grayton-Ripley 69 kV | Charles County Solar I | MD | Charles | Suspended | SMECO | 20 | 20 | 9.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1005_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1005_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1005_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1005_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 9/30/2028 | 9/30/2028 |  | N | No
AF1-006 | Fairview East 34.5 kV | Erie Solar | PA | Erie | In Service | PENELEC | 20 | 20 | 12.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1006_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1006_wmpa.pdf | Not Required | N/A | N/A | 11/25/2024 | 4/2/2019 | N/A | N/A | 1/9/2025 |  |  | 12/31/2024 | 12/31/2024 | 1/29/2025 | N | No
AF1-007 | Indian River 230 kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Suspended | DPL | 255.1 | 7.3 | 1.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1007_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1007_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_007_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_007_csa.pdf | Document Posted | N/A | N/A | 8/1/2029 | 4/1/2019 | N/A | N/A | 10/29/2029 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-008 | CPV NJ Solar |  | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 5/6/2019 |  | 12/31/2019 |  |  | N | No
AF1-009 | Dixon-McGirr |  | IL | Lee | Withdrawn | ComEd | 125 | 25 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1009_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 10/8/2020 |  | 12/31/2021 |  |  | N | No
AF1-010 | Schauff Road |  | IL | Lee | Withdrawn | ComEd | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1010_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 3/9/2020 |  | 12/31/2021 |  |  | N | No
AF1-011 | Schauff Road |  | IL | Lee | Withdrawn | ComEd | 255 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1011_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 9/29/2020 |  | 9/30/2021 |  |  | N | No
AF1-012 | Electric Junc-Nelson |  | IL | Lee | Withdrawn | ComEd | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1012_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 10/13/2023 |  | 9/30/2022 |  |  | N | No
AF1-013 | Dixon-McGirr |  | IL | Lee | Withdrawn | ComEd | 25 | 25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1013_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 3/9/2020 |  | 12/1/2020 |  |  | N | No
AF1-014 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 149.9 | 19.9 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_014_csa.pdf | Document Posted | N/A | N/A |  | 4/4/2019 | N/A | N/A | 6/6/2026 |  |  | 7/14/2026 | 7/14/2026 |  | N | No
AF1-015 | Easton-Steele 138 kV II | Crockett Solar Project | MD | Talbot | Withdrawn | DPL | 59 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_015_csa.pdf | Document Posted | N/A | N/A |  | 4/3/2019 | N/A | N/A | 3/31/2026 | 6/25/2025 |  | 3/31/2026 | 3/31/2026 |  | N | No
AF1-016 | Suffolk 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 71 | 20 | 7.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1016_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  | 2/20/2020 |  | 11/30/2021 |  |  | N | No
AF1-017 | Myrtle-Windsor 115 kV | Knoxville Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 91 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1017_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_017_csa.pdf | Document Posted | N/A | N/A | 6/15/2027 | 4/3/2019 | N/A | N/A | 6/22/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
AF1-018 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Engineering and Procurement | Dominion | 80 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1018_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1018_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_018_csa.pdf | Document Posted | N/A | N/A |  | 4/3/2019 | N/A | N/A | 12/31/2027 |  |  | 3/1/2026 | 3/1/2026 |  | N | No
AF1-019 | Branchville-Holiday Lakes 34.5 kV | Viridity Energy Solutions Montague Storage | NJ | Sussex | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1019_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1019_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_019_csa.pdf | Document Posted | N/A | N/A | 10/18/2024 | 4/6/2019 | N/A | N/A | 10/22/2024 |  |  | 1/31/2025 | 1/31/2025 | 12/20/2024 | N | No
AF1-020 5006187 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 300 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 4/1/2019 | 1/1/2025 | 1/1/2030 |  | 12/11/2019 |  |  |  |  | PP | No
AF1-021 | Bethelboro-Connellsville #1 25 kV | Dunbar Solar | PA | Fayette | In Service | APS | 14 | 14 | 8.4 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1021_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1021_wmpa.pdf | Not Required | N/A | N/A | 8/20/2024 | 4/17/2019 | N/A | N/A | 10/8/2024 |  |  | 11/29/2024 | 11/29/2024 | 10/18/2024 | N | No
AF1-022 | Lake Lynn-Uniontown 25 kV | Gans Solar Farm | PA | Fayette | In Service | APS | 14 | 14 | 8.4 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1022_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1022_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1022_wmpa.pdf | Not Required | N/A | N/A | 10/21/2024 | 4/17/2019 | N/A | N/A | 10/31/2024 |  |  | 11/29/2024 | 11/29/2024 | 12/3/2024 | N | No
AF1-023 | Atlantic-Red Bank 34 kV II | Hamilton Road Solar | NJ | Monmouth | In Service | JCPL | 20 | 0 | 8.4 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1023_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_023_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/18/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 8/6/2020 | N | No
AF1-024 | Freeland Municipal Authority |  | PA | Adams | Withdrawn | PPL | 19.9 | 19.9 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2019 | N/A | N/A |  | 5/21/2019 |  | 12/31/2021 |  |  | N | No
AF1-025 | Cedar Creek-Silver Run 230 kV |  | N/A | N/A | Withdrawn | DPL |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/af1025_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2019 | N/A | N/A |  | 9/21/2020 |  | 5/3/2019 |  |  | EE | No
AF1-026 | Edge Road Battery Storage (CIRs) | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/21/2020 | N | No
AF1-027 | Plumsted 537 Energy Storage (CIRs) | Plumsted Energy Storage Facility | NJ | Ocean | In Service | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/21/2020 | N | No
AF1-028 | Endless Caverns 115 kV | Prospect Power | VA | Rockingham | Under Construction | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1028_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_028_csa.pdf | Document Posted | N/A | N/A | 12/1/2025 | 5/13/2019 | N/A | N/A | 1/2/2026 |  |  | 2/1/2026 | 2/1/2026 |  | N | No
AF1-029 | Cavett Switch - West Van Wert 69 kV |  | OH | Van Wert | Withdrawn | AEP | 75 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1029_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2019 | N/A | N/A |  | 8/21/2023 |  | 12/31/2021 |  |  | N | No
AF1-030 - moved to TC1 | Sandwich-Plano 138 kV | Plano Skies Energy Center | IL | Kendall | Active | ComEd | 250 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1030_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-031 | Kings Dominion DP 115 kV |  | VA | Caroline | Withdrawn | Dominion | 93.5 | 93.5 | 60.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1031_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/17/2019 | N/A | N/A |  | 5/26/2022 |  | 12/31/2022 |  |  | N | No
AF1-032 | Suffolk 34.5 kV | Stratford Solar Center | VA | City of Suffolk | In Service | Dominion | 15 | 15 | 9.8 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1032_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1032_wmpa.pdf | Not Required | N/A | N/A |  | 5/18/2019 | N/A | N/A | 2/28/2023 |  |  | 2/28/2023 | 2/28/2023 | 1/4/2023 | N | No
AF1-033 | Poolesville 34 kV | Surry Solar Center | VA | Surry | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1033_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1033_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1033_wmpa.pdf | Not Required | N/A | N/A |  | 5/17/2019 | N/A | N/A | 2/29/2024 | 8/17/2023 |  | 2/28/2023 | 2/28/2023 |  | N | No
AF1-034 | Clinton-Stuart 345 kV |  | OH | Highland | Withdrawn | Dayton | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/22/2019 | N/A | N/A |  | 6/12/2019 |  | 11/1/2021 |  |  | N | No
AF1-035 | Clinton-Stuart 345 kV |  | OH | Highland | Withdrawn | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn | [5 empty] | Withdrawn | N/A |  |  | N/A | N/A |  | 5/22/2019 | N/A | N/A |  | 6/12/2019 |  | 11/1/2021 |  |  | N | No
AF1-036 | Carville 138 kV III | Concho Solar I | MD | Queen Anne's | Suspended | DPL | 86 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_036_csa.pdf | Document Posted | N/A | N/A |  | 5/24/2019 | N/A | N/A | 6/3/2027 |  |  | 6/3/2024 | 6/3/2024 |  | N | No
AF1-037 | C.P. Crane 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1037_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2019 | N/A | N/A |  | 3/9/2020 |  | 6/1/2021 |  |  | N | No
AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV | Mt Olive Creek Solar | KY | Russell | Engineering and Procurement | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_038_csa.pdf | Document Posted | N/A | N/A | 6/30/2026 | 6/8/2019 | N/A | N/A | 7/30/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AF1-039 | Listonburg-Highpoint 24.9 kV | Listonburg Solar | PA | Somerset | In Service | PENELEC | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1039_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1039_wmpa.pdf | Not Required | N/A | N/A | 10/17/2024 | 6/7/2019 | N/A | N/A | 12/9/2024 |  |  | 10/31/2024 | 10/31/2024 | 12/26/2024 | N | No
AF1-040 | Gratz Tap 69 kV | Momentum Gratz | PA | Dauphin | Suspended | PPL | 20 | 20 | 1 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1040_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1040_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_040_csa.pdf | Document Posted | N/A | N/A |  | 6/15/2019 | N/A | N/A |  |  |  | 9/6/2024 | 9/6/2024 |  | N | No
AF1-041 | Absecon 12.47 kV | Pear Street Solar | NJ | Atlantic | In Service | AEC | 2.4 | 2.4 | 0 | 2.4 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1041_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1041_wmpa.pdf | Not Required | N/A | N/A |  | 6/18/2019 | N/A | N/A |  |  |  | 3/3/2022 | 3/3/2022 | 5/8/2020 | N | No
AF1-042 | Garner DP-Lancaster 115 kV | Waller Solar I | VA | Lancaster | Engineering and Procurement | Dominion | 131 | 45 | 17.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1042_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_042_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_042_csa.pdf | Document Posted | N/A | N/A | 3/31/2027 | 6/24/2019 | N/A | N/A | 9/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-043 | Moshannon-East Towanda 230 kV |  | PA | Clinton | Withdrawn | PENELEC | 640 | 92 | 105 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1043_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  | 4/20/2023 |  | 1/1/2023 |  |  | N | No
AF1-044 | Wye Mills-Longwood 69 kV |  | MD | Allegany | Withdrawn | DPL | 45 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1044_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  | 2/7/2020 |  | 11/30/2021 |  |  | N | No
AF1-045 | Cedarville-Ford 138 kV | Clermont County Solar Project | OH | Clermont | Suspended | DEOK | 152.2 | 52.2 | 31.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_045_csa.pdf | Document Posted | N/A | N/A | 9/1/2024 | 6/29/2019 | N/A | N/A | 10/1/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF1-046 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1046_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  | 9/14/2023 |  | 12/1/2023 |  |  | N | No
AF1-047 | Mark Center 69 kV |  | OH | Defiance | Withdrawn | AEP | 94.8 | 34.8 | 20.88 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  | 9/14/2023 |  | 12/1/2023 |  |  | N | No
AF1-048 - moved to TC1 | Belvidere-Marengo |  | IL | McHenry | Withdrawn | ComEd | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1048_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  | 1/22/2025 |  | 12/1/2023 |  |  | N | No
AF1-049 | Berry Hill 138 kV | Southern Virginia Solar | VA | Pittsylvania | Under Construction | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1049_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1049_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_049_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/31/2026 | 7/12/2019 | N/A | N/A | 1/31/2027 |  |  | 3/30/2027 | 3/30/2027 |  | N | No
AF1-050 | Summer Shade - Green County 161 kV | Horseshoe Bend Solar | KY | Green | Engineering and Procurement | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_050_csa.pdf | Document Posted | N/A | N/A | 8/31/2026 | 7/14/2019 | N/A | N/A | 9/15/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AF1-051 | Gavin 765 kV | Gavin Unit No. 1 | OH | Gallia | In Service | AEP | 1360 | 11 | 11 | 11 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/13/2019 | N/A | N/A | 5/20/2025 |  |  | 5/31/2025 | 5/31/2025 | 5/21/2025 | N | No
AF1-052 | Mason 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 131.5 | 131.5 | 114.2 |  | Capacity | Generation Interconnection | Natural Gas; Other; Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1052_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2019 | N/A | N/A |  | 2/11/2021 |  | 12/31/2024 |  |  | N | No
AF1-053 | Givens-Mechanicsburg 138 kV | Hillclimber Solar | OH | Champaign | Engineering and Procurement | Dayton | 118 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1053_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_053_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2029 | 7/31/2019 | N/A | N/A | 8/30/2029 |  |  | 9/30/2029 | 9/30/2029 |  | N | No
AF1-054 | Givens-Mechanicsburg 138 kV | Hillclimber Solar | OH | Champaign | Engineering and Procurement | Dayton | 156.5 | 38.5 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1054_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1054_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_054_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2029 | 7/31/2019 | N/A | N/A | 8/30/2029 |  |  | 9/30/2029 | 9/30/2029 |  | N | No
AF1-055 | Wayne 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 69.5 | 69.5 | 41.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1055_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 2/19/2020 |  | 10/31/2021 |  |  | N | No
AF1-056 | Maysville/Masury 138 kV |  | PA | Mercer | Withdrawn | ATSI | 100 | 100 | 68.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 8/27/2019 |  | 10/1/2023 |  |  | N | No
AF1-057 | Jackson-Three Mile Island 230 kV II | Dover Solar | PA | York | Suspended | ME | 75 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1057_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1057_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_057_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2019 | N/A | N/A | 9/14/2026 |  |  | 10/14/2026 | 10/14/2026 |  | N | No
AF1-058 | Welco 34.5 kV | Watlington Solar | VA | Halifax | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1058_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1058_wmpa.pdf | Not Required | N/A | N/A |  | 8/1/2019 | N/A | N/A | 3/31/2023 |  |  | 11/30/2022 | 11/30/2022 | 3/8/2023 | N | No
AF1-059 | Brodnax-South Hill 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 99.2 | 99.2 | 99.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1059_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 9/12/2023 |  | 10/31/2021 |  |  | N | No
AF1-060 | Lena 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 110.34 | 10.34 | 10.34 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1060_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 6/23/2023 |  | 12/31/2020 |  |  | N | No
AF1-061 | Fayetteville 12.47 kV |  | PA | Franklin | Withdrawn | APS | 4 | 4 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1061_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 8/6/2020 |  | 12/10/2021 |  |  | N | No
AF1-062 | Jug Street 138 kV | Flint Grid | OH | Licking | Engineering and Procurement | AEP | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1062_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1062_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_062_csa.pdf | Document Posted | N/A | N/A | 10/1/2026 | 7/31/2019 | N/A | N/A | 10/19/2026 |  |  | 5/1/2027 | 5/1/2027 |  | N | No
AF1-063 | Lockwood Road 138 kV |  | OH | Defiance | Withdrawn | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1063_imp.htm | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_063_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 10/29/2024 |  | 3/31/2022 |  |  | N | No
AF1-064 | Weston 69 kV | Juliet Energy | OH | Wood | Under Construction | ATSI | 50 | 50 | 33.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1064_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1064_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_064_csa.pdf | Document Posted | N/A | N/A | 11/14/2025 | 7/31/2019 | N/A | N/A | 11/17/2025 |  |  | 2/27/2026 | 2/27/2026 |  | N | No
AF1-065 | Tidd-Wylie Ridge 345 kV III |  | WV | Brooke | Withdrawn | APS | 930 | 100 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1065_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2019 | N/A | N/A |  | 10/14/2020 |  | 6/1/2022 |  |  | N | No
AF1-066 | New Road 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 170 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1066_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/2/2019 | N/A | N/A |  | 8/8/2023 |  | 11/30/2021 |  |  | N | No
AF1-067 | Kings Dominion DP 115 kV |  | VA | Caroline | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1067_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2019 | N/A | N/A |  | 6/29/2023 |  | 12/16/2022 |  |  | N | No
AF1-068 | Boalsburg-Centre Hall 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1068_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2019 | N/A | N/A |  | 12/15/2020 |  | 1/10/2022 |  |  | N | No
AF1-069 | Carson-Rogers Rd 500 kV | Cassius Blue Solar | VA | Sussex | Engineering and Procurement | Dominion | 394 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1069_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_069_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2030 | 8/9/2019 | N/A | N/A | 6/15/2030 |  |  | 8/1/2031 | 8/1/2031 |  | N | No
AF1-070 | North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 350 | 350 | 255.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2019 | N/A | N/A |  | 10/1/2019 |  | 6/1/2022 |  |  | N | No
AF1-071 | College Corner 138 kV | Angelina Solar I | OH | Preble | Engineering and Procurement | AEP | 98 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1071_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_071_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/5/2027 | 8/13/2019 | N/A | N/A | 1/30/2027 |  |  | 4/1/2028 | 4/1/2028 |  | N | No
AF1-072 | Rocky Road |  | IL | Kane | Withdrawn | ComEd | 410.8 | 17.2 | 17.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1072_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/14/2019 | N/A | N/A |  | 9/11/2023 |  | 8/1/2019 |  |  | N | No
AF1-073 | Trowbridge 230 kV |  | NC | Washington | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1073_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 2/11/2020 |  | 10/31/2021 |  |  | N | No
AF1-074 | Waverly-Wakefield 115 kV |  | VA | Sussex | Withdrawn | Dominion | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1074_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2019 | N/A | N/A |  | 2/20/2020 |  | 6/30/2022 |  |  | N | No
AF1-075 | Harrisburg-Endless Caverns 230 kV | Skyline Solar | VA | Rockingham | Suspended | Dominion | 73 | 73 | 45.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_075_csa.pdf | Document Posted | N/A | N/A |  | 8/21/2019 | N/A | N/A |  |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AF1-076 | Southwest Lima 138 kV |  | OH | Allen | Withdrawn | AEP | 100 | 100 | 61.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1076_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/22/2019 | N/A | N/A |  | 9/14/2023 |  | 12/31/2021 |  |  | N | No
AF1-077 | Southwest Lima 138 kV |  | OH | Allen | Withdrawn | AEP | 200 | 100 | 61.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/22/2019 | N/A | N/A |  | 9/14/2023 |  | 12/31/2021 |  |  | N | No
AF1-078 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | In Service | Dayton | 144 | 45 | 18.9 | 45 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1078_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/28/2024 | 8/27/2019 | N/A | N/A | 12/19/2024 |  |  | 1/31/2025 | 1/31/2025 | 2/5/2025 | N | No
AF1-079 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 150 | 44.8 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1079_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2019 | N/A | N/A |  | 12/6/2022 |  | 11/1/2021 |  |  | N | No
AF1-080 | Deer Creek-Fisher Body-Mullin 138 kV |  | IN | Madison | Withdrawn | AEP | 220 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1080_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2019 | N/A | N/A |  | 9/29/2020 |  | 9/15/2021 |  |  | N | No
AF1-081 | Cumberland 230 kV |  | NJ | Atlantic | Withdrawn | AEC | 238 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1081_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2019 | N/A | N/A |  | 2/27/2020 |  | 6/30/2022 |  |  | N | No
AF1-082 | Heartsease-Mayo Dunbar DP |  | NC | Edgecombe | Withdrawn | Dominion | 93 | 18 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1082_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2019 | N/A | N/A |  | 4/8/2024 |  | 12/31/2020 |  |  | N | No
AF1-083 | Green County-Saloma 161 kV | Flat Run Solar | KY | Barren | Engineering and Procurement | EKPC | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1083_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1083_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_083_csa.pdf | Document Posted | N/A | N/A | 10/27/2026 | 8/31/2019 | N/A | N/A | 11/30/2026 |  |  | 12/15/2026 | 12/15/2026 |  | N | No
AF1-084 | Hartford-Almena 69 kV | Murch Solar | MI | Van Buren | Engineering and Procurement | AEP | 85 | 85 | 54.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1084_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1084_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_084_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2026 | 8/30/2019 | N/A | N/A | 10/22/2026 |  |  | 1/15/2027 | 1/15/2027 |  | N | No
AF1-085 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 77 | 77 | 32.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 4/26/2024 |  | 11/30/2022 |  |  | N | No
AF1-086 | Madera-Westover South 115 kV | Rogue's Wind | PA | Clearfield | Under Construction | PENELEC | 109.9 | 109.9 | 20.54 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1086_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_086_csa.pdf | Document Posted | N/A | N/A | 1/5/2026 | 8/30/2019 | N/A | N/A | 1/5/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AF1-087 | Bakers Pond-Bell Ave 115 kV II |  | VA | Accomack | Withdrawn | Dominion | 75 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1087_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 2/18/2020 |  | 6/1/2022 |  |  | N | No
AF1-088 - moved to TC1 | Sullivan 345 kV | Grain Belt Transmission | IN | Sullivan | Active | AEP | 1000 | 1000 | 1000 |  | Capacity | Merchant Transmission |  | DC | 1000 F/1000 NFTIR/0 F/1000 NFTWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/af1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/af1088_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AF1-089 | New Castle 69 kV |  | KY | Henry | Withdrawn | EKPC | 70 | 70 | 53.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1089_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 2/12/2020 |  | 6/1/2022 |  |  | N | No
AF1-090 | Kincaid-Pana | Rolling Farms Wind Project | IL | Christian | Engineering and Procurement | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1090_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_090_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/1/2029 | 8/30/2019 | N/A | N/A | 12/15/2029 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
AF1-091 | Varner - Sowers 138 kV | Sculpin Solar | IN | DeKalb | Engineering and Procurement | AEP | 180 | 180 | 138.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1091_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1091_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_091_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/18/2027 | 8/30/2019 | N/A | N/A | 6/1/2027 |  |  | 11/30/2027 | 11/30/2027 |  | N | No
AF1-092 | Huntington Jct. 138 kV | Bowfin Solar | IN | Huntington | Suspended | AEP | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1092_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_092_csa.pdf | Document Posted | N/A | N/A | 3/31/2028 | 8/30/2019 | N/A | N/A | 4/7/2028 |  |  | 6/30/2028 | 6/30/2028 |  | N | No
AF1-093 | Henderson-Stoneboro 69 kV | Jackson Center Solar II | PA | Mercer | Engineering and Procurement | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_093_csa.pdf | Document Posted | N/A | N/A | 5/31/2026 | 8/31/2019 | N/A | N/A | 6/29/2026 |  |  | 7/31/2026 | 7/31/2026 |  | N | No
AF1-094 | Union City-Cambridge Springs 34.5 kV | Franklin Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1094_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_094_csa.pdf | Document Posted | N/A | N/A | 7/15/2026 | 8/30/2019 | N/A | N/A | 7/31/2026 |  |  | 9/20/2026 | 9/20/2026 |  | N | No
AF1-095 | Hertlein Road-Winburne 34 kV |  | PA | Clearfield | Withdrawn | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 10/2/2019 |  | 1/1/2023 |  |  | N | No
AF1-096 | Titusville-Oil Creek 34.5 kV | Big Bell Solar | PA | Crawford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1096_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1096_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 2/21/2023 |  | 1/1/2023 |  |  | N | No
AF1-097 | Zion-E College Ave 34 kV |  | PA | Centre | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 9/19/2019 |  | 1/1/2023 |  |  | N | No
AF1-098 | Four Mile Jct-Corry East 115 kV | Wilson Solar | PA | Erie | Engineering and Procurement | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1098_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1098_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1098_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_098_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_098_csa.pdf | Document Posted | N/A | N/A | 10/29/2027 | 8/30/2019 | N/A | N/A | 11/12/2027 |  |  | 1/29/2028 | 1/29/2028 |  | N | No
AF1-099 - moved to TC1 | Moshannon-Milesburg 230 kV III |  | PA | Clearfield | Withdrawn | APS | 126.5 | 126.5 | 75.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1099_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  | 1/22/2025 |  | 4/1/2022 |  |  | N | No
AF1-100 - moved to TC1 | Shawville-Moshannon 230 kV |  | PA | Clearfield | Withdrawn | PENELEC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  | 6/21/2024 |  | 4/1/2022 |  |  | N | No
AF1-101 | Oyster Creek 230 kV III |  | NJ | Ocean | Withdrawn | JCPL | 800 | 800 | 224.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2019 | N/A | N/A |  | 7/15/2021 |  | 11/23/2022 |  |  | N | No
AF1-102 | Gans 138 kV II | Gans CT | PA | Fayette | In Service | APS | 96 | 0 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_102_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/6/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 3/11/2021 | N | No
AF1-103 | Warren 34.5 kV |  | PA | Warren | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1103_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 9/12/2023 |  | 6/1/2023 |  |  | N | No
AF1-104 | Erie West 34.5 kV | Elder West | PA | Erie | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1104_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1104_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1104_wmpa.pdf | Not Required | N/A | N/A |  | 9/10/2019 | N/A | N/A | 9/1/2026 | 11/15/2024 |  | 10/15/2026 | 10/15/2026 |  | N | No
AF1-105 | Glen Gardner 34.5 kV | Holly Glen | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_105_csa.pdf | Document Posted | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 4/17/2023 |  | 12/31/2024 | 12/31/2024 |  | N | No
AF1-106 | East Sayre 34.5 kV | Ellistown Solar & BESS | PA | Bradford | Engineering and Procurement | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1106_imp.htm | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1106_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1106_wmpa.pdf | Not Required | N/A | N/A |  | 9/10/2019 | N/A | N/A | 10/29/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-107 | Pohatcong 230 kV |  | NJ | Warren | Withdrawn | JCPL | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1107_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 4/13/2020 |  | 6/1/2023 |  |  | N | No
AF1-108 | East Flemington 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1108_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1108_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 11/22/2022 |  | 6/1/2023 |  |  | N | No
AF1-109 | Pleasant Valley 230 kV |  | NJ | Mercer | Withdrawn | PSEG | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1109_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 9/11/2023 |  | 6/1/2023 |  |  | N | No
AF1-110 | Kingsland 26 kV |  | NJ | N/A | Withdrawn | PSEG | 2 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 9/23/2019 |  |  |  |  | Y | No
AF1-111 | Kingsland 26 kV |  | NJ | N/A | Withdrawn | PSEG | 2 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 9/23/2019 |  |  |  |  | Y | No
AF1-112 | Centre Hall-Boalsburg 46 kV | Centre Hall | PA | Centre | Withdrawn | APS | 15 | 15 | 8.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1112_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1112_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1112_wmpa.pdf | Not Required | N/A | N/A | 7/31/2026 | 9/11/2019 | N/A | N/A | 8/31/2026 | 7/29/2024 |  | 10/31/2026 | 10/31/2026 |  | N | No
AF1-113 | Gristmill 345 kV |  | OH | Auglaize | Withdrawn | AEP | 180 | 180 | 137.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1113_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2019 | N/A | N/A |  | 9/14/2023 |  | 6/1/2022 |  |  | N | No
AF1-114 | Oak Grove-Dahlgren 230 kV | Gibson Solar I | VA | King George | Engineering and Procurement | Dominion | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1114_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1114_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_114_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_114_csa.pdf | Document Posted | N/A | N/A | 12/1/2026 | 9/12/2019 | N/A | N/A | 2/1/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-115 | Poolesville 230 kV |  | VA | Surry | Withdrawn | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1115_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2019 | N/A | N/A |  | 10/9/2020 |  | 12/1/2021 |  |  | N | No
AF1-116 - moved to TC1 | Marion County 161 kV |  | KY | Washington | Withdrawn | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1116_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2019 | N/A | N/A |  | 2/28/2025 |  | 12/29/2023 |  |  | N | No
AF1-117 | Atlanta-Stuart 345 kV |  | OH | Ross | Withdrawn | AEP | 200 | 200 | 152.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1117_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2019 | N/A | N/A |  | 9/14/2023 |  | 6/1/2023 |  |  | N | No
AF1-118 | Sorenson-Desoto 345 kV | Paddlefish Solar | IN | Wells | Engineering and Procurement | AEP | 350 | 350 | 268.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1118_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1118_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_118_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_118_csa.pdf | Document Posted | N/A | N/A | 10/16/2028 | 9/13/2019 | N/A | N/A | 11/1/2028 |  |  | 2/15/2029 | 2/15/2029 |  | N | No
AF1-119 | Keystone-Desoto 345 kV | Lake Trout Solar | IN | Blackford | Engineering and Procurement | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1119_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1119_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_119_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_119_csa.pdf | Document Posted | N/A | N/A | 10/29/2027 | 9/13/2019 | N/A | N/A | 11/15/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AF1-120 | East Fayette 2 138 kV | Arche Energy Project | OH | Fulton | In Service | ATSI | 107 | 40 | 26.6 | 40 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1120_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_120_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_120_csa.pdf | Document Posted | N/A | N/A | 9/7/2023 | 8/31/2019 | N/A | N/A | 10/11/2023 |  |  | 12/31/2023 | 12/31/2023 | 1/17/2024 | N | No
AF1-121 | Crain Highway 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1121_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  | 3/5/2020 |  | 11/30/2021 |  |  | N | No
AF1-122 | Cardington-Liberty 69 kV | Morrow County Solar II | OH | Morrow | Suspended | ATSI | 64 | 64 | 26.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1122_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1122_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_122_csa.pdf | Document Posted | N/A | N/A | 10/15/2028 | 9/17/2019 | N/A | N/A | 10/15/2028 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AF1-123 - moved to TC1 | Oceana 230 kV | Coastal Virginia Offshore Wind 1, OSS 1 - T1L11 | VA | City of Chesapeake | Active | Dominion | 833 | 833 | 253.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1123_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_123_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_123_csa.pdf | Document Posted | N/A | N/A | 6/30/2026 | 9/17/2019 | N/A | N/A | 8/20/2026 |  |  | 12/31/2025 |  |  | N | No
AF1-124 - moved to TC1 | Oceana 230 kV | Coastal Virginia Offshore Wind 2, OSS 2 – T2G07 | VA | City of Chesapeake | Active | Dominion | 836 | 836 | 254.1 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1124_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_124_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_124_csa.pdf | Document Posted | N/A | N/A | 3/30/2026 | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AF1-125 - moved to TC1 | Oceana 230 kV | Coastal Virginia Offshore Wind 3, OSS 3 – T3G15 | VA | City of Chesapeake | Active | Dominion | 820 | 820 | 249.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1125_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_125_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_125_csa.pdf | Document Posted | N/A | N/A | 5/29/2026 | 9/17/2019 | N/A | N/A | 6/30/2026 |  |  | 12/31/2024 |  |  | N | No
AF1-126 | Cookstown 230 kV |  | NJ | Burlington | Withdrawn | JCPL | 250 | 250 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1126_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  | 10/1/2020 |  | 10/22/2022 |  |  | N | No
AF1-127 | Avon 345 kV |  | KY | Fayette | Withdrawn | EKPC | 80 | 80 | 53.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1127_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  | 9/13/2023 |  | 12/1/2023 |  |  | N | No
AF1-128 - moved to TC1 | Chesterfield 230 kV | Chesterfield CT Units 1 and 2 | VA | Chesterfield | Active | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1128_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_128_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_128_csa.pdf | Document Posted | N/A | N/A | 3/31/2028 | 9/18/2019 | N/A | N/A | 6/30/2028 |  |  | 6/1/2023 |  |  | N | No
AF1-129 | Chesterfield 230 kV | Chesterfield CT Units 3&4 | VA | Chesterfield | Engineering and Procurement | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1129_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1129_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_129_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_129_csa.pdf | Document Posted | N/A | N/A | 3/31/2028 | 9/18/2019 | N/A | N/A | 6/30/2028 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
AF1-130 | Inez 138 kV | Martin County Solar Project | KY | Martin | Suspended | AEP | 190 | 190 | 133.9 | 111.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1130_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1130_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_130_csa.pdf | Document Posted | N/A | N/A | 6/12/2024 | 9/20/2019 | N/A | N/A | 10/10/2024 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AF1-131 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Withdrawn | APS | 16.15 | 16.15 | 9.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1131_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 9/28/2020 |  | 6/1/2021 |  |  | N | No
AF1-132 | Shingletown-Boalsburg 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1132_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 12/15/2020 |  | 4/1/2021 |  |  | N | No
AF1-133 | Pequest River-Richmond 34.5 kV | NH Gravel Hill at Martins Creek | PA | Northampton | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1133_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1133_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1133_wmpa.pdf | Not Required | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 6/9/2023 |  | 2/28/2023 | 2/28/2023 |  | N | No
AF1-134 | Philipsburg-Madera 34.5 kV | CL-Green Acres | PA | Clearfield | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1134_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1134_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1134_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2019 | N/A | N/A | 11/7/2027 |  |  | 1/6/2028 | 1/6/2028 |  | N | No
AF1-135 | Madera 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1135_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 3/19/2020 |  | 4/1/2022 |  |  | N | No
AF1-136 | Warfordsburg-Purcell Junction 34.5 kV | FU-Hanks Solar | PA | Fulton | Engineering and Procurement | APS | 15.72 | 15.72 | 9.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1136_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1136_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_136_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_136_csa.pdf | Document Posted | N/A | N/A | 9/16/2026 | 9/19/2019 | N/A | N/A | 10/12/2026 |  |  | 11/17/2026 | 11/17/2026 |  | N | No
AF1-137 | Newlinville 34.5 kV | Ch-Valley Solar | PA | Chester | Withdrawn | PECO | 9.8 | 9.8 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1137_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1137_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1137_wmpa.pdf | Not Required | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 4/27/2024 |  | 4/10/2023 | 4/10/2023 |  | N | No
AF1-138 | Huntingdon-Warrier Ridge 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1138_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 3/19/2020 |  | 4/1/2022 |  |  | N | No
AF1-139 | Thompson 34.5 kV |  | PA | Wayne | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1139_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 3/19/2020 |  | 6/1/2022 |  |  | N | No
AF1-140 | Claysburg 23 kV | BL-Diamond Bear Rocks | PA | Adams | Engineering and Procurement | PENELEC | 16.3 | 16.3 | 9.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1140_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1140_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1140_wmpa.pdf | Not Required | N/A | N/A | 9/6/2026 | 9/19/2019 | N/A | N/A | 10/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AF1-141 | Varner 138 kV | Thalassa Energy Project | IN | DeKalb | Withdrawn | AEP | 96 | 96 | 62.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1141_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1141_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 10/16/2024 |  | 5/31/2022 |  |  | N | No
AF1-142 - moved to TC1 | Moshannon-Milesburg 230 kV IV |  | PA | Clearfield | Withdrawn | APS | 328.9 | 202.4 | 121.44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1142_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  | 1/22/2025 |  | 4/1/2022 |  |  | N | No
AF1-143 | Lick Run 115 kV | Rockdale Solar | PA | Somerset | Engineering and Procurement | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1143_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1143_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_143_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2027 | 9/18/2019 | N/A | N/A | 11/16/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-144 | Hayden 345 kV | Hayden Run | OH | Franklin | Withdrawn | AEP | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1144_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 6/6/2024 |  | 12/1/2023 |  |  | N | No
AF1-145 | Flanders-Netcong 34.5 kV |  | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 10/7/2019 |  | 10/1/2021 |  |  | N | No
AF1-146 | Hoytdale -McClelland 345 kV | Firefly Solar | PA | Lawrence | Withdrawn | ATSI | 201.95 | 201.95 | 121.17 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1146_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1146_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_146_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_146_csa.pdf | Document Posted | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 12/2/2024 |  | 9/1/2026 | 9/1/2026 |  | N | No
AF1-147 | Poland Rd-Runway DP 230kV | Dulles Solar and BESS | VA | Loudoun | Under Construction | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1147_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1147_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_147_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_147_csa.pdf | Document Posted | N/A | N/A | 10/1/2025 | 9/20/2019 | N/A | N/A | 11/25/2025 |  |  | 10/31/2026 | 10/31/2026 |  | N | No
AF1-148 | Sorenson-Desoto 345 kV |  | IN | Wells | Withdrawn | AEP | 159 | 159 | 95.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1148_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1148_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 11/8/2024 |  | 4/30/2023 |  |  | N | No
AF1-149 | Graymont-Zion 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1149_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 10/1/2020 |  | 3/1/2021 |  |  | N | No
AF1-150 | Midfield 22.9 kV | Pittsburgh International Airport | PA | Allegheny | In Service | DL | 14.4 | 14.4 | 4.28 | 14.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1150_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1150_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1150_wmpa.pdf | Not Required | N/A | N/A | 4/1/2021 | 9/19/2019 | N/A | N/A | 4/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 10/28/2021 | N | No
AF1-151 | Fayetteville 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1151_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 3/6/2020 |  | 12/31/2022 |  |  | N | No
AF1-152 - moved to TC1 | Swamp 230 kV |  | NC | Pasquotank | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1152_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 1/22/2025 |  | 10/2/2023 |  |  | N | No
AF1-153 | Motion-Ridgeway 46 kV | Jakes Hollow Solar | PA | Elk | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1153_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1153_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1153_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2019 | N/A | N/A | 10/30/2027 |  |  | 12/29/2027 | 12/29/2027 |  | N | No
AF1-154 | Dauphin |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 10/8/2019 |  | 5/1/2022 |  |  | N | No
AF1-155 | Paper City-Wilcox 46 kV | EL-Mefferts Run | PA | Elk | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1155_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1155_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1155_wmpa.pdf | Not Required | N/A | N/A | 11/30/2025 | 9/19/2019 | N/A | N/A | 12/31/2025 | 5/16/2025 |  | 2/28/2026 | 2/28/2026 |  | N | No
AF1-156 | Braidwood-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1156_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 9/11/2023 |  | 9/30/2021 |  |  | N | No
AF1-157 | Laurel-Sussex 69 kV |  | DE | Sussex | Withdrawn | DPL | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1157_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  | 10/12/2020 |  | 12/31/2022 |  |  | N | No
AF1-158 | Edison-Gravel Pit 138 kV | Honeysuckle Solar Project | IN | St. Joseph | In Service | AEP | 150 | 150 | 90 | 150 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1158_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1158_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_158_csa.pdf | Document Posted | N/A | N/A | 4/23/2024 | 9/24/2019 | N/A | N/A | 6/6/2024 |  |  | 1/31/2025 | 1/31/2025 | 8/25/2025 | N | No
AF1-159 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | In Service | Dayton | 49.9 | 0 | 10.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1159_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1159_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_159_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_159_csa.pdf | Document Posted | N/A | N/A | 6/6/2025 | 9/21/2019 | N/A | N/A | 6/16/2025 |  |  | 6/25/2025 | 6/25/2025 | 6/27/2025 | N | No
AF1-160 | Silver Lake 69 kV |  | NJ | Camden | Withdrawn | AEC | 40 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1160_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/20/2019 | N/A | N/A |  | 3/22/2022 |  | 11/1/2021 |  |  | N | No
AF1-161 - moved to TC1 | Valley 138 kV | Decatur Battery Storage | MI | Van Buren | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1161_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF1-162 | Inez 138 kV | Threeforks Energy Storage | KY | Martin | Engineering and Procurement | AEP | 277 | 100 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1162_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1162_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_162_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2028 | 9/20/2019 | N/A | N/A | 4/1/2028 |  |  | 5/31/2028 | 5/31/2028 |  | N | No
AF1-163 | Barren-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 120 | 120 | 80.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  | 12/11/2019 |  | 6/1/2022 |  |  | N | No
AF1-164 | Southwest Lima 345 kV | Birch Solar | OH | Allen | Withdrawn | AEP | 300 | 300 | 195 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1164_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1164_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_164_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_164_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2019 | N/A | N/A |  | 1/9/2025 |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-165 | Campbelltown-Millars Quarry 69 kV | East Ridge Solar | PA | Lebanon | Withdrawn | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1165_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1165_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 12/5/2024 |  | 1/31/2027 | 1/31/2027 |  | N | No
AF1-166 | Target-Chambers No.5 34.5 kV | FR-BOYER MILL 1 | PA | Franklin | Withdrawn | APS | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1166_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1166_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1166_wmpa.pdf | Not Required | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 11/22/2023 |  | 2/28/2023 | 2/28/2023 |  | N | No
AF1-167 | West Freedom-C&K Coal 25 kV | CL-Route 58 B | PA | Clarion | Suspended | APS | 13.515 | 13.515 | 8.109 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1167_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1167_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1167_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2019 | N/A | N/A | 11/28/2025 |  |  | 1/31/2026 | 1/31/2026 |  | N | No
AF1-168 | Kingsland 26.4 kV I |  | NJ | Bergen | Withdrawn | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 10/8/2019 |  | 9/30/2020 |  |  | N | No
AF1-169 | Kingsland 26.4 kV II |  | NJ | Bergen | Withdrawn | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 10/8/2019 |  | 9/30/2020 |  |  | N | No
AF1-170 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1170_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1170_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 12/3/2024 |  | 2/15/2023 |  |  | N | No
AF1-171 | Jamestown-Hartstown 69 kV |  | PA | Crawford | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1171_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 12/15/2020 |  | 2/15/2023 |  |  | N | No
AF1-172 | Moshannon-Chapman 230 kV |  | PA | Clinton | Withdrawn | PENELEC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1172_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  | 3/2/2020 |  | 10/31/2022 |  |  | N | No
AF1-173 | Gretna DP-Shockoe DP 69 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 0 | 13.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1173_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 9/12/2023 |  | 12/15/2020 |  |  | N | No
AF1-174 | Newlinville 34.5 kv II | Ch-Goosetown Solar | PA | Chester | Withdrawn | PECO | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1174_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1174_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1174_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A | 6/30/2024 | 4/27/2024 |  | 6/1/2022 |  |  | N | No
AF1-175 | Donald C Cook-Jackson Road 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 152 | 152 | 91.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1175_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  | 4/16/2020 |  | 4/30/2023 |  |  | N | No
AF1-176 - moved to TC1 | Corey 138 kV | Three Lakes Solar | MI | St. Joseph | Active | AEP | 300 | 300 | 155.682 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1176_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF1-177 | Warren 115 kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 62 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1177_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_177_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 7/1/2020 | N | No
AF1-178 | Tolna 2 115 kV | Tolna Unit 2 | PA | York | In Service | ME | 21.5 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_178_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-179 | Tolna 1 115 kV | Tolna Unit 1 | PA | York | In Service | ME | 21 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1179_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_179_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-180 | Titus 4 & 5 69 kV | Titus Generating Station (Titus CT 4 and Titus CT 5) | PA | Berks | In Service | ME | 38.7 | 2 | 2 | 2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1180_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_180_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-181 | Shawville 3 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 593 | 3 | 3 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1181_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-182 | Shawville 4 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 597 | 4 | 4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1182_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_182_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-183 | Shawville 1 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 598 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1183_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_183_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-184 | Shawnee 1 34.5 kv | Shawnee Generating Station (CT 1) | PA | Monroe | In Service | ME | 21 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_184_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-185 | Sayreville 1-2-3 230 kV | Sayreville Facility (Raritan River) | NJ | Middlesex | In Service | JCPL | 171.7 | 0 | 5.5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-186 | Portland 5 230 kV | Portland Station Unit 5 | PA | Northampton | In Service | ME | 147.5 | 6.5 | 6.5 | 6.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1186_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_186_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-187 | Portland 3 & 4 115 kV | Portland Station Unit 3 and Unit 4 | PA | Northampton | In Service | ME | 39.8 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1187_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_187_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-188 | Orrtanna 115 kV | Orrtanna Station Unit C1 | PA | Adams | In Service | ME | 27 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1188_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_188_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-189 | Niles CT A 23 kV | Niles A CT | OH | Trumbull | In Service | ATSI | 26.1 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1189_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_189_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-190 | New Castle 4 69 kV | New Castle Generating Station | PA | Lawrence | In Service | ATSI | 93 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1190_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_190_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-191 | New Castle 5 138 kV | New Castle Generating Station | PA | Lawrence | In Service | ATSI | 145 | 4 | 4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1191_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_191_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-192 | Mountain 2 115 kV | Mountain Station Unit C2 | PA | Cumberland | In Service | ME | 55 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1192_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1192_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_192_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-193 | Hunterstown 115 kV | Hunterstown CT Facility | PA | Adams | In Service | ME | 65 | 4 | 4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1193_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1193_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_193_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-194 | Hamilton CT1 115 kV | Hamilton Station | PA | York | In Service | ME | 27 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1194_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_194_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-195 | Gilbert CT9 230 kV | Gilbert Station Unit 9 | NJ | Hunterdon | In Service | JCPL | 168 | 0 | 1 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1195_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1195_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_195_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-196 | Gilbert CT 5-6-7 230 kV | Gilbert Station 4x1 Combined Cycle (Unit 4, Unit 5, Unit 6, Unit 7, and Unit 8) | NJ | Hunterdon | In Service | JCPL | 302.5 | 0 | 14.5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1196_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_196_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-197 | Brunot Island 138 kV |  | PA | Allegheny | Withdrawn | DL | 295 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1197_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  | 3/5/2020 |  | 10/1/2019 |  |  | N | No
AF1-198 | Blossburg #1 CT 34.5 kV | Blossburg Station Unit 1 | PA | Tioga | In Service | PENELEC | 22.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1198_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1198_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_198_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2019 | N/A | N/A | 7/24/2023 |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-199 | Avon Lake 10 138 kV | Avon Lake Plant | OH | Lorain | Deactivated | ATSI | 36 | 4 | 4 | 4 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1199_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1199_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_199_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 7/1/2020 | N | No
AF1-200 - moved to TC1 | Plano 345 kV |  | IL | Kendall | Withdrawn | ComEd | 2100 | 2100 | 2035 |  | Capacity | Merchant Transmission |  | DC | 2035 F/NFTIR/2100 NF/TWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/af1200_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/af1200_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  | 1/22/2025 |  | 1/31/2025 |  |  | S | No
AF1-201 - moved to TC1 | Hayes-White Marsh 115 kV |  | VA | Gloucester | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1201_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1201_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  | 6/24/2024 |  | 12/31/2021 |  |  | N | No
AF1-202 | Keystone-Desoto 345 kV | Blackford Wind Energy Project | IN | Blackford | Under Construction | AEP | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1202_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1202_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1202_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_202_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_202_csa.pdf | Document Posted | N/A | N/A | 3/10/2026 | 9/25/2019 | N/A | N/A | 3/31/2026 |  |  | 9/15/2026 | 9/15/2026 |  | N | No
AF1-203 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | In Service | EKPC | 55 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1203_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1203_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1203_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_203_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_203_csa.pdf | Document Posted | N/A | N/A | 4/15/2024 | 9/30/2019 | N/A | N/A | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 | 6/7/2024 | N | No
AF1-204 - moved to TC1 | Eugene 345 kV | Vermilion Grove Wind | IN | Vermillion | Active | AEP | 255 | 255 | 63.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1204_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1204_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-205 | Napoleon Muni 138 kV | Henry County Solar | OH | Henry | Suspended | AMPT | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1205_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1205_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_205_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_205_csa.pdf | Document Posted | N/A | N/A | 6/1/2026 | 9/27/2019 | N/A | N/A | 7/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF1-206 | East Fayette 138 kV | CG Fulton County | OH | Fulton | Engineering and Procurement | ATSI | 199 | 199 | 119.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1206_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1206_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1206_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_206_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 2/28/2028 | 9/26/2019 | N/A | N/A | 3/31/2028 |  |  | 5/31/2028 | 5/31/2028 |  | N | No
AF1-207 | Reynolds-Olive #1 345 kV | Hoosier Line Solar | IN | White | Engineering and Procurement | AEP | 180 | 180 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1207_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1207_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1207_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_207_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/6/2027 | 9/27/2019 | N/A | N/A | 5/31/2027 |  |  | 9/15/2027 | 9/15/2027 |  | N | No
AF1-208 | Laurel-Roadstown 69 kV | Horse Run Solar I | NJ | Salem | Engineering and Procurement | AEC | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1208_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1208_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1208_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_208_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2028 | 9/26/2019 | N/A | N/A | 12/15/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AF1-209 | Guilford 34.5 kV | FR Boyer Mill 2 | PA | Franklin | Withdrawn | APS | 31.9 | 15.9 | 9.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1209_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1209_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1209_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1209_wmpa.pdf | Not Required | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 11/22/2023 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF1-210 | Burma 23 kV | CL-Route 58 S | PA | Clarion | Withdrawn | APS | 15.9 | 15.9 | 9.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1210_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1210_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1210_wmpa.pdf | Not Required | N/A | N/A | 2/28/2025 | 9/26/2019 | N/A | N/A | 3/31/2025 | 9/19/2024 |  | 6/1/2022 |  |  | N | No
AF1-211 | Campbelltown-Millars Quarry 69 kV | Palmyra Solar | PA | Lebanon | Withdrawn | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1211_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1211_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1211_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 12/5/2024 |  | 1/31/2027 | 1/31/2027 |  | N | No
AF1-212 | Campbelltown-Millars Quarry 69 kV | Bellegrove Solar | PA | Lebanon | Withdrawn | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1212_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1212_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1212_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 12/5/2024 |  | 1/31/2027 | 1/31/2027 |  | N | No
AF1-213 | Bionol-Madera 115 kV |  | PA | Clearfield | Withdrawn | PENELEC | 151.8 | 151.8 | 91.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1213_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 4/13/2020 |  | 6/1/2023 |  |  | N | No
AF1-214 | Nittany-Zion 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1214_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1214_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 12/3/2020 |  | 5/1/2022 |  |  | N | No
AF1-215 | Olive-Reynolds 345 kV | Mammoth North Solar Project | IN | Starke | In Service | AEP | 300 | 300 | 180 | 300 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1215_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1215_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1215_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_215_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_215_csa.pdf | Document Posted | N/A | N/A | 8/20/2024 | 9/28/2019 | N/A | N/A | 10/14/2024 |  |  | 7/31/2024 | 7/31/2024 | 11/8/2024 | N | No
AF1-216 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Withdrawn | PPL | 143.11 | 143.11 | 85.87 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1216_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1216_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1216_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 8/30/2023 |  | 5/31/2021 |  |  | N | No
AF1-217 | Edinboro -Cambridge Springs 34.5 kV | Crawford Solar II | PA | Crawford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1217_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1217_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1217_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1217_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2019 | N/A | N/A | 12/31/2025 | 6/27/2025 |  | 4/30/2027 | 4/30/2027 |  | N | No
AF1-218 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 10/17/2019 |  | 12/31/2020 |  |  | N | No
AF1-219 | Hunt Farm 69 kV |  | KY | Boyle | Withdrawn | EKPC | 30 | 30 | 20.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1219_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1219_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 9/9/2020 |  | 6/1/2022 |  |  | N | No
AF1-220 | Ridgway-Whetstone 115 kV |  | PA | Elk | Withdrawn | PENELEC | 151.7 | 151.7 | 91 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1220_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 8/4/2020 |  | 3/1/2022 |  |  | N | No
AF1-221 - moved to TC1 | College Corner-Drewersburg 138 kV |  | IN | Franklin | Withdrawn | AEP | 180 | 180 | 25.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1221_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AF1-222 | Oceanview Wind 2 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1326 | 510 | 140.25 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1222_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1222_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 8/28/2023 |  | 12/30/2025 |  |  | N | No
AF1-223 | Keystone-Desoto 345 kV | Blackford Solar Energy Project | IN | Jay | Under Construction | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1223_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1223_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1223_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_223_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/10/2026 | 9/27/2019 | N/A | N/A | 9/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AF1-224 | Fayetteville 34.5 kV | Fayetteville Solar | PA | Franklin | Withdrawn | APS | 31.9 | 11.9 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1224_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1224_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1224_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1224_wmpa.pdf | Not Required | N/A | N/A |  | 9/27/2019 | N/A | N/A | 6/1/2024 | 10/10/2023 |  | 3/31/2022 | 3/31/2022 |  | N | No
AF1-225 | Milnor 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1225_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1225_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 9/7/2023 |  | 12/30/2021 |  |  | N | No
AF1-226 | Bowmans Mill-Scott 69 kV | Cottontail Solar 7 | PA | Columbia | Suspended | PPL | 35 | 35 | 14.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1226_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1226_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1226_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_226_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_226_csa.pdf | Document Posted | N/A | N/A | 9/30/2028 | 9/28/2019 | N/A | N/A | 9/30/2028 |  |  | 11/30/2028 | 11/30/2028 |  | N | No
AF1-227 | Marysville – Gunn Road 345 kV | Union Solar | OH | Union | In Service | AEP | 325 | 325 | 195 | 325 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1227_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1227_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_227_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_227_csa.pdf | Document Posted | N/A | N/A | 4/9/2024 | 9/30/2019 | N/A | N/A | 5/14/2024 |  |  | 12/31/2024 | 12/31/2024 | 11/15/2024 | N | No
AF1-228 | Beatty-Greene 345 kV | Springwater Solar | OH | Madison | Engineering and Procurement | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1228_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1228_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1228_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_228_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/21/2026 | 9/27/2019 | N/A | N/A | 5/15/2026 |  |  | 8/31/2026 | 8/31/2026 |  | N | No
AF1-229 | Galion-South Berwick 345 kV | Tymochtee Solar | OH | Wyandot | Engineering and Procurement | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1229_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1229_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1229_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_229_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_229_csa.pdf | Document Posted | N/A | N/A | 4/21/2026 | 9/27/2019 | N/A | N/A | 5/15/2026 |  |  | 8/31/2026 | 8/31/2026 |  | N | No
AF1-230 | Chatfield 138 kV |  | OH | Crawford | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1230_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 2/5/2020 |  | 10/31/2022 |  |  | N | No
AF1-231 | New Church 138 kV |  | VA | Accomack | Withdrawn | DPL | 19 | 19 | 7.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1231_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1231_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1231_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 9/10/2024 |  | 12/31/2022 |  |  | N | No
AF1-232 | Allegheny-Somerset 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 160 | 160 | 104 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1232_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1232_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 1/19/2021 |  | 5/31/2022 |  |  | N | No
AF1-233 - moved to TC1 | Flemingsburg – Spurlock 138kV | AEUG Fleming Solar | KY | Fleming | Active | EKPC | 188.5 | 188.5 | 113.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1233_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1233_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_233_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-234 | Baldy-Wesnberg 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 11/11/2019 |  | 12/15/2022 |  |  | N | No
AF1-235 | Sunbury 500 kV |  | PA | Snyder | Withdrawn | PPL | 617 | 617 | 617 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1235_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 3/2/2020 |  | 5/1/2023 |  |  | N | No
AF1-236 | Mackeys 230 kV |  | NC | Tyrell | Withdrawn | Dominion | 1210 | 1210 | 459.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1236_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1236_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 8/19/2022 |  | 9/30/2024 |  |  | N | No
AF1-237 | Mercer 230 kV | Lamberton Road Battery | NJ | Mercer | Engineering and Procurement | PSEG | 170 | 170 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1237_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1237_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1237_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_237_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/13/2027 | 9/28/2019 | N/A | N/A | 6/16/2027 |  |  | 8/11/2027 | 8/11/2027 |  | N | No | This project slid to the next queue
AF1-238 - moved to TC1 | Sherman Ave - West Vineland 69 kV | South Orchard | NJ | Cumberland | Active | AEC | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1238_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1238_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No | This project slid to the next queue
AF1-239 | Sherman Ave - West Vineland 69 kV | South Orchard | NJ | Cumberland | Engineering and Procurement | AEC | 30 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1239_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1239_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1239_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1239_wmpa.pdf | Not Required | N/A | N/A | 3/1/2028 | 9/28/2019 | N/A | N/A | 5/1/2028 |  |  | 6/1/2028 | 6/1/2028 |  | N | No
AF1-240 - moved to TC1 | Timblin 34.5 kV | AR-PIERCE | PA | Armstrong | Active | PENELEC | 15.75 | 15.75 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1240_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1240_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF1-241 | Watson 12.47 kV |  | PA | Adams | Withdrawn | PPL | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1241_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/24/2020 |  | 7/1/2022 |  |  | N | No
AF1-242 | Wilcox-Paper City 46 kV |  | PA | Adams | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1242_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/19/2020 |  | 8/1/2022 |  |  | N | No
AF1-243 | Tasley 25 kV |  | VA | Accomack | Withdrawn | ODEC | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1243_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1243_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/9/2020 |  | 6/30/2020 |  |  | N | No
AF1-244 | Kingston 12 kV |  | MD | Somerset | Withdrawn | DPL | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1244_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1244_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/7/2021 |  | 6/30/2020 |  |  | N | No
AF1-245 | Hudson 230 kV | Hudson Energy Storage Facility | NJ | Hudson | Engineering and Procurement | PSEG | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1245_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1245_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1245_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_245_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/1/2028 | 9/30/2019 | N/A | N/A | 11/1/2028 |  |  | 12/1/2028 | 12/1/2028 |  | N | No
AF1-246 | Clover-Rawlings 500 kV |  | VA | Charlotte | Withdrawn | Dominion | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1246_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1246_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 4/23/2024 |  | 7/1/2022 |  |  | N | No
AF1-247 | Woodsdale 345 kV |  | OH | Butler | Withdrawn | DEOK | 50 | 50 | 30.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 1/27/2020 |  | 10/20/2021 |  |  | N | No
AF1-248 | Northern Neck 34.5 kV | Gardy’s Mill Solar | VA | Westmoreland | In Service | Dominion | 14 | 0 | 2.1 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1248_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1248_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1248_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1248_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A | 6/1/2023 |  |  | 12/30/2020 | 12/30/2020 | 6/1/2023 | N | No
AF1-249 | Nickel 12.47 kV | Nickel Solar | OH | Warren | In Service | DEOK | 19.92 | 19.92 | 14 | 19.92 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1249_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1249_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1249_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1249_wmpa.pdf | Not Required | N/A | N/A | 10/28/2024 | 10/2/2019 | N/A | N/A | 10/28/2024 |  |  | 10/18/2024 | 10/18/2024 | 12/5/2024 | N | No
AF1-250 | Maysville 69 kV II |  | PA | Mercer | Withdrawn | ATSI | 68 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1250_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1250_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 9/24/2021 |  | 6/30/2022 |  |  | N | No
AF1-251 | Avon-North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 220 | 220 | 132 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1251_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1251_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 9/13/2023 |  | 5/15/2023 |  |  | N | No
AF1-252 - moved to TC1 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 262.4 | 62.4 | 62.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1252_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1252_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/24/2024 |  | 9/1/2022 |  |  | N | No
AF1-253 - moved to TC1 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 305.6 | 43.2 | 43.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1253_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1253_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/24/2024 |  | 9/1/2022 |  |  | N | No
AF1-254 | Milnor-Huyetts 34.5 kV | FR-Williamsport | PA | Franklin | Under Construction | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1254_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1254_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1254_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1254_wmpa.pdf | Not Required | N/A | N/A | 10/31/2025 | 9/30/2019 | N/A | N/A | 11/19/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF1-255 | Osterburg-Claysburg 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 13.5 | 13.5 | 5.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1255_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/18/2020 |  | 12/31/2019 |  |  | N | No
AF1-257 | Hawks 2 12 kV |  | NJ | Hunterdon | In Service | JCPL | 3 | 0 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1257_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1257_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_257_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 5/10/2021 | N | No
AF1-258 | Rockawalkin 69 kV | Hebron Solar | MD | Wicomico | In Service | DPL | 15 | 0 | 3.2 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1258_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1258_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1258_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1258_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 11/5/2020 | N | No
AF1-259 | Price 25 kV | Church Hill Solar | MD | Queen Anne's | In Service | DPL | 6 | 0 | 0.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1259_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1259_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_259_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/10/2020 | N | No
AF1-260 | Allenwood-Larrabee 2 34.5 kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 7 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1260_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1260_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_260_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/8/2020 | N | No
AF1-261 | Burlington 26 kV | North American Solar | NJ | Burlington | In Service | PSEG | 7 | 0 | 0.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1261_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1261_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_261_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 6/1/2021 | N | No
AF1-262 | Upper Pittsgrove 12 kV | Pittsgrove Solar | NJ | Salem | In Service | AEC | 2 | 0 | 0.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1262_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1262_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_262_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/15/2022 | N | No
AF1-263 | Bennett-Farmingdale 2 34.5 kV |  | NJ | Salem | Withdrawn | JCPL | 2 | 0 | 0.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1263_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1263_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/2/2020 |  | 10/1/2019 |  |  | N | No
AF1-264 | Runnemede 13 kV | Owens Corning Solar | NJ | Gloucester | In Service | PSEG | 3 | 0 | 1.3 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1264_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1264_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_264_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/1/2021 | 9/30/2019 | N/A | N/A | 5/15/2021 |  |  | 9/30/2023 | 9/30/2023 | 6/1/2021 | N | No
AF1-265 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Withdrawn | Dominion | 435 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1265_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1265_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 9/12/2023 |  | 12/31/2022 |  |  | N | No
AF1-266 - moved to TC1 | Clubhouse-Sapony 230 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 223.5 | 74.5 | 74.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1266_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1266_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/24/2024 |  | 12/31/2022 |  |  | N | No
AF1-267 | Union City Tap 138 kV |  | KY | Madison | Withdrawn | EKPC | 54 | 54 | 37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1267_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1267_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 11/10/2020 |  | 1/31/2022 |  |  | N | No
AF1-268 | Desoto-Jay 138 kV | Hawthorn Solar | IN | Delaware | Engineering and Procurement | AEP | 83 | 83 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1268_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1268_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1268_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_268_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_268_csa.pdf | Document Posted | N/A | N/A | 9/30/2028 | 9/30/2019 | N/A | N/A | 10/1/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AF1-269 | Airey-Golden Hill 69 kV |  | MD | Dorchester | Withdrawn | DPL | 67 | 11 | 11 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1269_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 5/12/2020 |  | 12/31/2022 |  |  | N | No
AF1-270 - moved to TC1 | Blue Jacket-Kirby 138 kV |  | OH | Logan | Withdrawn | Dayton | 279.5 | 50 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1270_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1270_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/21/2024 |  | 12/31/2022 |  |  | N | No
AF1-271 | Keisters-Krendale 138 kV |  | PA | Butler | Withdrawn | APS | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1271_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1271_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/11/2021 |  | 12/31/2023 |  |  | N | No
AF1-271A | Gratz 69 kV | G Morris Solar | PA | Dauphin | Suspended | PPL | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1271a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1271A_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1271a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_271a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_271a_csa.pdf | Document Posted | N/A | N/A | 1/15/2026 | 9/27/2019 | N/A | N/A | 3/2/2026 |  |  | 4/15/2026 | 4/15/2026 |  | N | No
AF1-272 | Lucerne 115 kV | Hoodlebug Solar Energy Center | PA | Indiana | Engineering and Procurement | PENELEC | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1272_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1272_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1272_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_272_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 10/1/2019 | N/A | N/A | 6/21/2027 |  |  | 8/31/2027 | 8/31/2027 |  | N | No
AF1-273 | Allegheny 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1273_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1273_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/14/2020 |  | 12/31/2023 |  |  | N | No
AF1-274 | Harvey Run 115 kV |  | PA | Clearfield | Withdrawn | PENELEC | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1274_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 4/8/2020 |  | 12/31/2023 |  |  | N | No
AF1-275 | Cole 345 kV | Pleasant Prairie Solar Energy Center | OH | Franklin | Engineering and Procurement | AEP | 250 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1275_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1275_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1275_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_275_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2025 | 9/30/2019 | N/A | N/A | 6/1/2026 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-276 - moved to TC1 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Withdrawn | PENELEC | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1276_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/24/2024 |  | 6/29/2024 |  |  | N | No
AF1-277 - moved to TC1 | Lewis Run-Pierce Brook 2 230 kV |  | PA | McKean | Withdrawn | PENELEC | 200 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1277_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/21/2024 |  | 6/29/2024 |  |  | N | No
AF1-278 - moved to TC1 | Lewis Run-Pierce Brook 3 230 kV |  | PA | Mc Kean | Withdrawn | PENELEC | 280 | 80 | 53.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1278_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/21/2024 |  | 6/29/2024 |  |  | N | No
AF1-279 | Carlisle 138 kV |  | OH | Lorain | Withdrawn | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1279_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1279_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1279_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/20/2019 | N/A | N/A |  | 3/6/2023 |  | 12/15/2022 |  |  | N | No
AF1-280 - moved to TC1 | Nelson-Lee County | South Dixon Solar II | IL | Lee | Active | ComEd | 200 | 200 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1280_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1280_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-281 - moved to TC1 | Nelson-Lee County |  | IL | Lee | Withdrawn | ComEd | 220 | 20 | 3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1281_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1281_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 6/24/2024 |  | 12/1/2022 |  |  | N | No
AF1-282 | Stuart-Clinton 345 kV | Nuthatch Solar 5 | OH | Highland | Engineering and Procurement | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1282_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1282_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1282_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_282_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/31/2028 | 9/30/2019 | N/A | N/A | 4/1/2030 |  |  | 5/1/2030 | 5/1/2030 |  | N | No
AF1-283 | Stuart-Clinton 345 kV | Highland 3 Solar | OH | Highland | Engineering and Procurement | Dayton | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1283_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1283_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1283_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_283_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2030 | 9/30/2019 | N/A | N/A | 4/1/2030 |  |  | 5/1/2030 | 5/1/2030 |  | N | No
AF1-284 | Penn Mar-Garrett 138 kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1284_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/20/2020 |  | 12/31/2021 |  |  | N | No
AF1-285 | Gunn Road 345 kV | Scioto Solar | OH | Hardin | Under Construction | AEP | 130 | 100 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1285_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1285_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1285_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_285_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_285_csa.pdf | Document Posted | N/A | N/A | 4/1/2026 | 10/2/2019 | N/A | N/A | 5/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AF1-286 | East Sayre 34.5 kV II |  | PA | Bradford | Withdrawn | PENELEC | 13.6 | 13.6 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1286_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1286_imp.htm | Withdrawn |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1286_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1286_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 9/26/2023 |  | 2/28/2026 | 2/28/2026 |  | N | No
AF1-287 | Edinboro South 34.5 kV II | Crawford Solar III | PA | Crawford | Suspended | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1287_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1287_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1287_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1287_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2019 | N/A | N/A | 12/31/2026 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
AF1-288 | Curryville-Claysburg 115 kV I |  | PA | Bedford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1288_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 3/18/2020 |  | 3/1/2021 |  |  | N | No
AF1-289 | Curryville-Claysburg 115 kV II |  | PA | Bedford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1289_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 3/18/2020 |  | 3/1/2021 |  |  | N | No
AF1-290 | Feagans Mill-Millville 138 kV | Blake Solar | WV | Jefferson | In Service | APS | 80 | 80 | 40.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1290_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1290_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1290_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_290_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_290_csa.pdf | Document Posted | N/A | N/A | 11/17/2023 | 10/5/2019 | N/A | N/A | 11/28/2023 |  |  | 4/15/2024 | 4/15/2024 | 3/6/2024 | N | No
AF1-291 | Tyler 34.5 kV | Chester Solar Technology Park | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1291_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1291_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1291_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1291_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A | 7/30/2027 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AF1-291A | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 80 | 10 | 6 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1291a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1291a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1291a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_291a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_291a_csa.pdf | Document Posted | N/A | N/A | 10/20/2024 | 10/1/2019 | N/A | N/A | 11/17/2024 |  |  | 7/1/2024 | 7/1/2024 | 12/27/2024 | N | No
AF1-292 | Fields 34.5kV | Jarratt Solar | VA | Greensville | Engineering and Procurement | Dominion | 14.9 | 14.9 | 8.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1292_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1292_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1292_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1292_wmpa.pdf | Not Required | N/A | N/A | 5/31/2027 | 9/30/2019 | N/A | N/A | 6/30/2027 |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AF1-293 - moved to TC1 | Kidds Store-Fort Union 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 127.86 | 127.86 | 108.37 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1293_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1293_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/24/2024 |  | 6/30/2022 |  |  | N | No
AF1-294 - moved to TC1 | Jetersville-Ponton 115 kV | Amelia Energy Facility | VA | Amelia | Active | Dominion | 41 | 41 | 22.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1294_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1294_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-295 | Blain 115 kV II |  | PA | Perry | Withdrawn | PENELEC | 72 | 12 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1295_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/25/2020 |  | 12/31/2022 |  |  | N | No
AF1-296 - moved to TC1 | Garden Plain 138 kV | Gipper Wind Farm | IL | Whiteside | Active | ComEd | 190.89 | 190.89 | 33.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1296_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1296_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF1-297 | North Longview 500 kV |  | PA | Greene | Withdrawn | APS | 52.8 | 52.8 | 31.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1297_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1297_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/28/2020 |  | 4/1/2022 |  |  | N | No
AF1-298 | Desoto 345 kV |  | IN | Delaware | Withdrawn | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1298_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/6/2020 |  | 10/31/2023 |  |  | N | No
AF1-299 | Otter Point 34.5 kV I | Fairview Farms II | MD | Harford | In Service | BGE | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1299_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1299_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1299_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1299_wmpa.pdf | Not Required | N/A | N/A | 12/11/2024 | 9/30/2019 | N/A | N/A | 2/13/2025 |  |  | 12/30/2024 | 12/30/2024 | 5/1/2025 | N | No
AF1-300 | Otter Point 34.5 kV II | Fairview Farms I | MD | Harford | In Service | BGE | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1300_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1300_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1300_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1300_wmpa.pdf | Not Required | N/A | N/A | 12/11/2024 | 9/30/2019 | N/A | N/A | 2/13/2025 |  |  | 12/30/2024 | 12/30/2024 | 5/12/2025 | N | No
AF1-301 - moved to TC1 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 117 | 117 | 70 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1301_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1301_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/24/2024 |  | 12/31/2022 |  |  | N | No
AF1-302 | Brookville-Squab Hollow 138 kV |  | PA | Jefferson | Engineering and Procurement | PENELEC | 132 | 42 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1302_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1302_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1302_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_302_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_302_csa.pdf | Document Posted | N/A | N/A | 2/28/2026 | 9/30/2019 | N/A | N/A | 5/10/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AF1-303 | Vernon 115 kV |  | NJ | Atlantic | Withdrawn | JCPL | 107 | 107 | 21.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1303_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/18/2020 |  | 5/31/2022 |  |  | N | No
AF1-304 | Titusville-Grandview 115 kV |  | PA | Venango | Withdrawn | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1304_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1304_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 9/12/2023 |  | 12/31/2023 |  |  | N | No
AF1-305 | Maysville-Masury 138 kV |  | PA | Mercer | Withdrawn | ATSI | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1305_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1305_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/16/2020 |  | 12/31/2023 |  |  | N | No
AF1-306 - moved to TC1 | Squab Hollow 230 kV |  | PA | Elk | Withdrawn | APS | 197.2 | 197.2 | 49.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1306_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/21/2024 |  | 5/31/2023 |  |  | N | No | This project slid to the next queue
AF1-307 | Seward-Jackson Rd 115 kV |  | PA | Indiana | Withdrawn | PENELEC | 66.5 | 66.5 | 39.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1307_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1307_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/28/2020 |  | 12/31/2023 |  |  | N | No
AF1-308 | Waverly 138 kV |  | OH | Pike | Withdrawn | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1308_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/6/2020 |  | 12/31/2023 |  |  | N | No
AF1-309 | North Hanover 115 kV |  | PA | Adams | Withdrawn | ME | 32 | 32 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1309_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1309_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 9/24/2020 |  | 12/31/2023 |  |  | N | No
AF1-310 | Clover 230 kV |  | VA | Halifax | Withdrawn | Dominion | 300 | 300 | 114 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 11/5/2019 |  | 9/30/2022 |  |  | N | No
AF1-311 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1311_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1311_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/16/2023 |  | 9/30/2022 |  |  | N | No
AF1-312 | Dan River-Ridgeway 138 kV |  | NC | Rockingham | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/28/2019 |  | 12/31/2023 |  |  | N | No
AF1-313 | Wes Del-Royerton 138 kV |  | IN | Delaware | Withdrawn | AEP | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1313_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1313_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/9/2020 |  | 12/31/2022 |  |  | N | No
AF1-314 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 212 | 212 | 37.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1314_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 1/22/2025 |  | 9/15/2022 |  |  | N | No
AF1-315 | Cedarville-Ford 138 kV |  | OH | Clermont | Withdrawn | DEOK | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1315_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1315_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/9/2020 |  | 12/31/2023 |  |  | N | No
AF1-316 | Katydid Road 345 kV |  | IL | Grundy | Withdrawn | ComEd | 132 | 132 | 52.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1316_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/13/2020 |  | 6/1/2022 |  |  | N | No
AF1-317 | Electric Junction-Nelson 354 kV |  | IL | Lee | Withdrawn | ComEd | 175 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1317_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1317_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/23/2020 |  | 12/31/2023 |  |  | N | No
AF1-318 - moved to TC1 | Crescent Ridge-Corbin |  | IL | Putnam | Withdrawn | ComEd | 299.97 | 299.97 | 52.7947 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1318_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 6/21/2024 |  | 9/15/2022 |  |  | N | No
AF1-319 | Honda Marysville Tap 69 kV |  | OH | Union | Withdrawn | Dayton | 58 | 58 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1319_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1319_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 11/8/2024 |  | 3/31/2022 |  |  | N | No
AF1-320 | Merrill Creek 115 kV | Harmony Plains Solar and Storage Facility | NJ | Warren | Engineering and Procurement | JCPL | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1320_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1320_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1320_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_320_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_320_csa.pdf | Document Posted | N/A | N/A | 12/8/2028 | 10/1/2019 | N/A | N/A | 1/8/2029 |  |  | 12/28/2026 | 12/28/2026 |  | N | No
AF1-321 | Hooversville 115 kV I | SunEast Hooversville Solar | PA | Somerset | Suspended | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1321_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1321_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1321_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_321_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_321_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 9/30/2019 | N/A | N/A | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF1-322 | Meadow Lake 345 kV | Black Prairie Solar Park | IN | White | Engineering and Procurement | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1322_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1322_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1322_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_322_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/18/2026 | 9/23/2019 | N/A | N/A | 1/18/2027 |  |  | 7/1/2027 | 7/1/2027 |  | N | No
AF1-323 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Withdrawn | AEP | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1323_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1323_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 1/22/2025 |  | 12/12/2022 |  |  | N | No
AF1-324 | Greystone-West Denville 34.5 kV | Denville Storage Facility | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1324_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1324_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_324_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_324_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 12/3/2020 |  | 10/1/2021 | 10/1/2021 |  | N | No
AF1-325 | Sparta-Woodruff's Gap 34.5 kV | Houses Corner Storage | NJ | Sussex | Engineering and Procurement | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1325_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1325_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1325_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_325_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_325_csa.pdf | Document Posted | N/A | N/A | 10/23/2026 | 9/30/2019 | N/A | N/A | 10/30/2026 |  |  | 1/1/2026 | 1/1/2026 |  | N | No
AF1-326 | Pohatcong-Newburgh 34.5 kV | Mansfield #1 | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1326_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1326_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_326_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_326_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 12/3/2020 |  | 10/1/2021 | 10/1/2021 |  | N | No
AF1-327 | Pohatcong-Newburgh 34.5 kV | Mansfield #2 | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1327_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1327_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_327_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_327_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 12/3/2020 |  | 10/1/2021 | 10/1/2021 |  | N | No
AF1-328 | Hackettstown-Pohatcong 34.5 kV | Mansfield #3 | NJ | Warren | Engineering and Procurement | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1328_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1328_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1328_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_328_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_328_csa.pdf | Document Posted | N/A | N/A | 10/23/2026 | 9/30/2019 | N/A | N/A | 10/30/2026 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AF1-329 | Chickahominy 230 kV |  | VA | Charles City | Withdrawn | Dominion | 570 | 250 | 172.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 10/10/2019 |  | 9/1/2021 |  |  | N | No
AF1-330 | Marengo 34.5 kV |  | IL | McHenry | Withdrawn | ComEd | 20 | 20 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1330_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1330_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1330_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1330_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/14/2025 |  | 9/15/2021 |  |  | N | No
AF1-331 | Twombley Road | Rochelle Solar | IL | Ogle | Engineering and Procurement | ComEd | 60 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1331_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1331_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_331_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/31/2026 | 9/30/2019 | N/A | N/A | 1/1/2027 |  |  | 5/27/2028 | 5/27/2028 |  | N | No
AF1-332 | Electric Jct-Nelson |  | IL | Lee | Withdrawn | ComEd | 225 | 50 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1332_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/9/2020 |  | 12/31/2023 |  |  | N | No
AF1-333 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1333_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1333_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1333_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_333_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/30/2027 | 9/27/2019 | N/A | N/A | 8/16/2027 |  |  | 9/30/2027 | 9/30/2027 |  | N | No
AF1-334 | Northkill 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1334_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1334_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 8/4/2022 |  | 3/1/2021 |  |  | N | No
AF1-335 | Northkill 230 kV |  | PA | Berks | Withdrawn | ME | 101.2 | 101.2 | 60.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1335_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1335_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 1/15/2021 |  | 3/1/2021 |  |  | N | No
AF1-336 | Northkill 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1336_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1336_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 8/4/2022 |  | 3/1/2021 |  |  | N | No
AF1-337 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1337_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1337_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1337_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_337_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/30/2027 | 9/27/2019 | N/A | N/A | 8/16/2027 |  |  | 9/30/2027 | 9/30/2027 |  | N | No
AF1-338 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1338_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1338_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1338_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_338_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/30/2027 | 9/27/2019 | N/A | N/A | 8/16/2027 |  |  | 9/30/2027 | 9/30/2027 |  | N | No
AF1-339 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1339_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1339_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1339_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_339_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/30/2027 | 9/28/2019 | N/A | N/A | 8/16/2027 |  |  | 9/30/2027 | 9/30/2027 |  | N | No
AF2-001 | Hooversville 115 kV II | SunEast Hooversville Solar | PA | Somerset | Suspended | PENELEC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2001_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2001_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_001_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 10/1/2019 | N/A | N/A | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF2-002 | Hooversville 115 kV III | SunEast Hooversville Solar | PA | Somerset | Suspended | PENELEC | 50 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2002_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2002_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_002_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_002_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 10/1/2019 | N/A | N/A | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF2-003 | Powerton-Mole Creek |  | IL | Marshall | Withdrawn | ComEd | 303 | 303 | 53.328 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2003_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-004 | Beaver 345 kV | West Lorain Power Plant 345 kV | OH | Lorain | Engineering and Procurement | ATSI | 378.2 | 33 | 33 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2004_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2004_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_004_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 10/1/2019 | N/A | N/A | 1/14/2028 |  |  | 6/1/2031 | 6/1/2031 |  | N | No
AF2-005 | Beaver 138 kV | West Lorain 138 kV Power Plant | OH | Lorain | Engineering and Procurement | ATSI | 95.2 | 8 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2005_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_005_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_005_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2019 | N/A | N/A | 11/1/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AF2-006 | Jermyn Tap-Brownell 69 kV |  | PA | Lackawanna | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2006_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  | 4/13/2021 |  | 9/16/2021 |  |  | N | No
AF2-007 | Tinker Tap–East Carbondale 69 kV |  | PA | Lackawanna | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2007_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  | 10/8/2020 |  | 9/15/2021 |  |  | N | No
AF2-008 - moved to TC1 | Sullivan 345 kV | Grain Belt Transmission | IN | Sullivan | Active | AEP | 2000 | 1000 | 500 |  | Capacity | Merchant Transmission |  | DC | 500 FTIR/1000 NFTIR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/af2008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/af2008_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AF2-009 | Queen Street 34.5 kV |  | PA | York | Withdrawn | ME | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2019 | N/A | N/A |  | 1/10/2020 |  | 10/1/2021 |  |  | N | No
AF2-010 - moved to TC1 | Union City-Titusville 115 kV | Union Solar | PA | Erie | Active | PENELEC | 77 | 77 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2010_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-011 | Tait 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 690 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  | 9/3/2020 |  | 5/31/2020 |  |  | N | No
AF2-012 | Tait 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 794 | 104 | 104 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2012_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  | 9/1/2020 |  | 5/28/2021 |  |  | N | No
AF2-013 | Arnold's Corner-Dahlgren 230 kV | Harwood Power | VA | King George | Engineering and Procurement | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2013_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2013_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_013_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2029 | 10/15/2019 | N/A | N/A | 9/1/2029 |  |  | 10/1/2029 | 10/1/2029 |  | N | No
AF2-014 | Maddox Creek 345 kV | Wild Grains Solar | OH | Van Wert | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2014_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2014_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_014_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/1/2027 | 10/18/2019 | N/A | N/A | 11/1/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-015 | Essex-McCarter 230 kV |  | N/A | N/A | Withdrawn | PSEG | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2019 | N/A | N/A |  | 7/28/2021 |  | 10/23/2019 |  |  | EE | No
AF2-016 - moved to TC1 | Lewis 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 240 | 240 | 96 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  | 6/21/2024 |  | 5/31/2023 |  |  | N | No | This project slid to the next queue
AF2-017 | John's Creek 34 kV |  | KY | Pike | Withdrawn | AEP | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2019 | N/A | N/A |  | 3/6/2020 |  | 12/31/2021 |  |  | N | No
AF2-018 | Inez 138 kV | Lynn Bark Energy Center | KY | Martin | Engineering and Procurement | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2018_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2018_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_018_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/15/2028 | 11/1/2019 | N/A | N/A | 1/30/2028 |  |  | 3/30/2028 | 3/30/2028 |  | N | No
AF2-019 | Middle 69 kV | Middle Battery Storage | NJ | Cape May | Engineering and Procurement | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2019_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2019_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_019_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/31/2028 | 11/15/2019 | N/A | N/A | 2/1/2028 |  |  | 4/30/2028 | 4/30/2028 |  | N | No
AF2-020 | Carll's Corner 69 kV | Carll's Corner Battery Storage | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2020_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2020_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_020_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/2/2029 | 11/15/2019 | N/A | N/A | 2/1/2029 | 5/7/2025 |  | 5/31/2029 | 5/31/2029 |  | N | No
AF2-021 - moved to TC1 | Cedar 69 kV |  | NJ | Ocean | Withdrawn | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2021_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  | 5/31/2024 |  | 6/1/2021 |  |  | N | No
AF2-022 | Cumberland 138 kV |  | NJ | Cumberland | Withdrawn | AEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2022_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  | 9/1/2020 | 2 | 6/1/2021 |  |  | N | No
AF2-023 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 42.5 | 42.5 | 17 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  | 10/9/2023 |  | 6/1/2021 |  |  | N | No
AF2-024 | Mickleton 69 kV | Mickleton Battery Storage | NJ | Gloucester | Withdrawn | AEC | 24 | 24 | 9.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2024_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2024_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_024_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 2/29/2028 | 11/15/2019 | N/A | N/A | 3/1/2028 | 5/7/2025 |  | 5/31/2028 | 5/31/2028 |  | N | No
AF2-025 - moved to TC1 | Ontario 69 kV | Missouri Avenue Battery Storage Project | NJ | Atlantic | Engineering and Procurement | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_025_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 2/1/2028 | 11/15/2019 | N/A | N/A | 2/15/2028 |  |  | 4/30/2028 | 4/30/2028 |  | N | No
AF2-026 | Sherman Ave 138 kV |  | NJ | Cumberland | Withdrawn | AEC | 30 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2026_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  | 9/1/2020 |  | 6/1/2021 |  |  | N | No
AF2-027 | Zion Energy Center 345 kV | Zion Energy Center - BESS | IL | Lake | Engineering and Procurement | ComEd | 635 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2027_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_027_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/24/2027 | 11/15/2019 | N/A | N/A | 6/10/2027 |  |  | 8/25/2027 | 8/25/2027 |  | N | No
AF2-028 | Pumphrey 115 kV |  | MD | Baltimore County | Withdrawn | BGE |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/af2028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/af2028_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/af2_028_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/17/2019 | N/A | N/A | 6/1/2025 | 7/12/2024 |  | 6/1/2025 | 6/1/2025 |  | EE | No
AF2-029 | Ronco 500 kV | Fayette Energy Facility | PA | Fayette | Engineering and Procurement | APS | 726 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2029_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2029_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_029_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_029_csa.pdf | Document Posted | N/A | N/A | 10/1/2028 | 10/28/2019 | N/A | N/A | 10/15/2028 |  |  | 10/31/2028 | 10/31/2028 |  | N | No
AF2-030 | Ontelaunee 230 kV | Ontelaunee Power Generating Plant | PA | Berks | Engineering and Procurement | ME | 650 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2030_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_030_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/30/2027 | 10/28/2019 | N/A | N/A | 1/14/2028 |  |  | 2/29/2028 | 2/29/2028 |  | N | No
AF2-031 | Calumet | Calumet BESS | IL | Cook | Engineering and Procurement | ComEd | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2031_imp.html | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_031_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/1/2027 | 10/28/2019 | N/A | N/A | 11/15/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-032 | Kincaid 345 kV | Kincaid PV | IL | Christian | Engineering and Procurement | ComEd | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2032_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2032_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_032_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/15/2027 | 10/28/2019 | N/A | N/A | 9/29/2027 |  |  | 12/9/2027 | 12/9/2027 |  | N | No
AF2-033 | Miami Fort GT 138 kV |  | OH | Hamilton | Withdrawn | DEOK | 1076 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2033_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  | 6/7/2021 |  | 6/1/2021 |  |  | N | No
AF2-034 - moved to TC1 | Kendall 345kV |  | IL | Kendall | Withdrawn | ComEd | 1238.8 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2034_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  | 1/22/2025 |  | 6/1/2021 |  |  | N | No
AF2-035 - moved to TC1 | St. Johns 115 kV | Anna River Solar | VA | Hanover | Active | Dominion | 72 | 72 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2035_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2019 | N/A | N/A |  |  |  | 10/27/2023 |  |  | N | No
AF2-036 | Garner-Northern Neck 115 kV |  | VA | Richmond | Withdrawn | Dominion | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2019 | N/A | N/A |  | 1/23/2020 |  | 10/27/2023 |  |  | N | No
AF2-037 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 94 | 94 | 56.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2019 | N/A | N/A |  | 1/22/2025 |  | 7/1/2021 |  |  | N | No
AF2-038 | Printz 230 kV |  | PA | Delaware | Withdrawn | PECO | 661.5 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2038_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  | 4/20/2021 |  | 6/1/2021 |  |  | N | No
AF2-039 | Shawville-Clearfield 34.5 kV |  | PA | Clearfield | Engineering and Procurement | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2039_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2039_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2039_wmpa.pdf | Not Required | N/A | N/A | 6/1/2026 | 11/29/2019 | N/A | N/A | 7/3/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AF2-040 | Elk Run-Gainesville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2019 | N/A | N/A |  | 6/23/2023 |  | 10/1/2023 |  |  | N | No
AF2-041 - moved to TC1 | Nelson-Electric Junction 345 kV | Steward Creek Solar | IL | Lee | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2041_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2019 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-042 - moved to TC1 | Clover-Rawlings 500 kV | Randolph Solar | VA | Halifax | Active | Dominion | 500 | 500 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2042_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-043 | Suffolk 34.5 kV | Pleasant Hill Solar | VA | City of Suffolk | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2043_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2043_wmpa.pdf | Not Required | N/A | N/A |  | 12/11/2019 | N/A | N/A | 3/31/2023 |  |  | 12/31/2022 | 12/31/2022 | 6/20/2023 | N | No
AF2-044 | Highland-Sammis and Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 940 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/10/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 10/20/2020 | N | No
AF2-045 | Cambria Nug 115 kV | Cambria Energy | PA | Cambria | Withdrawn | PENELEC | 20 | 20 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/13/2019 | N/A | N/A |  | 10/8/2021 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF2-046 - moved to TC1 | Tunis-Mapleton 115 kV | Murphy Solar | NC | Hertford | Active | Dominion | 126 | 126 | 83.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2046_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-047 - moved to TC1 | Creswell-Riders Creek 115 kV |  | NC | Washington | Withdrawn | Dominion | 150 | 150 | 99.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  | 6/24/2024 |  | 6/1/2022 |  |  | N | No
AF2-048 | Rio-Lick 138 kV | Dixon Solar | OH | Jackson | Engineering and Procurement | AEP | 140 | 70 | 46.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2048_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_048_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/21/2026 | 12/19/2019 | N/A | N/A | 1/4/2027 |  |  | 2/28/2028 | 2/28/2028 |  | N | No
AF2-049 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 180 | 60 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2049_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2019 | N/A | N/A |  | 9/12/2023 |  | 12/1/2021 |  |  | N | No
AF2-050 - moved to TC1 | Bear Rock-Johnstown 230 kV | Maple Hill-Fiddlers 1 SP (Bear Rock) | PA | Cambria | Active | PENELEC | 150 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2050_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AF2-051 | Geneva 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2020 | N/A | N/A |  | 4/27/2021 |  | 6/1/2023 |  |  | N | No
AF2-052 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Withdrawn | PENELEC | 55 | 55 | 37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2052_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2020 | N/A | N/A |  | 8/28/2020 |  | 6/1/2023 |  |  | N | No
AF2-053 | Chickahominy 500kV |  | VA | Charles City | Withdrawn | Dominion | 1800 | 200 | 200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/26/2019 | N/A | N/A |  | 1/21/2020 |  | 6/1/2024 |  |  | N | No
AF2-054 | Wan 34.5 kV | Camellia Solar | VA | Gloucester | In Service | Dominion | 19.9 | 19.9 | 11.94 | 19.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2054_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2054_wmpa.pdf | Not Required | N/A | N/A | 12/2/2024 | 1/11/2020 | N/A | N/A | 4/15/2025 |  |  | 8/29/2027 | 8/29/2027 | 4/12/2025 | N | No
AF2-055 | Plaintation Creek 69 kV |  | VA | Northampton | Withdrawn | ODEC | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2055_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2020 | N/A | N/A |  | 6/4/2024 |  | 6/1/2025 |  |  | N | No
AF2-056 - moved to TC1 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2056_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2023 |  |  | N | No
AF2-057 | Grassfield 34.5 kV | Cedar Energy Center | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2057_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2057_wmpa.pdf | Not Required | N/A | N/A |  | 1/22/2020 | N/A | N/A | 11/1/2025 | 11/17/2023 |  | 12/1/2024 | 12/1/2024 |  | N | No
AF2-058 | Fairton 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 2.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2058_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  | 9/1/2020 |  | 3/31/2021 |  |  | Y | No
AF2-059 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 97 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2059_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  | 4/26/2024 |  | 11/30/2022 |  |  | N | No
AF2-060 | Wattsville 12 kV | Scout Storage I | VA | Accomack | Engineering and Procurement | DPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2060_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2060_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2060_wmpa.pdf | Not Required | N/A | N/A | 3/1/2026 | 1/25/2020 | N/A | N/A | 3/1/2026 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AF2-061 | Wattsville 69kV | Scout Energy Storage | VA | Accomack | Withdrawn | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2061_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2061_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/24/2020 | N/A | N/A |  | 11/5/2024 |  | 6/30/2021 |  |  | N | No
AF2-062 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Withdrawn | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2062_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  | 9/3/2020 |  | 5/31/2023 |  |  | N | No
AF2-063 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2063_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2020 | N/A | N/A |  | 1/22/2025 |  | 2/1/2023 |  |  | N | No
AF2-064 | Flanders 115 kV |  | NJ | Warren | Withdrawn | JCPL | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2020 | N/A | N/A |  | 2/20/2020 |  | 12/18/2020 |  |  | N | No
AF2-065 - moved to TC1 | Surry-Hopewell 230 kV |  | VA | Surry | Withdrawn | Dominion | 300 | 150 | 76.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2065_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  | 6/24/2024 |  | 10/21/2021 |  |  | N | No
AF2-066 | West Manchester-Crown 69kV |  | OH | Preble | Withdrawn | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2066_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  | 9/11/2024 |  | 10/3/2022 |  |  | N | No
AF2-067 | West Manchester 69 kV |  | OH | Preble | Withdrawn | Dayton | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2067_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2067_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  | 9/11/2024 |  | 10/3/2022 |  |  | N | No
AF2-068 - moved to TC1 | Jay 138 kV | Rosegold Solar | IN | Blackford | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2068_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-069 - moved to TC1 | Crescent Ridge 138 kV | Lone Tree Wind Farm | IL | Bureau | Active | ComEd | 87.8 | 8.4 | 1.98 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2069_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/4/2021 |  |  | N | No
AF2-070 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Withdrawn | ComEd | 72.6 | 18.15 | 3.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2070_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 1/22/2025 |  | 10/4/2021 |  |  | N | No
AF2-071 | Windsor 230 kV |  | NJ | Mercer | Withdrawn | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2071_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 10/9/2023 |  | 3/1/2023 |  |  | N | No
AF2-072 | Larrabee 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2072_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 2/21/2023 |  | 3/1/2023 |  |  | N | No
AF2-073 | Nucor Steel-Suffolk 230 kV |  | NC | Gates | Withdrawn | Dominion | 90 | 90 | 54.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 7/2/2020 |  | 3/1/2024 |  |  | N | No
AF2-074 | Nucor Steel-Suffolk 230 kV |  | NC | Gates | Withdrawn | Dominion | 130 | 40 | 24.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 7/2/2020 |  | 3/1/2024 |  |  | N | No
AF2-075 | Bartonsville-Meadow Brook 138 kV III | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 130 | 50 | 30 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_075_csa.pdf | Document Posted | N/A | N/A | 10/20/2024 | 2/1/2020 | N/A | N/A | 11/17/2024 |  |  | 7/1/2024 | 7/1/2024 | 12/27/2024 | N | No
AF2-076 | Suffolk-Nucor Steel 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2076_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 7/23/2021 |  | 12/1/2023 |  |  | N | No
AF2-077 | White Marsh 34.5 kV | Winterberry Solar | VA | Gloucester | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2077_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2077_wmpa.pdf | Not Required | N/A | N/A |  | 2/1/2020 | N/A | N/A | 6/26/2024 |  |  | 8/14/2024 | 8/14/2024 | 6/4/2024 | N | No
AF2-078 | Reynolds-Olive #1 345 kV | Honey Creek Solar | IN | White | Engineering and Procurement | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2078_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_078_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/6/2027 | 2/1/2020 | N/A | N/A | 3/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-079 | Greenville-West Milton 138 kV |  | OH | Darke | Withdrawn | Dayton | 165 | 165 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2079_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 9/19/2023 |  | 10/31/2023 |  |  | N | No
AF2-080 - moved to TC1 | Chinquapin-Everetts 230 kV | Brookfield Pitt Solar | NC | Pitt | Active | Dominion | 150 | 70 | 48.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2080_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF2-081 - moved to TC1 | Moyock 230 kV | Currituck Solar | NC | Currituck | Active | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2081_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-082 | Dauphin PG Tie–Dauphin Juniata Tie 69 k | Upper Paxton Solar | PA | Dauphin | Withdrawn | PPL | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2082_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2082_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_082_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 1/31/2020 | N/A | N/A | 6/30/2027 | 6/26/2025 |  | 8/31/2027 | 8/31/2027 |  | N | No
AF2-083 | Kenzie Creek-Stone Lake 69 kV | Gemstone Solar | MI | Cass | Engineering and Procurement | AEP | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2083_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2083_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_083_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_083_csa.pdf | Document Posted | N/A | N/A | 10/1/2027 | 1/31/2020 | N/A | N/A | 11/1/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-084 | Honda-Marysville Tap 69 kV |  | OH | Union | Withdrawn | Dayton | 100 | 42 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 11/8/2024 |  | 12/30/2022 |  |  | N | No
AF2-085 | Midlothian 34.5 kV | Dry Bridge Energy Center | VA | Chesterfield | In Service | Dominion | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2085_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2085_wmpa.pdf | Not Required | N/A | N/A |  | 2/4/2020 | N/A | N/A | 8/29/2023 |  |  | 12/31/2023 | 12/31/2023 | 11/21/2023 | N | No
AF2-086 | Scott Tap-Bowmans Mill Tap 69 kV | Stoneybrook Solar | PA | Columbia | Engineering and Procurement | PPL | 19.6 | 19.6 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2086_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_086_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/30/2027 | 2/3/2020 | N/A | N/A | 10/29/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-087 | East Altoona-Pinecroft 12.47 kV | Antis Solar Facility | PA | Blair | Withdrawn | PENELEC | 7.25 | 7.25 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2087_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2087_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2087_wmpa.pdf | Not Required | N/A | N/A |  | 2/3/2020 | N/A | N/A |  | 11/9/2023 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF2-088 | Shawville-Clearfield 34.5 kV II |  | PA | Clearfield | Engineering and Procurement | PENELEC | 20 | 6.5 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2088_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2088_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2088_wmpa.pdf | Not Required | N/A | N/A | 6/1/2026 | 2/5/2020 | N/A | N/A | 7/3/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AF2-089 | Titusville 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 25 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2089_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2020 | N/A | N/A |  | 8/27/2020 |  | 12/31/2021 |  |  | N | No
AF2-090 | Central Hardin 138 kV |  | KY | Hardin | Withdrawn | EKPC | 110 | 110 | 73.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2090_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2020 | N/A | N/A |  | 12/16/2024 |  | 10/1/2022 |  |  | N | No
AF2-091 | Oak Grove-Dahlgren 230 kV | Gibson Solar I | VA | King George | Engineering and Procurement | Dominion | 134 | 34 | 14.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2091_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_091_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/1/2026 | 2/7/2020 | N/A | N/A | 2/1/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-092 | Snake Spring-Bedford Area 23 kV | Magenta Solar | PA | Bedford | Suspended | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2092_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_092_csa.pdf | Document Posted | N/A | N/A | 5/31/2026 | 2/11/2020 | N/A | N/A | 5/31/2026 |  |  | 8/11/2026 | 8/11/2026 |  | N | No
AF2-093 | Derry 12.47 kV |  | PA | Montour | Withdrawn | PPL | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2093_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2020 | N/A | N/A |  | 8/25/2020 |  | 12/31/2021 |  |  | N | No
AF2-094 | Huntington Jct. 138 kV |  | IN | Huntington | Withdrawn | AEP | 190 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2094_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2094_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  | 1/17/2025 |  | 2/1/2022 |  |  | N | No
AF2-095 - moved to TC1 | Davis Creek 138 kV | Kankakee Solar | IL | Kankakee | Active | ComEd | 144 | 144 | 86.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2095_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-096 - moved to TC1 | Braidwood-East Frankfort 345 kV |  | IL | Will | Withdrawn | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  | 1/22/2025 |  | 5/31/2022 |  |  | N | No
AF2-097 | Fairview East 34.5 kV II |  | PA | Erie | Withdrawn | PENELEC | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2097_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/13/2020 | N/A | N/A |  | 9/21/2020 |  | 12/31/2021 |  |  | N | No
AF2-098 | Crittenden 12 kV |  | KY | Grant | Withdrawn | DEOK | 3.45 | 3.45 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2020 | N/A | N/A |  | 4/30/2020 |  | 12/31/2020 |  |  | Y | No
AF2-099 | Taxville 2 13.2 kV | PA York Garber 2 | PA | York | Withdrawn | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2099_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2099_wmpa.pdf | Not Required | N/A | N/A |  | 1/28/2020 | N/A | N/A |  | 4/8/2024 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF2-100 | Taxville 1 13.2 kV | PA York Garber 1 | PA | York | Withdrawn | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2100_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2100_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2100_wmpa.pdf | Not Required | N/A | N/A |  | 1/28/2020 | N/A | N/A |  | 4/8/2024 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF2-101 | Allen 13.2 kV | PA Cumberland Diehl | PA | Cumberland | Withdrawn | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2101_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2101_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2101_wmpa.pdf | Not Required | N/A | N/A |  | 1/28/2020 | N/A | N/A |  | 4/8/2024 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF2-102 | Germantown 13.2 kV | PA Adams Ramsburg | PA | Adams | Withdrawn | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2102_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2102_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2102_wmpa.pdf | Not Required | N/A | N/A | 12/1/2024 | 1/29/2020 | N/A | N/A | 12/1/2024 | 2/23/2024 |  | 2/1/2025 | 2/1/2025 |  | N | No
AF2-103 | Haviland 138 kV | Northwest Ohio Wind | OH | Paulding | In Service | AEP | 103.15 | 3.15 | 1.32 | 3.15 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/17/2020 | N/A | N/A | 6/30/2025 |  |  | 2/1/2021 | 2/1/2021 | 6/1/2021 | N | No
AF2-104 | Somerset 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2104_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2020 | N/A | N/A |  | 12/8/2020 |  | 6/1/2020 |  |  | N | No
AF2-105 | Morgans Cut-Glen Lyn #2 138 kV | Bella Terra | VA | Pulaski | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2105_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2105_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  | 8/19/2024 |  | 12/31/2026 | 12/31/2026 |  | N | No
AF2-106 | Hazel Hollow-Glen Lyn #1 138 kV | Pulaski Solar | VA | Pulaski | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2106_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2106_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_106_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/26/2027 | 1/31/2020 | N/A | N/A | 12/10/2027 |  |  | 2/28/2028 | 2/28/2028 |  | N | No
AF2-107 | Clifford 138 kV | Amherst Solar | VA | Amherst | Engineering and Procurement | AEP | 50 | 50 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2107_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_107_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2028 | 2/24/2020 | N/A | N/A | 10/23/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AF2-108 | Locks 34.5 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2108_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2020 | N/A | N/A |  | 8/2/2022 |  | 10/31/2022 |  |  | N | No
AF2-109 | Church 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2109_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2020 | N/A | N/A |  | 8/21/2020 |  | 10/31/2022 |  |  | N | No
AF2-110 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Suspended | Dominion | 69 | 20 | 7.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_110_csa.pdf | Document Posted | N/A | N/A | 5/7/2026 | 2/27/2020 | N/A | N/A | 5/29/2026 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AF2-111 - moved to TC1 | North Clark-Spurlock 345 kV | Goldfinch Solar | KY | Mason | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2111_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-112 | Oakland-Gorman 69 kV | Webb Solar | MD | Garrett | Withdrawn | APS | 10 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2112_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 9/5/2023 |  | 6/1/2022 |  |  | N | No
AF2-113 | Clinton-Stuart 345 kV |  | OH | Clinton | Withdrawn | Dayton | 375 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 3/26/2020 |  | 12/31/2022 |  |  | N | No
AF2-114 | Old Chapel-Millville 138 kV II |  | WV | Jefferson | Withdrawn | APS | 92.5 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2114_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2114_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 10/17/2024 |  | 9/30/2022 |  |  | N | No
AF2-115 - moved to TC1 | Jetersville-Ponton 115 kV | Amelia Energy Facility | VA | Amelia | Active | Dominion | 66 | 25 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2115_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-116 | McConnellsburg 138 kV | Great Cove Solar | PA | Fulton | Withdrawn | APS | 90 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2116_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2116_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 11/20/2024 |  | 9/30/2027 | 9/30/2027 |  | N | No
AF2-117 | Warfordsburg-McConnellsburg 138 kV | Spring Run Solar | PA | Fulton | Withdrawn | APS | 70 | 70 | 46.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2117_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2117_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 12/18/2024 |  | 12/31/2030 | 12/31/2030 |  | N | No
AF2-118 | Gilbert-Morris Park (A-27) 34.5 kV II |  | NJ | Warren | Withdrawn | JCPL | 39.99 | 19.99 | 3.999 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2118_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 9/15/2020 |  | 3/31/2021 |  |  | N | No
AF2-119 | Bristers-Sowego 115 kV |  | VA | Fauquier | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2119_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2119_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 6/7/2024 |  | 12/12/2022 |  |  | N | No
AF2-120 - moved to TC1 | Garner-Northern Neck 115 kV | Cerulean Solar and Mulberry BESS | VA | Richmond | Active | Dominion | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2120_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_120_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_120_csa.pdf | Document Posted | N/A | N/A | 12/1/2025 | 2/28/2020 | N/A | N/A | 2/6/2026 |  |  | 12/1/2023 |  |  | N | No
AF2-122 | Kirk 138 kV | Union Ridge Solar | OH | Licking | Under Construction | AEP | 107.7 | 107.7 | 64.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2122_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2122_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_122_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 2/29/2020 | N/A | N/A | 11/15/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF2-123 | National-Tangy 138 kV |  | OH | Madison | Withdrawn | ATSI | 49 | 49 | 20.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2123_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 8/14/2023 |  | 12/31/2023 |  |  | N | No
AF2-124 | Kyger Creek-Pierce 345 kV |  | OH | Highland | Withdrawn | OVEC | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2124_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 12/13/2024 |  | 12/31/2023 |  |  | N | No
AF2-125 | Varner 138 kV |  | IN | DeKalb | Withdrawn | AEP | 150 | 54 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2125_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2125_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 10/16/2024 |  | 4/3/2023 |  |  | N | No
AF2-126 - moved to TC1 | Weston 69 kV II | Juliet Energy | OH | Wood | Active | ATSI | 62 | 12 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2126_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-127 | Lockwood Road 138 kV |  | OH | Defiance | Withdrawn | AEP | 68 | 38 | 24.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2127_imp.htm | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_127_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 10/29/2024 |  | 3/31/2022 |  |  | N | No
AF2-128 - moved to TC1 | Crescent Ridge-Corbin 138 kV |  | IL | Lasalle | Withdrawn | ComEd | 79.5 | 79.5 | 13.992 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 6/25/2024 |  | 8/26/2024 |  |  | N | No
AF2-129 | Sharon-Mercer 69 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2129_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2129_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/3/2020 | N/A | N/A |  | 6/9/2023 |  | 6/30/2023 |  |  | N | No
AF2-130 | Cobalt Corners 34.5 kV | Cobalt Solar | PA | Clarion | In Service | PENELEC | 18.9 | 18.9 | 11.34 | 18.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2130_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_130_csa.pdf | Document Posted | N/A | N/A | 3/24/2025 | 3/4/2020 | N/A | N/A | 5/14/2025 |  |  | 6/15/2025 | 6/15/2025 | 5/26/2025 | N | No
AF2-131 | Cooper 34.5 kV |  | PA | York | Withdrawn | PECO | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2131_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  | 8/25/2020 |  | 6/1/2022 |  |  | N | No
AF2-132 | Reynolds-Olive #1 345 kV | Mammoth Central Energy Center | IN | Pulaski | Engineering and Procurement | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2132_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2132_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_132_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/8/2026 | 3/4/2020 | N/A | N/A | 6/1/2026 |  |  | 2/9/2027 | 2/9/2027 |  | N | No
AF2-133 | Reynolds-Olive #2 345 kV | Mammoth South Energy Center | IN | Pulaski | Engineering and Procurement | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2133_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_133_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2026 | 3/4/2020 | N/A | N/A | 6/15/2026 |  |  | 2/6/2027 | 2/6/2027 |  | N | No
AF2-134 | Olive-Reynolds #2 345 kV | Mammoth North Solar Project | IN | Starke | In Service | AEP | 400 | 100 | 60 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2134_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_134_csa.pdf | Document Posted | N/A | N/A | 8/20/2024 | 3/7/2020 | N/A | N/A | 10/14/2024 |  |  | 6/30/2024 | 6/30/2024 | 10/21/2024 | N | No
AF2-135 | Rockwood-Confluence 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2135_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2020 | N/A | N/A |  | 9/11/2020 |  | 6/1/2022 |  |  | N | No
AF2-136 | Swamp 230 kV |  | NC | Perquimans | Withdrawn | Dominion | 208 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2136_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2020 | N/A | N/A |  | 9/12/2023 |  | 11/1/2022 |  |  | N | No
AF2-137 | Marysville-Sorenson 765 kV | Grange Solar | OH | Logan | Withdrawn | AEP | 500 | 500 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2137_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2137_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/6/2020 | N/A | N/A |  | 2/27/2025 |  | 12/31/2029 | 12/31/2029 |  | N | No
AF2-138 | Flanders-West Wharton 34.5 kV | Mount Olive Solar Farm | NJ | Morris | In Service | JCPL | 19.8 | 19.8 | 8.32 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2138_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2138_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_138_csa.pdf | Document Posted | N/A | N/A | 11/1/2022 | 3/10/2020 | N/A | N/A | 11/1/2022 |  |  | 5/31/2023 | 5/31/2023 | 3/15/2023 | N | No
AF2-139 | Gilbert-Warren Glen 34.5 kV | Holland Solar Farm | NJ | Hunterdon | In Service | JCPL | 16.3 | 8.8 | 3.7 | 16 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2139_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_139_csa.pdf | Document Posted | N/A | N/A |  | 3/10/2020 | N/A | N/A |  |  |  | 8/31/2022 | 8/31/2022 | 7/28/2022 | N | No
AF2-140 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 907 | 0 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2140_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_140_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 9/1/2024 | 9/1/2024 | 12/31/2021 | N | No
AF2-141 | Lick Run 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 100 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2141_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2141_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2020 | N/A | N/A |  | 7/11/2024 |  | 7/1/2023 |  |  | N | No
AF2-142 - moved to TC1 | Nevada 345 kV | Otter Creek Wind Farm | IL | Lasalle | Active | ComEd | 300 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2142_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-143 - moved to TC1 | Powerton-Nevada 345 kV | Osagrove Flats Wind | IL | Lasalle | Active | ComEd | 300 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2143_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-144 | Powhatan 34.5 kV | Scott 1 BESS | VA | Powhatan | In Service | Dominion | 17 | 17 | 10.2 | 17 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2144_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2144_wmpa.pdf | Not Required | N/A | N/A |  | 3/12/2020 | N/A | N/A | 5/31/2023 |  |  | 6/1/2023 | 6/1/2023 | 6/1/2023 | N | No
AF2-145 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Withdrawn | PPL | 194.1 | 51 | 30.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2145_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2145_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/12/2020 | N/A | N/A |  | 8/30/2023 |  | 12/31/2021 |  |  | N | No
AF2-146 | Hill Valley-Valley REC 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2146_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  | 4/16/2021 |  | 9/1/2023 |  |  | N | No
AF2-147 | McVeytown-Strodes Mill 46 kV |  | PA | Mifflin | Withdrawn | PENELEC | 13.1 | 13.1 | 7.86 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2147_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  | 8/23/2020 |  | 9/1/2023 |  |  | N | No
AF2-148 | Shade Gap-Three Springs KTS 23 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2148_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  | 4/16/2021 |  | 9/1/2023 |  |  | N | No
AF2-149 | Sharp Road 69 kV | Frasier Solar | OH | Knox | Engineering and Procurement | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2149_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2149_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_149_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_149_csa.pdf | Document Posted | N/A | N/A | 11/1/2027 | 3/12/2020 | N/A | N/A | 11/15/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AF2-150 | Galion 138 kV | Blossom Solar | OH | Morrow | Under Construction | ATSI | 88 | 88 | 36.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2150_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2150_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_150_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_150_csa.pdf | Document Posted | N/A | N/A | 1/31/2026 | 3/13/2020 | N/A | N/A | 2/14/2026 |  |  | 7/31/2026 | 7/31/2026 |  | N | No
AF2-151 | Dillsburg 13.2 kV | PA York Hess | PA | York | Withdrawn | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2151_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2151_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2151_wmpa.pdf | Not Required | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 10/15/2024 |  | 9/30/2022 | 9/30/2022 |  | N | No
AF2-152 | Morgantown CT5 230 kV |  | MD | Charles | Deactivated | PEPCO | 56 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2152_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 2/28/2021 |  |  | N | No
AF2-153 | Morgantown CT4 230 kV |  | MD | Charles | Deactivated | PEPCO | 56 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2153_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 2/28/2021 |  |  | N | No
AF2-154 | Dickerson H2 CT 230 kV | Dickerson HCT1, HCT2, DCT1 | MD | Montgomery | In Service | PEPCO | 173 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2154_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_154_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 4/1/2023 | 4/1/2023 | 5/31/2023 | N | No
AF2-155 | Chalk Point CT3-CT6 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 461.9 | 13 | 13 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2155_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 2/28/2021 |  |  | N | No
AF2-156 | Chalk Point CT2 69 kV | Chalk Point CT 2 | MD | Prince George's | In Service | PEPCO | 30 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2156_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_156_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 6/22/2023 | 6/22/2023 | 5/31/2023 | N | No
AF2-157 | Chalk Point CT1 69 kV |  | MD | Prince George's | Withdrawn | PEPCO | 20 | 0 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2157_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 2/28/2021 |  |  | N | No
AF2-158 | Chalk Point Unit 4 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 589.3 | 4 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2158_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 2/28/2021 |  |  | N | No
AF2-159 | Chalk Point ST3 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 598.17 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 2/28/2021 |  |  | N | No
AF2-160 | Brunot Island 138 kV |  | PA | Allegheny | Withdrawn | DL | 283.5 | 3.5 | 3.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2160_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 12/13/2022 |  | 4/1/2020 |  |  | N | No
AF2-161 | Mount Rock 12.47 kV | Ritner Solar | PA | Cumberland | Withdrawn | PPL | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2161_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2161_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2161_wmpa.pdf | Not Required | N/A | N/A |  | 3/16/2020 | N/A | N/A |  | 10/15/2024 |  | 4/17/2023 | 4/17/2023 |  | N | No
AF2-162 | Keystone-Desoto 345 kV | Lake Trout Solar | IN | Blackford | Engineering and Procurement | AEP | 245 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2162_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2162_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_162_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_162_csa.pdf | Document Posted | N/A | N/A | 10/29/2027 | 3/16/2020 | N/A | N/A | 11/15/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AF2-163 | Lick Run 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 34.5 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2163_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2020 | N/A | N/A |  | 9/12/2023 |  | 10/3/2022 |  |  | N | No
AF2-164 - moved to TC1 | Handsome Lake 345 kV |  | PA | Venango | Withdrawn | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2164_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2020 | N/A | N/A |  | 6/21/2024 |  | 9/15/2023 |  |  | N | No
AF2-165 | Clark Summit-Emlenton 34.5 kV | Cardinal Solar | PA | Venango | In Service | PENELEC | 18.9 | 18.9 | 11.34 | 18.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2165_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2165_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2165_wmpa.pdf | Not Required | N/A | N/A | 12/10/2024 | 3/19/2020 | N/A | N/A | 7/15/2025 |  |  | 7/31/2025 | 7/31/2025 | 7/22/2025 | N | No
AF2-166 | Emlenton 34.5 kV | Long Bridge | PA | Venango | Suspended | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2166_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2166_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_166_csa.pdf | Document Posted | N/A | N/A | 6/1/2026 | 3/18/2020 | N/A | N/A | 6/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF2-167 | Eaton Crest-Red Bank 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2167_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2020 | N/A | N/A |  | 9/4/2020 |  | 9/30/2021 |  |  | N | No
AF2-168 | Princeton University 69 kV | Princeton University Generating Facility | NJ | Mercer | In Service | PSEG | 5 | 5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas; Solar; Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2168_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_168_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_168_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2020 | N/A | N/A |  |  |  | 4/27/2023 | 4/27/2023 | 3/2/2022 | N | No
AF2-169 | BL England 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 552 | 552 | 155 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 6/9/2020 |  | 6/1/2023 |  |  | N | No
AF2-170 | Erie West-Springboro 34.5 kV |  | PA | Erie | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 9/4/2020 |  | 9/15/2022 |  |  | N | No
AF2-171 - moved to TC1 | Madisonville 115 kV |  | VA | Prince Edward | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2171_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 1/22/2025 |  | 3/31/2022 |  |  | N | No
AF2-172 | Newport 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2172_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 1/14/2021 |  | 6/1/2022 |  |  | N | No
AF2-173 - moved to TC1 | Desoto 345 kV | Esker Solar Park | IN | Delaware | Active | AEP | 340 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-174 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 11 | 11 | 4.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2174_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 4/26/2021 |  | 9/30/2021 |  |  | N | No
AF2-175 | Straban 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2175_imp.htm | Withdrawn |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2175_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2175_wmpa.pdf | Not Required | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 9/19/2023 |  | 2/1/2025 | 2/1/2025 |  | N | No
AF2-176 - moved to TC1 | Masury-Maysville 138 kV |  | PA | Mercer | Withdrawn | ATSI | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2176_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  | 6/21/2024 |  | 9/15/2022 |  |  | N | No
AF2-177 - moved to TC1 | Sorenson-DeSoto #2 345 kV | Blackford County Wind Farm | IN | Blackford | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2177_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-178 | Roxbury 23 kV II | Whitetail Solar 1 | PA | Franklin | In Service | PENELEC | 13.5 | 0 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_178_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 1/12/2021 | N | No
AF2-179 | St. Thomas-Mercersburg 34.5 kV II | Whitetail Solar 2 | PA | Franklin | In Service | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2179_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_179_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 1/12/2021 | N | No
AF2-180 | St. Thomas-Guilford 34.5 kV II | St Thomas Township Solar Facility | PA | Franklin | In Service | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2180_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_180_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 1/12/2021 | N | No
AF2-181 | Lexington Park 69 kV |  | MD | St. Mary's | Withdrawn | SMECO | 20 | 0 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2181_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  | 9/14/2020 |  | 9/1/2021 |  |  | N | No
AF2-182 - moved to TC1 | Nelson-Lee County 345 kV II |  | IL | Lee | Active | ComEd | 500 | 300 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2182_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-183 - moved to TC1 | Nelson-Lee County 345 kV |  | IL | Lee | Withdrawn | ComEd | 600 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2183_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  | 6/24/2024 |  | 12/1/2022 |  |  | N | No
AF2-184 | McConnelsburg-Mercersburg 34 kV II |  | PA | Franklin | In Service | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_184_csa.pdf | Document Posted | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/7/2020 |  | 5/1/2023 | N | No
AF2-185 | Mercersburg-Milnor 34.5 kV II | Elk Hill Solar 2 | PA | Franklin | In Service | APS | 15 | 0 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 1/4/2021 | N | No
AF2-186 | South Cecil 69 kV |  | OH | Paulding | Withdrawn | AEP | 45 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2186_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  | 7/18/2023 |  | 12/31/2023 |  |  | N | No
AF2-187 | Brookside-Cloverdale 138 kV | Canal Road | OH | Wayne | Engineering and Procurement | ATSI | 120 | 120 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2187_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2187_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_187_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/30/2027 | 3/22/2020 | N/A | N/A | 10/18/2027 |  |  | 11/30/2027 | 11/30/2027 |  | N | No
AF2-188 | Reynolds-Meadow Lake #1 345 kV |  | IN | White | Withdrawn | AEP | 112 | 112 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2188_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  | 9/14/2023 |  | 6/30/2023 |  |  | N | No
AF2-189 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2189_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  | 9/17/2021 |  | 6/30/2023 |  |  | N | No
AF2-190 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Withdrawn | AEP | 260 | 260 | 156 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2190_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  | 9/10/2020 |  | 6/30/2023 |  |  | N | No
AF2-191 | New Carlisle 138 kV |  | IN | St. Joseph | Withdrawn | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2191_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  | 10/16/2024 |  | 6/30/2023 |  |  | N | No
AF2-192 | Frenchtown Solar-West Flemington 34.5 kV | Barbertown Solar | NJ | Hunterdon | Suspended | JCPL | 7 | 7 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2192_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2192_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2192_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_192_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_192_csa.pdf | Document Posted | N/A | N/A | 2/13/2026 | 3/23/2020 | N/A | N/A | 3/2/2026 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
AF2-193 - moved to TC1 | Indian River 230 kV I |  | DE | Sussex | Withdrawn | DPL | 440 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2193_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2193_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  | 6/21/2024 |  | 10/31/2026 |  |  | N | No
AF2-194 - moved to TC1 | Indian River 230 kV II |  | DE | Sussex | Withdrawn | DPL | 880 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2194_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  | 6/21/2024 |  | 10/31/2026 |  |  | N | No
AF2-195 | Queen Street 115 kV |  | PA | York | Withdrawn | ME | 171.7 | 171.7 | 68.68 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2195_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  | 9/11/2020 |  | 12/31/2022 |  |  | N | No
AF2-196 | Cedar Neck 69 kV II |  | DE | Sussex | Withdrawn | DPL | 150 | 30 | 9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2196_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  | 8/1/2022 |  | 6/1/2022 |  |  | N | No
AF2-197 | East Towanda 115 kV |  | PA | Bradford | Withdrawn | PENELEC | 100.8 | 100.8 | 40.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2197_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  | 9/8/2023 |  | 10/1/2022 |  |  | N | No
AF2-198 | Heath 69 kV |  | OH | Licking | Withdrawn | AEP | 22.4 | 22.4 | 8.96 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2198_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2198_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  | 9/8/2023 |  | 10/15/2022 |  |  | N | No
AF2-199 - moved to TC1 | Nelson-Electric Junction 345 kV | Steward Creek Solar | IL | Lee | Active | ComEd | 400 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2199_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2199_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-200 - moved to TC1 | Nelson-Electric Junction 345 kV | Steward Creek Solar | IL | Lee | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2200_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2200_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-201 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 199 | 199 | 51.4 |  | Capacity | Generation Interconnection | Wind; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2201_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  | 1/22/2025 |  | 5/31/2023 |  |  | N | No
AF2-202 | Landis 12 V |  | NJ | Salem | Withdrawn | AEC | 2.7 | 2.7 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2202_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  | 9/9/2020 |  | 6/30/2021 |  |  | N | No
AF2-203 | Rohrsburg 12.5 kV |  | PA | Columbia | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2203_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2203_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 4/12/2021 |  | 5/31/2022 |  |  | N | No
AF2-204 | Van Buren-Delaware 138 kV |  | IN | Grant | Withdrawn | AEP | 110 | 110 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2204_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2204_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2204_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/24/2020 | N/A | N/A |  | 1/17/2025 |  | 6/1/2023 |  |  | N | No
AF2-205 | Olive-Reynolds #2 345 kV | Moss Creek Solar | IN | Pulaski | Engineering and Procurement | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2205_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2205_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_205_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/22/2026 | 3/25/2020 | N/A | N/A | 1/15/2027 |  |  | 3/22/2027 | 3/22/2027 |  | N | No
AF2-206 | Larrabee-Point Pleasant 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 15.4 | 15.4 | 6.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2206_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  | 9/11/2020 |  | 12/31/2021 |  |  | N | No
AF2-207 | Nelson 69 kV |  | DE | Sussex | Withdrawn | DPL | 50.4 | 50.4 | 20.16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2207_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2207_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  | 9/12/2023 |  | 10/15/2022 |  |  | N | No
AF2-208 | Colora 230 kV |  | MD | Cecil | Withdrawn | DPL | 100.8 | 100.8 | 40.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2208_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2208_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  | 9/1/2023 |  | 10/15/2022 |  |  | N | No
AF2-209 - moved to TC1 | South Hicksville-Sowers 138 kV |  | OH | Defiance | Withdrawn | AEP | 140 | 140 | 19.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2209_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2209_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 1/22/2025 |  | 6/2/2023 |  |  | N | No
AF2-210 | Foster-Garver Road 345 kV |  | OH | Pickaway | Withdrawn | DEOK | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2210_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 3/8/2021 |  | 12/31/2023 |  |  | N | No
AF2-211 | College Corner 138 kV |  | IN | Henry | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2211_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2211_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 4/15/2021 |  | 12/31/2023 |  |  | N | No
AF2-212 | Shelby 138 kV |  | IN | Jay | Withdrawn | Dayton | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2212_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2212_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 4/15/2021 |  | 12/31/2023 |  |  | N | No
AF2-213 | Zions View-Smith Street 115 kV |  | PA | York | Withdrawn | ME | 81.2 | 81.2 | 32.48 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2213_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2213_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 8/14/2023 |  | 10/15/2022 |  |  | N | No
AF2-214 | Heartsease DP-Anaconda 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 151.2 | 151.2 | 60.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2214_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 8/24/2020 |  | 12/2/2022 |  |  | N | No
AF2-215 | Saint Thomas-LeMasters Junction 34.5 kV | Mercersburg Road Solar | PA | Franklin | Withdrawn | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2215_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2215_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2215_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2215_wmpa.pdf | Not Required | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 3/1/2024 |  | 4/12/2024 | 4/12/2024 |  | N | No
AF2-216 | Blue Jacket-Kirby 138 kV |  | OH | Union | Withdrawn | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2216_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 9/3/2020 |  | 8/30/2024 |  |  | N | No
AF2-217 | Hyatt-Marysville 345 kV |  | OH | Union | Withdrawn | AEP | 220 | 220 | 132 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2217_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 9/3/2020 |  | 8/30/2024 |  |  | N | No
AF2-218 | Gettysburg 69 kV |  | OH | Darke | Withdrawn | Dayton | 49.99 | 49.99 | 29.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2218_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 8/28/2020 |  | 8/30/2024 |  |  | N | No
AF2-219 |  |  | NC | Halifax | Withdrawn | Dominion | 58 | 58 | 38.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 4/22/2020 |  | 12/31/2023 |  |  | N | No
AF2-220 | Hickman-River Bend 69 kV |  | VA | Pulaski | Withdrawn | AEP | 37 | 37 | 22.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2220_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 8/27/2020 |  | 6/30/2023 |  |  | N | No
AF2-221 | Scalp Level 22.9 kV | Stony Creek Solar | PA | Somerset | Suspended | PENELEC | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2221_imp.html | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2221_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2221_wmpa.pdf | Not Required | N/A | N/A |  | 3/25/2020 | N/A | N/A | 8/1/2025 |  |  | 10/1/2025 | 10/1/2025 |  | N | No
AF2-222 - moved to TC1 | Madisonville DP-Twitty's Creek 115 kV | Courthouse Solar | VA | Charlotte | Active | Dominion | 167 | 167 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2222_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2222_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_222_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_222_csa.pdf | Document Posted | N/A | N/A | 12/31/2026 | 3/25/2020 | N/A | N/A | 3/31/2027 |  |  | 5/31/2023 |  |  | N | No
AF2-223 | Marysville 345 kV |  | OH | Union | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2223_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2223_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 9/14/2023 |  | 10/1/2023 |  |  | N | No
AF2-224 | Allen 345 kV | Flatrock Creek Solar I | IN | Allen | Engineering and Procurement | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2224_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2224_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2224_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_224_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/1/2028 | 3/26/2020 | N/A | N/A | 5/15/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AF2-225 - moved to TC1 | McLean 345 kV | Bright Stalk Generating Facility | IL | McLean | Active | ComEd | 500 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2225_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2225_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-226 - moved to TC1 | Katydid Road 345 kV | Top Crop Generating Facility | IL | Lasalle | Active | ComEd | 350 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2226_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2226_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-227 | Martins Creek–Cherry Hill 69 kV |  | PA | Northampton | Withdrawn | PPL | 63.75 | 63.75 | 38.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2227_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 9/13/2023 |  | 6/30/2023 |  |  | N | No
AF2-228 | Brunner Island 13.8 kV |  | PA | York | Withdrawn | PPL | 61 | 61 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2228_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2228_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 8/8/2023 |  | 6/30/2023 |  |  | N | No
AF2-229 | Roxbury 23 kV | Gobbler Knob | PA | Cumberland | Engineering and Procurement | PENELEC | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2229_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2229_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2229_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_229_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 8/31/2027 | 3/26/2020 | N/A | N/A | 9/14/2027 |  |  | 11/30/2027 | 11/30/2027 |  | N | No
AF2-230 | Lock 34 kV |  | PA | Montgomery | Withdrawn | PECO | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2230_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2230_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 8/25/2020 |  | 6/1/2020 |  |  | N | No
AF2-231 | Belleville 12.47 kV |  | PA | Mifflin | Withdrawn | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2231_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2231_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 10/19/2020 |  | 6/1/2020 |  |  | N | No
AF2-232 | Bowmanns Mill Tap-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 75 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2232_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2232_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 9/13/2023 |  | 12/15/2021 |  |  | N | No
AF2-233 | Penns-Richfield Tie #1 69 kV | Washington East Solar | PA | Snyder | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2233_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2233_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2233_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_233_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/30/2026 | 3/26/2020 | N/A | N/A | 10/30/2026 |  |  | 12/30/2026 | 12/30/2026 |  | N | No
AF2-234 | Sunbury Yard #1-Richfield Tie #2 69 kV | Washington West Solar | PA | Snyder | Engineering and Procurement | PPL | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2234_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2234_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2234_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_234_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/30/2026 | 3/26/2020 | N/A | N/A | 10/30/2026 |  |  | 12/30/2026 | 12/30/2026 |  | N | No
AF2-235 | Titusville-Oil Creek 34.5 kV | Big Bell Solar | PA | Crawford | Withdrawn | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2235_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2235_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2235_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_235_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/30/2027 | 3/27/2020 | N/A | N/A | 6/7/2027 | 8/28/2025 |  | 7/31/2027 | 7/31/2027 |  | N | No
AF2-236 | Jamestown-Hartstown 69 kV |  | PA | Crawford | Withdrawn | ATSI | 28 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2236_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 9/14/2020 |  | 2/15/2023 |  |  | N | No
AF2-237 | Union City-Cambridge Springs 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 30 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2237_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 9/14/2020 |  | 1/1/2023 |  |  | N | No
AF2-238 | Mansfield-South Troy 34.5 kV | Farmers Valley Solar | PA | Bradford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2238_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2238_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2238_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_238_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/30/2027 | 3/26/2020 | N/A | N/A | 5/14/2027 |  |  | 7/31/2027 | 7/31/2027 |  | N | No
AF2-239 | Wyalusing-Hollenback WRC 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 20 | 20 | 11.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2239_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2239_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 3/25/2021 |  | 11/30/2021 |  |  | N | No
AF2-240 | North Orwell 12.47 kV |  | PA | Bradford | Withdrawn | PENELEC | 7 | 7 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2240_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2240_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 3/19/2021 |  | 11/30/2021 |  |  | N | No
AF2-241 | Athens-Milan 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 20 | 20 | 11.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2241_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2241_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  | 3/29/2021 |  | 11/30/2021 |  |  | N | No
AF2-242 | Wharton 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 80 | 80 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2242_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2242_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 3/25/2021 |  | 9/30/2023 |  |  | N | No
AF2-243 | Clark Summit 34.5 kV | Pearl Solar | PA | Venango | Withdrawn | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2243_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2243_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2243_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2243_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 7/3/2026 | 3/21/2025 |  | 9/2/2026 | 9/2/2026 |  | N | No
AF2-244 | Powhatan 34.5 kV |  | VA | Powhatan | Withdrawn | Dominion | 15 | 15 | 9.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2244_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 1/6/2021 |  | 3/31/2023 |  |  | N | No
AF2-245 | Spurlock-Flemingsburg 138 kV |  | KY | Mason | Withdrawn | EKPC | 132 | 132 | 79.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2245_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 8/31/2020 |  | 6/1/2023 |  |  | N | No
AF2-246 | Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 58 | 58 | 38.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/16/2020 |  | 12/29/2023 |  |  | N | No
AF2-247 | Bustleton 13.2 kV | FLR Florence Landfill | NJ | Burlington | In Service | PSEG | 5 | 5 | 2.1 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2247_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2247_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_247_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_247_csa.pdf | Document Posted | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/30/2022 | 6/30/2022 | 3/2/2022 | N | No
AF2-248 | Edgewood 12 kV I |  | MD | Wicomico | Withdrawn | DPL | 7.2 | 7.2 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2248_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2248_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/21/2021 |  | 6/1/2020 |  |  | N | No
AF2-249 | Edgewood 12 kV II | Citron Storage | MD | Wicomico | Withdrawn | DPL | 3 | 3 | 0.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2249_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2249_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2249_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2249_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 2/28/2025 | 7/11/2024 |  | 11/30/2023 | 11/30/2023 |  | N | No
AF2-250 | Edgewood 12 kV III | Kumquat Solar | MD | Wicomico | In Service | DPL | 1.95 | 1.95 | 1.1 | 1.95 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2250_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2250_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2250_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2250_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/31/2022 | 7/31/2022 | 10/19/2022 | N | No
AF2-251 | Susquehanna unit 1 230 kV |  | PA | Luzerne | Withdrawn | PPL | 1310 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2251_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2251_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 11/30/2022 |  | 8/1/2020 |  |  | N | No
AF2-252 | Blue Mound 345 kV | Twin Groves Storage I | IL | McLean | Engineering and Procurement | ComEd | 248 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2252_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2252_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_252_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/1/2027 | 3/27/2020 | N/A | N/A | 12/1/2027 |  |  | 1/28/2028 | 1/28/2028 |  | N | No
AF2-253 | McClelland-Shenango 345 kV |  | PA | Lawrence | Withdrawn | ATSI | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2253_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 9/14/2020 |  | 6/1/2022 |  |  | N | No
AF2-254 | Cookstown-New Lisbon 34.5 kV | NJ Land Phase II | NJ | Burlington | Suspended | JCPL | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2254_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2254_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_254_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_254_csa.pdf | Document Posted | N/A | N/A | 4/1/2025 | 3/27/2020 | N/A | N/A | 5/1/2025 |  |  | 6/1/2025 | 6/1/2025 |  | N | No
AF2-255 | Iron Bridge 34.5 kV | Bradley Ridge Solar | VA | Chesterfield | Withdrawn | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2255_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2255_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2255_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2255_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 5/19/2022 |  | 11/30/2023 | 11/30/2023 |  | N | No
AF2-256 | Tyler 34.5 kV | Bradley Bridge Solar | VA | Chesterfield | Withdrawn | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2256_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2256_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2256_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2256_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 5/19/2022 |  | 11/30/2023 | 11/30/2023 |  | N | No
AF2-257 | Tyler 34.5 kV |  | VA | Chesterfield | Withdrawn | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2257_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2257_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 5/24/2022 |  | 12/12/2022 |  |  | N | No
AF2-258 | Harrowgate 34.5 kV |  | VA | Chesterfield | Withdrawn | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2258_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2258_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 5/24/2022 |  | 12/12/2022 |  |  | N | No
AF2-259 | Locks 34.5 kV |  | VA | Chesterfield | Withdrawn | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2259_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2259_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 9/8/2023 |  | 12/12/2022 |  |  | N | No
AF2-260 | Stephensburg-Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 85 | 85 | 53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2260_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2260_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2260_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/7/2025 |  | 12/31/2023 |  |  | N | No
AF2-261 | Harwood-Susquehanna #1 230 kV |  | PA | Luzerne | Withdrawn | PPL | 75 | 75 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2261_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 8/28/2020 |  | 11/30/2023 |  |  | N | No
AF2-262 | Freeland #1 Tap-Jeddo-Highland 69 kV |  | PA | Luzerne | Withdrawn | PPL | 45 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2262_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 8/28/2020 |  | 12/31/2023 |  |  | N | No
AF2-263 - moved to TC1 | Shelby 138 kV |  | OH | Shelby | Withdrawn | Dayton | 98 | 98 | 58.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2263_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2263_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 6/21/2024 |  | 7/1/2022 |  |  | N | No
AF2-264 | Tunis 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2264_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 8/24/2020 |  | 3/30/2023 |  |  | N | No
AF2-265 | South Troy-Athens 34.5 kV | Big Pond Solar Power Plant | PA | Bradford | Withdrawn | PENELEC | 15 | 15 | 8.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2265_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2265_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_265_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_265_csa.pdf | Document Posted | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 8/29/2023 |  | 9/1/2022 | 9/1/2022 |  | N | No
AF2-266 | Clover 230 kV |  | VA | Charlotte | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2266_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2266_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 3/29/2021 |  | 7/1/2022 |  |  | N | No
AF2-267 | Lancaster 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 210.9 | 210.9 | 37.1184 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2267_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 9/15/2020 |  | 3/31/2022 |  |  | N | No
AF2-268 | Orrtanna 13.2 kV | AD-Chambersburg | PA | Adams | Withdrawn | ME | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2268_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2268_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2268_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2268_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/5/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-269 | Adams Y Solar II |  | PA | N/A | Withdrawn | ME |  | 3.72 |  |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/27/2020 |  | 7/1/2021 |  |  | Y | No
AF2-270 | Bedford South RCB-Bedford Area 23 kV | BE-Chalybeate | PA | Bedford | Withdrawn | PENELEC | 3.721 | 3.72 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2270_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2270_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2270_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2270_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 10/6/2023 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-271 | Pemberton-Sinking Valley 12.47 kV | BL-Kettle | PA | Blair | Withdrawn | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2271_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2271_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2271_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2271_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 3/11/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-272 | Bernville 13.2 kV | BR-Swissdale | PA | Blair | Withdrawn | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2272_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2272_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2272_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2272_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 3/11/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-273 | Sligo 25 kV | CL-Route 58 R | PA | Clarion | Withdrawn | APS | 4 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2273_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2273_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2273_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2273_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 8/19/2022 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-274 | Lardin 12.47 kV | FA-Rockwell | PA | Fayette | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2274_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2274_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2274_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2274_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2020 | N/A | N/A | 7/31/2024 | 12/18/2023 |  | 9/30/2024 | 9/30/2024 |  | Y | No
AF2-275 | Guilford 12.47 kV | FR-Social Island | PA | Franklin | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2275_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2275_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2275_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2275_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/5/2024 |  | 4/9/2026 | 4/9/2026 |  | Y | No
AF2-276 | Guilford 12.47 kV | FR-Statler | PA | Franklin | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2276_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2276_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2276_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2276_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/5/2024 |  | 4/9/2026 | 4/9/2026 |  | Y | No
AF2-277 | Richland 12.47 kV | BU-Union | PA | Bucks | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2277_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2277_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2277_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2277_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-278 | Halifax 12.47 kV | DA-Matamoras | PA | Dauphin | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2278_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2278_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2278_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2278_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-279 | Letort 12.47 kV | LA-Blue Rock | PA | Lancaster | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2279_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2279_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2279_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2279_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-280 | Buck 12.47 kV | LA-Buck | PA | Lancaster | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2280_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2280_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2280_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2280_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-281 | Lynnville 13.2 kV | LH-Decatur | PA | Lehigh | Withdrawn | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2281_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2281_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2281_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2281_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/25/2024 |  | 4/9/2026 | 4/9/2026 |  | Y | No
AF2-282 | Edelle 12.47 kV | LK-Justus | PA | Lackawanna | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2282_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2282_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2282_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2282_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 6/28/2022 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-283 | Greenfield 12.47 kV | LK-Route 106 | PA | Lackawanna | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2283_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2283_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2283_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2283_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 9/29/2023 | 9/29/2023 |  | Y | No
AF2-284 | Watson 12.47 kV | NO-Oakes | PA | Northumberland | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2284_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2284_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2284_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2284_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/2/2023 | 2/2/2023 |  | Y | No
AF2-285 | W. Damascus 12.47 kV | WA-Cohechton 1 | PA | Wayne | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2285_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2285_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2285_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2285_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-286 | Shermansdale 12.47 kV | PE-Windy Hill | PA | Perry | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2286_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2286_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2286_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2286_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 6/28/2022 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-287 | Green Park 12.47 kV | PE-Green Park | PA | Perry | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2287_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2287_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2287_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2287_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-288 | Benvenue 12.47 kV | PE-Dellville | PA | Perry | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2288_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2288_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2288_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2288_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 9/1/2024 | 9/1/2024 |  | Y | No
AF2-289 | Watson 12.47 kV | NO-Vincent | PA | Northumberland | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2289_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2289_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2289_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2289_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 9/1/2024 | 9/1/2024 |  | Y | No
AF2-290 | Derry 12.47 kV | NO-Mexico | PA | Montour | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2290_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2290_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2290_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2290_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-291 | Sporn South-Leon 138 kV | New Haven Solar | WV | Mason | Engineering and Procurement | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2291_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2291_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2291_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_291_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_291_csa.pdf | Document Posted | N/A | N/A | 10/15/2027 | 3/28/2020 | N/A | N/A | 11/1/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AF2-292 | South Union 12.47 kV | FA-Morgantown | PA | Fayette | Withdrawn | APS | 1.17 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2292_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2292_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2292_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2292_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2020 | N/A | N/A |  | 1/2/2024 |  | 4/9/2026 | 4/9/2026 |  | Y | No
AF2-293 | Beech Creek 12.47 kV | CT-Industrial Park | PA | Clinton | Withdrawn | APS | 1.17 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2293_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2293_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2293_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2293_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2020 | N/A | N/A |  | 3/11/2024 |  | 4/9/2026 | 4/9/2026 |  | Y | No
AF2-294 | Thompson 34.5 kV |  | PA | Wayne | Suspended | PENELEC | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2294_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2294_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2294_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2294_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2020 | N/A | N/A | 2/1/2025 |  |  | 3/31/2025 | 3/31/2025 |  | N | No
AF2-295 | Wilcox-Paper City 46 kV | Evergreen Solar | PA | Elk | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2295_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2295_imp.htm | Document Posted |  | In Progress | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2295_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2295_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2020 | N/A | N/A |  | 1/31/2025 |  | 7/30/2027 | 7/30/2027 |  | N | No
AF2-296 - moved to TC1 | Madera 34.5 kV | CL- Belsena Solar | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2296_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2296_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AF2-297 - moved to TC1 | Sedge Hill 115 kV | Sedge Hill Solar | VA | Halifax | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2297_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2297_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 3/12/2022 |  |  | N | No
AF2-298 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Engineering and Procurement | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2298_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2298_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2298_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_298_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/1/2027 | 3/30/2020 | N/A | N/A | 12/1/2027 |  |  | 1/2/2028 | 1/2/2028 |  | N | No
AF2-299 - moved to TC1 | Fields 34.5 kV | Jarratt Energy Facility 2 | VA | Greensville | Active | Dominion | 18 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2299_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2299_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-300 | St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2300_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2300_imp.htm | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 3/28/2025 |  | 12/12/2022 |  |  | N | No
AF2-301 | Poolesville-Winchester 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2301_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 8/27/2020 |  | 12/12/2023 |  |  | N | No
AF2-302 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Withdrawn | AEP | 75 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2302_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2302_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/12/2022 |  |  | N | No
AF2-303 | Edgecombe 230 kV | Swift Creek Solar | NC | Edgecombe | Engineering and Procurement | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2303_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2303_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2303_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_303_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2029 | 3/30/2020 | N/A | N/A | 8/1/2029 |  |  | 9/1/2029 | 9/1/2029 |  | N | No | This project slid to the next queue
AF2-304 | Surry-Hopewell 230 kV | Bear Island Solar | VA | Surry | Engineering and Procurement | Dominion | 89 | 89 | 89 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2304_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2304_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2304_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_304_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2028 | 3/30/2020 | N/A | N/A | 7/1/2028 |  |  | 9/1/2028 | 9/1/2028 |  | N | No | This project slid to the next queue
AF2-305 | Brokaw-Lanesville 345 kV | Alta Farms II | IL | DeWitt | In Service | ComEd | 197 | 0 | 9.2 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2305_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2305_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_305_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/2/2024 | 9/2/2024 | 5/20/2023 | N | No
AF2-306 | Hope-Blevins Valley Tap 69 kV | Flat Top Solar | KY | Barren | Withdrawn | EKPC | 26 | 26 | 26 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2306_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2306_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2306_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_306_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/1/2027 | 3/30/2020 | N/A | N/A | 9/1/2027 | 4/10/2025 |  | 10/31/2027 | 10/31/2027 |  | N | No
AF2-307 - moved to TC1 | Hope-Belvins Valley Tap 69 kV | Flat Top Solar | KY | Bath | Active | EKPC | 64.2 | 64.2 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2307_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2307_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-308 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2308_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2308_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 10/14/2024 |  | 9/1/2023 |  |  | N | No
AF2-309 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2309_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2309_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 10/14/2024 |  | 9/1/2023 |  |  | N | No
AF2-310 | Jennings-Hoyes Road 34.5 kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2310_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2310_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 5/18/2021 |  | 11/30/2022 |  |  | N | No
AF2-311 | Gilboa-Jones Branch 138 kV | Nicholas Solar | WV | Nicholas | Engineering and Procurement | APS | 100 | 100 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2311_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2311_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2311_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_311_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_311_csa.pdf | Document Posted | N/A | N/A | 10/31/2028 | 3/30/2020 | N/A | N/A | 11/14/2028 |  |  | 2/28/2029 | 2/28/2029 |  | N | No
AF2-312 | Carrolltown-Patton 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 18 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2312_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 9/4/2020 |  | 9/1/2022 |  |  | N | No
AF2-313 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 19.9 | 19.9 | 12.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2313_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2313_imp.html | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 9/12/2023 |  | 8/15/2021 |  |  | N | No
AF2-314 | Vandergrift-Guffy Junction 25 kV | Ponytail Solar | PA | Armstrong | Withdrawn | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2314_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2314_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2314_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2314_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2020 | N/A | N/A | 9/30/2023 | 7/31/2024 |  | 9/30/2023 | 9/30/2023 |  | N | No
AF2-315 | Susquehanna Unit 2 500 kV |  | PA | Luzerne | Withdrawn | PPL | 1310 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2315_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2315_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 11/30/2022 |  | 8/1/2020 |  |  | N | No
AF2-316 | Gilboa-Jones Branch 138 kV II | Deep Lake Solar | WV | Nicholas | Engineering and Procurement | APS | 150 | 150 | 82.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2316_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2316_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2316_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_316_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2028 | 3/30/2020 | N/A | N/A | 11/14/2028 |  |  | 2/28/2029 | 2/28/2029 |  | N | No
AF2-317 | Hill Topper 345 kV | Whitney Hill Wind Farm | IL | Logan | In Service | ComEd | 65 | 0 | 15.68 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2317_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2317_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_317_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 9/1/2022 | N | No
AF2-318 | East Towanda-New Albany 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2318_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2318_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 4/14/2021 |  | 4/1/2022 |  |  | N | No
AF2-319 - moved to TC1 | Katydid Road 345 kV | Top Crop Generating Facility | IL | Lasalle | Active | ComEd | 400 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2319_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2319_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-320 | Dumont-Stillwell 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 48 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 9/23/2020 |  | 6/1/2023 |  |  | EE | No
AF2-321 - moved to TC1 | Stryker-Ridgeville 138 kV |  | OH | Williams | Withdrawn | ATSI | 148 | 148 | 88.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2321_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AF2-322 | Hoytdale-McClelland 345 kV | Firefly Solar | PA | Lawrence | Withdrawn | ATSI | 401.62 | 199.67 | 119.802 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2322_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2322_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2322_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_322_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_322_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 12/2/2024 |  | 9/1/2026 | 9/1/2026 |  | N | No
AF2-323 | Geneva-Franklin Tap 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2323_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 9/25/2020 |  | 4/1/2022 |  |  | N | No
AF2-324 - moved to TC1 | Edgecombe 230 kV |  | NC | Edgecombe | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2324_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 1/22/2025 |  | 11/30/2022 |  |  | N | No
AF2-325 | Jacktown 12 kV | SBC Solar | MD | Dorchester | Engineering and Procurement | DPL | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2325_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2325_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2325_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2325_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2020 | N/A | N/A | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-326 | Battleboro 34.5kV |  | NC | Edgecombe | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2326_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 7/22/2020 |  | 8/3/2023 |  |  | N | No
AF2-327 | Wakefield 13 kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2327_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 7/22/2020 |  | 8/3/2023 |  |  | N | No
AF2-328 | Inez-Johns Creek 138 kV |  | KY | Pike | Withdrawn | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2328_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2328_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 3/1/2024 |  | 12/1/2023 |  |  | N | No
AF2-329 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Withdrawn | ComEd | 292.2 | 42.2 | 42.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2329_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2329_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/1/2023 |  |  | N | No
AF2-330 | Claysburg-Summit 115 kV |  | PA | Cambria | Withdrawn | PENELEC | 70 | 70 | 48.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2330_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 9/11/2020 |  | 12/31/2022 |  |  | N | No
AF2-331 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2331_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2331_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2331_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 3/28/2025 |  | 12/31/2023 |  |  | N | No
AF2-332 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2332_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2332_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2332_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 3/28/2025 |  | 12/31/2023 |  |  | N | No
AF2-333 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2333_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2333_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2333_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 3/28/2025 |  | 12/31/2023 |  |  | N | No
AF2-334 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 140 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2334_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2334_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2334_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 3/28/2025 |  | 12/31/2023 |  |  | N | No
AF2-335 - moved to TC1 | Delaware-Royerton 138 kV | Royerton Solar and Storage | IN | Delaware | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2335_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2335_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-336 | Snake Spring 115 kV I | Snake Spring Solar I & II | PA | Bedford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2336_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2336_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2336_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 8/14/2024 |  | 2/1/2028 | 2/1/2028 |  | N | No
AF2-337 | Snake Spring 115 kV II |  | PA | Bedford | Withdrawn | PENELEC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2337_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2337_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2337_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 8/14/2024 |  | 12/31/2023 |  |  | N | No
AF2-338 | Snake Spring 115 kV III |  | PA | Bedford | Withdrawn | PENELEC | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2338_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2338_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2023 |  |  | N | No
AF2-339 | Snake Spring 115 kV IV |  | PA | Bedford | Withdrawn | PENELEC | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2339_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2339_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2023 |  |  | N | No
AF2-340 |  |  | PA | Adams | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/10/2020 |  | 12/31/2023 |  |  | N | No
AF2-341 | Maysville138 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2341_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2341_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/23/2021 |  | 12/31/2023 |  |  | N | No
AF2-342 | Maysville138 kV II |  | PA | Mercer | Withdrawn | ATSI | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2342_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2342_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/23/2021 |  | 12/31/2023 |  |  | N | No
AF2-343 | Maysville 138 kV III |  | PA | Mercer | Withdrawn | ATSI | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2343_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2343_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/23/2021 |  | 12/31/2023 |  |  | N | No
AF2-344 | Maysville 138 kV IV |  | PA | Mercer | Withdrawn | ATSI | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2344_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2344_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/23/2021 |  | 12/31/2023 |  |  | N | No
AF2-345 | Maysville 138 kV V |  | PA | Mercer | Withdrawn | ATSI | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2345_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2345_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/23/2021 |  | 12/31/2023 |  |  | N | No
AF2-346 | Electric Junction-Nelson 345 kV |  | IL | Lee | Withdrawn | ComEd | 250 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2346_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2346_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 10/13/2023 |  | 12/31/2023 |  |  | N | No
AF2-347 | Bowling Green 2-Tontogony 69 kV |  | N/A | N/A | Withdrawn | ATSI |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  | 9/28/2020 |  | 3/30/2020 |  |  | EE | No
AF2-348 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Madison | Withdrawn | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2348_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2348_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/22/2025 |  | 7/1/2022 |  |  | N | No
AF2-349 - moved to TC1 | SILVER LAKE- CHERRY VALLEY 345 KV | Pleasant Grove Solar | IL | McHenry | Active | ComEd | 300 | 300 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2349_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2349_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-350 - moved to TC1 | Kensington 138 kV | Grand Marsh Solar | IL | Kankakee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2350_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2350_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-351 - moved to TC1 | Kensington 138 kV |  | IL | Kankakee | Withdrawn | ComEd | 120 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2351_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2351_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 6/24/2024 |  | 12/1/2023 |  |  | N | No
AF2-352 | Blue Mound 345 kV | Twin Groves Storage II | IL | McLean | Engineering and Procurement | ComEd | 248 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2352_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2352_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_352_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/27/2027 | 3/31/2020 | N/A | N/A | 11/10/2027 |  |  | 1/28/2028 | 1/28/2028 |  | N | No
AF2-353 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 800 | 560 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2353_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/14/2020 |  | 9/1/2023 |  |  | N | No
AF2-354 | Washington 34.5 kV II | Washington Solar PH II | NJ | Warren | Engineering and Procurement | JCPL | 19.8 | 11 | 4.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2354_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2354_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_354_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_354_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A | 4/16/2026 |  |  | 8/29/2025 | 8/29/2025 |  | N | No
AF2-355 - moved to TC1 | West Gerrard-J.K. Smith 345 kV |  | KY | Madison | Withdrawn | EKPC | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2355_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2355_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/22/2025 |  | 7/1/2022 |  |  | N | No
AF2-356 | Albright-Mt. Zion 138 kV | CPV Backbone Solar | MD | Garrett | Under Construction | APS | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2356_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2356_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2356_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_356_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_356_csa.pdf | Document Posted | N/A | N/A | 10/25/2025 | 3/31/2020 | N/A | N/A | 10/27/2025 |  |  | 8/31/2025 | 8/31/2025 |  | N | No
AF2-357 | Nipetown-Reid 138 kV |  | MD | Washington | Withdrawn | APS | 24 | 24 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2357_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2357_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 3/29/2021 |  | 12/31/2023 |  |  | N | No
AF2-358 - moved to TC1 | Airey-Vienna 69 kV | Choptank Solar and Storage | MD | Dorchester | Active | DPL | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2358_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2358_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-359 | Olive-University Park 345 kV | Bluestem Solar | IN | LaPorte | Engineering and Procurement | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2359_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2359_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2359_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_359_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_359_csa.pdf | Document Posted | N/A | N/A | 5/15/2027 | 3/31/2020 | N/A | N/A | 6/15/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
AF2-360 | Keeney-Steele 230 kV |  | MD | Allegany | Withdrawn | DPL | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 5/1/2020 |  | 12/15/2023 |  |  | N | No
AF2-361 | Mifflintown Tap 69 kV | Walker Solar Two | PA | Juniata | Engineering and Procurement | PPL | 80 | 80 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2361_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2361_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2361_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_361_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_361_csa.pdf | Document Posted | N/A | N/A | 5/19/2026 | 3/31/2020 | N/A | N/A | 5/26/2026 |  |  | 9/19/2026 | 9/19/2026 |  | N | No
AF2-362 |  |  | VA | Lancaster | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/22/2020 |  | 12/12/2023 |  |  | N | No
AF2-363 | Cherry Valley-Glidden 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 81.4 | 81.4 | 48.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2363_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2363_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2363_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 12/2/2024 |  | 12/31/2020 |  |  | N | No
AF2-364 | Wayne Red 138 kV |  | IL | N/A | Withdrawn | ComEd | 81.4 | 81.4 | 48.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2364_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2364_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/1/2021 |  | 12/31/2022 |  |  | N | No
AF2-365 - moved to TC1 | Munfordville KU Tap-Horse Cave Jct. 69 kV | Hart Solar | KY | Hart | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2365_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2365_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-366 | Crego Rd 138 kV | Red Maple Solar | IL | Adams | Engineering and Procurement | ComEd | 94.9 | 94.9 | 56.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2366_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2366_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2366_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_366_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/8/2027 | 3/31/2020 | N/A | N/A | 11/22/2027 |  |  | 2/7/2028 | 2/7/2028 |  | N | No
AF2-367 | Neville 23 kV | Emsworth Back Channel Dam Hydroelectric Project | PA | Allegheny | Withdrawn | DL | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2367_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2367_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2367_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2367_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 10/31/2031 | 2/14/2025 |  | 12/31/2024 | 12/31/2024 |  | N | No
AF2-368 | Pine Creek 23 kV | Allegheny Lock and Dam No. 2 Hydroelectric Project | PA | Allegheny | Withdrawn | DL | 9.5 | 9.5 | 9.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2368_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2368_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2368_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2368_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 10/31/2029 | 2/13/2025 |  | 12/31/2029 | 12/31/2029 |  | N | No
AF2-369 | Kirby 138 kV |  | OH | Union | Withdrawn | ATSI | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2369_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/11/2020 |  | 12/31/2022 |  |  | N | No
AF2-370 - moved to TC1 | Delaware-Royerton 138 kV | Royerton Solar and Storage | IN | Delaware | Active | AEP | 100 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2370_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2370_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-371 | Harrison-Good Hope 138 kV | Carnation | OH | Fairfield | Engineering and Procurement | AEP | 84 | 84 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2371_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2371_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2371_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_371_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_371_csa.pdf | Document Posted | N/A | N/A | 12/31/2027 | 3/31/2020 | N/A | N/A | 1/30/2028 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AF2-372 | Black Branch 34.5 kV |  | VA | Lunenburg | Withdrawn | Dominion | 19.95 | 19.95 | 7.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2372_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 8/20/2020 |  | 11/26/2021 |  |  | N | No
AF2-373 | Mount Laurel 115 kV |  | VA | Halifax | Withdrawn | Dominion | 14.25 | 14.25 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2373_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 8/26/2020 |  | 5/30/2022 |  |  | N | No
AF2-374 | Woodland 34.5 kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2374_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/3/2020 |  | 10/29/2021 |  |  | N | No
AF2-375 | Ebersole-Fostoria 138 kV | South Branch Solar | OH | Hancock | Engineering and Procurement | AEP | 129.6 | 129.6 | 77.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2375_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2375_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2375_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_375_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_375_csa.pdf | Document Posted | N/A | N/A | 4/15/2027 | 3/31/2020 | N/A | N/A | 5/15/2027 |  |  | 2/28/2026 | 2/28/2026 |  | N | No
AF2-376 - moved to TC1 | Timber Switch 138 kV | Paulding Storage II | OH | Paulding | Active | AEP | 149 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2376_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2376_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-377 | Logtown 138 kV | Timber Road Storage III | OH | Paulding | Engineering and Procurement | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2377_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2377_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2377_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_377_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/18/2028 | 3/31/2020 | N/A | N/A | 11/1/2028 |  |  | 3/17/2029 | 3/17/2029 |  | N | No
AF2-378 | Cambridge 12 kV | GGC Solar | MD | Dorchester | Engineering and Procurement | DPL | 2.65 | 2.65 | 1.11 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2378_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2378_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2378_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2378_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 3/31/2026 |  |  | 3/31/2024 | 3/31/2024 |  | N | No
AF2-379 | Princess Anne 25 kV | RHC Solar | MD | Somerset | Under Construction | DPL | 3.9 | 3.9 | 1.638 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2379_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2379_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2379_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2379_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2020 | N/A | N/A | 3/16/2026 |  |  | 12/1/2024 | 12/1/2024 |  | N | No
AF2-380 | Karns City-Bear Creek 25 kV | Richardson Solar | PA | Clarion | Withdrawn | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2380_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2380_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2380_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2380_wmpa.pdf | Not Required | N/A | N/A | 4/30/2027 | 3/31/2020 | N/A | N/A | 5/31/2027 | 3/17/2025 |  | 7/30/2027 | 7/30/2027 |  | N | No
AF2-381 - moved to TC1 | Bedford North-Central City West 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2381_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2020 | N/A | N/A |  | 6/21/2024 |  | 6/30/2023 |  |  | N | No | This project slid to the next queue
AF2-382 | Hurley 69 kV | Buchanan County Solar | VA | Buchanan | Engineering and Procurement | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2382_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2382_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2382_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_382_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/15/2028 | 3/31/2020 | N/A | N/A | 5/22/2028 |  |  | 9/30/2028 | 9/30/2028 |  | N | No
AF2-383 | Tolna 115 kV | Tolna Energy Center | PA | York | Engineering and Procurement | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2383_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2383_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2383_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_383_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2027 | 3/31/2020 | N/A | N/A | 12/15/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AF2-384 | Brunot Island 138 kV | Brunot Island | PA | Allegheny | Withdrawn | DL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2384_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2384_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2384_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 3/25/2025 |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-385 | Nelson 69 kV |  | DE | Sussex | Withdrawn | DPL | 75 | 75 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2385_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2385_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 10/14/2021 |  | 10/31/2022 |  |  | N | No
AF2-386 | Bryan 69 kV |  | OH | Williams | Withdrawn | ATSI | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2386_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 10/16/2020 |  | 12/31/2022 |  |  | N | No
AF2-387 | Hillsboro-Steele 138 kV |  | MD | Queen Anne's | Withdrawn | DPL | 100 | 100 | 66.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2387_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2387_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/1/2021 |  | 12/1/2023 |  |  | N | No
AF2-388 - moved to TC1 | Keystone-Desoto 345 kV | Prairie Creek Wind | IN | Blackford | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2388_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2388_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-389 | Kenzie Creek-Stone Lake 69 kV | Prairie Refuge Solar | MI | Cass | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2389_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2389_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2389_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_389_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/26/2027 | 3/31/2020 | N/A | N/A | 12/13/2027 | 8/26/2025 |  | 5/31/2028 | 5/31/2028 |  | N | No
AF2-390 | Kenzie Creek138 kV |  | MI | Cass | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/30/2020 |  | 10/31/2023 |  |  | N | No
AF2-391 - moved to TC1 | Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2391_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2391_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/14/2025 |  | 6/15/2023 |  |  | N | No
AF2-392 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Lee | Active | ComEd | 199 | 199 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2392_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-393 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Withdrawn | ComEd | 259 | 60 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2393_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2393_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/22/2025 |  | 9/1/2024 |  |  | N | No
AF2-394 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Withdrawn | ComEd | 299 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2394_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2394_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/22/2025 |  | 9/1/2024 |  |  | N | No
AF2-395 | Flatlick 765 kV | Rolling Hills Generating | OH | Vinton | In Service | AEP | 1045 | 51.1 | 89.6 | 51.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2395_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2395_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_395_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_395_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 4/1/2023 | 4/1/2023 | 2/7/2023 | N | No
AF2-396 - moved to TC1 | Stinger 138 kV | Cass County Solar | MI | Cass | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2396_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2396_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-397 - moved to TC1 | Fork Union-Mt. Eagle 230 kV |  | VA | Fluvanna | Withdrawn | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2397_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2397_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2020 | N/A | N/A |  | 6/24/2024 |  | 12/15/2023 |  |  | N | No
AF2-398 | Necessity-Dinnerbell 12.47 kV | Fike Solar | PA | Fayette | Withdrawn | APS | 3 | 3 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2398_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2398_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2398_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2398_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 10/8/2024 |  | 9/30/2023 | 9/30/2023 |  | N | No
AF2-399 | Crewe 12.5 kV |  | VA | Nottoway | Withdrawn | Dominion | 5.225 | 5.225 | 1.938 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2399_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/8/2020 |  | 10/29/2021 |  |  | N | No
AF2-400 | Franklin 13.2 kV | Delaware Road Solar | VA | Southampton | Withdrawn | Dominion | 7.13 | 7.125 | 2.7075 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2400_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2400_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2400_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2400_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2020 | N/A | N/A | 5/1/2024 | 9/6/2023 |  | 5/31/2022 | 5/31/2022 |  | N | No
AF2-401 | Culpeper 34.5 kV | Stevensburg Road Solar | VA | Culpeper | Withdrawn | Dominion | 9.27 | 9.272 | 3.523 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2401_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2401_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2401_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2401_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 5/11/2021 |  | 10/31/2022 | 10/31/2022 |  | N | No
AF2-402 | Ivor-Oak Ridge 115 kV |  | VA | Southampton | Withdrawn | Dominion | 16.625 | 16.625 | 6.3175 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2402_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/3/2020 |  | 6/30/2022 |  |  | N | No
AF2-403 - moved to TC1 | Shockoe DP-Chatham 69 kV | Shockoe Storage / Shockoe DP-Chatham 69 kV | VA | Fluvanna | Withdrawn | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2403_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2403_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/22/2025 |  | 12/15/2022 |  |  | N | No
AF2-404 - moved to TC1 | Gladys DP-Stonemill 69 kV | Pigeon Run Solar and Storage | VA | Campbell | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2404_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2404_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-405 | East Sayre 34.5 kV III | Elm Line Energy Storage | PA | Bradford | Withdrawn | PENELEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2405_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2405_imp.htm | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 12/24/2024 |  | 6/1/2021 |  |  | N | No
AF2-406 - moved to TC1 | Sayre 115 kV |  | PA | Bradford | Withdrawn | PENELEC | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2406_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 6/21/2024 |  | 6/1/2022 |  |  | N | No
AF2-407 - moved to TC1 | Fall Creek 345 kV | Liberty II Storage | IN | Madison | Active | AEP | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2407_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2407_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-408 | Fall Creek 138 kV | Fall Creek Energy Storage | IN | Madison | Engineering and Procurement | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2408_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2408_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2408_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_408_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2027 | 3/31/2020 | N/A | N/A | 10/30/2027 |  |  | 1/15/2028 | 1/15/2028 |  | N | No
AF2-409 | Vienna 138 kV |  | MD | Dorchester | Withdrawn | DPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2409_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2409_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/6/2021 |  | 6/1/2022 |  |  | N | No
AF2-410 | Vienna 18 kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/24/2020 |  | 6/1/2021 |  |  | N | No
AF2-411 | Mainesburg 345 kV |  | PA | Clinton | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2411_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 12/8/2020 |  | 6/1/2023 |  |  | N | No
AF2-412 - moved to TC1 | Mainesburg 115 kV |  | PA | Tioga | Withdrawn | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2412_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AF2-413 | Raritan River 230 kV | Woods Landing Energy Storage | NJ | Atlantic | Engineering and Procurement | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2413_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2413_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2413_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_413_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_413_csa.pdf | Document Posted | N/A | N/A | 11/30/2029 | 3/31/2020 | N/A | N/A | 12/29/2028 |  |  | 1/31/2030 | 1/31/2030 |  | N | No
AF2-414 | Bergen 345 kV |  | NJ | Hudson | Withdrawn | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2414_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2414_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/11/2023 |  | 6/1/2023 |  |  | N | No
AF2-415 | Bergen 138 kV | Two Rivers Storage | NJ | Hudson | Engineering and Procurement | PSEG | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2415_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2415_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2415_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_415_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/30/2028 | 3/31/2020 | N/A | N/A | 5/15/2028 |  |  | 5/30/2028 | 5/30/2028 |  | N | No
AF2-416 | Bergen 26 kV | Railroad Avenue Energy Storage | NJ | Hudson | Suspended | PSEG | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2416_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2416_imp.html | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2416_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2416_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2020 | N/A | N/A | 4/1/2026 |  |  | 6/1/2026 | 6/1/2026 |  | N | No
AF2-417 | West Damascus Tap-West Damascus 69 kV | WA-Cochecton 2 | PA | Adams | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2417_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2417_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2417_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_417_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/30/2026 | 3/31/2020 | N/A | N/A | 10/31/2026 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-418 | Millville Tap 69 kV |  | PA | Columbia | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2418_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2418_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/13/2023 |  | 10/1/2021 |  |  | N | No
AF2-419 | Hunt Farm-Ballard 69 kV |  | KY | Boyle | Withdrawn | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2419_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/14/2020 |  | 11/1/2021 |  |  | N | No
AF2-420 | Hunt Farm-Ballard 69 kV |  | KY | Boyle | Withdrawn | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2420_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/14/2020 |  | 10/1/2021 |  |  | N | No
AF2-421 | East Hazelton-Weatherly Tap 69 | Club Ford Energy Center | PA | Adams | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2421_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2421_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2421_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_421_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 8/30/2027 | 4/1/2020 | N/A | N/A | 9/30/2027 |  |  | 3/1/2028 | 3/1/2028 |  | N | No
AF2-422 | East Hazelton 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2422_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 8/27/2020 |  | 3/1/2022 |  |  | N | No
AF2-423 | East Hazelton 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2423_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/16/2020 |  | 3/1/2022 |  |  | N | No
AF2-424 | Reed-Reed Tap #1 69 kV | Shamrock Energy Center | PA | Northumberland | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2424_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2424_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2424_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_424_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/2/2026 | 3/31/2020 | N/A | N/A | 12/18/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
AF2-425 | Reed-Reed Tap#1 69 kV | Shamrock Energy Center | PA | Adams | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2425_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2425_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2425_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_425_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/2/2026 | 3/31/2020 | N/A | N/A | 12/18/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
AF2-426 | Bethelboro 12.47 kV | FA-Auto Auction | PA | Fayette | Withdrawn | APS | 1.17 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2426_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2426_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2426_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2426_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/2/2024 |  | 4/9/2026 | 4/9/2026 |  | Y | No
AF2-427 | Watson 12.47 kV | Glidepath Ventures | PA | Northumberland | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2427_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2427_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2427_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2427_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-428 | West Boyertown 13.2 kV | BR-Water | PA | Berks | Withdrawn | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2428_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2428_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2428_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2428_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/24/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-429 | South Hamburg 34.5 kV | BR-Mountain View | PA | Berks | Withdrawn | ME | 3.721 | 3.72 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2429_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2429_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2429_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2429_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/2/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-430 | Moselem 13.2 kV | BR-Allentown | PA | Berks | Withdrawn | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2430_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2430_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2430_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2430_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/2/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-431 | Baldy 13.2 kV | BR-Kutztown | PA | Berks | Withdrawn | ME | 1.166 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2431_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2431_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2431_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2431_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 1/2/2024 |  | 9/30/2022 | 9/30/2022 |  | Y | No
AF2-432 | University 12.47 kV |  | PA | Columbia | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2432_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2432_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2432_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2432_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 9/1/2024 | 11/22/2023 |  | 2/1/2023 | 2/1/2023 |  | Y | No
AF2-433 | Columbia-Geisinger Tap #1 69 kV | Frosty Valley Energy Center | PA | Columbia | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2433_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2433_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2433_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_433_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/30/2026 | 3/31/2020 | N/A | N/A | 12/1/2026 |  |  | 1/15/2027 | 1/15/2027 |  | N | No
AF2-434 | Columbia-Geisinger Tap #1 69 kV | Frosty Valley Energy Center | MD | Anne Arundel | Engineering and Procurement | PPL | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2434_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2434_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2434_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_434_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/30/2026 | 3/31/2020 | N/A | N/A | 12/1/2026 |  |  | 1/15/2027 | 1/15/2027 |  | N | No
AF2-435 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Withdrawn | BGE | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2435_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/2/2020 |  | 9/1/2023 |  |  | N | No
AF2-436 | Wyalusing 34.5 kV II | Wyalusing 34.5 kV | PA | Bradford | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2436_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2436_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_436_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_436_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 3/18/2021 | N | No
AF2-437 | Oxbow 34.5 kV III | Oxbow Creek Energy | PA | Wyoming | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2437_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2437_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_437_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_437_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 1/11/2021 | N | No
AF2-438 | Heidleberg-Lavino 69 kV |  | PA | Mercer | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2438_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2438_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 9/13/2023 |  | 12/31/2023 |  |  | N | No
AF2-439 | Roxbury-Carlisle 115 kV |  | PA | Adams | Withdrawn | PENELEC | 50 | 50 | 26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2439_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2439_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/23/2021 |  | 12/31/2023 |  |  | N | No
AF2-440 | Hillsboro-Middleboro 138 kV | Palomino Solar | OH | Highland | Engineering and Procurement | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2440_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2440_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2440_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_440_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_440_csa.pdf | Document Posted | N/A | N/A | 6/15/2027 | 3/31/2020 | N/A | N/A | 5/15/2027 |  |  | 8/15/2027 | 8/15/2027 |  | N | No
AF2-441 - moved to TC1 | Burnham 138kV |  | IL | Cook | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2441_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AF2-442 | Vernon 115 kV |  | NJ | Sussex | Withdrawn | JCPL | 84 | 84 | 0 |  | Energy | Merchant Transmission |  | AC | 84 NFTIR/NFTWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/af2442_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/af2442_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/25/2022 |  | 5/31/2023 |  |  | S | No
AF2-443 | Vernon 115 kV |  | NJ | Sussex | Withdrawn | JCPL | 84 | 84 | 0 |  | Energy | Merchant Transmission |  | AC | 84 NFTIR/NFTWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/af2443_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/af2443_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 7/25/2022 |  | 5/31/2023 |  |  | S | No
AF2-444 | Reed-Reed Tap #2 69 kV |  | PA | Northumberland | Withdrawn | PPL | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2444_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2444_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2444_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 12/18/2024 |  | 6/1/2021 |  |  | N | No
AF2-445A | Fishbach-Port Carbon 69 kV | Norwegian Solar | PA | Northumberland | Suspended | PPL | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2445a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2445a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2445a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_445a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_445a_csa.pdf | Document Posted | N/A | N/A | 9/2/2024 | 4/1/2020 | N/A | N/A |  |  |  | 9/24/2024 | 9/24/2024 |  | N | No
AG1-001 | US Silica-Unimin 69 kV | Santos Solar | NJ | Cumberland | Withdrawn | AEC | 31 | 31 | 11.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1001_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1001_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/3/2020 | N/A | N/A |  | 1/10/2025 |  | 3/1/2023 |  |  | N | No
AG1-002 | Kennywood 23 kV |  | PA | Allegheny | Withdrawn | DL | 5.25 | 5.25 | 5.25 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/16/2020 | N/A | N/A |  | 5/22/2020 |  | 12/31/2022 |  |  | N | No
AG1-003 | Marysville-Sorenson 765 kV | Grange Solar | OH | Logan | Withdrawn | AEP | 900 | 400 | 226 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1003_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1003_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2020 | N/A | N/A |  | 2/12/2025 |  | 12/31/2023 |  |  | N | No
AG1-004 | Marysville-Sorenson 765 kV | Grange Solar | OH | Logan | Withdrawn | AEP | 1100 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1004_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1004_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2020 | N/A | N/A |  | 2/12/2025 |  | 12/31/2023 |  |  | N | No
AG1-005 - moved to TC1 | Corbin-Crescent Ridge 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2020 | N/A | N/A |  | 1/22/2025 |  | 10/1/2023 |  |  | N | No
AG1-006 | Jay 138 kV |  | IN | Jay | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2020 | N/A | N/A |  | 6/15/2020 |  | 10/1/2023 |  |  | N | No
AG1-007 | Tar River 12.5 kV | Lillie Solar | NC | Edgecombe | Engineering and Procurement | Dominion | 9.4 | 9.4 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1007_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_007_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/1/2026 | 5/1/2020 | N/A | N/A | 10/1/2026 |  |  | 6/1/2028 | 6/1/2028 |  | N | No
AG1-008 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 126 | 126 | 83.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1008_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2020 | N/A | N/A |  |  |  | 12/15/2024 |  |  | N | No
AG1-009 | Hopewell-Surry 230kV |  | VA | Surry | Withdrawn | Dominion | 150 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2020 | N/A | N/A |  | 9/12/2023 |  | 6/30/2022 |  |  | N | No
AG1-010 | Ladysmith-CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 180 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2020 | N/A | N/A |  | 9/12/2023 |  | 6/30/2022 |  |  | N | No
AG1-011 - moved to TC1 | Colonial Trail 230 kV |  | VA | Surry | Withdrawn | Dominion | 160 | 160 | 160 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2022 |  |  | N | No
AG1-012 | Meadow Brook-Strasburg 138 kV II | Foxglove Solar Storage Uprate | VA | Frederick | Withdrawn | APS | 75 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1012_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  | 9/12/2023 |  | 6/30/2022 |  |  | N | No
AG1-013 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 120 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  | 7/28/2023 |  | 6/30/2022 |  |  | N | No
AG1-014 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Withdrawn | Dominion | 500 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  | 9/8/2023 |  | 12/1/2021 |  |  | N | No
AG1-015 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Withdrawn | Dominion | 400 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1015_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  | 9/8/2023 |  | 12/1/2021 |  |  | N | No
AG1-016 | Flanders 12.5 kV |  | NJ | Warren | Withdrawn | JCPL | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  | 6/4/2020 |  | 12/18/2020 |  |  | N | No
AG1-017 | Jay 138 kV | Bitter Ridge Wind Farm | IN | Jay | Under Construction | AEP | 142.64 | 12.64 | 2.26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1017_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_017_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 7/21/2025 | 5/6/2020 | N/A | N/A | 10/31/2025 |  |  | 7/14/2025 | 7/14/2025 |  | N | No
AG1-018 | Nipetown-Reid 138 kV |  | MD | Washington | Withdrawn | APS | 32 | 8 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1018_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2020 | N/A | N/A |  | 2/26/2021 |  | 12/31/2023 |  |  | N | No
AG1-019 - moved to TC1 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Withdrawn | Dominion | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1019_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/20/2020 | N/A | N/A |  | 6/24/2024 |  | 10/31/2023 |  |  | N | No
AG1-020 | New Road 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 400 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/20/2020 | N/A | N/A |  | 6/16/2020 |  | 10/31/2023 |  |  | N | No
AG1-021 - moved to TC1 | Jetersville-Ponton 115 kV | Amelia Energy Facility | VA | Amelia | Active | Dominion | 86 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1021_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2020 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AG1-022 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Withdrawn | AEP | 95 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2020 | N/A | N/A |  | 1/22/2025 |  | 12/12/2023 |  |  | N | No
AG1-023 | North Anna-Louisa 230 kV |  | VA | Louisa | Withdrawn | Dominion | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2020 | N/A | N/A |  | 9/12/2023 |  | 10/1/2023 |  |  | N | No
AG1-024 | Centerburg 138 kV | Harvey Solar I | OH | Licking | Engineering and Procurement | AEP | 235 | 85 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1024_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1024_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_024_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2027 | 6/1/2020 | N/A | N/A | 10/29/2027 |  |  | 1/15/2029 | 1/15/2029 |  | N | No
AG1-025 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 117 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1025_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/2/2020 | N/A | N/A |  | 4/26/2024 |  | 10/31/2023 |  |  | N | No
AG1-027 | Suffolk-Holland 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 127.5 | 127.5 | 82.11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1027_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2020 | N/A | N/A |  | 9/27/2021 |  | 12/31/2024 |  |  | N | No
AG1-028 | Suffolk-Holland 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 127.5 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1028_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2020 | N/A | N/A |  | 9/27/2021 |  | 12/31/2024 |  |  | N | No
AG1-029 | Weirton Solar 24 kV | Weirton Solar 24 kV | WV | Hancock | Withdrawn | APS | 30 | 30 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1029_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1029_wmpa.pdf | Not Required | N/A | N/A |  | 6/10/2020 | N/A | N/A | 6/1/2024 | 9/15/2023 |  | 10/1/2024 | 10/1/2024 |  | N | No
AG1-030 - moved to TC1 | Victoria DP-Martin DP 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2020 | N/A | N/A |  | 6/24/2024 |  | 1/1/2023 |  |  | N | No
AG1-031 | Elk Run D.P.-Gainesville 230 kV | Alameda Solar | VA | Fauquier | Withdrawn | Dominion | 90 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1031_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_031_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 6/10/2020 | N/A | N/A |  |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-032 | Lightfoot 34.5 kV |  | VA | James City | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2020 | N/A | N/A |  | 7/10/2020 |  | 10/1/2022 |  |  | N | No
AG1-033 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1033_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/12/2020 | N/A | N/A |  | 9/16/2021 |  | 12/31/2021 |  |  | N | No
AG1-034 | Centerburg 138 kV | Harvey Solar I | OH | Licking | Engineering and Procurement | AEP | 362.5 | 127.5 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1034_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1034_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_034_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2027 | 6/12/2020 | N/A | N/A | 10/29/2027 |  |  | 1/15/2029 | 1/15/2029 |  | N | No
AG1-035 | Ahoskie 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2020 | N/A | N/A |  | 8/12/2020 |  | 12/31/2021 |  |  | N | No
AG1-036 | Tunis 34.5 kV |  | NC | Bertie | Withdrawn | Dominion | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1036_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2020 | N/A | N/A |  | 3/17/2021 |  | 12/31/2021 |  |  | N | No
AG1-037 | Ahoskie 34.5 kV | NC3 Ahoskie South Solar Project | NC | Hertford | Engineering and Procurement | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1037_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1037_wmpa.pdf | Not Required | N/A | N/A |  | 6/16/2020 | N/A | N/A | 5/31/2027 |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AG1-038 | Garner DP-Lancaster 115 kV | Waller Solar I | VA | Lancaster | Engineering and Procurement | Dominion | 176 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1038_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_038_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/31/2027 | 6/16/2020 | N/A | N/A | 9/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-039 | Galion 138 kV II | Blossom Solar | OH | Morrow | Under Construction | ATSI | 144 | 56 | 23.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1039_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_039_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/31/2026 | 6/18/2020 | N/A | N/A | 2/14/2026 |  |  | 7/31/2026 | 7/31/2026 |  | N | No
AG1-040 | Morgan Street-Mount Hope 34.5 kV | Nichols Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1040_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1040_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_040_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/1/2026 | 6/20/2020 | N/A | N/A | 11/27/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-041 | Osterburg-Bedford North 23 kV | Salt Solar | PA | Bedford | Withdrawn | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1041_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1041_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_041_csa.pdf | Document Posted | N/A | N/A | 5/15/2025 | 6/25/2020 | N/A | N/A | 4/20/2026 | 7/22/2025 |  | 7/25/2026 | 7/25/2026 |  | N | No
AG1-042 | Hayden 345 kV |  | OH | Franklin | Withdrawn | AEP | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/26/2020 | N/A | N/A |  | 8/19/2021 |  | 12/1/2023 |  |  | N | No
AG1-043 | Sowego 115 kV |  | VA | Accomack | Withdrawn | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1043_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/26/2020 | N/A | N/A |  | 10/1/2021 |  | 12/12/2023 |  |  | N | No
AG1-044 | Whiteside County | Rock River ESS | IL | Whiteside | In Service | ComEd | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1044_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1044_wmpa.pdf | Not Required | N/A | N/A |  | 7/1/2020 | N/A | N/A | 4/30/2021 |  |  | 7/30/2021 | 7/30/2021 | 12/27/2021 | Y | No
AG1-045 | Redbud-Gaylord 34.5 kV | Redbud-Gaylord 34.5 kV | VA | Frederick | Suspended | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1045_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1045_wmpa.pdf | Not Required | N/A | N/A |  | 7/3/2020 | N/A | N/A | 10/31/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AG1-046 | Freeport 138 kV |  | N/A | N/A | Withdrawn | ComEd |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/9/2020 | N/A | N/A |  | 8/27/2020 |  | 7/6/2020 |  |  | EE | No
AG1-047 | Jay 138 kV | Sun Chief Solar Farm | IN | Jay | Engineering and Procurement | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1047_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_047_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_047_csa.pdf | Document Posted | N/A | N/A | 5/18/2026 | 7/13/2020 | N/A | N/A | 6/1/2026 |  |  | 3/31/2027 | 3/31/2027 |  | N | No
AG1-048 | Jetersville-Ponton 115 kV |  | VA | Amelia | Withdrawn | Dominion | 106.25 | 106.25 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  | 9/12/2023 |  | 12/1/2022 |  |  | N | No
AG1-049 | College Corner 138 kV |  | OH | Preble | Withdrawn | AEP | 80 | 0 | 17.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1049_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  | 9/14/2023 |  | 12/31/2021 |  |  | N | No
AG1-050 | Milton 69 kV |  | PA | Northumberland | Withdrawn | PPL | 90 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  | 11/15/2024 |  | 6/30/2022 |  |  | N | No
AG1-051 - moved to TC1 | Maysville 69 kV III |  | PA | Mercer | Withdrawn | ATSI | 70 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/18/2020 | N/A | N/A |  | 7/18/2024 |  | 6/30/2022 |  |  | N | No
AG1-052 | Zionsview-Middletown 115 kV II | Strinestown Solar and BESS | PA | York | Withdrawn | ME | 99.6 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1052_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1052_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  | 12/26/2024 |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-053 | Jackson-Three Mile Island 230 kV III | Dover Solar and BESS | PA | York | Withdrawn | ME | 95 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1053_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1053_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  | 12/2/2024 |  | 6/23/2026 | 6/23/2026 |  | N | No
AG1-054 | Potter-Harlan 69 kV | Green Meadows Solar | PA | Lawrence | Engineering and Procurement | ATSI | 40 | 40 | 25.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1054_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1054_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_054_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_054_csa.pdf | Document Posted | N/A | N/A | 3/31/2027 | 7/21/2020 | N/A | N/A | 4/20/2027 |  |  | 5/31/2027 | 5/31/2027 |  | N | No
AG1-055 | Bergen 230 kV |  | NJ | Bergen | Withdrawn | PSEG | 0 |  |  |  | Energy | Merchant Transmission |  | DC | 660 NR TIR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ag1055_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/22/2020 | N/A | N/A |  | 1/29/2021 |  | 6/1/2022 |  |  | S | No
AG1-056 | Stryker-Ridgeville 138 kV |  | OH | Williams | Withdrawn | ATSI | 202 | 54 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1056_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/22/2020 | N/A | N/A |  | 2/26/2021 |  | 12/31/2023 |  |  | N | No
AG1-057 | Harmony Village 230 kV |  | VA | Middlesex | Withdrawn | Dominion | 100 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1057_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2023 |  |  | N | No
AG1-058 |  |  | VA | Greensville | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2020 | N/A | N/A |  | 7/31/2020 |  | 4/1/2022 |  |  | N | No
AG1-059 | Robbins 138 kV |  | PA | Westmoreland | Withdrawn | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1059_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1059_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/29/2020 | N/A | N/A |  | 12/11/2024 |  | 1/1/2023 |  |  | N | No
AG1-060 - moved to TC1 | Eldred 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 174.8 | 174.8 | 25.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1060_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2020 | N/A | N/A |  | 6/24/2024 |  | 5/31/2022 |  |  | N | No
AG1-061 - moved to TC1 | Laurel-Sharptown 69 kV |  | DE | Sussex | Withdrawn | DPL | 109.3 | 109.3 | 65.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1061_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2020 | N/A | N/A |  | 6/25/2024 |  | 12/31/2021 |  |  | N | No
AG1-062 | Flanders-Pohatcong Mountain 34.5 kV | Independence Solar Farm | NJ | Warren | Withdrawn | JCPL | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1062_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1062_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 5/10/2024 |  | 6/10/2027 | 6/10/2027 |  | N | No
AG1-063 | Fairhaven 13,8 kV | Fairhaven Battery Energy Storage System | MD | Anne Arundel | In Service | BGE | 2.5 | 2.5 | 0.7 | 2.5 | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1063_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1063_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2020 | N/A | N/A | 9/19/2024 |  |  | 9/30/2024 | 9/30/2024 | 9/19/2024 | N | No
AG1-064 | Plaza 34.5 kV | Bermuda Energy | VA | City of Richmond | Withdrawn | Dominion | 19.1 | 19.1 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1064_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1064_wmpa.pdf | Not Required | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 6/24/2022 |  | 12/1/2023 |  |  | N | No
AG1-065 | Plaza 34.5 kV | Bermuda Energy | VA | City of Richmond | Withdrawn | Dominion | 19.1 | 19.1 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1065_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1065_wmpa.pdf | Not Required | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 6/24/2022 |  | 12/1/2023 |  |  | N | No
AG1-066 | Bonnyman 69 kV | Bright Mountain Solar | KY | Perry | Engineering and Procurement | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1066_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1066_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_066_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2026 | 7/30/2020 | N/A | N/A | 10/23/2026 |  |  | 1/27/2027 | 1/27/2027 |  | N | No
AG1-067 | Temple Hill 69 kV |  | KY | Barren | Withdrawn | EKPC | 38 | 38 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1067_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_067_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 4/16/2025 |  | 6/30/2023 |  |  | N | No
AG1-068 | London-Tangy 69 kV |  | OH | Adams | Withdrawn | ATSI | 49.9 | 49.9 | 30.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1068_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 10/4/2021 |  | 6/30/2023 |  |  | N | No
AG1-069 |  |  | VA | Warren | Withdrawn | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 9/23/2020 |  | 1/1/2023 |  |  | N | No
AG1-070 - moved to TC1 | Bon Ayr 69 kV | Wood Duck 100 MW | KY | Barren | Active | EKPC | 45 | 45 | 32.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1070_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-071 - moved to TC1 | Bon Ayr 69 kV | Wood Duck 100 MW | KY | Barren | Active | EKPC | 100 | 55 | 37.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1071_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-072 | Hillsboro-Steele 138 kV II |  | MD | Queen Anne's | Withdrawn | DPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1072_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  | 9/28/2021 |  | 12/1/2023 |  |  | N | No
AG1-073 | St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 9/24/2020 |  | 4/1/2022 |  |  | N | No
AG1-074 | St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 9/24/2020 |  | 4/1/2022 |  |  | N | No
AG1-075 - moved to TC1 | Purdy-Sapony 115 kV |  | VA | Greensville | Withdrawn | Dominion | 150 | 150 | 93.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 1/22/2025 |  | 10/15/2024 |  |  | N | No
AG1-076 | Fostoria Central 138 kV | South Branch Solar | OH | Hancock | Suspended | AEP | 205 | 0 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_076_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AG1-077 | Allegheny Tunnel 23 kV |  | KY | Magoffin | Withdrawn | PENELEC | 3.7 | 3.7 | 0 |  | Energy | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1077_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 9/21/2021 |  | 5/31/2022 |  |  | Y | No
AG1-078 |  |  | MD | Garrett | Withdrawn | APS | 60 | 60 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 8/18/2020 |  | 9/30/2023 |  |  | N | No
AG1-079 | New Meredith 69 kV | TES Blue Hen Solar 23 | DE | Kent | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1079_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1079_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 8/3/2021 |  | 11/1/2021 | 11/1/2021 |  | Y | No
AG1-080 | Delair-Locust Street 69 kV | Buckeye Pennsauken Solar Urban Renewal LLC | NJ | Camden | Withdrawn | PSEG | 19.9 | 19.9 | 10.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1080_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_080_csa.pdf | Document Posted | N/A | N/A |  | 8/1/2020 | N/A | N/A |  | 9/7/2023 |  | 5/31/2025 | 5/31/2025 |  | N | No
AG1-081 | Poolesville 34.5 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 1/15/2021 |  | 12/1/2021 |  |  | N | No
AG1-082 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1082_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG1-083 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2021 |  |  | N | No
AG1-084 | Earlys 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 17.5 | 17.5 | 10.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1084_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 10/8/2021 |  | 12/31/2021 |  |  | N | No
AG1-085 | Earlys 34.5 |  | NC | Hertford | Withdrawn | Dominion | 17.5 | 17.5 | 10.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1085_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 10/8/2021 |  | 12/31/2021 |  |  | N | No
AG1-086 | Findlay 23 kV | Findlay Solar Park | PA | Allegheny | Engineering and Procurement | DL | 17.5 | 17.5 | 10.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1086_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1086_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1086_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2020 | N/A | N/A | 12/31/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-087 | Milford-Cartanza 230 kV |  | DE | Sussex | Withdrawn | DPL | 440 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 9/12/2023 |  | 10/31/2026 |  |  | N | No
AG1-088 | Carll's Corner-Sherman Ave 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 49.7 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2021 |  |  | N | No
AG1-089 | Grandview-Clifftop 138 kV |  | WV | N/A | Withdrawn | AEP | 120 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1089_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1089_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 2/18/2025 |  | 12/31/2021 |  |  | N | No
AG1-090 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 95 | 95 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1090_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2020 | N/A | N/A |  |  |  | 8/1/2023 |  |  | N | No
AG1-091 | Hickman-River Bend 69 kV |  | VA | Pulaski | Withdrawn | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1091_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 10/9/2024 |  | 6/30/2023 |  |  | N | No
AG1-092 | Hickman-River Bend 69 kV |  | VA | Pulaski | Withdrawn | AEP | 50 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1092_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 10/4/2021 |  | 6/30/2023 |  |  | N | No
AG1-093 | Halifax-Chase City 115 kV |  | VA | Halifax | Withdrawn | Dominion | 120 | 120 | 92 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1093_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  | 3/4/2021 |  | 12/15/2023 |  |  | N | No
AG1-094 | Burches Hill 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 265.3 | 35.3 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1094_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2020 | N/A | N/A |  | 9/12/2023 |  | 8/31/2021 |  |  | N | No
AG1-095 | General Office-Rustoleum 34.5 kV | Downsville Solar | MD | Washington | Withdrawn | APS | 16 | 16 | 10.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1095_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1095_wmpa.pdf | Not Required | N/A | N/A |  | 8/14/2020 | N/A | N/A |  | 8/14/2023 |  | 9/30/2022 | 9/30/2022 |  | N | No
AG1-096 | Rineyville 69 kV |  | KY | Hardin | Withdrawn | EKPC | 55 | 55 | 36.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2020 | N/A | N/A |  | 9/13/2023 |  | 10/31/2023 |  |  | N | No
AG1-097 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Withdrawn | APS | 92.5 | 0 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1097_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1097_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 8/17/2020 | N/A | N/A |  | 10/17/2024 |  | 9/30/2022 |  |  | N | No
AG1-098 - moved to TC1 | Briery-Clover 230 kV |  | VA | Mecklenburg | Active | Dominion | 107 | 107 | 64.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1098_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-099 | Westernport 34.5 kV | Jade Meadow III | MD | Garrett | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1099_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1099_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1099_wmpa.pdf | Not Required | N/A | N/A |  | 8/19/2020 | N/A | N/A | 10/31/2025 | 7/31/2024 |  | 12/31/2025 | 12/31/2025 |  | N | No
AG1-100 | Venango-Saegertown 34.5 kV | Henry Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1100_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_100_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2026 | 8/18/2020 | N/A | N/A | 10/26/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-101 | Oakland-Gorman 69 kV |  | MD | Garrett | Withdrawn | APS | 20 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/2020 | N/A | N/A |  | 9/5/2023 |  | 6/1/2022 |  |  | N | No
AG1-102 | White Marsh 34.5 kV |  | VA | Gloucester | Withdrawn | Dominion | 19 | 19 | 6.16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1102_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/21/2020 | N/A | N/A |  | 6/11/2024 |  | 7/1/2022 |  |  | N | No
AG1-103 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Withdrawn | AEC | 44 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_103_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2020 | N/A | N/A | 12/31/2026 | 3/18/2025 |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-104 | Waugh Chapel 230 kV | Chapel Energy Storage Facility | MD | Anne Arundel | Engineering and Procurement | BGE | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1104_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1104_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_104_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 8/25/2020 | N/A | N/A | 2/1/2029 |  |  | 6/1/2029 | 6/1/2029 |  | N | No
AG1-105 - moved to TC1 | Mount Laurel-Barnes Junction 115 kV |  | VA | Halifax | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1105_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-106 - moved to TC1 | Thelma 230 kV |  | NC | Northhampton | Active | Dominion | 143 | 23 | 16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1106_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-107 | Hillsboro-Middleboro 138 kV | Palomino Solar | OH | Highland | Engineering and Procurement | AEP | 200 | 150 | 85.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1107_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_107_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_107_csa.pdf | Document Posted | N/A | N/A | 5/15/2027 | 8/31/2020 | N/A | N/A | 6/15/2027 |  |  | 8/15/2027 | 8/15/2027 |  | N | No
AG1-108 | Larrabee 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 50 | 0 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1108_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 2/20/2023 |  | 3/1/2023 |  |  | N | No
AG1-109 - moved to TC1 | Valley 138 kV | Decatur Battery Storage | MI | Van Buren | Active | AEP | 50 | 0 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1109_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-110 | Silver Lake 69 kV |  | NJ | Camden | Withdrawn | AEC | 40 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1110_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 3/22/2022 |  | 11/1/2022 |  |  | N | No
AG1-111 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 20 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1111_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 3/16/2021 |  | 11/1/2022 |  |  | N | No
AG1-112 | William 138 kV |  | WV | Tucker | Withdrawn | APS | 66 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1112_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 3/10/2021 |  | 11/1/2022 |  |  | N | No
AG1-113 | Somerset Windpower 22.86 kV |  | PA | Somerset | Withdrawn | PENELEC | 9 | 0 | 3.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1113_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 2/22/2021 |  | 6/1/2022 |  |  | N | No
AG1-114 | Meyersdale North 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 30 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1114_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 12/1/2022 |  | 11/1/2022 |  |  | N | No
AG1-115 | Buxmont 69 kV |  | PA | Bucks | Withdrawn | PPL | 200 | 0 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1115_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 3/28/2023 |  | 11/1/2022 |  |  | N | No
AG1-116 | Newport-South Millville 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 59.7 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1116_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 9/12/2023 |  | 12/3/2021 |  |  | N | No
AG1-117 | Churchtown-Upper Pittsgrove 138 kV |  | NJ | Salem | Withdrawn | AEC | 149.3 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1117_imp.htm | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 6/28/2024 |  | 12/3/2021 |  |  | N | No
AG1-118 - moved to TC1 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1118_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-119 - moved to TC1 | Wayne-Byron 345 kV |  | IL | DeKalb | Withdrawn | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1119_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 6/24/2024 |  | 12/29/2023 |  |  | N | No
AG1-120 - moved to TC1 | Glidden-Cherry Valley 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 118.6 | 118.6 | 71.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 1/22/2025 |  | 12/29/2023 |  |  | N | No
AG1-121 - moved to TC1 | Kewanee-Streator 138 kV |  | IL | Bureau | Withdrawn | ComEd | 294.7 | 294.7 | 51.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1121_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2024 |  |  | N | No
AG1-122 | London-National 138 kV |  | OH | Madison | Withdrawn | ATSI | 70 | 70 | 41.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1122_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 2/22/2021 |  | 12/1/2024 |  |  | N | No
AG1-123 - moved to TC1 | Amherst 69 kV |  | VA | Amherst | Withdrawn | AEP | 65 | 65 | 38.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 6/21/2024 |  | 12/1/2024 |  |  | N | No
AG1-124 - moved to TC1 | Gladstone 138 kV | Wild Rose Solar Project | VA | Nelson | Active | AEP | 90 | 90 | 53.01 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1124_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-125 | Marysville-Flatlick 765 kV | Oak Run Solar Project | OH | Madison | Engineering and Procurement | AEP | 400 | 400 | 234.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1125_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1125_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_125_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_125_csa.pdf | Document Posted | N/A | N/A | 10/30/2029 | 8/31/2020 | N/A | N/A | 11/30/2029 |  |  | 12/31/2030 | 12/31/2030 |  | N | No
AG1-126 | Marysville-Flatlick 765 kV | Oak Run Solar Project | OH | Madison | Engineering and Procurement | AEP | 400 | 400 | 234.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1126_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1126_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_126_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/30/2029 | 8/31/2020 | N/A | N/A | 11/30/2029 |  |  | 12/31/2030 | 12/31/2030 |  | N | No
AG1-127 - moved to TC1 | Crego Rd 138 kV |  | IL | DeKalb | Active | ComEd | 190 | 95.1 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1127_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-128 | Shady Oaks 138 kV |  | IL | Lee | Withdrawn | ComEd | 294.2 | 294.2 | 51.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1128_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 3/24/2021 |  | 12/31/2024 |  |  | N | No
AG1-129 | US Silica - Unimin 69 kV |  | NJ | Atlantic | Withdrawn | AEC | 51 | 51 | 30.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1129_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  | 10/1/2021 |  | 6/1/2022 |  |  | N | No
AG1-130 | Burlington 26 kV | NAES | NJ | Burlington | Engineering and Procurement | PSEG | 5 | 5 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1130_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_130_csa.pdf | Document Posted | N/A | N/A | 4/29/2027 | 9/1/2020 | N/A | N/A | 5/21/2027 |  |  | 2/28/2026 | 2/28/2026 |  | N | No
AG1-131 | Edinburg 115 kV |  | VA | Shenandoah | Withdrawn | Dominion | 25.6 | 25.6 | 15.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1131_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2020 | N/A | N/A |  | 9/12/2023 |  | 8/1/2022 |  |  | N | No
AG1-132 | Tait 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 606 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1132_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2020 | N/A | N/A |  | 10/18/2023 |  | 6/1/2021 |  |  | N | No
AG1-133 - moved to TC1 | North Anna-Ladysmith 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 128 | 128 | 76.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1133_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2020 | N/A | N/A |  | 6/24/2024 |  | 12/1/2024 |  |  | N | No
AG1-134 - moved to TC1 | Kings Dominion DP 115 kV |  | VA | King William | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1134_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2020 | N/A | N/A |  | 6/24/2024 |  | 12/1/2024 |  |  | N | No
AG1-135 - moved to TC1 | Garner-Lancaster 115 kV | Moon Corner Solar | VA | Richmond | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1135_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_135_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_135_csa.pdf | Document Posted | N/A | N/A | 12/1/2025 | 9/3/2020 | N/A | N/A | 2/1/2026 |  |  | 12/1/2024 |  |  | N | No
AG1-136 | Cloverdale-Burlington Height 138 kV | Gateway Grid | VA | Botetourt | Withdrawn | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1136_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1136_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/3/2020 | N/A | N/A |  | 3/3/2025 |  | 2/28/2028 | 2/28/2028 |  | N | No
AG1-137 | Harrisonburg 230 kV |  | VA | Rockingham | Withdrawn | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1137_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2020 | N/A | N/A |  | 9/13/2021 |  | 10/22/2023 |  |  | N | No
AG1-138 | Wolfs Corners 34.5 kV |  | PA | Clarion | Withdrawn | PENELEC | 25 | 5 | 4.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1138_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2020 | N/A | N/A |  | 11/1/2021 |  | 9/15/2022 |  |  | N | No
AG1-139 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 25 | 5 | 4.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1139_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2020 | N/A | N/A |  | 11/1/2021 |  | 9/15/2022 |  |  | N | No
AG1-140 | Union City 34.5 kV | Great Lake Growers | PA | Erie | Suspended | PENELEC | 2.62 | 2.62 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1140_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1140_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1140_wmpa.pdf | Not Required | N/A | N/A |  | 9/3/2020 | N/A | N/A |  |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-141 | Hempfield 12.47 kV | Hempfield CSG 1 | PA | Westmoreland | Withdrawn | APS | 5 | 5 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1141_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1141_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1141_wmpa.pdf | Not Required | N/A | N/A |  | 9/3/2020 | N/A | N/A |  | 8/21/2024 |  | 9/30/2022 | 9/30/2022 |  | N | No
AG1-142 | Bethelboro 12.47 kV | North Union CSG 1 | PA | Fayette | Withdrawn | APS | 2.5 | 2.5 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1142_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1142_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1142_wmpa.pdf | Not Required | N/A | N/A |  | 9/4/2020 | N/A | N/A |  | 9/25/2024 |  | 9/30/2022 | 9/30/2022 |  | N | No
AG1-143 | Gainesville-Loudoun 230 kV |  | VA | Prince William | Withdrawn | Dominion | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1143_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2020 | N/A | N/A |  | 8/17/2023 |  | 10/22/2023 |  |  | N | No
AG1-144 | Phillipsburg 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1144_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2020 | N/A | N/A |  | 3/2/2021 |  | 6/1/2022 |  |  | N | No
AG1-145 | Lightfoot 34.5 kV | Norge Solar | VA | James City | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1145_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1145_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1145_wmpa.pdf | Not Required | N/A | N/A |  | 9/10/2020 | N/A | N/A | 10/20/2023 |  |  | 10/1/2023 | 10/1/2023 | 11/30/2023 | N | No
AG1-146 - moved to TC1 | Garner DP-Lancaster 115 kV | Merry Point Solar | VA | Lancaster | Active | Dominion | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1146_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-147 - moved to TC1 | Garner DP-Lancaster 115 kV | Merry Point Solar | VA | Lancaster | Active | Dominion | 100 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1147_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-148 | McCarter 26.4 kV | Rutgers Generation | NJ | Essex | In Service | PSEG | 5 | 5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1148_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1148_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1148_wmpa.pdf | Not Required | N/A | N/A |  | 9/12/2020 | N/A | N/A | 3/21/2024 |  |  | 1/12/2024 | 1/12/2024 | 3/21/2024 | N | No
AG1-149 | Kingston 12 kV II |  | MD | Somerset | Withdrawn | DPL | 11 | 3 | 3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1149_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1149_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2020 | N/A | N/A |  | 6/7/2021 |  | 12/1/2021 |  |  | N | No
AG1-150 | Wattsville 69 kV II |  | VA | Accomack | Withdrawn | DPL | 80 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1150_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2020 | N/A | N/A |  | 9/12/2023 |  | 12/1/2021 |  |  | N | No
AG1-151 - moved to TC1 | Endless Caverns 115 kV |  | VA | Rockingham | Withdrawn | Dominion | 300 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1151_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1151_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2020 | N/A | N/A |  | 6/24/2024 |  | 10/30/2023 |  |  | N | No
AG1-152 | Remington CT 230 kV | Remington BESS | VA | Fauquier | Engineering and Procurement | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1152_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1152_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_152_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 6/1/2029 | 9/10/2020 | N/A | N/A | 8/1/2029 |  |  | 9/1/2029 | 9/1/2029 |  | N | No
AG1-153 - moved to TC1 | Heritage 500 kV | Brunswick Battery Storage | VA | Brunswick | Active | Dominion | 75 | 75 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1153_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_153_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_153_csa.pdf | Document Posted | N/A | N/A | 6/22/2028 | 9/10/2020 | N/A | N/A | 7/8/2028 |  |  | 12/1/2023 |  |  | N | No
AG1-154 - moved to TC1 | Ladysmith CT 230 kV | Ladysmith Battery Storage | VA | Caroline | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1154_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-155 | Cloverdale 34.5 kV |  | VA | Botetourt | Withdrawn | AEP | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1155_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2020 | N/A | N/A |  | 2/17/2021 |  | 10/22/2023 |  |  | N | No
AG1-156 | Jack Frost-Lake Harmony 69 kV | Mora Solar | PA | Carbon | Engineering and Procurement | PPL | 60 | 60 | 39.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1156_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1156_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_156_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/30/2027 | 9/10/2020 | N/A | N/A | 10/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-157 | Macungie-Emmaus Tie 69 kV |  | PA | Lehigh | Withdrawn | PPL | 7.37 | 7.37 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1157_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2020 | N/A | N/A |  | 9/13/2023 |  | 6/16/2022 |  |  | N | No
AG1-158 | Middletown 34.5 kV |  | PA | Delaware | Withdrawn | PECO | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1158_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/11/2020 | N/A | N/A |  | 2/15/2023 |  | 6/16/2022 |  |  | N | No
AG1-159 | Cox-Whitakers 115 kV |  | NC | Halifax | Withdrawn | Dominion | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1159_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2020 | N/A | N/A |  | 5/3/2024 |  | 12/15/2022 |  |  | N | No
AG1-160 - moved to TC1 | Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 75 | 75 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1160_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2020 | N/A | N/A |  | 6/24/2024 |  | 12/1/2023 |  |  | N | No
AG1-161 | Conesville 138 kV |  | OH | Coshocton | Withdrawn | AEP | 58.9 | 58.9 | 58.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1161_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2020 | N/A | N/A |  | 3/5/2021 |  | 12/1/2022 |  |  | N | No
AG1-162 | Sporn 138 kV |  | WV | Mason | Withdrawn | AEP | 27.4 | 27.4 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1162_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2020 | N/A | N/A |  | 9/14/2023 |  | 12/1/2022 |  |  | N | No
AG1-163 | West Millersport 138 kV | Ripley Solar II | OH | Fairfield | Withdrawn | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1163_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1163_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_163_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/1/2027 | 9/14/2020 | N/A | N/A | 10/15/2027 | 6/27/2025 |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-164 | East Hazelton-Weatherly Tap 69 kV | Club Ford Energy Center | PA | Luzerne | Engineering and Procurement | PPL | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1164_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1164_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_164_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/30/2026 | 9/16/2020 | N/A | N/A | 12/30/2026 |  |  | 3/1/2027 | 3/1/2027 |  | N | No
AG1-165 | East Hazelton-Weatherly Tap 69 kV | Club Ford Energy Center | PA | Luzerne | Engineering and Procurement | PPL | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1165_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1165_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_165_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/30/2026 | 9/17/2020 | N/A | N/A | 12/30/2026 |  |  | 3/1/2027 | 3/1/2027 |  | N | No
AG1-166 - moved to TC1 | Lone Pine 115 kV | NW-Rocky Ford Solar | VA | Nottoway | Active | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1166_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-167 - moved to TC1 | Lone Pine 115 kV | NW-Rocky Ford Solar | VA | Nottoway | Active | Dominion | 35 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1167_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-168 - moved to TC1 | Lone Pine 115 kV | NW-Rocky Ford Solar | VA | Nottoway | Active | Dominion | 50 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1168_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-169 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1169_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 1/22/2025 |  | 10/15/2021 |  |  | N | No
AG1-170 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 10 | 10 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1170_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 1/22/2025 |  | 10/15/2021 |  |  | N | No
AG1-171 | Hopewell-Surry 230kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1171_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1171_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 3/28/2025 |  | 10/15/2021 |  |  | N | No
AG1-172 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1172_imp.htm | Document Posted |  |  |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 3/28/2025 |  | 10/15/2021 |  |  | N | No
AG1-173 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1173_imp.htm | Document Posted |  |  |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 3/28/2025 |  | 10/15/2021 |  |  | N | No
AG1-174 - moved to TC1 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1174_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 6/24/2024 |  | 10/15/2021 |  |  | N | No
AG1-175 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1175_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 9/12/2023 |  | 10/15/2021 |  |  | N | No
AG1-176 | Briery-Clover 230 kV |  | VA | Prince Edward | Withdrawn | Dominion | 149.5 | 149.5 | 89.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1176_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  | 8/17/2023 |  | 11/1/2023 |  |  | N | No
AG1-177 | Union City 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1177_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 3/10/2021 |  | 3/1/2024 |  |  | N | No
AG1-178 - moved to TC1 | Carson-Suffolk 500 kV |  | VA | Sussex | Withdrawn | Dominion | 500 | 500 | 324.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1178_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-179 - moved to TC1 | Brunswick-Gasburg 69 kV |  | VA | Sussex | Withdrawn | Dominion | 50 | 50 | 33.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1179_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-180 - moved to TC1 | Brunswick-Gasburg 69 kV |  | VA | Sussex | Withdrawn | Dominion | 50 | 0 | 16.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1180_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-181 - moved to TC1 | Pamplin-Chase City 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 150 | 150 | 101.09 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1181_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-182 | Millville-Old Chapel 138 kV | Soapstone Solar and BESS | VA | Clarke | Withdrawn | APS | 100 | 100 | 65.21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1182_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1182_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 10/9/2024 |  | 6/30/2023 |  |  | N | No
AG1-183 | St. Johns DP-REC 115 kV |  | VA | King and Queen | Withdrawn | Dominion | 50 | 50 | 35.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1183_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 9/1/2021 |  | 6/30/2023 |  |  | N | No
AG1-184 - moved to TC1 | Carson-Suffolk 500 kV |  | VA | Sussex | Withdrawn | Dominion | 500 | 0 | 175.06 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1184_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-185 - moved to TC1 | Pamplin-Chase City 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 150 | 0 | 48.91 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1185_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-186 | Millville-Old Chapel 138 kV | Soapstone Solar and BESS | VA | Clarke | Withdrawn | APS | 100 | 0 | 34.79 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1186_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1186_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 10/9/2024 |  | 6/30/2023 |  |  | N | No
AG1-187 | St. Johns DP-REC 115 kV |  | VA | King and Queen | Withdrawn | Dominion | 50 | 0 | 14.48 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1187_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 9/1/2021 |  | 6/30/2023 |  |  | N | No
AG1-188 | Manitou-Oyster Creek 34.5 kV | Lacey Sand Solar | NJ | Ocean | Engineering and Procurement | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1188_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1188_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_188_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/31/2027 | 9/17/2020 | N/A | N/A | 5/14/2027 |  |  | 6/30/2027 | 6/30/2027 |  | N | No
AG1-189 | Oyster Creek-Bamber Lake 34.5 | Southern Ocean Waretown Solar | NJ | Ocean | Engineering and Procurement | JCPL | 12 | 12 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1189_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1189_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_189_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2027 | 9/17/2020 | N/A | N/A | 12/17/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-190 | Burlington 26 kV |  | NJ | Burlington | Withdrawn | PSEG | 13.2 | 13.2 | 5.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1190_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 3/18/2021 |  | 12/17/2021 |  |  | N | No
AG1-191 | Chester-Pohatcong Mountain 34.5 kV | South Combe | NJ | Morris | Partially in Service - Under Construction | JCPL | 15.4 | 15.4 | 6.5 | 15.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1191_imp.html | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1191_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_191_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_191_csa.pdf | Document Posted | N/A | N/A | 7/19/2025 | 9/17/2020 | N/A | N/A | 8/20/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AG1-192 | Perry-Stoneboro 69 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1192_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  | 3/9/2021 |  | 1/15/2023 |  |  | N | No
AG1-193 | Utica Junction 34.5 kV | Foster Run | PA | Venango | Suspended | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1193_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1193_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1193_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1193_wmpa.pdf | Not Required | N/A | N/A | 6/30/2026 | 9/18/2020 | N/A | N/A | 7/31/2026 |  |  | 8/28/2026 | 8/28/2026 |  | N | No
AG1-194 - moved to TC1 | Nuttall 138 kV |  | WV | Fayette | Withdrawn | AEP | 79 | 79 | 27 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1194_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2020 | N/A | N/A |  | 1/22/2025 |  | 12/1/2023 |  |  | N | No
AG1-195 - moved to TC1 | Valley 230 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1195_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1195_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2023 |  |  | N | No
AG1-196 - moved to TC1 | Grottoes 115 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1196_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2023 |  |  | N | No
AG1-197 | Morgan Street-Cochranton 34.5 kV | Morgan Street-Cochranton 34.5 kV | PA | Crawford | Suspended | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1197_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1197_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1197_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1197_wmpa.pdf | Not Required | N/A | N/A | 1/30/2026 | 9/19/2020 | N/A | N/A | 2/27/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AG1-198 | Union City 34.5 kV | Union City 34.5 kV | PA | Erie | Under Construction | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1198_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1198_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1198_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1198_wmpa.pdf | Not Required | N/A | N/A | 11/21/2025 | 9/18/2020 | N/A | N/A | 12/17/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AG1-199 - moved to TC1 | Allen Junction 345 kV |  | OH | Lucas | Withdrawn | ATSI | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1199_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2020 | N/A | N/A |  | 6/21/2024 |  | 6/1/2023 |  |  | N | No
AG1-200 | Kingsland 13 kV |  | NJ | Bergen | Withdrawn | PSEG | 3.984 | 3.984 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1200_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1200_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2020 | N/A | N/A |  | 2/16/2021 |  | 12/1/2021 |  |  | N | No
AG1-201 | Hadley 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 10 | 10 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 11/20/2020 |  | 12/31/2022 |  |  | N | No
AG1-202 | Springboro 12.47 kV |  | PA | Crawford | Withdrawn | PENELEC | 10 | 10 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1202_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1202_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 9/7/2023 |  | 12/31/2022 |  |  | N | No
AG1-203 | Reels Corner 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1203_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1203_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 9/7/2023 |  | 12/31/2022 |  |  | N | No
AG1-204 | West Berwick 12.47 kV |  | PA | Columbia | Withdrawn | PPL | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1204_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 3/10/2021 |  | 12/31/2022 |  |  | N | No
AG1-205 | Rockwood 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1205_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 9/7/2023 |  | 12/31/2022 |  |  | N | No
AG1-206 | Snyder Twp 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1206_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 9/7/2023 |  | 12/31/2022 |  |  | N | No
AG1-207 | Vandalia 69 kV | Prairie Flyer Energy Storage | OH | Montgomery | Engineering and Procurement | Dayton | 85 | 85 | 85 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1207_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1207_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1207_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_207_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2028 | 9/22/2020 | N/A | N/A | 5/20/2028 |  |  | 6/1/2028 | 6/1/2028 |  | N | No
AG1-208 | Sideview-Mt Sterling 69 kV |  | KY | Montgomery | Withdrawn | EKPC | 35 | 35 | 21.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1208_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 2/23/2021 |  | 12/31/2022 |  |  | N | No
AG1-209 | Gretna 12.5 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 7 | 7 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1209_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1209_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 5/24/2023 |  | 12/30/2022 |  |  | N | No
AG1-210 | Northern Neck 34.5 kV | Haynesville Energy Storage | VA | Richmond | Engineering and Procurement | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1210_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1210_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1210_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1210_wmpa.pdf | Not Required | N/A | N/A | 4/30/2027 | 9/23/2020 | N/A | N/A | 5/31/2027 |  |  | 8/9/2027 | 8/9/2027 |  | N | No
AG1-211 |  |  | VA | Mecklenburg | Withdrawn | Dominion | 15 | 15 | 6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 10/20/2020 |  | 12/30/2022 |  |  | N | No
AG1-212 |  |  | VA | King George | Withdrawn | Dominion | 7 | 7 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 10/20/2020 |  | 12/30/2022 |  |  | N | No
AG1-213 | St Johns 13.2 kV | Poplar Energy Storage | VA | Caroline | Withdrawn | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1213_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1213_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1213_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1213_wmpa.pdf | Not Required | N/A | N/A |  | 9/23/2020 | N/A | N/A | 12/31/2025 | 12/17/2024 |  | 6/30/2024 | 6/30/2024 |  | N | No
AG1-214 | Grottoes 12.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 19 | 19 | 7.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1214_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1214_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 5/24/2023 |  | 12/31/2022 |  |  | N | No
AG1-215 | Fort Pickett 13.2 kV |  | VA | Nottoway | Withdrawn | Dominion | 14 | 14 | 5.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1215_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1215_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 5/12/2023 |  | 12/30/2022 |  |  | N | No
AG1-217 | Cent Hardin-Kargle 69 kV Upgrade |  | KY | Unknown | Withdrawn | EKPC |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ag1217_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  | 12/16/2024 |  | 12/20/2022 |  |  | EE | No
AG1-218 | Marysville-Tangy 345 kV |  | OH | Union | Withdrawn | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1218_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1218_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1218_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  | 1/8/2025 |  | 3/31/2024 |  |  | N | No
AG1-219 - moved to TC1 | Layland 69 kV |  | WV | Fayette | Withdrawn | AEP | 75 | 75 | 39.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1219_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1219_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  | 6/21/2024 |  | 12/1/2023 |  |  | N | No
AG1-220 | West Dekalb 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1220_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  | 3/16/2021 |  | 12/31/2023 |  |  | N | No
AG1-221 | Poland Rd-Runway DP 230 kV | Dulles Solar and BESS | VA | Loudoun | Engineering and Procurement | Dominion | 150 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1221_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_221_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/5/2025 | 9/23/2020 | N/A | N/A | 7/15/2026 |  |  | 10/31/2027 | 10/31/2027 |  | N | No
AG1-222 | Guardian-Twin Branch 138 kV |  | IN | Elkhart | Withdrawn | AEP | 250 | 150 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1222_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1222_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1222_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  | 1/28/2025 |  | 5/31/2023 |  |  | N | No
AG1-223 | Larrabee-Allaire 34.5 kV | Monmouth Solar 1 | NJ | Monmouth | Engineering and Procurement | JCPL | 15.4 | 15.4 | 6.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1223_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1223_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1223_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_223_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/19/2025 | 9/23/2020 | N/A | N/A | 12/23/2025 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-224 - moved to TC1 | Pendleton-Tanners Creek 138 kV |  | IN | Fayette | Withdrawn | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1224_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2020 | N/A | N/A |  | 6/21/2024 |  | 12/1/2023 |  |  | N | No
AG1-225 - moved to TC1 | Adams 138 kV |  | IN | Adams | Withdrawn | AEP | 346 | 346 | 207 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1225_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2020 | N/A | N/A |  | 6/21/2024 |  | 12/1/2023 |  |  | N | No
AG1-226 - moved to TC1 | Eugene-Dequine 345 kV |  | IN | Fountain | Active | AEP | 450 | 450 | 142 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1226_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-227 | Altamont-Tuscarora 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1227_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2020 | N/A | N/A |  | 9/13/2023 |  | 6/1/2023 |  |  | N | No
AG1-228 | Alta Haute-Tuscarora 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1228_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1228_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2020 | N/A | N/A |  | 9/13/2023 |  | 6/1/2023 |  |  | N | No
AG1-231 | Glady Run–Xenia 69 kV |  | OH | Greene | Withdrawn | Dayton | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1231_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1231_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1231_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 3/28/2025 |  | 3/31/2023 |  |  | N | No
AG1-232 | Magley 138 kV | Magley Solar Energy Center | IN | Adams | Engineering and Procurement | AEP | 135 | 135 | 81 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1232_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1232_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1232_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_232_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_232_csa.pdf | Document Posted | N/A | N/A | 12/31/2028 | 9/25/2020 | N/A | N/A | 1/30/2029 |  |  | 3/31/2029 | 3/31/2029 |  | N | No
AG1-233 | Hazleton - Lake Lynn 138 kV | Glade Run Solar Energy Center | WV | Preston | Withdrawn | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1233_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1233_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1233_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 1/8/2025 |  | 6/30/2028 | 6/30/2028 |  | N | No
AG1-234 | Hinton-Ronceverte 115 kV |  | WV | Greenbrier | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1234_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 3/3/2021 |  | 12/31/2024 |  |  | N | No
AG1-235 | Fentress-Sligo 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 192 | 192 | 115.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1235_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2024 |  |  | N | No
AG1-236 - moved to TC1 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 380 | 180 | 23.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1236_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-237 | Dequine-Eugene 345 kV | Warren County Wind Energy Center | IN | N/A | Engineering and Procurement | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1237_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1237_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1237_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_237_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_237_csa.pdf | Document Posted | N/A | N/A | 10/15/2028 | 9/25/2020 | N/A | N/A | 10/31/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AG1-238 | Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1238_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 3/17/2021 |  | 8/31/2024 |  |  | N | No
AG1-239 | Blue Bell-Canton Central 138 kV | Stark Solar | OH | Stark | Withdrawn | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1239_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1239_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1239_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_239_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_239_csa.pdf | Document Posted | N/A | N/A | 10/31/2028 | 9/25/2020 | N/A | N/A | 11/30/2028 | 4/24/2025 |  | 12/31/2028 | 12/31/2028 |  | N | No
AG1-240 | Trinity 69 kV |  | VA | Botetourt | Withdrawn | AEP | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 12/8/2020 |  | 6/1/2024 |  |  | N | No
AG1-241 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1241_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 4/28/2021 |  | 12/31/2022 |  |  | N | No
AG1-242 | Beccaria 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1242_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 9/7/2023 |  | 12/31/2022 |  |  | N | No
AG1-243 | Guilford-Fayetteville 34.5 kV |  | PA | Franklin | Withdrawn | APS | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1243_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 5/26/2023 |  | 12/31/2022 |  |  | N | No
AG1-244 | Middleburg 12.47 kV |  | PA | Snyder | Withdrawn | PPL | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1244_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 3/10/2021 |  | 12/31/2022 |  |  | N | No
AG1-245 | Wakefield 12.47 kV |  | PA | Lancaster | Withdrawn | PPL | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1245_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 3/10/2021 |  | 12/31/2022 |  |  | N | No
AG1-246 | Gates Hill-Luzerne 25 kV |  | PA | Fayette | Withdrawn | APS | 7.5 | 7.5 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1246_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1246_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1246_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1246_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 8/23/2023 |  | 9/1/2024 | 9/1/2024 |  | N | No
AG1-247 | North Orwell 12.47 kV |  | PA | Bradford | Withdrawn | PENELEC | 7.5 | 7.5 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1247_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 4/28/2021 |  | 12/31/2022 |  |  | N | No
AG1-248 | York Storage 115 kV |  | PA | York | Withdrawn | ME | 170 | 119 | 4.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1248_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 5/23/2023 |  | 10/31/2022 |  |  | N | No
AG1-249 | Mechanicsburg-Darby 138 kV |  | OH | Union | Withdrawn | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1249_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 3/9/2021 |  | 10/31/2023 |  |  | N | No
AG1-251 | McDowell 12.47 kV | Springfield CSG 1 | PA | Delaware | Suspended | ATSI | 3.875 | 3.88 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1251_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1251_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1251_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1251_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 8/31/2024 | 8/31/2024 |  | N | No
AG1-252 | Henderson 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 3.875 | 3.875 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1252_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1252_imp.htm | Document Posted |  |  |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/25/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2021 |  |  | N | No
AG1-253 | Erie East-Union City 34.5 kV | Greenfield CSG 1 | PA | Erie | Suspended | PENELEC | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1253_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1253_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1253_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1253_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 5/30/2025 | 5/30/2025 |  | N | No
AG1-254 | Salem-Woodstown 69 kV | Fenwick Creek Solar | NJ | Atlantic | Engineering and Procurement | AEC | 38 | 38 | 25.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1254_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1254_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1254_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_254_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 8/1/2027 | 9/25/2020 | N/A | N/A | 8/15/2027 |  |  | 9/1/2028 | 9/1/2028 |  | N | No
AG1-255 | Churchtown-Quinton 69 kV |  | NJ | Salem | Withdrawn | AEC | 55 | 55 | 36.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1255_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1255_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2020 | N/A | N/A |  | 9/12/2023 |  | 12/31/2023 |  |  | N | No
AG1-256 | Northern Neck 230 kV |  | VA | Accomack | Withdrawn | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1256_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1256_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 10/5/2021 |  | 1/1/2023 |  |  | N | No
AG1-258 | Madisonburg Jct-Millheim 46 kV |  | PA | Centre | Withdrawn | APS | 39.8 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1258_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 2/25/2021 |  | 8/1/2023 |  |  | N | No
AG1-259 | Sunbury-Dalmatia 69 kV | Boyles Run Solar | PA | Northumberland | Engineering and Procurement | PPL | 15.9 | 15.9 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1259_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1259_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1259_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_259_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/29/2027 | 9/28/2020 | N/A | N/A | 3/1/2027 |  |  | 4/30/2027 | 4/30/2027 |  | N | No
AG1-260 | Sunbury-Dalmatia 69 kV | Boyles Run Solar | PA | Northumberland | Engineering and Procurement | PPL | 31.8 | 15.9 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1260_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1260_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1260_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_260_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 1/29/2027 | 9/28/2020 | N/A | N/A | 3/1/2027 |  |  | 4/30/2027 | 4/30/2027 |  | N | No
AG1-262 | Lower Mount Bethel 230 kV |  | PA | Northampton | Withdrawn | PPL | 85 | 85 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1262_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1262_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 9/13/2023 |  | 10/31/2022 |  |  | N | No
AG1-263 | Gloucester 230 kV |  | NJ | Camden | Withdrawn | PSEG | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1263_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1263_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 9/11/2023 |  | 10/31/2021 |  |  | N | No
AG1-267 | Martins Creek 69 kV |  | PA | Northampton | Withdrawn | PPL | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1267_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1267_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 9/13/2023 |  | 10/31/2021 |  |  | N | No
AG1-268 | Essex 230 kV |  | NJ | Essex | Withdrawn | PSEG | 80 | 80 | 40.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1268_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1268_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 5/30/2023 |  | 10/31/2022 |  |  | N | No
AG1-272 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1272_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 1/22/2025 |  | 3/1/2022 |  |  | N | No
AG1-273 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1273_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-274 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1274_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-275 | Gladys DP-Stone Mill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1275_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 2/26/2021 |  | 3/1/2022 |  |  | N | No
AG1-276 | Gladys DP-Stone Mill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1276_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 2/26/2021 |  | 3/1/2022 |  |  | N | No
AG1-277 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Withdrawn | PPL | 40 | 40 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1277_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1277_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-278 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Withdrawn | PPL | 60 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1278_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1278_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-279 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Withdrawn | PPL | 80 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1279_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1279_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-280 | Claysburg-Puzzletown 46 kV |  | PA | Blair | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1280_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1280_imp.pdf | Withdrawn |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 9/18/2023 |  | 3/1/2022 |  |  | N | No
AG1-281 | Claysburg-HCR Tap 46 kV | BL-Hileman Hollow | PA | Blair | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1281_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1281_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1281_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_281_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/1/2026 | 9/30/2020 | N/A | N/A | 12/15/2026 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-282 | Dunnsville 34.5 kV | EX-Tidewater LLC | VA | Essex | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1282_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1282_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1282_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1282_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2020 | N/A | N/A | 5/31/2027 |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AG1-283 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Withdrawn | PPL | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1283_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1283_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 8/26/2024 |  | 9/30/2023 |  |  | N | No
AG1-284 - moved to TC1 | Fork Union 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1284_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 6/24/2024 |  | 9/30/2023 |  |  | N | No
AG1-285 - moved to TC1 | Chase City-Central 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1285_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-286 | Johnson Mountain 138 kV |  | VA | Campbell | Withdrawn | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1286_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 3/5/2021 |  | 12/1/2022 |  |  | N | No
AG1-287 | South Boston 12.5 kV |  | VA | Halifax | Withdrawn | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1287_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 3/17/2021 |  | 12/1/2022 |  |  | N | No
AG1-288 - moved to TC1 | Lake of the Woods DP-Wilderness DP 115 kV |  | VA | Orange | Withdrawn | Dominion | 150 | 150 | 96.59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1288_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-289 - moved to TC1 | Lake of the Woods DP-Wilderness DP 115 kV |  | VA | Orange | Withdrawn | Dominion | 150 | 0 | 53.41 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1289_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 6/24/2024 |  | 6/30/2023 |  |  | N | No
AG1-290 | Wagner 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1290_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1290_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1290_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 8/21/2023 |  | 10/31/2021 |  |  | N | No
AG1-291 | Neville 23 kV | Emsworth Main Channel Hydroelectric Project 2 | PA | Allegheny | Withdrawn | DL | 16.8 | 16.8 | 13.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1291_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1291_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1291_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1291_wmpa.pdf | Not Required | N/A | N/A | 10/3/2025 | 9/28/2020 | N/A | N/A | 11/1/2025 | 5/19/2025 |  | 12/15/2025 | 12/15/2025 |  | N | No
AG1-292 | Midland 138 kV |  | PA | Beaver | Withdrawn | DL | 36.6 | 36.6 | 21.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1292_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 3/28/2021 |  | 12/31/2023 |  |  | N | No
AG1-293 | Hartstown 12.47 kV |  | PA | Crawford | Withdrawn | APS | 7.5 | 7.5 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1293_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1293_imp.htm | Document Posted |  |  |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/28/2020 | N/A | N/A |  | 8/17/2023 |  | 12/31/2022 |  |  | N | No
AG1-294 |  |  | PA | Adams | Withdrawn | ME | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 10/21/2020 |  | 12/31/2022 |  |  | N | No
AG1-295 | Blairsville East 23 kV |  | PA | Indiana | Withdrawn | PENELEC | 7.5 | 7.5 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1295_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 4/28/2021 |  | 12/31/2022 |  |  | N | No
AG1-296 | Snyder Township 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1296_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1296_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 9/7/2023 |  | 12/31/2022 |  |  | N | No
AG1-297 - moved to TC1 | Hanna-Tanners Creek 345 kV |  | IN | Shelby | Active | AEP | 300 | 300 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1297_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-298 - moved to TC1 | Calumet-Burnham 345 kV |  | IL | Cook | Withdrawn | ComEd | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1298_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2023 |  |  | N | No
AG1-299 | U.S. Silica 12.47 kV |  | NJ | Atlantic | Withdrawn | AEC | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1299_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1299_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 10/1/2021 |  | 12/31/2021 |  |  | N | No
AG1-300 | U.S Silica II 12.47 kV |  | NJ | Cumberland | Withdrawn | AEC | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1300_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1300_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 10/1/2021 |  | 12/31/2021 |  |  | N | No
AG1-301 | Miller REC-Warrior Ridge 46 kV | Scarecrow Solar | PA | Huntingdon | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1301_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1301_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1301_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_301_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/1/2027 | 9/29/2020 | N/A | N/A | 4/12/2027 |  |  | 5/1/2027 | 5/1/2027 |  | N | No
AG1-302 | Olive-Reynolds #1 345 kV | Mammoth Central II Energy Center | IN | Pulaski | Engineering and Procurement | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1302_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1302_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1302_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_302_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/9/2026 | 9/29/2020 | N/A | N/A | 11/30/2026 |  |  | 1/15/2028 | 1/15/2028 |  | N | No
AG1-303 | Geneva 115 kV | Victory Solar | PA | Crawford | Withdrawn | PENELEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1303_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1303_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1303_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 12/10/2024 |  | 6/30/2026 | 6/30/2026 |  | N | No
AG1-304 5078473 | PJM-HUDSON |  | N/A | N/A | Withdrawn |  |  | 62 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/29/2020 | 6/1/2022 | 6/1/2023 |  | 10/6/2020 |  |  |  |  | PP | No
AG1-305 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 63 | 63 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1305_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1305_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 1/22/2025 |  | 7/1/2022 |  |  | N | No
AG1-306 - moved to TC1 | Fawkes-Dale 138 kV |  | KY | Madison | Withdrawn | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1306_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 6/21/2024 |  | 10/1/2023 |  |  | N | No
AG1-307 | Old Chapel-Millville 138 kV | Franklintown Farm Solar and BESS | WV | Jefferson | Engineering and Procurement | APS | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1307_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1307_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1307_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_307_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2028 | 9/29/2020 | N/A | N/A | 6/30/2028 |  |  | 7/30/2028 | 7/30/2028 |  | N | No
AG1-308 - moved to TC1 | Shawville-Philipsburg 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 19.9 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1308_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1308_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 6/21/2024 |  | 8/1/2022 |  |  | N | No
AG1-309 | Byron 345 kV |  | PA | Washington | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission |  | DC | 2035 F/NFTIR/2100 NF/TWR | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/ag1309_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 3/24/2021 |  | 1/31/2025 |  |  | S | No
AG1-310 | Crystal Hill-Perth 115 kV |  | VA | Halifax | Withdrawn | Dominion | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1310_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 2/23/2021 |  | 10/3/2022 |  |  | N | No
AG1-311 | Apple Grove 138 kV | Riverview Solar I | WV | Mason | Withdrawn | AEP | 99 | 99 | 69.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1311_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1311_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1311_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_311_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 4/3/2025 |  | 6/30/2023 |  |  | N | No
AG1-312 | Earleys-Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 140 | 140 | 112 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1312_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 3/4/2021 |  | 12/29/2023 |  |  | N | No
AG1-313 | Jackson DP-Occoneechee 115 kV |  | NC | Northhampton | Withdrawn | Dominion | 46 | 46 | 27.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1313_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 9/12/2023 |  | 10/9/2023 |  |  | N | No
AG1-314 | Rural Retreat 138 kV |  | VA | Smyth | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 12/14/2020 |  | 6/1/2024 |  |  | N | No
AG1-315 | Lardin-Grays Landing 12.47 kV | Woodside Solar | PA | Fayette | Withdrawn | APS | 2 | 2 | 0.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1315_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1315_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1315_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1315_wmpa.pdf | Not Required | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 8/23/2023 |  | 9/30/2023 | 9/30/2023 |  | N | No
AG1-316 | Sherwill 69 kV |  | VA | Campbell | Withdrawn | AEP | 75 | 75 | 54.96 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1316_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 9/14/2023 |  | 6/30/2024 |  |  | N | No
AG1-317 | Livingston 13.8 kV | National Harbor – Battery Storage | MD | Prince George's | Withdrawn | PEPCO | 1 | 1 | 0.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1317_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1317_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1317_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1317_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 4/29/2024 |  | 2/28/2024 | 2/28/2024 |  | N | No
AG1-318 | Ocean Bay 12 kV | Ocean City-Battery Storage | MD | Worcester | Withdrawn | DPL | 1 | 1 | 0.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1318_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1318_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1318_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1318_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 6/9/2026 | 5/30/2025 |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-319 - moved to TC1 | Napoleon Muni 138 kV |  | OH | Henry | Withdrawn | AMPT | 105 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1319_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 11/1/2022 |  |  | N | No
AG1-320 - moved to TC1 | Glendale-Stephensburg 69 kV | Stonecrop Solar | KY | Hardin | Active | EKPC | 82 | 82 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1320_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1320_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-321 - moved to TC1 | Dresden-Pontiac Midpoint 345 kV |  | IL | Livingston | Withdrawn | ComEd | 200 | 200 | 126.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1321_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 10/1/2023 |  |  | N | No
AG1-322 | Birchwood 230 kV |  | VA | Accomack | Withdrawn | Dominion | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1322_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1322_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/1/2021 |  | 9/1/2023 |  |  | N | No
AG1-323 - moved to TC1 | Blue Jacket 138 kV | Bellefontaine PV and BESS Project | OH | Logan | Active | Dayton | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1323_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1323_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AG1-324 | Jay-Desoto 138 kV | New Jay PV & BESS | IN | Jay | Engineering and Procurement | AEP | 39 | 39 | 27.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1324_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1324_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1324_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_324_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_324_csa.pdf | Document Posted | N/A | N/A | 1/8/2027 | 9/30/2020 | N/A | N/A | 1/22/2027 |  |  | 9/17/2027 | 9/17/2027 |  | N | No
AG1-325 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Withdrawn | Dominion | 50 | 50 | 26 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1325_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/5/2021 |  | 9/1/2023 |  |  | N | No
AG1-327 | Ringgold – East Waynesboro 138 kV |  | PA | Franklin | Withdrawn | APS | 35 | 35 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1327_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1327_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/1/2021 |  | 12/31/2023 |  |  | N | No
AG1-328 | Kirby-Blue Jacket 138 kV |  | OH | Union | Withdrawn | ATSI | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1328_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/10/2021 |  | 9/30/2023 |  |  | N | No
AG1-329 | Conneaut 12.47 kV |  | PA | Crawford | Withdrawn | PENELEC | 5 | 5 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1329_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/5/2021 |  | 7/31/2022 |  |  | N | No
AG1-330 | Beavertown 12.47 kV | ASD Brick Plant PA2 Solar | PA | Beaver | Withdrawn | PPL | 5 | 5 | 4.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1330_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1330_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1330_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1330_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/23/2022 |  | 3/1/2024 | 3/1/2024 |  | N | No
AG1-331 | Conneaut-Conneaut Tap 69 kV |  | PA | Crawford | Withdrawn | ATSI | 5 | 5 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1331_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/27/2021 |  | 7/31/2022 |  |  | N | No
AG1-332 | Oxford 13.2 kV |  | PA | Adams | Withdrawn | ME | 5 | 5 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1332_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 5/13/2021 |  | 7/31/2022 |  |  | N | No
AG1-333 | Lake Como-Pine Mills 12.47 kV |  | PA | Wayne | Withdrawn | PENELEC | 5 | 5 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1333_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 5/13/2021 |  | 7/31/2022 |  |  | N | No
AG1-334 | Canal 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 5 | 5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1334_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/5/2021 |  | 7/31/2022 |  |  | N | No
AG1-335 | Wheatland 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1335_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1335_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/5/2021 |  | 7/31/2022 |  |  | N | No
AG1-336 | Hunter 12.47 kV | ASD Hilcrest PA2 Solar | PA | Northumberland | Withdrawn | PPL | 5 | 5 | 3.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1336_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1336_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1336_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1336_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/23/2022 |  | 3/1/2024 | 3/1/2024 |  | N | No
AG1-337 | Elizabethville 12.47 kV | ASD Market PA2 Solar | PA | Dauphin | Withdrawn | PPL | 5 | 5 | 3.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1337_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1337_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1337_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1337_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/23/2022 |  | 3/1/2024 | 3/1/2024 |  | N | No
AG1-338 | Curryville-RKB-Yellow Creek 23 kV I |  | PA | Bedford | Withdrawn | PENELEC | 5 | 5 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1338_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1338_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/9/2021 |  | 6/30/2023 |  |  | N | No
AG1-339 | Curryville-RKB-Yellow Creek 23 kV II |  | PA | Bedford | Withdrawn | PENELEC | 5 | 5 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1339_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/4/2021 |  | 6/30/2023 |  |  | N | No
AG1-340 | Curryville 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1340_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/27/2021 |  | 6/30/2024 |  |  | N | No
AG1-341 - moved to TC1 | Summer Shade 161 kV | Summer Shade Solar | KY | Metcalfe | Active | EKPC | 106 | 106 | 63.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1341_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1341_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG1-342 - moved to TC1 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 36 | 36 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1342_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-343 - moved to TC1 | Boykins-Murphy 115 kV |  | VA | Southampton | Withdrawn | Dominion | 62.5 | 62.5 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1343_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/1/2023 |  |  | N | No
AG1-344 | Culpeper 34.5 kV |  | VA | Culpeper | Withdrawn | Dominion | 29.27 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1344_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1344_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/10/2021 |  | 6/1/2022 |  |  | N | No
AG1-345 | Crewe 12.5 kV |  | VA | Nottoway | Withdrawn | Dominion | 8 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1345_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1345_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/8/2021 |  | 6/1/2022 |  |  | N | No
AG1-346 - moved to TC1 | Mount Jackson DP 115 kV |  | VA | Shenandoah | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1346_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1346_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/1/2022 |  |  | N | No
AG1-347 | Briery DP-Clover 230 kV |  | VA | Lunenburg | Withdrawn | Dominion | 100 | 100 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1347_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 12/1/2024 |  |  | N | No
AG1-348 | Pequest River-Washington 34.5 kV | Foul Rift Solar Farm | NJ | Warren | In Service | JCPL | 19.8 | 19.8 | 8.316 | 15.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1348_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1348_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1348_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_348_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/10/2025 | 10/1/2020 | N/A | N/A | 3/21/2025 |  |  | 11/15/2025 | 11/15/2025 | 4/25/2025 | N | No
AG1-349 | Olive-Reynolds #2 345 kV | Mayapple Solar | IN | Pulaski | Engineering and Procurement | AEP | 260 | 260 | 156 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1349_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1349_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1349_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_349_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/14/2027 | 9/30/2020 | N/A | N/A | 10/7/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-351 | Harrison-Good Hope 138 kV | Carnation | OH | Fairfield | Engineering and Procurement | AEP | 142 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1351_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1351_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1351_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_351_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_351_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AG1-352 | Hunt Farm Junction 69 kV |  | KY | Boyle | Withdrawn | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1352_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1352_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/28/2021 |  | 12/31/2023 |  |  | N | No
AG1-353 - moved to TC1 | Green County-Marion County 161 kV |  | KY | Taylor | Withdrawn | EKPC | 98 | 98 | 58.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1353_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-354 - moved to TC1 | Summershade-Green County 161 kV |  | KY | Green | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1354_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-355 | Scalp Level-Hooversville 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 54 | 54 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1355_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 2/26/2021 |  | 12/31/2023 |  |  | N | No
AG1-356 | Somerset-Allegheny 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 36 | 36 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1356_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 2/26/2021 |  | 12/31/2023 |  |  | N | No
AG1-357 | Clover-Rawlings 500 kV |  | VA | Lunenburg | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1357_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 12/1/2024 |  |  | N | No
AG1-358 | Howard-Melmore 138 kV |  | OH | Crawford | Withdrawn | AEP | 58 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1358_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/8/2021 |  | 12/31/2023 |  |  | N | No
AG1-359 - moved to TC1 | Fentress 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 127.5 | 127.5 | 127.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1359_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/1/2024 |  |  | N | No
AG1-360 | Costen 25 kV | Costen Solar | MD | Somerset | In Service | DPL | 8.75 | 8.75 | 0 | 8.75 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1360_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1360_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1360_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1360_wmpa.pdf | Not Required | N/A | N/A | 9/30/2024 | 10/1/2020 | N/A | N/A | 9/30/2024 |  |  | 8/30/2024 | 8/30/2024 | 10/7/2024 | N | No
AG1-361 | Lexington Park 69 kV |  | MD | St. Mary's | Withdrawn | SMECO | 20 | 0 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1361_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/16/2021 |  | 3/31/2023 |  |  | N | No
AG1-362 | Wernersville 12.47 kV | Furnace View Farms | PA | Berks | Suspended | PPL | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1362_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1362_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1362_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1362_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 | 12/29/2023 |  | N | No
AG1-363 | Black Oak-Hatfield 500 kV | Jade Meadow III Solar Facility | MD | Garrett | Engineering and Procurement | APS | 300 | 300 | 220 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1363_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1363_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1363_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_363_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_363_csa.pdf | Document Posted | N/A | N/A | 1/31/2028 | 9/30/2020 | N/A | N/A | 2/14/2028 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AG1-364 - moved to TC1 | Deep Creek 115 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1364_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 11/30/2023 |  |  | N | No
AG1-365 | Allen 345 kV | Flatrock Creek Solar II | IN | Allen | Engineering and Procurement | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1365_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1365_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1365_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_365_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/1/2028 | 9/30/2020 | N/A | N/A | 5/15/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AG1-366 | Allen 345 kV | Flatrock Creek Storage I | IN | Allen | Engineering and Procurement | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1366_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1366_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1366_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_366_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/1/2028 | 9/30/2020 | N/A | N/A | 5/15/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AG1-367 - moved to TC1 | DeSoto 345 kV |  | IN | Delaware | Active | AEP | 440 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1367_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-368 | Tillman 138 kV | Tillman Solar Park | IN | Allen | Engineering and Procurement | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1368_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1368_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1368_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_368_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_368_csa.pdf | Document Posted | N/A | N/A | 5/28/2028 | 9/30/2020 | N/A | N/A | 10/1/2029 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
AG1-369 | Logtown 138 kV | Timber Road Solar Park III | OH | Paulding | Engineering and Procurement | AEP | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1369_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1369_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1369_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_369_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/18/2028 | 9/30/2020 | N/A | N/A | 11/1/2028 |  |  | 3/17/2029 | 3/17/2029 |  | N | No
AG1-371 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 600 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1371_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 11/1/2024 |  |  | N | No
AG1-372 | Nelson-Electric Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 200 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1372_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/16/2021 |  | 11/1/2024 |  |  | N | No
AG1-373 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 600 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1373_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1373_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 11/1/2024 |  |  | N | No
AG1-374 - moved to TC1 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1374_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-375 - moved to TC1 | Sorenson-Desoto 345 kV |  | IN | Blackford | Active | AEP | 300 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1375_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-376 | Sorenson-DeSoto 345 kV |  | IN | Blackford | Withdrawn | AEP | 30 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1376_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/9/2021 |  | 10/31/2024 |  |  | N | No
AG1-377 - moved to TC1 | Philipsburg 115 kV | Black Moshannon Solar | PA | Centre | Active | PENELEC | 115 | 20 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1377_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1377_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 8/15/2023 |  |  | N | No
AG1-378 - moved to TC1 | Philipsburg 115 kV | Black Moshannon Solar | PA | Centre | Active | PENELEC | 135 | 20 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1378_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1378_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 8/15/2023 |  |  | N | No
AG1-379 - moved to TC1 | Minonk 345 kV |  | IL | Woodford | Withdrawn | ComEd | 200 | 200 | 137.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1379_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 8/31/2023 |  |  | N | No
AG1-380 | Corwin-Elk 138 kV |  | OH | Jackson | Withdrawn | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1380_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/30/2021 |  | 12/31/2023 |  |  | N | No
AG1-381 | Hope 69 kV |  | KY | Montgomery | Withdrawn | EKPC | 27 | 27 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1381_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/9/2021 |  | 12/31/2023 |  |  | N | No
AG1-382 | SGC Tap-Reese REC 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1382_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1382_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 7/25/2024 |  | 3/1/2022 |  |  | N | No
AG1-383 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 15.43 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1383_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1383_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 3/1/2022 |  |  | N | No
AG1-384 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1384_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-385 | Motion-Ridgeway 46 kV |  | PA | Washington | Withdrawn | APS | 20 | 20 | 15.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1385_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/24/2021 |  | 3/1/2022 |  |  | N | No
AG1-386 | Smith-Francis Junction 25 kV | Smith-Francis Junction 25 kV | PA | Washington | In Service | APS | 20 | 20 | 15.42 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1386_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1386_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1386_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1386_wmpa.pdf | Not Required | N/A | N/A | 5/16/2025 | 10/2/2020 | N/A | N/A | 7/3/2025 |  |  | 6/30/2025 | 6/30/2025 | 7/11/2025 | N | No
AG1-387 | Beth 33-Lilly 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1387_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/4/2021 |  | 3/1/2022 |  |  | N | No
AG1-388 | Dunnsville 34.5 kV | Ex-Umphlette LLC | VA | Essex | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1388_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1388_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1388_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1388_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/28/2023 |  | 3/31/2023 | 3/31/2023 |  | N | No
AG1-392 - moved to TC1 | Gold 115 kV I |  | PA | Potter | Withdrawn | PENELEC | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1392_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-392A - moved to TC1 | Gold 115 kV II |  | PA | Potter | Withdrawn | PENELEC | 60 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1391_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-392B - moved to TC1 | Gold 115 kV III |  | PA | Potter | Withdrawn | PENELEC | 75 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1390_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-392C - moved to TC1 | Gold 115 kV IV |  | PA | Potter | Withdrawn | PENELEC | 90 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1389_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2022 |  |  | N | No
AG1-393 - moved to TC1 | Fort Pickett DP 34.5 kV | DW-Lew Jones Solar | VA | Dinwiddie | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1393_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1393_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-394 - moved to TC1 | Boykins 34.5 kV | SH-Mehrrin Solar | VA | Southampton | Active | Dominion | 14.2 | 14.2 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1394_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1394_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-395 | Philipsburg-Karthaus 34.5 kV 2 |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1395_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 2/26/2021 |  | 3/1/2022 |  |  | N | No
AG1-396 | Dauphin-Pine Grove 69 kV |  | PA | Dauphin | Withdrawn | PPL | 7.5 | 7.5 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1396_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/10/2021 |  | 3/30/2022 |  |  | N | No
AG1-397 | Walston 12 kV | Walston Solar | MD | Wicomico | Withdrawn | DPL | 9.972 | 9.972 | 4.1882 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1397_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1397_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1397_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1397_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 4/1/2026 | 7/15/2025 |  | 6/30/2025 | 6/30/2025 |  | N | No
AG1-398 | Brokaw-Lanesville 345 kV | Alta Farms II | IL | Fulton | In Service | ComEd | 197 | 0 | 7.33 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1398_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1398_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_398_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/2/2024 | 9/2/2024 | 5/20/2023 | N | No
AG1-399 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1399_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 9/24/2024 |  |  | N | No
AG1-400 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1400_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 9/24/2024 |  |  | N | No
AG1-402 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1402_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 9/24/2024 |  |  | N | No
AG1-403 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 188 | 188 | 33.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1403_fea.pdf | Withdrawn |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 12/18/2024 |  | 9/24/2024 |  |  | N | No | This project slid to the next queue
AG1-404 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1404_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 9/24/2024 |  |  | N | No
AG1-405 - moved to TC1 | Walnut Grove-Asahi 69 kV | Sunflower Prairie | KY | McLean | Active | EKPC | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1405_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1405_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-406 - moved to TC1 | Walnut Grove-Asahi 69 kV | Sunflower Prairie | KY | McLean | Active | EKPC | 79 | 22 | 22 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1406_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1406_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-408 |  |  | OH | Fulton | Withdrawn | ATSI | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/20/2020 |  | 9/25/2024 |  |  | N | No
AG1-410 - moved to TC1 | Maddox Creek-RP Mone 345 kV | Butterfly Meadows | OH | Van Wert | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1410_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1410_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-411 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1411_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-412 - moved to TC1 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Withdrawn | Dominion | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1412_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1412_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/1/2023 |  |  | N | No
AG1-413 | South Hill-Bordnax 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 69.5 | 69.5 | 41.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1413_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 7/1/2024 |  |  | N | No
AG1-414 | Mississinewa 138 kV | BR Solar Sheriff 1 | IN | Grant | Engineering and Procurement | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1414_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1414_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1414_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_414_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_414_csa.pdf | Document Posted | N/A | N/A | 1/31/2028 | 9/30/2020 | N/A | N/A | 2/14/2028 |  |  | 4/20/2028 | 4/20/2028 |  | N | No
AG1-415 | Double Toll Gate-Old Chapel 138 kV | Beckett Solar | VA | Clarke | Engineering and Procurement | APS | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1415_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1415_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1415_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_415_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/12/2026 | 9/30/2020 | N/A | N/A | 1/12/2027 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AG1-416 | Sleepy Hollow 138 kV | Flowing Springs Farm | WV | Jefferson | Withdrawn | APS | 125 | 125 | 91 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1416_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1416_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1416_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_416_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2028 | 9/30/2020 | N/A | N/A | 7/14/2028 | 6/26/2025 |  | 8/31/2028 | 8/31/2028 |  | N | No
AG1-417 | Gateway 69 kV |  | IN | Whitley | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1417_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1417_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/11/2024 |  | 12/29/2023 |  |  | N | No
AG1-418 | Gateway 69 kV |  | IN | Whitley | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1418_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1418_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/11/2024 |  | 12/29/2023 |  |  | N | No
AG1-419 | Lynnville-South Hamburg 69 kV | Mountain Trail Solar | PA | Berks | Withdrawn | ME | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1419_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1419_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1419_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/28/2024 |  | 1/31/2028 | 1/31/2028 |  | N | No
AG1-420 | Campbell-Kiesters 138 kV |  | PA | Butler | Withdrawn | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1420_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1420_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1420_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/11/2024 |  | 12/29/2023 |  |  | N | No
AG1-421 - moved to TC1 | Lexington-Dooms 230 kV |  | VA | Augusta | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1421_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1421_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/29/2023 |  |  | N | No
AG1-422 - moved to TC1 | Lexington-Dooms 230 kV |  | VA | Augusta | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1422_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1422_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/29/2023 |  |  | N | No
AG1-423 - moved to TC1 | Byron-Wayne 345 kV |  | IL | DeKalb | Withdrawn | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1423_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/29/2023 |  |  | N | No
AG1-424 - moved to TC1 | Sowers 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1424_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1424_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/29/2023 |  |  | N | No
AG1-425 - moved to TC1 | Groton 138 kV |  | OH | Erie | Withdrawn | ATSI | 125 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1425_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 10/31/2023 |  |  | N | No
AG1-426 - moved to TC1 | Bremo-Scottsville 138 kV |  | VA | Buckingham | Withdrawn | AEP | 149.5 | 0 | 17 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1426_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/2/2024 |  | 10/31/2023 |  |  | N | No
AG1-427 - moved to TC1 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 118.56 | 118.56 | 71.136 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1427_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2024 |  |  | N | No
AG1-428 - moved to TC1 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Withdrawn | Dominion | 46.8 | 46.8 | 28.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1428_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2024 |  |  | N | No
AG1-429 | Tasley - Oak Hall 69 kV |  | VA | Accomack | Withdrawn | ODEC | 58.7 | 58.7 | 35.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1429_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1429_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 5/26/2022 |  | 12/31/2024 |  |  | N | No
AG1-431 | Mackeys 230 kV |  | NC | Washington | Withdrawn | Dominion | 1210 | 0 | 266.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1431_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/19/2022 |  | 12/31/2024 |  |  | N | No
AG1-431A | Mackeys 230 kV |  | NC | Washington | Withdrawn | Dominion | 1210 | 0 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1431a_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/19/2022 |  | 12/31/2024 |  |  | N | No
AG1-432 - moved to TC1 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1432_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2024 |  |  | N | No
AG1-433 - moved to TC1 | Keystone-DeSoto 345 kV |  | IN | Blackford | Active | AEP | 300 | 100 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1433_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-434 - moved to TC1 | Electric Junction-Nelson 345 kV |  | IL | Lee | Withdrawn | ComEd | 175 | 175 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1434_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-435 - moved to TC1 | Kewanee-Hennepin 138 kV |  | IL | Bureau | Withdrawn | ComEd | 150 | 150 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1435_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 2/21/2025 |  | 12/31/2023 |  |  | N | No
AG1-436 - moved to TC1 | Olive-University Park 345 kV | Bluestem Solar | IN | LaPorte | Active | AEP | 250 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1436_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1436_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-437 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1437_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-438 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1438_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-439 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Withdrawn | Dominion | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1439_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-440 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1440_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2023 |  |  | N | No
AG1-441 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1441_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2023 |  |  | N | No
AG1-442 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Withdrawn | Dominion | 135 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1442_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-443 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Withdrawn | Dominion | 135 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1443_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-444 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Withdrawn | Dominion | 330 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1444_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2023 |  |  | N | No
AG1-445 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 101 | 26 | 26 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1445_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2023 |  |  | N | No
AG1-446 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 101 | 26 | 26 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1446_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/31/2023 |  |  | N | No
AG1-447 - moved to TC1 | Olive-University Park 345 kV | Bluestem Solar | IN | LaPorte | Active | AEP | 305 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1447_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1447_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-448 | Olive-University Park 345 kV |  | IN | LaPorte | Withdrawn | AEP | 360 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1448_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1448_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/27/2022 |  | 12/31/2023 |  |  | N | No
AG1-449 - moved to TC1 | Rawlings-Carson 500 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 436 | 122 | 122 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1449_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2022 |  |  | N | No
AG1-450 - moved to TC1 | Airey-Vienna 69 kV II | Choptank Solar and Storage | MD | Dorchester | Active | DPL | 125 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1450_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1450_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-451 - moved to TC1 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1451_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 12/31/2022 |  |  | N | No
AG1-453 - moved to TC1 | Guardian 138 kV |  | IN | Noble | Withdrawn | AEP | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1453_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1453_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 12/31/2023 |  |  | N | No
AG1-454 - moved to TC1 | Guardian 138 kV |  | IN | Noble | Withdrawn | AEP | 190 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1454_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1454_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 12/31/2022 |  |  | N | No
AG1-455 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 112.5 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1455_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1455_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1455_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 12/3/2024 |  | 12/31/2022 |  |  | N | No
AG1-456 - moved to TC1 | Wildcat 138 kV |  | OH | Highland | Withdrawn | AEP | 180 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1456_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1456_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 12/31/2022 |  |  | N | No
AG1-457 | Somerset-Rockwood 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 54 | 54 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1457_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/1/2021 |  | 12/31/2023 |  |  | N | No
AG1-458 | Marlow-Bedington 138 kV |  | MD | Washington | Withdrawn | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1458_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/1/2021 |  | 12/31/2023 |  |  | N | No
AG1-459 | Marlow-Bedington 138 kV |  | MD | Washington | Withdrawn | APS | 14 | 14 | 5.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1459_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/2/2021 |  | 12/31/2023 |  |  | N | No
AG1-460 - moved to TC1 | Kincaid-Pana 345 kV | Black Diamond Solar | IL | Christian | Active | ComEd | 329 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1460_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1460_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-461 | Mumford 69 kV |  | DE | Sussex | Withdrawn | DPL | 30 | 30 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1461_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1461_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/20/2021 |  | 12/31/2023 |  |  | N | No
AG1-462 - moved to TC1 | Cordova 345 kV |  | IL | Whiteside | Active | ComEd | 255 | 255 | 153 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1462_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-463 | Maysville 69 kV IV |  | PA | Mercer | Withdrawn | ATSI | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1463_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/19/2021 |  | 5/21/2024 |  |  | N | No
AG1-464 | Harrington 69 kV |  | DE | Kent | Withdrawn | DPL | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1464_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1464_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 9/17/2023 |  |  | N | No
AG1-465 | North Hanover-Gitts Run 115 kV |  | PA | York | Withdrawn | ME | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1465_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1465_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 3/5/2025 |  |  | N | No
AG1-466 | Orange 34.5 kV |  | VA | Orange | Withdrawn | Dominion | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1466_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1466_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 12/19/2022 |  |  | N | No
AG1-467 | Somerset 34.5 kV |  | VA | Orange | Withdrawn | Dominion | 15.6 | 15.6 | 9.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1467_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1467_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 12/28/2022 |  |  | N | No
AG1-468 | Martinsville-Figsboro 34.5 kV |  | VA | Henry | Withdrawn | AEP | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1468_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1468_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/31/2021 |  | 10/31/2022 |  |  | N | No
AG1-469 | Gordonsville 34.5 kV | Turkey Solar | VA | Louisa | Engineering and Procurement | Dominion | 14.04 | 14.04 | 9.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1469_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1469_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1469_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1469_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 5/31/2027 |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AG1-470 | Ringgold 138 kV |  | MD | Washington | Withdrawn | APS | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1470_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  | 9/8/2023 |  | 9/6/2024 |  |  | N | No
AG1-471 - moved to TC1 | Up Church-Wayne County 69 kV | Barrelhead | KY | Wayne | Active | EKPC | 54 | 54 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1471_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1471_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AG1-472 | Seymour-Cave City 69 kV |  | KY | Hart | Withdrawn | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1472_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/13/2023 |  | 10/9/2023 |  |  | N | No
AG1-473 - moved to TC1 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 53.9 | 53.9 | 32.34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1473_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2024 |  |  | N | No
AG1-474 |  |  | PA | Centre | Withdrawn | APS | 70 | 70 | 49 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/28/2020 |  | 6/1/2024 |  |  | N | No
AG1-475 | Mickelton 230 kV |  | NJ | Gloucester | Withdrawn | AEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1475_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 4/26/2021 |  | 6/1/2023 |  |  | N | No
AG1-476 | Mickelton 230 kV II |  | NJ | Gloucester | Withdrawn | AEC | 869 | 0 | 33.1 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1476_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1476_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 8/21/2023 |  | 6/1/2023 |  |  | N | No
AG1-477 | Grundy County 34.5 kV |  | IL | Grundy | Withdrawn | ComEd | 18 | 18 | 14.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1477_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/11/2023 |  | 12/29/2023 |  |  | N | No
AG1-478 | Wilmington 34.5 kV | Wilmington Solar Energy Project | IL | Will | Engineering and Procurement | ComEd | 19.9 | 19.9 | 15.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1478_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1478_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1478_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1478_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 9/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-479 | Grundy County 34.5 kV II |  | IL | Grundy | Withdrawn | ComEd | 19.9 | 19.9 | 15.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 12/3/2020 |  | 12/29/2023 |  |  | N | No
AG1-480 | Shawnee 34.5 kV | Shawnee Solar and BESS | PA | Monroe | Engineering and Procurement | ME | 18.2 | 18.2 | 18.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1480_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1480_imp.htm | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1480_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1480_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 10/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-481 | Warren 34.5 kV |  | PA | Warren | Withdrawn | PENELEC | 15.53 | 15.53 | 15.53 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1481_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1481_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/1/2021 |  | 6/1/2024 |  |  | N | No
AG1-482 | Hamilton 115 kV | Hamilton Solar and BESS | PA | Adams | Engineering and Procurement | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1482_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1482_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1482_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_482_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/1/2027 | 9/30/2020 | N/A | N/A | 1/7/2028 |  |  | 2/1/2028 | 2/1/2028 |  | N | No
AG1-483 - moved to TC1 | Dickerson 230 kV | Fourth Quarter | MD | Montgomery | Engineering and Procurement | PEPCO | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1483_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1483_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_483_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 12/15/2029 | 10/1/2020 | N/A | N/A | 11/1/2029 |  |  | 2/1/2030 | 2/1/2030 |  | N | No
AG1-484 | Mountain 115 kV |  | PA | Cumberland | Withdrawn | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1484_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1484_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/1/2021 |  | 6/1/2024 |  |  | N | No
AG1-485 | Brunot Island 138 kV |  | PA | Allegheny | Withdrawn | DL | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1485_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1485_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1485_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/25/2025 |  | 6/1/2024 |  |  | N | No
AG1-486 | Orrtanna 115 kV | Orrtanna | PA | Adams | Engineering and Procurement | ME | 42 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1486_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1486_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1486_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_486_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/31/2027 | 9/30/2020 | N/A | N/A | 11/30/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AG1-487 | Gilbert 230 kV | Gilbert Solar and BESS | NJ | Hunterdon | Engineering and Procurement | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1487_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1487_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1487_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_487_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 2/28/2027 | 9/30/2020 | N/A | N/A | 4/1/2027 |  |  | 6/1/2027 | 6/1/2027 |  | N | No
AG1-488 - moved to TC1 | Marion Co 161 kV |  | KY | Marion | Withdrawn | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1488_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/21/2024 |  | 9/30/2022 |  |  | N | No
AG1-489 | McClelland-Hoytdale 345 kV |  | PA | Lawrence | Withdrawn | ATSI | 175 | 175 | 145 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1489_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1489_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1489_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/27/2024 |  | 6/1/2023 |  |  | N | No
AG1-490 | Shenango-McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 125 | 125 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1490_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1490_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/16/2021 |  | 6/1/2023 |  |  | N | No
AG1-491 | Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1491_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/13/2023 |  | 6/30/2023 |  |  | N | No
AG1-492 | Kargle to Elizabethtown 69 kV |  | KY | Unknown | Withdrawn | EKPC |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ag1492_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 12/16/2024 |  | 12/20/2022 |  |  | EE | No
AG1-493 | Blue Jacket to Blue Jacket Tap 69 kV |  | OH | Logan | Withdrawn | Dayton |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ag1493_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/1/2024 |  | 12/13/2022 |  |  | EE | No
AG1-494 - moved to TC1 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1494_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-495 | Gilbert-Rocktown 34.5 kV | Ridge Road Solar Farm | NJ | Hunterdon | Engineering and Procurement | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1495_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1495_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1495_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_495_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 7/1/2027 | 9/30/2020 | N/A | N/A | 9/2/2027 |  |  | 10/1/2027 | 10/1/2027 |  | N | No
AG1-496 | East Flemington 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6.6 | 6.6 | 2.772 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1496_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/24/2021 |  | 12/17/2021 |  |  | N | No
AG1-497 - moved to TC1 | Cartanza 230 kV |  | DE | Kent | Withdrawn | DPL | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1497_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1497_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/30/2023 |  |  | N | No
AG1-498 | Mount Bethel 12.47 kV | Martins Creek Solar | PA | Northampton | Withdrawn | PPL | 8.8 | 8.8 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1498_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1498_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1498_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1498_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 5/30/2024 |  | 4/1/2025 | 4/1/2025 |  | N | No
AG1-499 | Lambs 12.47 kV | Esky Solar Project | NJ | Gloucester | Under Construction | AEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1499_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1499_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1499_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1499_wmpa.pdf | Not Required | N/A | N/A | 2/1/2026 | 9/30/2020 | N/A | N/A | 2/1/2026 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
AG1-500 | Beaver 345 kV | West Lorain Power Plant 345 kV | OH | Lorain | Engineering and Procurement | ATSI | 784.6 | 406.4 | 385.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1500_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1500_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1500_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_500_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 9/30/2020 | N/A | N/A | 1/14/2028 |  |  | 6/1/2031 | 6/1/2031 |  | N | No
AG1-501 | Beaver 138 kV | West Lorain 138 kV Power Plant | OH | Lorain | Engineering and Procurement | ATSI | 106.5 | 11.3 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1501_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1501_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1501_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_501_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_501_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2020 | N/A | N/A | 11/1/2028 |  |  | 12/31/2028 | 12/31/2028 |  | N | No
AG1-502 - moved to TC1 | Oak Green 115 kV |  | VA | Orange | Withdrawn | Dominion | 80 | 80 | 64 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1502_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1502_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/30/2023 |  |  | N | No
AG1-503 - moved to TC1 | Oak Green 115 kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1503_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1503_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/30/2023 |  |  | N | No
AG1-504 | Glenbrook-Salem 69 kV |  | PA | Luzerne | Withdrawn | PPL | 68 | 68 | 41.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1504_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1504_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/5/2021 |  | 12/31/2023 |  |  | N | No
AG1-505 - moved to TC1 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1505_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 7/1/2024 |  |  | N | No
AG1-506 - moved to TC1 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1506_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 7/1/2024 |  |  | N | No
AG1-507 | Calumet 138 kV | Southeast Chicago Energy Project (aka SCEP) | IL | Cook | Withdrawn | ComEd | 296 | 296 | 296 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1507_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1507_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_507_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/29/2024 |  | 6/1/2024 | 6/1/2024 |  | N | No
AG1-508 | Point Lookout 69 kV | Fiddlers Ridge Wind Facility | VA | Grayson | Engineering and Procurement | AEP | 63.3 | 63.3 | 9.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1508_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1508_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1508_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_508_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/15/2028 | 9/30/2020 | N/A | N/A | 4/1/2028 |  |  | 6/15/2028 | 6/15/2028 |  | N | No
AG1-509 | Point Lookout 69 kV |  | VA | Grayson | Withdrawn | AEP | 105.4 | 105.4 | 15.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1509_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1509_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/29/2022 |  | 3/1/2025 |  |  | N | No
AG1-510 | Kittatinny-Blairstown 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1510_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1510_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1510_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 7/15/2024 |  | 6/1/2024 |  |  | N | No
AG1-511 | Kittatinny 230 kV | Mt Vernon Solar | NJ | Warren | Engineering and Procurement | JCPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1511_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1511_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1511_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_511_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_511_csa.pdf | Document Posted | N/A | N/A | 5/31/2028 | 9/30/2020 | N/A | N/A | 7/10/2028 |  |  | 7/31/2028 | 7/31/2028 |  | N | No
AG1-512 | University Park North 345 kV | University Park North Energy Center | IL | Will | Withdrawn | ComEd | 646 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1512_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1512_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1512_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_512_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_512_csa.pdf | Document Posted | N/A | N/A | 9/30/2026 | 9/30/2020 | N/A | N/A | 10/14/2026 | 8/6/2025 |  | 1/11/2027 | 1/11/2027 |  | N | No
AG1-513 | Aurora 138 kV | Aurora Battery Storage | IL | Will | Suspended | ComEd | 1056 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1513_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1513_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1513_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_513_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_513_csa.pdf | Document Posted | N/A | N/A | 4/1/2028 | 10/1/2020 | N/A | N/A | 5/1/2028 |  |  | 6/1/2028 | 6/1/2028 |  | N | No
AG1-514 | Springdale CT III 138 kV | Springdale | PA | Allegheny | Withdrawn | APS | 106 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1514_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1514_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1514_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_514_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1_514_csa.pdf | Document Posted | N/A | N/A | 4/1/2027 | 9/30/2020 | N/A | N/A | 5/1/2027 | 8/14/2025 |  | 6/1/2027 | 6/1/2027 |  | N | No
AG1-515 | Guilford 138 kV | Chambersburg Energy | PA | Franklin | Withdrawn | APS | 110 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1515_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1515_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1515_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_515_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/31/2027 | 9/30/2020 | N/A | N/A | 4/30/2027 | 8/7/2025 |  | 5/31/2027 | 5/31/2027 |  | N | No
AG1-516 | Gans 138 kV | Gans Energy CT and BESS | PA | Fayette | Withdrawn | APS | 106 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1516_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1516_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1516_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/11/2024 |  | 5/21/2027 | 5/21/2027 |  | N | No
AG1-517 | Osage 138 kV | Beechurt Natural Gas | WV | Monongalia | Engineering and Procurement | APS | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1517_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1517_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1517_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_517_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/30/2027 | 9/30/2020 | N/A | N/A | 12/14/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AG1-518 | Suffolk 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1518_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1518_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 9/1/2023 |  |  | N | No
AG1-519 | Cash's Corner 230 kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1519_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1519_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/16/2021 |  | 10/28/2022 |  |  | N | No
AG1-520 | Hooversville-Rockingham 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 4 | 4 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1520_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1520_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 1/1/2022 |  |  | Y | No
AG1-521 | Dixon-McGirr Road 138 kV |  | IL | Lee | Withdrawn | ComEd | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1521_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/16/2021 |  | 10/30/2023 |  |  | N | No
AG1-522 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1522_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2023 |  |  | N | No
AG1-523 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 600 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1523_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2023 |  |  | N | No
AG1-524 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 900 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1524_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2023 |  |  | N | No
AG1-525 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 1200 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1525_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 6/1/2023 |  |  | N | No
AG1-526 - moved to TC1 | West Garrard 345 kV |  | KY | Garrard | Active | EKPC | 222 | 222 | 133.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1526_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-527 | Imperial-Joffre 138 kV | Beech Hollow Solar | PA | Allegheny | Withdrawn | APS | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1527_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1527_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1527_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/6/2025 |  | 7/31/2028 | 7/31/2028 |  | N | No
AG1-528 | Tenmile - Sundial 138 kV |  | WV | N/A | Withdrawn | AEP | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1528_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1528_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1528_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/29/2025 |  | 6/1/2023 |  |  | N | No
AG1-530 |  |  | OH | Clark | Withdrawn | ATSI | 54 | 54 | 35.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/16/2020 |  | 12/31/2023 |  |  | N | No
AG1-531 - moved to TC1 | Poolesville-Winchester 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 54 | 54 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1531_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 12/12/2023 |  |  | N | No
AG1-532 | Fields 34.5 kV | Fields 2 | VA | Greensville | Engineering and Procurement | Dominion | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1532_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1532_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1532_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1532_wmpa.pdf | Not Required | N/A | N/A | 5/31/2027 | 9/30/2020 | N/A | N/A | 6/30/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AG1-533 | Bartonsville-Meadowbrook 138 kV IV | Bartonsville Energy Facility | VA | Frederick | Withdrawn | APS | 170 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1533_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1533_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/14/2024 |  | 12/12/2023 |  |  | N | No
AG1-534 | Evergreen Mills 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1534_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1534_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 6/1/2023 |  |  | N | No
AG1-536 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 137 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1536_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG1-537 - moved to TC1 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Withdrawn | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1537_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1537_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 10/1/2024 |  |  | N | No
AG1-538 - moved to TC1 | Remington-Gordonsville 230 kV |  | VA | Culpeper | Withdrawn | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1538_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1538_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 10/1/2024 |  |  | N | No
AG1-539 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1539_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 10/1/2024 |  |  | N | No
AG1-540 | Berry Hill 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 55 | 55 | 21.35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1540_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/5/2021 |  | 10/1/2024 |  |  | N | No
AG1-541 | St. Johns 115 kV |  | VA | Hanover | Withdrawn | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1541_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1541_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 10/1/2024 |  |  | N | No
AG1-542 |  |  | VA | Greensville | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 10/16/2020 |  | 10/1/2024 |  |  | N | No
AG1-543 |  |  | VA | Charles City | Withdrawn | Dominion | 325 | 325 | 211.764 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/5/2020 |  | 10/1/2024 |  |  | N | No
AG1-544 | Bakers Pond DP 115 kV |  | VA | Prince George | Withdrawn | Dominion | 60 | 60 | 39.048 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1544_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 10/1/2024 |  |  | N | No
AG1-545 | W. Quaker Rd-Disputanta 34.5 kV |  | VA | Prince George | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1545_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1545_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/17/2021 |  | 10/1/2024 |  |  | N | No
AG1-546 | Ebony-Elams Road 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 150 | 97.62 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1546_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/17/2021 |  | 10/1/2024 |  |  | N | No
AG1-547 - moved to TC1 | Mount Airy-Chatham 69 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 50 | 50 | 32.54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1547_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 10/1/2024 |  |  | N | No
AG1-548 - moved to TC1 | Erie South-Union City 115 kV |  | PA | Erie | Active | PENELEC | 150 | 150 | 45 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1548_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG1-549 - moved to TC1 | Keystone 230 kV |  | PA | Armstrong | Withdrawn | PENELEC | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1549_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/22/2025 |  | 10/31/2022 |  |  | N | No
AG1-550 | Mount Eagle-Fork Union 230 kV |  | VA | Fluvanna | Withdrawn | Dominion | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1550_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 3/5/2021 |  | 9/1/2023 |  |  | N | No
AG1-551 - moved to TC1 | Parmele 34.5 kV | Parnell Solar | NC | Martin | Active | Dominion | 19.99 | 19.99 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1551_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1551_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/15/2023 |  |  | N | No
AG1-552 - moved to TC1 | Carolina 34.5 kV |  | NC | Northhampton | Active | Dominion | 18 | 18 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1552_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/15/2023 |  |  | N | No
AG1-553 - moved to TC1 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 260 | 260 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1553_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-554 | South Kenton 138 kV | Scioty Solar | OH | Hardin | Engineering and Procurement | AEP | 49.99 | 49.99 | 32.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1554_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1554_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1554_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_554_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 7/1/2027 | 9/30/2020 | N/A | N/A | 7/15/2027 |  |  | 10/1/2027 | 10/1/2027 |  | N | No
AG1-555 | Dequine 345 kV | Rainbow Trout | IN | Tippecance | Engineering and Procurement | AEP | 120 | 120 | 88.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1555_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1555_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1555_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ag1_555_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/30/2027 | 9/30/2020 | N/A | N/A | 11/15/2027 |  |  | 1/31/2028 | 1/31/2028 |  | N | No
AG1-556 - moved to TC1 | Lexington 115 kV |  | VA | Rockbridge | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1556_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/24/2024 |  | 6/1/2024 |  |  | N | No
AG1-557 | Curdsville DP 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 12/14/2020 |  | 10/21/2022 |  |  | N | No
AG1-558 | Buckner 34.5 kV | Horsepen Branch Solar | VA | Louisa | Engineering and Procurement | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1558_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1558_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1558_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1558_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 8/31/2027 |  |  | 10/29/2027 | 10/29/2027 |  | N | No
AG1-559 | Caroline Pines 22 kV | Reedy Creek | VA | Hanover | Engineering and Procurement | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1559_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1559_imp.htm | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1559_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1559_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 8/31/2027 |  |  | 10/27/2027 | 10/27/2027 |  | N | No
AG1-560 | Shade Gap-Roxbury 115 kV II |  | PA | Franklin | Withdrawn | PENELEC | 100.1 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1560_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 6/30/2023 |  |  | N | No
AG1-561 | Roxbury-Greene 138 kV II |  | PA | Franklin | Withdrawn | PENELEC | 80.3 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1561_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 9/12/2023 |  | 6/1/2022 |  |  | N | No
AG1-562 | Marysville-Gunn Road 345 kV | Taylor Creek | OH | Hardin | Withdrawn | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1562_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1562_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ag1562_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 1/28/2025 |  | 3/31/2028 | 3/31/2028 |  | N | No
AG1-563 | Bennett-Farmingdale 2 34.5 kV | AG1-563 | NJ | Monmouth | In Service | JCPL | 2 | 0 | 0.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1563_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1563_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_563_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2020 |  | 7/16/2021 | N | No
AG2-001 | St. Johns DP 115 kV |  | VA | Essex | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  | 12/18/2024 |  | 9/30/2022 |  |  | N | No
AG2-002 | Galion 138 kV III |  | OH | Morrow | Withdrawn | ATSI | 164 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-003 | West Millersport 138 kV |  | OH | Fairfield | Withdrawn | AEP | 120 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-004 | East Sidney-Quincy 138 kV |  | OH | Champaign | Withdrawn | Dayton | 164 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  | 12/18/2024 |  | 11/30/2021 |  |  | N | No
AG2-005 - moved to TC2 | Garner-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-006 | Centerburg-Conesville 138 kV |  | OH | Licking | Withdrawn | AEP | 177.5 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  | 12/18/2024 |  | 10/31/2023 |  |  | N | No
AG2-007 | Lanexa-Dunnsville 230 kV |  | VA | King William | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/6/2020 | N/A | N/A |  | 3/28/2024 |  | 11/15/2023 |  |  | N | No
AG2-008 - moved to TC2 | Erie South-Warren 230 kV |  | PA | Erie | Withdrawn | PENELEC | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2020 | N/A | N/A |  | 7/3/2025 |  | 3/30/2023 |  |  | N | No
AG2-009 - moved to TC2 | Erie South-Warren 230 kV II |  | PA | Erie | Withdrawn | PENELEC | 80 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2020 | N/A | N/A |  | 6/19/2025 |  | 3/30/2023 |  |  | N | No
AG2-010 - moved to TC2 | Peninsula-Whealton 115 kV |  | VA | City of Hampton | Active | Dominion | 100 | 100 | 75.96 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/9/2020 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AG2-011 | Laurel Mountain 138 kV |  | WV | Barbour | Withdrawn | APS | 56.3 | 56.3 | 34.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/2020 | N/A | N/A |  | 12/18/2024 |  | 4/1/2024 |  |  | N | No
AG2-012 | Lardin 12 kV |  | PA | Fayette | Withdrawn | APS | 0.165 | 0.165 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2012_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2012_wmpa.pdf | Not Required | N/A | N/A |  | 10/15/2020 | N/A | N/A |  | 3/8/2023 |  | 12/31/2023 | 12/31/2023 |  | Y | No
AG2-013 | Marysville-Sorenson 765 kV |  | OH | Logan | Withdrawn | AEP | 1300 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2020 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-014 - moved to TC2 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-016 - moved to TC2 | Oyster Creek-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2020 | N/A | N/A |  |  |  | 12/17/2021 |  |  | N | No
AG2-017 | New Castle-Clay Village 69 kV |  | KY | Shelby | Withdrawn | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2020 | N/A | N/A |  | 12/7/2020 |  | 9/30/2022 |  |  | N | No
AG2-018 |  |  | OH | Morgan | Withdrawn | AEP | 105 | 105 | 73.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2020 | N/A | N/A |  | 11/18/2020 |  | 4/29/2022 |  |  | N | No
AG2-019 | Chase City 12.5 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 15 | 15 | 6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 12/18/2024 |  | 12/30/2022 |  |  | N | No
AG2-020 - moved to TC2 | Arnolds Corner 34.5 kV |  | VA | King George | Withdrawn | Dominion | 7 | 7 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 7/3/2025 |  | 12/30/2022 |  |  | N | No
AG2-021 | Crossroads 13.2 kV |  | PA | York | Withdrawn | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 10/15/2024 |  | 12/15/2021 |  |  | N | No
AG2-022 | Ebenezer 12.47 kV |  | PA | Dauphin | Withdrawn | PPL | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 8/8/2024 |  | 12/15/2021 |  |  | N | No
AG2-023 | Mechanicsburg 12.47 kV |  | PA | Cumberland | Withdrawn | PPL | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 8/8/2024 |  | 12/15/2021 |  |  | N | No
AG2-024 | Allen 13.2 kV |  | PA | Cumberland | Withdrawn | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 10/15/2024 |  | 12/15/2021 |  |  | N | No
AG2-025 | Mountain 13.2 kV |  | PA | Cumberland | Withdrawn | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 10/15/2024 |  | 12/15/2021 |  |  | N | No
AG2-026 | Leesport 34.5 kV |  | PA | Berks | Withdrawn | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 10/15/2024 |  | 12/15/2021 |  |  | N | No
AG2-027 | Orrtanna 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 10/15/2024 |  | 12/15/2021 |  |  | N | No
AG2-028 | Lincoln 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  | 10/15/2024 |  | 12/15/2021 |  |  | N | No
AG2-029 - moved to TC2 | Forest G. Hipple-Collingwood 345 kV |  | IN | Noble | Active | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-030 | White Stone-Harmony Village 115 kV |  | N/A | N/A | Withdrawn | Dominion |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Issued |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2020 | N/A | N/A |  | 6/1/2022 |  | 10/26/2020 |  |  | EE | No
AG2-031 | East Canton-Robertsville 69 kV |  | OH | Stark | Withdrawn | AEP | 49.9 | 30.2 | 22.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2020 | N/A | N/A |  | 11/11/2024 |  | 1/1/2023 |  |  | N | No
AG2-032 | Mannington 230 kV |  | NJ | Salem | Withdrawn | AEC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2020 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-033 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 137 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/4/2020 | N/A | N/A |  | 4/26/2024 |  | 10/31/2023 |  |  | N | No
AG2-034 | Emporia-Pleasant Hill 115 kV |  | VA | Greensville | Withdrawn | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/4/2020 | N/A | N/A |  | 12/18/2024 |  | 10/1/2024 |  |  | N | No
AG2-035 - moved to TC2 | Salem - Woodstown 69 kV |  | NJ | Salem | Withdrawn | AEC | 71 | 33 | 22 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2020 | N/A | N/A |  | 2/11/2025 |  | 12/31/2021 |  |  | N | No
AG2-036 | Mantua 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2020 | N/A | N/A |  | 12/18/2024 |  | 12/31/2021 |  |  | N | No
AG2-037 - moved to TC2 | Findlay-Clinton 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 4.7 | 2.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2020 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AG2-038 | Boyers DP 25 kV |  | PA | Venango | Withdrawn | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  | 12/18/2024 |  | 3/30/2022 |  |  | N | No
AG2-039 | Erie West-Fairview East 34.5 kV |  | PA | Erie | Withdrawn | PENELEC | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  | 12/18/2024 |  | 3/30/2022 |  |  | N | No
AG2-040 | Garman-Greenwich Mine 34.5 kV |  | PA | Indiana | Withdrawn | PENELEC | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  | 12/18/2024 |  | 3/30/2022 |  |  | N | No
AG2-041 | Jamestown Tap-Maysville 69 kV |  | PA | Mercer | Withdrawn | ATSI | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  | 12/18/2024 |  | 3/30/2022 |  |  | N | No
AG2-042 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/11/2020 |  | 12/31/2021 |  |  | Y | No
AG2-043 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/11/2020 |  | 12/31/2021 |  |  | Y | No
AG2-044 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/11/2020 |  | 12/31/2021 |  |  | Y | No
AG2-045 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/11/2020 |  | 7/31/2022 |  |  | Y | No
AG2-046 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/11/2020 |  | 7/31/2022 |  |  | Y | No
AG2-047 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/11/2020 |  | 12/31/2021 |  |  | Y | No
AG2-048 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2020 | N/A | N/A |  | 12/22/2020 |  | 12/31/2021 |  |  | Y | No
AG2-049 - moved to TC2 | Van Dorn 34.5 kV |  | VA | Arlington | Active | Dominion | 20 | 0 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AG2-050 | Randle Cliff 13.8 kV | CHESAPEAKE BEACH BESS | MD | Calvert | In Service | BGE | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2050_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2050_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2050_wmpa.pdf | Not Required | N/A | N/A |  | 11/25/2020 | N/A | N/A | 5/1/2023 |  |  | 5/1/2023 | 5/1/2023 | 5/9/2023 | Y | No
AG2-051 | St. Johns DP 115 kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2020 | N/A | N/A |  | 12/18/2024 |  | 3/31/2023 |  |  | N | No
AG2-052 5090276 | NIPS-PJM |  | N/A | N/A | Confirmed |  |  | 2 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ag2052_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/3/2020 | 2/1/2021 | 2/1/2026 | [6 empty] | PP | No
AG2-053 - moved to TC2 | Fulton 138 kV |  | OH | Fulton | Withdrawn | ATSI | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2020 | N/A | N/A |  | 7/2/2025 |  | 9/25/2024 |  |  | N | No
AG2-054 - moved to TC2 | Fulton 138 kV |  | OH | Fulton | Withdrawn | ATSI | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2020 | N/A | N/A |  | 7/2/2025 |  | 9/25/2024 |  |  | N | No
AG2-055 | Deans 500 kV |  | NJ | Middlesex | Withdrawn | PSEG | 1300 | 1300 | 370.92 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2020 | N/A | N/A |  | 12/19/2024 |  | 11/1/2027 |  |  | N | No
AG2-056 | Gore 138 kV |  | VA | Frederick | Withdrawn | APS | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2020 | N/A | N/A |  | 11/7/2024 |  | 5/31/2022 |  |  | N | No
AG2-057 - moved to TC2 | Cardington-Liberty 69 kV II |  | OH | Morrow | Active | ATSI | 74 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/7/2020 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AG2-058 | Harmony Village-White Marsh 115 kV |  | VA | Gloucester | Withdrawn | Dominion | 70 | 70 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/8/2020 | N/A | N/A |  | 12/18/2024 |  | 6/3/2024 |  |  | N | No
AG2-059 | Clubhouse-Lakeview 230 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 80 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/8/2020 | N/A | N/A |  | 12/10/2024 |  | 6/3/2024 |  |  | N | No
AG2-060 | Hanover-Plymouth 69 kV |  | PA | Luzerne | Withdrawn | UGI | 12.6 | 12.6 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2020 | N/A | N/A |  | 12/18/2024 |  | 3/8/2022 |  |  | N | No
AG2-061 - moved to TC2 | Dana 345 kV |  | IL | Lasalle | Active | ComEd | 200 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-062 - moved to TC2 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 147 | 21.609 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/15/2020 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AG2-063 - moved to TC2 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 54 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/16/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-064 | St Johns DP 115 kV |  | VA | Caroline | Withdrawn | Dominion | 41 | 41 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/17/2020 | N/A | N/A |  | 12/18/2024 |  | 10/31/2023 |  |  | N | No
AG2-065 | River Ridge 34.5 kV |  | VA | Prince William | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2020 | N/A | N/A |  | 8/23/2022 |  | 12/15/2021 |  |  | N | No
AG2-066 | Rockcastle 138 kV |  | VA | Bedford | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2020 | N/A | N/A |  | 11/7/2024 |  | 5/30/2022 |  |  | N | No
AG2-067 | Heritage-Wake 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-068 - moved to TC2 | Heritage - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-069 - moved to TC2 | Heritage - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 250 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-070 | Chickhominy-Surry 500 kV |  | VA | Charles City | Withdrawn | Dominion | 325 | 325 | 228 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  | 12/18/2024 |  | 10/1/2024 |  |  | N | No
AG2-071 | Cumberland 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2020 | N/A | N/A |  | 1/3/2022 |  | 12/31/2021 |  |  | N | No
AG2-072 - moved to TC2 | Rockport 765 kV |  | IN | Spencer | Active | AEP | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2021 | N/A | N/A |  |  |  | 5/31/2026 |  |  | N | No
AG2-073 - moved to TC2 | Crooksville 69 kV |  | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-074 - moved to TC2 | Meckesville Tap 69kV |  | PA | Carbon | Active | PPL | 38 | 38 | 26.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/15/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-075 | Hartland 12.47 kV |  | OH | Fayette | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2021 | N/A | N/A |  | 3/22/2021 |  | 9/14/2022 |  |  | Y | No
AG2-076 | Raritan River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 660 | 660 | 660 |  | Capacity | Merchant Transmission |  | DC | 660 F/TIR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2021 | N/A | N/A |  | 12/18/2024 |  | 1/1/2024 |  |  | S | No
AG2-077 - moved to TC2 | Clover-Rawlings 500 kV |  | VA | Charlotte | Active | Dominion | 700 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-078 | Lappans 34.5 kV |  | MD | Washington | Withdrawn | APS | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2021 | N/A | N/A |  | 12/18/2024 |  | 5/23/2022 |  |  | N | No
AG2-079 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Withdrawn | APS | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2021 | N/A | N/A |  | 12/18/2024 |  | 4/11/2022 |  |  | N | No
AG2-080 - moved to TC2 | Lexington 115 kV |  | VA | Rockbridge | Withdrawn | Dominion | 100 | 100 | 78 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2021 | N/A | N/A |  | 7/7/2025 |  | 6/1/2024 |  |  | N | No
AG2-081 - moved to TC2 | Mt. Sterling-Fogg Pike 69 kV |  | KY | Montgomery | Active | EKPC | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-082 - moved to TC2 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 200 | 200 | 133.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-083 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-084 - moved to TC2 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  | 4/3/2025 |  | 12/31/2023 |  |  | N | No
AG2-085 - moved to TC2 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 140 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-086 - moved to TC2 | Mt. Jackson DP-Mt. Jackson 115 kV |  | VA | Shenandoah | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AG2-087 | Pennsauken 12 kV |  | NJ | Camden | Withdrawn | PSEG | 2.49 | 2.49 | 0.772 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/5/2021 | N/A | N/A |  | 4/6/2021 |  | 1/1/2022 |  |  | N | No
AG2-088 - moved to TC2 | Midlothian 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 4/15/2022 |  |  | N | No
AG2-089 | Pelikan-Kennaloyal 25 kV |  | PA | Westmoreland | Withdrawn | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2022 |  |  | N | No
AG2-090 - moved to TC2 | Scalp Level 23 kV IV |  | PA | Somerset | Active | PENELEC | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 1/31/2023 |  |  | N | No
AG2-091 - moved to TC2 | Scalp Level 23 kV V |  | PA | Somerset | Active | PENELEC | 20 | 6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-092 - moved to TC2 | Todd 69 kV |  | MD | Dorchester | Withdrawn | DPL | 50 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  | 7/7/2025 |  | 12/31/2021 |  |  | N | No
AG2-093 - moved to TC2 | Colonial Trail-Hopewell 230 kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-094 - moved to TC2 | Summer Shade-Green County 161 kV |  | KY | Metcalfe | Withdrawn | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2021 | N/A | N/A |  | 5/5/2025 |  | 4/1/2024 |  |  | N | No
AG2-095 - moved to TC2 | Hopewell 34.5 kV (Circuit 313) |  | VA | Prince George | Active | Dominion | 18 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 12/8/2023 |  |  | N | No
AG2-096 - moved to TC2 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | PA | Dauphin | Withdrawn | PPL | 55 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 6/26/2025 |  | 12/1/2022 |  |  | N | No
AG2-097 | Altoona-Raystown 230 kV II |  | PA | Blair | Withdrawn | PENELEC | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 8/7/2024 |  | 6/30/2022 |  |  | N | No
AG2-098 - moved to TC2 | Copperstone-North Lebanon 230 kV II |  | PA | Lebanon | Withdrawn | ME | 70 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 2/10/2025 |  | 6/30/2022 |  |  | N | No
AG2-099 - moved to TC2 | Moshannon-Milesburg 230 kV V |  | PA | Centre | Withdrawn | APS | 161.98 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 3/3/2025 |  | 6/30/2022 |  |  | N | No
AG2-100 - moved to TC2 | Moshannon-Milesburg 230 kV VI |  | PA | Centre | Withdrawn | APS | 161.98 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 3/3/2025 |  | 6/30/2022 |  |  | N | No
AG2-101 | Princess Anne–Loretto 69 kV |  | MD | Somerset | Withdrawn | DPL | 58.6 | 58.6 | 35.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-102 | Oak Hall-Perdue 69 kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-103 | Oak Hall-Hallwood 69 kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-104 - moved to TC2 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 253.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AG2-105 | Marysville-Flatlick 765 kV |  | OH | Madison | Withdrawn | AEP | 800 | 400 | 253.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2026 |  |  | N | No
AG2-106 - moved to TC2 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-107 - moved to TC2 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-108 | Milford-Cool Springs 230 kV |  | DE | Sussex | Withdrawn | DPL | 460 | 460 | 130.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2026 |  |  | N | No
AG2-109 - moved to TC2 | Fitchville-New London 69 kV |  | OH | Huron | Active | ATSI | 40 | 40 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-110 | Marysville-Tangy 345 kV |  | OH | Union | Withdrawn | AEP | 300 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2024 |  |  | N | No
AG2-111 - moved to TC2 | Perth 34.5 kV Substation (Circuit 408) |  | VA | Campbell | Active | Dominion | 14.5 | 14.5 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 2/6/2023 |  |  | N | No
AG2-112 - moved to TC2 | Perth 34.5 kV Substation (Circuit 404) |  | VA | Halifax | Active | Dominion | 15.2 | 15.2 | 9.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 3/24/2023 |  |  | N | No
AG2-113 | Nokesville-Vint Hill 230 kV |  | VA | Prince William | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 8/10/2022 |  |  | N | No
AG2-114 - moved to TC2 | Dresden-Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-115 | Mt. Hermon 25 kV |  | MD | Wicomico | Withdrawn | DPL | 8.47 | 8.466 | 3.5557 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 8/29/2022 |  |  | N | No
AG2-116 - moved to TC2 | Olive-Reynolds 345 #1 345 kV |  | IN | White | Withdrawn | AEP | 300 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 7/3/2025 |  | 10/31/2023 |  |  | N | No
AG2-117 | Olive-Reynolds #2 345 kV |  | IN | White | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2023 |  |  | N | No
AG2-118 | Ford-Cedarville 138 kV |  | OH | Clermont | Withdrawn | DEOK | 84 | 84 | 56.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2024 |  |  | N | No
AG2-119 - moved to TC2 | Galion-Roberts South 138 kV II |  | OH | Marion | Active | ATSI | 80 | 80 | 53.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-120 - moved to TC2 | Everetts 34.5 kV |  | NC | Martin | Active | Dominion | 21 | 21 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/15/2024 |  |  | N | No
AG2-121 - moved to TC2 | Mackeys 230 kV |  | NC | Washington | Active | Dominion | 140 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-122 | Crystal Hill - Halifax 115 kV |  | VA | Halifax | Withdrawn | Dominion | 64.7 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/17/2024 |  | 6/30/2022 |  |  | N | No
AG2-123 | Sedge Hill - Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 75.1 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/17/2024 |  | 6/30/2022 |  |  | N | No
AG2-124 - moved to TC2 | Shackleford-Harmony 115 kV |  | VA | King and Queen | Active | Dominion | 149.9 | 0 | 33.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-125 - moved to TC2 | Camden-Crystal 69 kV |  | OH | Preble | Active | Dayton | 69.9 | 0 | 15.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-126 - moved to TC2 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-127 | Gladstone 138 kV |  | VA | Nelson | Withdrawn | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2024 |  |  | N | No
AG2-128 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AG2-129 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AG2-130 - moved to TC2 | Colby Tap-Valley 138 kV |  | MI | Van Buren | Withdrawn | AEP | 55 | 55 | 37.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2021 | N/A | N/A |  | 3/30/2025 |  | 12/31/2026 |  |  | N | No
AG2-131 - moved to TC2 | Almena-Valley 69 kV |  | MI | Van Buren | Withdrawn | AEP | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2021 | N/A | N/A |  | 3/31/2025 |  | 12/31/2026 |  |  | N | No
AG2-132 - moved to TC2 | Hartford-South Haven 69 kV |  | MI | Van Buren | Withdrawn | AEP | 15 | 15 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2021 | N/A | N/A |  | 3/30/2025 |  | 12/31/2026 |  |  | N | No
AG2-133 | South Creek 69 kV |  | VA | Appomattox | Withdrawn | Dominion | 52.44 | 52.44 | 34.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2021 | N/A | N/A |  | 1/23/2024 |  | 12/31/2023 |  |  | N | No
AG2-134 |  |  | PA | Montgomery | Withdrawn | PPL | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2021 | N/A | N/A |  | 2/25/2021 |  | 8/31/2022 |  |  | N | No
AG2-135 | Hoffman Estates 12.5 kV | Patel Brothers Energy Storage System | OH | Pickaway | Withdrawn | ComEd | 0.28 | 0.28 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2135_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2135_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2135_wmpa.pdf | Not Required | N/A | N/A |  | 2/4/2021 | N/A | N/A |  | 1/10/2022 |  | 4/15/2022 | 4/15/2022 |  | Y | No
AG2-136 | Lake Lynn-Lardin 138 kV |  | PA | Fayette | Withdrawn | APS | 119.6 | 119.6 | 74.152 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2021 | N/A | N/A |  | 4/23/2021 |  | 12/31/2023 |  |  | N | No
AG2-137 | Surry-Chuckatuck 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 70 | 70 | 43.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/8/2021 | N/A | N/A |  | 12/18/2024 |  | 6/3/2024 |  |  | N | No
AG2-138 | Olive-University Park 345 kV |  | IN | LaPorte | Withdrawn | AEP |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/9/2021 | N/A | N/A |  | 10/20/2023 |  | 6/1/2022 |  |  | EE | No
AG2-139 | Lincoln 771-4 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/9/2021 | N/A | N/A |  | 8/9/2024 |  | 8/1/2022 |  |  | N | No
AG2-140 | Wylie Ridge 345 kV |  | N/A | N/A | Withdrawn | APS |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Issued |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2021 | N/A | N/A |  | 9/29/2023 |  | 6/1/2022 |  |  | EE | No
AG2-141 | Wylie Ridge-Toronto 345 kV |  | PA | Adams | Withdrawn | APS |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2021 | N/A | N/A |  | 10/23/2023 |  | 6/1/2022 |  |  | EE | No
AG2-142 | Bowman's Mill 69 kV |  | PA | Columbia | Withdrawn | PPL | 13 | 13 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2021 | N/A | N/A |  | 10/6/2023 |  | 11/30/2023 |  |  | N | No
AG2-143 - moved to TC2 | Burma-Sligo 25 kV |  | PA | Clarion | Withdrawn | APS | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2021 | N/A | N/A |  | 3/14/2025 |  | 12/31/2026 |  |  | N | No
AG2-144 | Carlls Corner 12 kV |  | NJ | Salem | Withdrawn | AEC | 1.5 | 1.5 | 0.63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2021 | N/A | N/A |  | 3/11/2022 |  |  |  |  | N | No
AG2-145 | Page-Bethel 138 kV |  | VA | Pulaski | Withdrawn | APS | 100 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 8/3/2023 |  | 6/30/2022 |  |  | N | No
AG2-146 | Werner 230 kV-Ravenwood 345 kV |  | NJ | Middlesex | Withdrawn | JCPL | 1242 | 1242 | 0 |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2026 |  |  | S | No
AG2-147 | Pontiac Midpoint 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2024 |  |  | N | No
AG2-148 - moved to TC2 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 86 | 86 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-149 - moved to TC2 | Galion-South Berwick 345 kV |  | OH | Crawford | Active | AEP | 400 | 314 | 52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-150 - moved to TC2 | River Dock 23 kV |  | PA | Allegheny | Withdrawn | DL | 5.25 | 5.25 | 5.25 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2021 | N/A | N/A |  | 4/7/2025 |  | 12/31/2022 |  |  | N | No
AG2-151 - moved to TC2 | Trices Lake - James River Tap 115 kV |  | VA | Cumberland | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2021 | N/A | N/A |  |  |  | 2/2/2024 |  |  | N | No
AG2-152 - moved to TC2 | Banister-Bear Skin 138 kV |  | VA | Pittsylvania | Active | AEP | 131 | 131 | 79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2021 | N/A | N/A |  |  |  | 2/2/2024 |  |  | N | No
AG2-153 | Headquarters-Sideview 69 kV |  | KY | Bourbon | Withdrawn | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2023 |  |  | N | No
AG2-154 | Danville 12 kV |  | PA | Northumberland | Withdrawn | PPL | 1 | 1 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2022 |  |  | N | No
AG2-155 | Linden 12 kV |  | PA | Lycoming | Withdrawn | PPL | 2.8 | 2.8 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2022 |  |  | N | No
AG2-156 | Montgomery 12 kV |  | PA | Lycoming | Withdrawn | PPL | 5.1 | 5.1 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2022 |  |  | N | No
AG2-157 | Ashfield 12 kV |  | PA | Carbon | Withdrawn | PPL | 1.5 | 1.5 | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2022 |  |  | N | No
AG2-158 |  |  | KY | Russell | Withdrawn | EKPC | 44 | 44 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 2/26/2021 |  | 9/15/2023 |  |  | N | No
AG2-159 - moved to TC2 | Williamstown 69 kV |  | KY | Grant | Active | EKPC | 61 | 61 | 57.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-160 |  |  | KY | Adair | Withdrawn | EKPC | 53 | 53 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 3/16/2021 |  | 9/15/2023 |  |  | N | No
AG2-161 - moved to TC2 | Wheelabrator Frackville-Gilberton 69 kV |  | PA | Schuylkill | Active | PPL | 43 | 43 | 18.06 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-162 - moved to TC2 | Jefferson-Greentown 765 kV |  | IN | Rush | Active | AEP | 115 | 115 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-163 - moved to TC2 | Dequine-Eugene 345 kV |  | IN | Fountain | Active | AEP | 700 | 250 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-164 - moved to TC2 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 385 | 270 | 35.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-165 - moved to TC2 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-166 - moved to TC2 | Newville-Nottingham Tap 1 69 kV |  | PA | Cumberland | Active | PPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 8/18/2023 |  |  | N | No
AG2-167 | Morgan Street-Cochranton 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 20 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-168 | Clinch River-Copper Ridge 138 kV |  | VA | Russell | Withdrawn | AEP | 95 | 95 | 63.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-169 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 70 | 70 | 46.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-170 | Whitewater Valley Power Station 69 kV |  | IN | Wayne | Withdrawn | AEP | 88 | 88 | 58.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-171 - moved to TC2 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 7/3/2024 |  |  | N | No
AG2-172 | Kittatinny 230 kV |  | NJ | Warren | Withdrawn | JCPL | 450 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2022 |  |  | N | No
AG2-173 | Twin Branch-Meridian 345 kV |  | IN | Whitley | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-174 | Jack Frost-Lake Harmony 69 kV |  | PA | Carbon | Withdrawn | PPL | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/30/2024 |  |  | N | No
AG2-175 | Van Wert-Delphos 69 kV |  | OH | Van Wert | Withdrawn | AEP | 65 | 65 | 49 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-176 - moved to TC2 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 1/31/2024 |  |  | N | No
AG2-177 | Limecrest-Woodruff's Gap 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 2/23/2022 |  |  | N | No
AG2-178 | Remington 34.5 kV |  | VA | Fauquier | Withdrawn | Dominion | 14.125 | 14.125 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/30/2022 |  |  | N | No
AG2-179 - moved to TC2 | Coburg 69 kV |  | KY | Adair | Active | EKPC | 60 | 60 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-180 | Paulsboro 69 kV |  | NJ | Gloucester | Withdrawn | AEC | 79 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 2/25/2021 |  |  | N | No
AG2-181 - moved to TC2 | Airey - Golden Hill 69 kV |  | MD | Dorchester | Active | DPL | 28 | 28 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-182 - moved to TC2 | Doubs-Bismark 500 kV |  | VA | Frederick | Active | Dominion | 200 | 200 | 133.3333 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-183 |  |  | KY | Hardin | Withdrawn | EKPC | 45 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 3/19/2021 |  | 12/31/2022 |  |  | N | No
AG2-184 - moved to TC2 | Harbert Metering 138 kV |  | KY | Knott | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-185 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Withdrawn | PPL | 40 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 8/26/2024 |  | 5/1/2024 |  |  | N | No
AG2-186 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Withdrawn | PPL | 45.2 | 5.2 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 8/26/2024 |  | 6/1/2024 |  |  | N | No
AG2-187 | Amherst-Riverville 138 kV |  | VA | Amherst | Withdrawn | AEP | 115 | 40 | 33.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2024 |  |  | N | No
AG2-188 - moved to TC2 | Farmville - Buckingham 230 kV |  | VA | Cumberland | Active | Dominion | 140 | 140 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-189 - moved to TC2 | Washington-Furnace Brook Tap 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  | 6/26/2025 |  | 2/23/2022 |  |  | N | No
AG2-190 | Huffman 138 kV |  | VA | Carroll | Withdrawn | AEP | 77.4 | 77.4 | 46.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  | 3/31/2021 |  | 10/31/2024 |  |  | N | No
AG2-191 - moved to TC2 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AG2-192 - moved to TC2 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 19 | 19 | 11.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-193 - moved to TC2 | Turner 34.5 kV |  | VA | Henrico | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-194 | Pierce-Kyger Creek 345 kV |  | OH | Highland | Withdrawn | OVEC | 170 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  | 12/13/2024 |  | 12/31/2024 |  |  | N | No
AG2-195 | Dowling 138 kV |  | OH | Wood | Withdrawn | ATSI | 53 | 53 | 22.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-196 |  |  | MD | Baltimore County | Withdrawn | BGE | 9.3 | 9.3 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2021 | N/A | N/A |  | 3/25/2021 |  | 12/30/2022 |  |  | N | No
AG2-197 | Nelson- Electrical Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 295.9 | 295.9 | 52 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-198 - moved to TC2 | Briery - Finneywood 230 kV |  | VA | Prince Edward | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2021 | N/A | N/A |  |  |  | 2/25/2024 |  |  | N | No
AG2-199 | Birchwood-NUG 230 kV |  | VA | King George | Withdrawn | Dominion | 55 | 55 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2021 | N/A | N/A |  | 12/18/2024 |  | 10/10/2023 |  |  | N | No
AG2-200 - moved to TC2 | North Warren–Russell 34.5 kV |  | PA | Warren | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-201 | Carwick Junction 25 kV |  | PA | Clarion | Withdrawn | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2021 | N/A | N/A |  | 4/26/2021 |  | 1/15/2023 |  |  | N | No
AG2-202 - moved to TC2 | Reusens 12.47 kV |  | VA | City of Lynchburg | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  | 3/11/2025 |  | 10/31/2022 |  |  | N | No
AG2-203 | Perkins Park 12.47 kV |  | VA | City of Lynchburg | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2022 |  |  | N | No
AG2-204 | Athenia 26 kV |  | NJ | Essex | Withdrawn | PSEG | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  | 12/19/2024 |  | 10/31/2022 |  |  | N | No
AG2-205 | Bonney Forge 23 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 3.7 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2205_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2205_wmpa.pdf | Not Required | N/A | N/A |  | 3/6/2021 | N/A | N/A |  | 6/2/2023 |  | 3/31/2024 | 3/31/2024 |  | Y | No
AG2-206 - moved to TC2 | Tennessee Gas-East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 48 | 48 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-207 | Brandon Shores 230 kV |  | MD | Anne Arundel | Withdrawn | BGE | 275 | 275 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  | 12/12/2024 |  | 3/31/2023 |  |  | N | No
AG2-208 - moved to TC2 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 70 | 70 | 44.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-209 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Withdrawn | Dominion | 70 | 0 | 20.76 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2021 | N/A | N/A |  | 12/17/2024 |  | 6/30/2024 |  |  | N | No
AG2-210 |  |  | VA | Orange | Withdrawn | Dominion | 70 | 70 | 44.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2021 | N/A | N/A |  | 3/29/2021 |  | 6/30/2024 |  |  | N | No
AG2-211 |  |  | VA | Orange | Withdrawn | Dominion | 70 | 0 | 20.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2021 | N/A | N/A |  | 3/29/2021 |  | 6/30/2024 |  |  | N | No
AG2-212 - moved to TC2 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 400 | 200 | 26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-213 - moved to TC2 | Gary D.P Tap - Gary D.P 115 kV |  | VA | Lunenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-214 | Red House D.P - Sugar Hill 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 60 | 60.17 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-215 - moved to TC2 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 0 | 36.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-216 - moved to TC2 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 144 | 0 | 25.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-217 | Watkins Corner 34.5 kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20.9 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  | 9/17/2024 |  | 4/29/2023 |  |  | N | No
AG2-218 | La Rue 69 kV |  | OH | Marion | Withdrawn | AEP | 49.5 | 49.5 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/2/2024 |  |  | N | No
AG2-219 - moved to TC2 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 715 | 330 | 42.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-220 - moved to TC2 | East Towanda-South Troy 115 kV |  | PA | Bradford | Active | PENELEC | 31 | 31 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AG2-221 - moved to TC2 | South Troy - North Towanda 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AG2-222 | Tanners Creek-Hanna 345 kV |  | IN | Rush | Withdrawn | AEP | 83 | 83 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/2/2024 |  |  | N | No
AG2-223 | Allen Junction 345 kV |  | OH | Lucas | Withdrawn | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2023 |  |  | N | No
AG2-224 | Essex 230 kV |  | NJ | Essex | Withdrawn | PSEG | 90 | 90 | 36 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  | 5/30/2023 |  | 12/31/2022 |  |  | N | No
AG2-225 | Wagner 115 kV |  | MD | Anne Arundel | Withdrawn | BGE | 135 | 115 | 46 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  | 12/12/2024 |  | 12/31/2022 |  |  | N | No
AG2-226 | Martins Creek 69 kV II |  | PA | Northampton | Withdrawn | PPL | 52 | 52 | 20.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2021 | N/A | N/A |  | 10/17/2024 |  | 12/31/2022 |  |  | N | No
AG2-227 | Harwood 69 kV |  | PA | Luzerne | Withdrawn | PPL | 33 | 33 | 13.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2021 | N/A | N/A |  | 11/28/2023 |  | 10/31/2022 |  |  | N | No
AG2-228 - moved to TC2 | Washington-Furnace Brook Tap 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 11.2 | 11.2 | 4.704 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  | 6/26/2025 |  | 3/31/2022 |  |  | N | No
AG2-229 | Floyd 138 kV |  | VA | Floyd | Withdrawn | AEP | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  | 12/18/2024 |  | 1/1/2024 |  |  | N | No
AG2-230 - moved to TC2 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-231 | Arrowhead 12 kV |  | PA | Monroe | Withdrawn | PPL | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2021 | N/A | N/A |  | 9/5/2023 |  | 12/1/2023 |  |  | N | No
AG2-232 | Saint Thomas - CNG 34.5 kV |  | PA | Franklin | Withdrawn | APS | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-233 | Montgomery Hydroelectric 23 kV |  | PA | Beaver | Withdrawn | DL | 20 | 20 | 17.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-234 | Neville 23 kV |  | PA | Allegheny | Withdrawn | DL | 20 | 3.2 | 1.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-235 | Lincoln-Berrywood 69 kV |  | OH | Delaware | Withdrawn | AEP | 73 | 73 | 30.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-236 - moved to TC2 | Potter-Harlan 69 kV |  | PA | Lawrence | Active | ATSI | 60 | 20 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  |  |  | 10/30/2024 |  |  | N | No
AG2-237 - moved to TC2 | Thelma 230kV |  | NC | Northhampton | Active | Dominion | 323 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-238 - moved to TC2 | Earleys 230 kV |  | NC | Hertford | Active | Dominion | 99.9 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-239 - moved to TC2 | Hickory-Shawboro 230 kV |  | NC | Currituck | Active | Dominion | 120 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-240 - moved to TC2 | Old Church 34.5 kV |  | VA | Hanover | Active | Dominion | 25 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-241 | Roadstown 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 47 | 47 | 31.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  | 12/18/2024 |  | 9/15/2023 |  |  | N | No
AG2-242 | Olive-University Park 345 kV |  | IN | Adams | Withdrawn | AEP |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  | 12/14/2023 |  | 6/1/2023 |  |  | EE | No
AG2-243 | Rome-Orwell 36 kV |  | OH | Ashtabula | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-244 | Winfield-Presrite Corp 36 kV |  | OH | Ashtabula | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-245 - moved to TC2 | Olive - Reynolds #1 345 kV |  | IN | Starke | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-246 | Whitehouse-Lone Gum 138 kV |  | VA | Bedford | Withdrawn | AEP | 102.1 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 4/12/2024 |  | 6/30/2022 |  |  | N | No
AG2-247 - moved to TC2 | Northwestern REC Dixonburg-Vernon 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  | 2/6/2025 |  | 1/15/2023 |  |  | N | No
AG2-248 - moved to TC2 | East Elkhart – Elcona Tap 138 kV |  | IN | Elkhart | Active | AEP | 100 | 100 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-249 - moved to TC2 | Stoneboro-Perry 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-250 - moved to TC2 | Stoneboro-Perry 69 kV II |  | PA | Mercer | Active | ATSI | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-251 | Dilworth 69 kV |  | OH | Trumbull | Withdrawn | ATSI | 29 | 29 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-252 | Dilworth 69 kV II |  | OH | Trumbull | Withdrawn | ATSI | 49 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-253 | Dilworth 69 kV III |  | OH | Trumbull | Withdrawn | ATSI | 69 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-254 | New Lisbon 12.47 kV |  | NJ | Burlington | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 12/18/2024 |  | 3/30/2022 |  |  | N | No
AG2-255 | South Hampton 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 12/19/2024 |  | 3/30/2022 |  |  | N | No
AG2-256 |  |  | NJ | Somerset | Withdrawn | PSEG | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 4/12/2021 |  | 6/15/2022 |  |  | N | No
AG2-257 |  |  | NJ | Ocean | Withdrawn | JCPL | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 4/13/2021 |  | 9/15/2022 |  |  | N | No
AG2-258 | Carson – Rogers Road 500 kV |  | VA | Accomack | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2024 |  |  | N | No
AG2-259 | Sherwood - Kidds Store 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/18/2024 |  | 3/4/2024 |  |  | N | No
AG2-260 - moved to TC2 | Crystal Hill - Perth 115 kV |  | VA | Halifax | Withdrawn | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 3/31/2025 |  | 12/1/2025 |  |  | N | No
AG2-261 | Lake View - Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-262 - moved to TC2 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 47 | 11 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-263 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Withdrawn | Dayton | 40 | 40 | 31.14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-264 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Withdrawn | Dayton | 60 | 20 | 14.74 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-265 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Withdrawn | Dayton | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-266 | National-Tangy 138 kV II |  | OH | Madison | Withdrawn | ATSI | 57 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/1/2023 |  | 12/31/2024 |  |  | N | No
AG2-267 | Branchton 12.47 kV |  | PA | Butler | Withdrawn | APS | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-268 | Sedge Hill 230 kV |  | VA | Halifax | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-269 | Chesterfield 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-270 - moved to TC2 | Clover 230 kV |  | VA | Halifax | Active | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-271 | Indian River 230 kV |  | DE | Sussex | Withdrawn | DPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-272 - moved to TC2 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 55 | 55 | 21.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-273 | Wurno 138 kV |  | VA | Pulaski | Withdrawn | AEP | 120 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 4/5/2023 |  | 12/31/2023 |  |  | N | No
AG2-274 | Hebron 69 kV II |  | MD | Wicomico | Withdrawn | DPL | 45.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2022 |  |  | N | No
AG2-275 | Southwest 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-276 | Tyler 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-277 | Robinson 69 kV |  | OH | Fayette | Withdrawn | Dayton | 40 | 40 | 34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-278 | Robinson 69 kV |  | OH | Fayette | Withdrawn | Dayton | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-279 - moved to TC2 | Hagerstown-Conservit 34.5 kV |  | MD | Washington | Active | APS | 20 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AG2-280 | Walker 34.5 kV |  | PA | Pike | Withdrawn | ME | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-281 - moved to TC2 | Church 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-282 - moved to TC2 | Kuranga Power Generator |  | OH | Butler | Withdrawn | DEOK | 10 | 10 | 3.102 |  | Capacity | Generation Interconnection | Solar; Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 2/12/2025 |  | 2/10/2022 |  |  | N | No
AG2-283 | Yorktown 230 kV |  | VA | York | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-284 - moved to TC2 | Catharpin 230 kV |  | VA | Prince William | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2023 |  |  | N | No
AG2-285 | Loudoun 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-286 | Clifton 230 kV |  | VA | Fairfax | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-287 | Beaumeade 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-288 - moved to TC2 | Stonewall 138 kV |  | VA | Frederick | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-289 - moved to TC2 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 66.6 | 66.6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-290 - moved to TC2 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 105 | 38.4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-291 | Williams Central 115 kV |  | PA | Susquehanna | Withdrawn | PENELEC | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 8/13/2024 |  | 12/31/2023 |  |  | N | No
AG2-292 | Scotch Hollow 230 kV |  | PA | Bradford | Withdrawn | PENELEC | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 8/13/2024 |  | 11/30/2023 |  |  | N | No
AG2-293 | Williams Potter Tap 115 kV |  | PA | Susquehanna | Withdrawn | PENELEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 8/13/2024 |  | 12/31/2023 |  |  | N | No
AG2-294 | MacNew 115 kV |  | PA | Susquehanna | Withdrawn | PENELEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  | 8/13/2024 |  | 12/31/2023 |  |  | N | No
AG2-295 | Price 25 kV |  | MD | Queen Anne's | Withdrawn | DPL | 15.5 | 15.5 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 9/3/2021 |  | 10/1/2023 |  |  | N | No
AG2-296 | South Berwick - Galion 345 kV |  | OH | Crawford | Withdrawn | AEP | 430 | 30 | 19.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/18/2024 |  | 12/2/2024 |  |  | N | No
AG2-297 - moved to TC2 | Cumberland 230 kV |  | NJ | Cumberland | Active | AEC | 19 | 19 | 11.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG2-298 - moved to TC2 | Sulphur Creek-Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-299 | Hurley 69 kV |  | VA | Buchanan | Withdrawn | AEP | 75 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2024 |  |  | N | No
AG2-300 - moved to TC2 | Meadow Brook 138 kV |  | VA | Frederick | Active | APS | 100 | 100 | 70 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-301 | Morgantown 230 kV |  | MD | Charles | Withdrawn | PEPCO | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-302 | Dickerson 230 kV |  | MD | Montgomery | Withdrawn | PEPCO | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-303 | Birchwood 230 kV |  | VA | King George | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-304 - moved to TC2 | Liberty 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-305 | Bristers 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-306 | Possum Point 230 kV |  | VA | Prince William | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-307 | Roundtable 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-308 | Cumberland 138 kV |  | MD | Allegany | Withdrawn | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2025 |  |  | N | No
AG2-309 | Lanexa 230 kV |  | VA | New Kent | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-310 - moved to TC2 | Matt Funk 138 kV |  | VA | Roanoke | Active | AEP | 100 | 100 | 70 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-311 - moved to TC2 | Smith Mountain 138 kV |  | VA | Bedford | Active | AEP | 75 | 75 | 52.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-312 | Suffolk - Sunbury 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-313 | Burches Hill 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 265.3 | 0 | 35.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  | 9/12/2023 |  | 8/31/2021 |  |  | N | No
AG2-314 - moved to TC2 | Gilboa-Jones Branch 138 kV III |  | WV | Nicholas | Withdrawn | APS | 150 | 0 | 67 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 11/27/2024 |  | 5/1/2024 |  |  | N | No
AG2-315 | Twin Branch - Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 302.2 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2023 |  |  | N | No
AG2-316 | Sandwich-Plano 138 KV |  | IL | Kendall | Withdrawn | ComEd | 292.2 | 0 | 49.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2023 |  |  | N | No
AG2-317 | Barren - Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 155 | 35 | 23.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-318 | Spotsylvania 115 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-319 | Brandon Shores 230 kV |  | MD | Anne Arundel | Withdrawn | BGE | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2025 |  |  | N | No
AG2-320 - moved to TC2 | Ladysmith 230 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-321 | Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-322 | Skiffs Creek 230 kV |  | VA | James City | Withdrawn | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-323 | Shelhorn 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-324 | Buttermilk 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-325 | Pacific 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-326 | Reston 230 kV |  | VA | Fairfax | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-327 - moved to TC2 | Tennessee Gas-East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 58 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-328 - moved to TC2 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 600 | 200 | 26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-329 - moved to TC2 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 400 | 0 | 156 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-330 - moved to TC2 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 600 | 200 | 156 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-331 - moved to TC2 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 715 | 200 | 156 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-332 - moved to TC2 | East Elkhart – Elcona Tap 138 kV |  | IN | Elkhart | Active | AEP | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-333 | Martinsville - Highland 69 kV |  | OH | Fayette | Withdrawn | Dayton | 49 | 49 | 38.05 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2023 |  |  | N | No
AG2-334 | Miller REC - Warrior Ridge 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 30 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 12/18/2024 |  | 1/15/2023 |  |  | N | No
AG2-335 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 20 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 4/29/2022 |  | 5/31/2023 |  |  | N | No
AG2-336 - moved to TC2 | Midway 138 kV |  | OH | Henry | Withdrawn | ATSI | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 7/1/2025 |  | 11/30/2023 |  |  | N | No
AG2-337 - moved to TC2 | Midway 138 kV II |  | OH | Henry | Withdrawn | ATSI | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 7/1/2025 |  | 11/30/2023 |  |  | N | No
AG2-338 - moved to TC2 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-339 - moved to TC2 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-340 | South Boston 12.5 kV Line |  | VA | Halifax | Withdrawn | Dominion | 11.25 | 11.25 | 6.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  | 4/16/2021 |  | 12/1/2024 |  |  | N | No
AG2-341 - moved to TC2 | Ridge Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-342 | Milford - Cool Springs 230 kV II |  | DE | Sussex | Withdrawn | DPL | 900 | 440 | 124.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2026 |  |  | N | No
AG2-343 - moved to TC2 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 100 | 100 | 78 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-344 - moved to TC2 | Dequine 345 bkV |  | IN | N/A | Active | AEP | 100 | 100 | 78 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-345 - moved to TC2 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 150 | 50 | 39 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-346 | Clubhouse – Freeman 115 kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 100 | 65.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 11/22/2022 |  | 10/15/2024 |  |  | N | No
AG2-347 - moved to TC2 | Indian River 230 kV II |  | DE | Sussex | Active | DPL | 448.8 | 448.8 | 121.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 8/31/2025 |  |  | N | No
AG2-348 - moved to TC2 | Indian River 230 kV II |  | DE | Sussex | Withdrawn | DPL | 897.6 | 897.6 | 242.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 2/25/2025 |  | 8/31/2025 |  |  | N | No
AG2-349 | Double Toll Gate-Mead Brook 138 kV |  | VA | Frederick | Withdrawn | APS | 47.77 | 47.77 | 28.662 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  | 3/31/2021 |  | 10/31/2024 |  |  | N | No
AG2-350 | Smithfield 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 250 | 250 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/22/2022 |  | 4/1/2023 |  |  | N | No
AG2-351 | Beatty-London 138 kV III |  | OH | Madison | Withdrawn | ATSI | 196 | 0 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/18/2024 |  | 2/28/2023 |  |  | N | No
AG2-352 | Laurel Lake 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-353 | Hammett 12.47 kV |  | PA | Erie | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-354 - moved to TC2 | Ragland - Grant Branch 138 kV |  | WV | Mingo | Withdrawn | AEP | 100 | 100 | 72.92 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 2/6/2025 |  | 9/30/2024 |  |  | N | No
AG2-355 - moved to TC2 | North Muskingum River - Philo 138 kV |  | OH | Morgan | Withdrawn | AEP | 125 | 125 | 82.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 3/28/2025 |  | 6/1/2024 |  |  | N | No
AG2-356 - moved to TC2 | South Troy - Canton 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-357 - moved to TC2 | Wilton 345 kV |  | IL | Will | Withdrawn | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 7/3/2025 |  | 11/15/2024 |  |  | N | No
AG2-358 | Midway 345 kV |  | OH | Henry | Withdrawn | ATSI | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/18/2024 |  | 11/15/2024 |  |  | N | No
AG2-359 | Hillcrest 345 kV |  | OH | Brown | Withdrawn | DEOK | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/18/2024 |  | 11/15/2024 |  |  | N | No
AG2-360 - moved to TC2 | Broadford 138 kV |  | VA | Smyth | Active | AEP | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-361 | Lanexa – Dunnsville 230 kV |  | VA | New Kent | Withdrawn | Dominion | 100 | 100 | 63.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-362 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Withdrawn | Dominion | 100 | 0 | 36.54 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-363 - moved to TC2 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-364 - moved to TC2 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 500 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-365 - moved to TC2 | Conneaut Tap-Werner 69 kV |  | PA | Mercer | Active | ATSI | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-366 - moved to TC2 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-367 | VEPCO South Creek - Pamplin 115 kV |  | VA | Appomattox | Withdrawn | Dominion | 100 | 100.28 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 1/27/2025 |  | 12/1/2025 |  |  | N | No
AG2-368 | Scottsville - CVEC Delivery 69 kV Point |  | VA | Buckingham | Withdrawn | AEP | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-369 - moved to TC2 | Heritage - Wake 500 kV |  | VA | Greensville | Active | Dominion | 86 | 86 | 51.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-370 - moved to TC2 | Tillman 138 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-371 | Newville 12 kV |  | PA | Cumberland | Withdrawn | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 8/7/2024 |  | 6/30/2023 |  |  | N | No
AG2-372 | Lock 34.5 kV |  | PA | Chester | Withdrawn | PECO | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2023 |  |  | N | No
AG2-373 | Nittany-Zion 46 kV |  | PA | Centre | Withdrawn | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 8/7/2024 |  | 6/30/2023 |  |  | N | No
AG2-374 | Warfordsburg 12 kV |  | PA | Tioga | Withdrawn | APS | 3 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2374_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2374_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 10/30/2023 |  | 12/31/2023 | 12/31/2023 |  | Y | No
AG2-375 - moved to TC2 | Fostoria Central 345 kV |  | OH | Hancock | Withdrawn | AEP | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 7/3/2025 |  | 11/15/2024 |  |  | N | No
AG2-376 | Beatty 345 kV |  | OH | Franklin | Withdrawn | AEP | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 12/17/2024 |  | 11/15/2024 |  |  | N | No
AG2-377 | West Unity – Exit 2/Holiday City Tap 69 kV |  | OH | Williams | Withdrawn | ATSI | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2023 |  |  | N | No
AG2-378 - moved to TC2 | North Hampton – Medway 69 kV |  | OH | Clark | Active | ATSI | 74 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-379 - moved to TC2 | Easton - Steele 138 kV III |  | MD | Talbot | Withdrawn | DPL | 79 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 7/7/2025 |  | 9/15/2023 |  |  | N | No
AG2-380 - moved to TC2 | Carville 138 kV IV |  | MD | Queen Anne's | Active | DPL | 106 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-381 | Church - Oil City 138 kV II |  | MD | Caroline | Withdrawn | DPL | 112 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 12/18/2024 |  | 9/15/2023 |  |  | N | No
AG2-382 - moved to TC2 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/20/2024 |  |  | N | No
AG2-383 | Conesville 138 kV |  | OH | Coshocton | Withdrawn | AEP | 58.9 | 58.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 9/29/2023 |  | 10/27/2023 |  |  | N | No
AG2-384 - moved to TC2 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 60 | 60 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-385 - moved to TC2 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 128 | 54 | 36.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-386 - moved to TC2 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Withdrawn | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 3/14/2025 |  | 4/1/2023 |  |  | N | No
AG2-387 | Cargill 115 kV (SVEC) |  | VA | Rockingham | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 6/29/2023 |  | 10/15/2023 |  |  | N | No
AG2-388 | Pole 249 6094 12.47 kV |  | VA | Campbell | Withdrawn | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2022 |  |  | N | No
AG2-389 | Trexlertown 12 kV | LH Church | VA | City of Lynchburg | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2389_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2389_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2389_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2389_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/22/2023 |  | 4/18/2024 | 4/18/2024 |  | Y | No
AG2-390 | Upper Providence 34.5 kV |  | PA | Adams | Withdrawn | PECO | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 4/8/2024 |  | 6/21/2022 |  |  | Y | No
AG2-391 | Route 30-Laurich 12 kV |  | OH | Montgomery | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2391_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/2/2024 |  | 12/31/2023 | 12/31/2023 |  | Y | No
AG2-392 | Meason 12 kV |  | OH | Montgomery | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2392_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 8/11/2023 |  | 12/31/2023 | 12/31/2023 |  | Y | No
AG2-393 | Springboro Solar 12 kV |  | VA | Buckingham | Withdrawn | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 5/24/2021 |  | 6/21/2022 |  |  | Y | No
AG2-394 | Rohrsburg 12 kV | CO-Zaners Rohrsburg | VA | City of Lynchburg | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2394_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2394_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2394_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2394_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/12/2023 |  | 4/18/2024 | 4/18/2024 |  | Y | No
AG2-395 | West Berwick 12 kV | CO-Ridge | VA | City of Lynchburg | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2395_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2395_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2395_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2395_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/12/2023 |  | 4/18/2024 | 4/18/2024 |  | Y | No
AG2-397 | West Boyertown 13.2 kV |  | PA | Columbia | Withdrawn | ME | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2397_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2397_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/28/2023 |  | 2/28/2025 | 2/28/2025 |  | Y | No
AG2-398 | Fairfield 12 kV |  | PA | Lycoming | Withdrawn | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 8/7/2024 |  | 6/30/2023 |  |  | N | No
AG2-399 | Harrisville Jct - All Min 25 kV |  | PA | Adams | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2399_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2399_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 8/9/2023 |  | 12/31/2023 | 12/31/2023 |  | Y | No
AG2-400 - moved to TC2 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-401 - moved to TC2 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-402 - moved to TC2 | Allen 345 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-403 - moved to TC2 | Meadow Brook - Mt. Storm 500 kV |  | WV | Hardy | Active | APS | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-404 - moved to TC2 | Meadow Brook - Mt. Storm 500 kV II |  | WV | Hardy | Active | APS | 250 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-405 - moved to TC2 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 0 | 10.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-406 - moved to TC2 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 0 | 10.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-407 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-408 - moved to TC2 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 0 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AG2-409 | Granite 115 kV |  | MD | Allegany | Withdrawn | BGE | 0 | 0 | 0 |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/14/2023 |  | 6/1/2023 |  |  | EE | No
AG2-410 | Watkins Corner 34.5 kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 11/18/2024 |  | 11/1/2023 |  |  | N | No
AG2-411 - moved to TC2 | Statler Hill 115 kV |  | PA | Somerset | Active | PENELEC | 63 | 63 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AG2-412 | Greentown - Hummel Creek 138 kV |  | IN | Grant | Withdrawn | AEP | 100 | 100 | 78.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 9/12/2022 |  | 10/31/2024 |  |  | N | No
AG2-413 | Brush Junction - Pleasant Gap 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-414 | Axton 138 kV |  | VA | Henry | Withdrawn | AEP | 350 | 350 | 210 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-415 | Gold – Tennessee Gas 115 kV |  | PA | Potter | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-416 | Edinboro South - Venango Junction 115 kV II |  | PA | Crawford | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-417 | Clinton 69 kV II |  | PA | Lycoming | Withdrawn | PPL | 100 | 100 | 88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-418 - moved to TC2 | Blain 115 kV |  | PA | Perry | Active | PENELEC | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-419 | 3 Bridges Rd 34.5 kV |  | MD | Caroline | Withdrawn | DPL | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2023 |  |  | N | No
AG2-420 - moved to TC2 | Eclipse #2 34.5 kV |  | PA | Venango | Active | PENELEC | 25 | 25 | 14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-421 | High Street 12.47 kV |  | NJ | Cumberland | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | Y | No
AG2-422 | Bustleton 13 kV | Burlington Energy Storage | NJ | Atlantic | Withdrawn | PSEG | 1.2 | 1.2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2422_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2422_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2422_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2422_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 2/22/2022 |  | 12/12/2023 | 12/12/2023 |  | Y | No
AG2-423 - moved to TC2 | Cherry Run–Harmony 138 kV |  | WV | Barbour | Active | APS | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-424 - moved to TC2 | Bonnieville - Lebanon 138 kV |  | KY | Larue | Active | EKPC | 63.25 | 63.25 | 34.95 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-425 | Jackson Road - Nanty Glo 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2023 |  |  | N | No
AG2-426 - moved to TC2 | Wakefield - Waverly 115 kV |  | VA | Sussex | Active | Dominion | 50 | 50 | 47.66 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-427 - moved to TC2 | Waverly 115 kV |  | VA | Sussex | Active | Dominion | 85 | 85 | 66.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-428 - moved to TC2 | Wakefield 115 kV |  | VA | Sussex | Active | Dominion | 170 | 170 | 135.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-429 - moved to TC2 | Burma - Armstrong 138 kV |  | PA | Clarion | Active | APS | 69 | 69 | 53.86 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-430 - moved to TC2 | Sunbury-Dalmatia 69 kV II |  | PA | Northumberland | Active | PPL | 60 | 60 | 37.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-431 | Sapony 34.5 kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 20 | 12.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 11/1/2023 |  |  | N | No
AG2-432 | Mount Airy - Wythe 138 kV |  | VA | Wythe | Withdrawn | AEP | 45 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-433 | Sabinsville 115 kV |  | PA | Tioga | Withdrawn | PENELEC | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/10/2024 |  | 9/30/2024 |  |  | N | No
AG2-434 | Rockwood 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 8/7/2024 |  | 6/30/2023 |  |  | N | No
AG2-435 | Crossroads 13.2 kV II |  | PA | York | Withdrawn | ME | 4.6 | 4.6 | 2.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 8/7/2024 |  | 6/30/2023 |  |  | N | No
AG2-436 - moved to TC2 | Carson - Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-437 | Monarch I Interconnection 500 kV |  | VA | Greensville | Withdrawn | Dominion | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2023 |  |  | N | No
AG2-438 - moved to TC2 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 10 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG2-439 - moved to TC2 | Oxbow 34.5 kV |  | PA | Wyoming | Active | PENELEC | 9.8 | 9.8 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG2-440 - moved to TC2 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-441 - moved to TC2 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 225 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-442 - moved to TC2 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-443 | Benner 12 kV |  | OH | Montgomery | Withdrawn | Dayton | 4 | 4 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/28/2022 |  |  | N | No
AG2-444 - moved to TC2 | Bixby - Biers Run 345 kV |  | OH | Pickaway | Active | AEP | 163 | 163 | 122.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-445 | Adkins - Atlanta 345 kV |  | OH | Pickaway | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-446 | Cedar Creek 138 kV |  | DE | New Castle | Withdrawn | DPL | 114.3 | 0 | 25.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 11/15/2022 |  |  | N | No
AG2-447 - moved to TC2 | Cedar Creek 138 kV VII |  | DE | New Castle | Active | DPL | 134.3 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/1/2024 |  |  | N | No
AG2-448 - moved to TC2 | Cross School - Westvaco 138 kV |  | WV | Mineral | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/24/2024 |  |  | N | No
AG2-449 - moved to TC2 | Jefferson-Greentown 765 kV |  | IN | Rush | Active | AEP | 835 | 120 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-450 - moved to TC2 | Bridgeport 230 kV |  | NJ | Gloucester | Active | AEC | 219 | 219 | 115.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AG2-451 - moved to TC2 | Chambers 230 kV |  | NJ | Salem | Active | AEC | 240 | 240 | 123 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-452 | SW Lima - Shelby 345 kV |  | OH | Auglaize | Withdrawn | AEP | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 3/31/2024 |  |  | N | No
AG2-453 - moved to TC2 | Lasalle - Plano 345 kV |  | IL | Kendall | Active | ComEd | 280 | 280 | 196 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-454 - moved to TC2 | Dequine - Eugene 345 kV |  | IN | Fountain | Withdrawn | AEP | 300 | 300 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 4/6/2025 |  | 3/31/2024 |  |  | N | No
AG2-455 - moved to TC2 | Dequine - Sullivan 345 kV |  | IN | Fountain | Withdrawn | AEP | 280 | 280 | 196 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 4/6/2025 |  | 3/31/2024 |  |  | N | No
AG2-456 - moved to TC2 | Pierce Brook-Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 80 | 80 | 55.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-457 - moved to TC2 | Pierce Brook - Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 160 | 80 | 55.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-458 - moved to TC2 | Kittatinny-Newton 34.5 kV II |  | NJ | Sussex | Active | JCPL | 19.8 | 0 | 1.89 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AG2-459 - moved to TC2 | Allenwood-Larrabee 34.5 kV II |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 0.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-460 - moved to TC2 | East Flemington-Lebanon 34.5 kV II |  | NJ | Hunterdon | Active | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-461 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Withdrawn | Dominion | 88 | 88 | 57.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/15/2024 |  |  | N | No
AG2-462 - moved to TC2 | Progress Park - Glen Lyn 138 kV |  | VA | Wythe | Withdrawn | AEP | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 6/9/2025 |  | 10/31/2024 |  |  | N | No
AG2-463 | Gold – Tennessee Gas 115 kV II |  | PA | Potter | Withdrawn | APS | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-464 | Feagans Mill - Stonewall 138 kV |  | WV | Jefferson | Withdrawn | APS | 80 | 80 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-465 | South Tiffin - West End Fostoria 138 kV |  | OH | Seneca | Withdrawn | AEP | 79 | 79 | 29.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-466 - moved to TC2 | Culloden - Wyoming 765 kV |  | WV | N/A | Withdrawn | AEP | 330 | 330 | 198 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  | 7/3/2025 |  | 6/30/2024 |  |  | N | No
AG2-467 - moved to TC2 | Beason 345 kV |  | IL | Logan | Withdrawn | ComEd | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AG2-468 | Sedge Hill – Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 3/14/2024 |  | 12/31/2025 |  |  | N | No
AG2-469 - moved to TC2 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-470 | Fostoria - Lemoyne 345 kV |  | OH | Wood | Withdrawn | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-471 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-472 | Jennings-Hazelton 138kV |  | WV | Preston | Withdrawn | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-473 | Brody 138 kV |  | MI | Cass | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-474 | Mottville 138 kV |  | MI | St. Joseph | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-475 | Chickahominy - Surry 500 kV |  | VA | Charles City | Withdrawn | Dominion | 500 | 500 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2024 |  |  | N | No
AG2-476 - moved to TC2 | Hokes-Grantley 69 kV II |  | PA | York | Active | ME | 20 | 0 | 0.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-477 - moved to TC2 | Hokes-Jackson 69 kV III |  | PA | York | Active | ME | 20 | 0 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2022 |  |  | N | No
AG2-478 - moved to TC2 | Hokes-Jackson 69 kV IV |  | PA | York | Active | ME | 20 | 0 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-479 - moved to TC2 | Penns Tap-Richfield Tie 69 kV II |  | PA | Snyder | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-480 | Derry Tap-Derry Bus 69 kV II |  | PA | Montour | Withdrawn | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2022 |  |  | N | No
AG2-481 - moved to TC2 | Derry Tap-Derry Bus 69 kV III |  | PA | Northumberland | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2022 |  |  | N | No
AG2-482 | Bowman's Mill-Scott 69 kV II |  | PA | Columbia | Withdrawn | PPL | 35 | 0 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 11/15/2022 |  |  | N | No
AG2-483 | Bowman's Mill Tap-Scott 69 kV III |  | PA | Columbia | Withdrawn | PPL | 75 | 0 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 11/15/2022 |  |  | N | No
AG2-484 - moved to TC2 | Mifflintown Bus-Mifflintown Tap 69 kV II |  | PA | Juniata | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-485 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Withdrawn | PPL | 20 | 0 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 11/30/2022 |  |  | N | No
AG2-486 | Bloomsburg-Columbia 69 kV II |  | PA | Columbia | Withdrawn | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2022 |  |  | N | No
AG2-487 - moved to TC2 | Madison - Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 152.5 | 0 | 10.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AG2-488 | Southwest Lima 345 kV |  | OH | Allen | Withdrawn | AEP | 300 | 0 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-489 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Withdrawn | AEP | 75 | 0 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-490 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Withdrawn | AEP | 75 | 0 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-491 - moved to TC2 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-492 - moved to TC2 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-493 | Phillipsburg Bus II 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/3/2024 |  | 6/21/2022 |  |  | Y | No
AG2-494 | Keewaydin 34.5 kV |  | OH | Madison | Withdrawn | PENELEC | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/23/2021 |  | 6/21/2022 |  |  | Y | No
AG2-495 | Phillipsburg Bus I 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 2/9/2022 |  |  |  |  | Y | No
AG2-496 | Bloom 34.5 kV |  | OH | Madison | Withdrawn | PENELEC | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/23/2021 |  | 6/21/2022 |  |  | Y | No
AG2-497 | Tangy 138 kV |  | OH | Delaware | Withdrawn | ATSI | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-498 - moved to TC2 | Obetz 138 kV |  | OH | Franklin | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AG2-499 | Bixby 345 kV |  | OH | Franklin | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AG2-500 | Townsend 138 kV II |  | DE | New Castle | Withdrawn | DPL | 50 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2024 |  |  | N | No
AG2-501 | Sedge Hill - Mount Laurel 115 kV |  | VA | Halifax | Withdrawn | Dominion | 51 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2024 |  |  | N | No
AG2-502 | Sedge Hill - Person 115 kV |  | VA | Halifax | Withdrawn | Dominion | 70 | 0 | 7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2024 |  |  | N | No
AG2-503 | Adams 138 kV |  | OH | Adams | Withdrawn | AEP | 49.9 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2024 |  |  | N | No
AG2-504 | Delano 138 kV |  | OH | Ross | Withdrawn | AEP | 49.9 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2024 |  |  | N | No
AG2-505 - moved to TC2 | Westvaco - Mt Zion 138 kV |  | MD | Garrett | Active | APS | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-506 | Carson 230 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/2/2024 |  |  | N | No
AG2-507 | Crewe - Victoria DP 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-508 | Dry Bread 230 kV |  | VA | Greensville | Withdrawn | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AG2-509 - moved to TC2 | Robinson 69 kV |  | WV | N/A | Withdrawn | AEP | 55 | 55 | 36.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 3/4/2025 |  | 6/1/2024 |  |  | N | No
AG2-510 | Double Toll Gate 138 kV |  | VA | Clarke | Withdrawn | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 6/28/2023 |  | 12/30/2024 |  |  | N | No
AG2-511 | Double Toll Gate - Millville 138 kV |  | VA | Clarke | Withdrawn | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 5/18/2021 |  | 12/30/2024 |  |  | N | No
AG2-512 | Sulphur Creek-Loretto 69 kV |  | KY | Marion | Withdrawn | EKPC | 17.5 | 17.5 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2023 |  |  | N | No
AG2-513 | Hodgenville-Sulphur Creek 69 kV |  | KY | Larue | Withdrawn | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2023 |  |  | N | No
AG2-514 | Midway 345 kV II |  | OH | Henry | Withdrawn | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/13/2024 |  | 10/31/2023 |  |  | N | No
AG2-515 - moved to TC2 | Midway 345 kV III |  | OH | Lucas | Active | ATSI | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-516 - moved to TC2 | Pecatonica 138kV |  | IL | Winnebago | Active | ComEd | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-517 | Cordova Energy Center 345kV |  | IL | Rock Island | Withdrawn | ComEd | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2023 |  |  | N | No
AG2-518 - moved to TC2 | Tech Drive 138 kV |  | VA | Montgomery | Active | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 1/1/2024 |  |  | N | No
AG2-519 - moved to TC2 | Royerton - Desoto 138 kV |  | IN | Delaware | Active | AEP | 111 | 111 | 87.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-520 | Ritchie 69 kV |  | MD | Prince George's | Withdrawn | PEPCO | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2024 |  |  | N | No
AG2-521 | Fork Union 230 kV |  | VA | Fluvanna | Withdrawn | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/10/2024 |  | 3/1/2024 |  |  | N | No
AG2-522 - moved to TC2 | Five Forks 115 kV |  | NC | Warren | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/30/2025 |  |  | N | No
AG2-523 | Bakers Pond 115 kV |  | VA | Prince George | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 3/31/2022 |  |  |  |  | N | No
AG2-524 - moved to TC2 | LaSalle Station - Mazon 138 kV |  | IL | Grundy | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-525 | Bonney Forge 23 kV II |  | MI | Cass | Withdrawn | PENELEC | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/13/2021 |  | 6/1/2023 |  |  | Y | No
AG2-526 | Oak Grove – Saunders DP 230 kV |  | VA | Westmoreland | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-527 - moved to TC2 | Kewanee-Toulon 138 kV |  | IL | Stark | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AG2-528 - moved to TC2 | Bustleburg Tap - Fairfield DP 115 kV |  | VA | Rockbridge | Withdrawn | Dominion | 140 | 140 | 72.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 6/6/2025 |  | 10/31/2024 |  |  | N | No
AG2-529 | Harrisonburg - Endless Caverns 230 kV |  | VA | Rockingham | Withdrawn | Dominion | 150 | 151.734 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2024 |  |  | N | No
AG2-530 | Mannington Mills - Woodstown 69 kV |  | NJ | Salem | Withdrawn | AEC | 19.975 | 19.975 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-531 - moved to TC2 | Greystone - West Denville 34.5 kV |  | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/31/2025 |  | 7/31/2022 |  |  | N | No
AG2-532 - moved to TC2 | Pohatcong-Newburgh Tap 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-533 - moved to TC2 | Newburgh-Pohatcong 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AG2-534 - moved to TC2 | Flanders-Pohatcong Mountain R722 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-535 - moved to TC2 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | NJ | Warren | Active | JCPL | 40 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-536 | Buckeye - Ringoes 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 8/31/2022 |  |  | N | No
AG2-537 | Ringoes-Copper Hill Solar 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 8/31/2022 |  |  | N | No
AG2-538 - moved to TC2 | Ridgeway - Motion Control 46 kV |  | PA | Elk | Withdrawn | APS | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 2/28/2025 |  | 10/15/2022 |  |  | N | No
AG2-539 | Mechanicsburg - Darby 138 kV |  | OH | Union | Withdrawn | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 5/14/2025 |  |  | N | No
AG2-540 | Clubhouse - Jarratt 115 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/10/2024 |  | 6/3/2024 |  |  | N | No
AG2-541 - moved to TC2 | Perth - Crystal Hill 115 kV |  | VA | Halifax | Active | Dominion | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-542 - moved to TC2 | North Shenandoah – Merck 115 kV |  | VA | Rockingham | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 3/31/2025 |  | 6/3/2024 |  |  | N | No
AG2-543 | Suffolk - Earleys 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/3/2024 |  |  | N | No
AG2-544 - moved to TC2 | Silver Lake 345 kV |  | IL | McHenry | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AG2-545 - moved to TC2 | Silver Lake 345 kV |  | IL | McHenry | Active | ComEd | 600 | 400 | 160 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AG2-546 | Van Buren - Delaware 138 kV |  | IN | Grant | Withdrawn | AEP | 150 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2023 |  |  | N | No
AG2-547 | New Liberty - Boutwell 138 kV |  | OH | Hancock | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/13/2024 |  | 9/1/2024 |  |  | N | No
AG2-548 - moved to TC2 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-549 | Rineyville 69 kV |  | KY | Hardin | Withdrawn | EKPC | 40 | 40 | 26.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AG2-550 - moved to TC2 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-551 - moved to TC2 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 150 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-552 | Bullitt County 161 kV |  | KY | Bullitt | Withdrawn | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2024 |  |  | N | No
AG2-553 - moved to TC2 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-554 | East End 46 kV |  | PA | Centre | Withdrawn | APS | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-555 | Clarion 12 kV |  | PA | Clarion | Withdrawn | PENELEC | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-556 | Sullivan - Dequine 345 kV |  | IN | Vigo | Withdrawn | AEP | 339.1 | 339.1 | 253.387 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 3/2/2023 |  | 1/1/2024 |  |  | N | No
AG2-557 | Spring Mills - Millheim 46 kV |  | PA | Centre | Withdrawn | APS | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2023 |  |  | N | No
AG2-558 - moved to TC2 | Shawville - Phillipsburg 34.5 kV II |  | PA | Clearfield | Withdrawn | APS | 39.8 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/23/2025 |  | 4/1/2023 |  |  | N | No
AG2-559 - moved to TC2 | Shawville - Phillipsburg 34.5 kV III |  | PA | Clearfield | Withdrawn | APS | 59.7 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/23/2025 |  | 4/1/2024 |  |  | N | No
AG2-560 - moved to TC2 | Phillipsburg (Karthaus) 34.5 kV |  | PA | Clearfield | Withdrawn | APS | 79.6 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/23/2025 |  | 4/1/2025 |  |  | N | No
AG2-561 - moved to TC2 | Glory - Glen Campbell 34.5 kV |  | PA | Indiana | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-562 - moved to TC2 | Elderberry 345 kV |  | IN | St. Joseph | Active | AEP | 767 | 52 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-563 | Gasburg 69 kV |  | VA | Brunswick | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 9/24/2024 |  |  | N | No
AG2-564 - moved to TC2 | Sulphur Springs 138 kV |  | OH | Crawford | Active | AEP | 49.99 | 49.99 | 32.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AG2-565 | Kidds Store - Sherwood 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 110 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/29/2024 |  |  | N | No
AG2-566 - moved to TC2 | Briery - Finneywood 230 kV |  | VA | Prince Edward | Active | Dominion | 110 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-567 | Stanville - Dewey 138 kV |  | KY | N/A | Withdrawn | AEP | 200 | 200 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/24/2024 |  |  | N | No
AG2-568 - moved to TC2 | Stink Run – Sundial 138 kV |  | WV | N/A | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 2/25/2024 |  |  | N | No
AG2-569 | Rogers Road - Carson 500 kV |  | VA | Greensville | Withdrawn | Dominion | 150 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/25/2024 |  |  | N | No
AG2-570 - moved to TC2 | Heritage - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 400 | 400 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-571 - moved to TC2 | Heritage - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 500 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-572 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 10/9/2023 |  | 3/25/2024 |  |  | N | No
AG2-573 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Withdrawn | AEP | 80 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 10/9/2023 |  | 3/29/2024 |  |  | N | No
AG2-574 | Sowers 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/30/2021 |  | 12/29/2023 |  |  | N | No
AG2-575 - moved to TC2 | Crego Rd. 138 kV |  | IL | DeKalb | Active | ComEd | 290 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-576 | Varner 345 kV |  | IN | DeKalb | Withdrawn | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-577 | Jay 138 kV |  | IN | Jay | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-578 | Jay 69 kV |  | IN | Jay | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-579 | Fostoria 138 kV |  | OH | Hancock | Withdrawn | AEP | 205 | 0 | 41 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/29/2023 |  |  | N | No
AG2-580 - moved to TC2 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  | 3/6/2025 |  | 10/1/2024 |  |  | N | No
AG2-581 - moved to TC2 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-582 - moved to TC2 | Flint Run 500 kV |  | WV | Doddridge | Active | APS | 2100 | 2100 | 2075 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/1/2026 |  |  | N | No
AG2-583 - moved to TC2 | Bremo - Cartersville 230 kV |  | VA | Cumberland | Active | Dominion | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AG2-584 | Double Toll Gate - Meadowbrook 138 kV |  | VA | Frederick | Withdrawn | APS | 90 | 90 | 46.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2024 |  |  | N | No
AG2-585 - moved to TC2 | Kensignton 138kV |  | IL | Kankakee | Active | ComEd | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-586 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 31 | 31 | 18.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/11/2021 |  | 6/1/2024 |  |  | N | No
AG2-587 - moved to TC2 | Graceton 230 kV |  | MD | Harford | Withdrawn | BGE | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/7/2025 |  | 6/1/2024 |  |  | N | No
AG2-588 | Kittatinny - Blairstown 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-589 - moved to TC2 | Ravenswood - Hemlock 69 kV |  | OH | Meigs | Active | AEP | 20 | 20 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-590 - moved to TC2 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 92.1 | 38.2 | 22.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/30/2025 |  | 6/1/2024 |  |  | N | No
AG2-591 | Bluebell-Sancap Tap 69 kV |  | OH | Mahoning | Withdrawn | ATSI | 61 | 61 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-592 | West Cambridge - Vienna 69 kV |  | MD | Dorchester | Withdrawn | DPL | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-593 | Benton-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-594 - moved to TC2 | Benton-Scott 69 kV II |  | PA | Columbia | Withdrawn | PPL | 20 | 20 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 6/1/2024 |  |  | N | No
AG2-595 - moved to TC2 | LaRue - North Waldo 138 kV |  | OH | Marion | Withdrawn | AEP | 65 | 65 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 6/1/2024 |  |  | N | No
AG2-596 | Renaker-Avon 138 kV |  | KY | Scott | Withdrawn | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-597 | Broadford 138 kV |  | VA | Smyth | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AG2-598 | Knob Lick-JB Galloway Tap 69 kV |  | KY | Metcalfe | Withdrawn | EKPC | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/11/2024 |  | 11/30/2025 |  |  | N | No
AG2-599 - moved to TC2 | Furnace Brook-Warren 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 2/18/2025 |  | 4/30/2021 |  |  | N | No
AG2-600 - moved to TC2 | American Can-BASF 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/7/2025 |  | 4/30/2021 |  |  | N | No
AG2-601 | Milton 69 kV III |  | PA | Northumberland | Withdrawn | PPL | 90 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 9/16/2022 |  |  | N | No
AG2-602 - moved to TC2 | Maysville 69 kV V |  | PA | Mercer | Withdrawn | ATSI | 50 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 3/11/2025 |  | 9/15/2022 |  |  | N | No
AG2-603 - moved to TC2 | Huffman 138 kV |  | VA | Carroll | Withdrawn | AEP | 77 | 77 | 77 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 6/9/2025 |  | 10/31/2024 |  |  | N | No
AG2-604 | Edgemont 138 kV |  | VA | Montgomery | Withdrawn | AEP | 94 | 94 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2024 |  |  | N | No
AG2-605 | Skimmer - Abert 69 kV |  | VA | Amherst | Withdrawn | AEP | 37 | 37 | 24.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 10/29/2024 |  | 6/1/2024 |  |  | N | No
AG2-606 - moved to TC2 | Sunbury-Juniata 500 kV |  | PA | Perry | Withdrawn | PPL | 89 | 89 | 35.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 6/1/2024 |  |  | N | No
AG2-607 - moved to TC2 | St. Johns - Dunbrook 34.5 kV |  | VA | King and Queen | Withdrawn | Dominion | 20 | 20 | 12.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 11/1/2023 |  |  | N | No
AG2-608 | Unionville - Locust 115 kV |  | VA | Orange | Withdrawn | Dominion | 80 | 80 | 64 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/11/2024 |  | 11/15/2023 |  |  | N | No
AG2-609 | Unionville - Locust Grove 115 kV |  | VA | Orange | Withdrawn | Dominion | 40 | 40 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/11/2024 |  | 11/15/2023 |  |  | N | No
AG2-610 | Gold 12.5 kV |  | PA | Potter | Withdrawn | PENELEC | 4.998 | 4.998 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-611 | Hamlin 12 kV |  | PA | Wayne | Withdrawn | PPL | 4.998 | 4.998 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-612 | Lakeville 12 kV |  | PA | Wayne | Withdrawn | PPL | 4.998 | 4.998 | 4.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-613 | Tower Hill 34.5 kV |  | PA | Tioga | Withdrawn | PENELEC | 5 | 5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2021 |  | 12/31/2023 |  |  | N | No
AG2-614 | Mansfield 12 kV |  | PA | Tioga | Withdrawn | PENELEC | 5 | 5 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-615 - moved to TC2 | Carlos Junction-Garrett 138 kV |  | MD | Allegany | Active | APS | 100 | 100 | 62.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-616 - moved to TC2 | Churchtown - Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 50 | 50 | 32.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-617 - moved to TC2 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Active | BGE | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-618 - moved to TC2 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 110 | 110 | 71.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-619 | Carville 138 kV |  | MD | Queen Anne's | Withdrawn | DPL | 150 | 150 | 102.45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 5/17/2021 |  | 12/31/2023 |  |  | N | No
AG2-620 | Remington 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 6/21/2023 |  | 5/31/2023 |  |  | N | No
AG2-621 - moved to TC2 | Hoytdale 138 kV |  | PA | Beaver | Active | ATSI | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-622 | Hanover 230 kV |  | VA | Hanover | Withdrawn | Dominion | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/22/2022 |  | 5/31/2023 |  |  | N | No
AG2-623 |  |  | DE | New Castle | Withdrawn | DPL |  |  |  |  | Energy | Generation Interconnection | Other |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 5/17/2021 |  | 9/1/2021 |  |  | Y | No
AG2-624 | Pequest River-Furnace Brook Tap 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/20/2024 |  | 4/30/2021 |  |  | N | No
AG2-625 - moved to TC2 | Pequest River-Furnace Brook Tap 34.5 kV II |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-626 - moved to TC2 | Pequest River-Furnace Brook Tap 34.5 kV III |  | NJ | Warren | Active | JCPL | 12.5 | 12.5 | 5.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-627 - moved to TC2 | Woodstown-High Street 69 kV |  | NJ | Gloucester | Active | AEC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-628 | Spring Creek - Millcreek 138 kV |  | OH | Miami | Withdrawn | Dayton | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-629 | Tasley - Oak Hall 69 kV II |  | VA | Accomack | Withdrawn | ODEC | 58.76 | 0 | 23.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 6/20/2024 |  | 4/1/2025 |  |  | N | No
AG2-630 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 118.56 | 0 | 47.43 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-631 - moved to TC2 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 4/1/2025 |  |  | N | No
AG2-632 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-633 | Gary DP - Lunenburg 115 kV |  | VA | Lunenburg | Withdrawn | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-634 | Gary DP – Lunenburg 115 kV |  | VA | Lunenburg | Withdrawn | Dominion | 125 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-635 | Heritage 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 270 | 270 | 162 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-636 | Heritage 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 270 | 0 | 108 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-637 - moved to TC2 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-638 | Kingsland 69 kV |  | IN | Wells | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-639 - moved to TC2 | Chickahominy 230 kV |  | VA | Charles City | Withdrawn | Dominion | 340 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/3/2025 |  | 4/1/2025 |  |  | N | No
AG2-640 - moved to TC2 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Withdrawn | Dominion | 46.8 | 0 | 18.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 2/24/2025 |  | 4/1/2025 |  |  | N | No
AG2-641 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-642 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 80 | 0 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-643 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-644 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AG2-645 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/15/2022 |  |  | N | No
AG2-646 - moved to TC2 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/10/2024 |  |  | N | No
AG2-647 | Bolton - Bennsville 69 kV |  | MD | Charles | Withdrawn | SMECO | 9.2 | 9.2 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/31/2023 |  |  | N | No
AG2-648 | Germantown 13.2 kV |  | PA | Adams | Withdrawn | ME | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-649 | North Hanover 13.2 kV |  | PA | York | Withdrawn | ME | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2023 |  | 8/30/2023 |  |  | N | No
AG2-650 | Newberry 13.2 kV |  | PA | York | Withdrawn | ME | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2023 |  | 12/1/2023 |  |  | N | No
AG2-651 | Central City West 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 10 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 9/7/2023 |  | 8/30/2023 |  |  | N | No
AG2-652 | Siegfried-Hauto 69 kV IV |  | PA | Carbon | Withdrawn | PPL | 20 | 20 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/31/2024 |  |  | N | No
AG2-653 | Siegfried-Hauto 69 kV V |  | PA | Carbon | Withdrawn | PPL | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 3/31/2024 |  |  | N | No
AG2-654 - moved to TC2 | Craigsville - Leards Crossing 12 kV |  | PA | Armstrong | Active | APS | 14.7 | 14.7 | 8.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG2-655 - moved to TC2 | Mt. Storm-Bismark 500 kV |  | WV | Grant | Withdrawn | Dominion | 500 | 500 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 7/7/2025 |  | 6/30/2024 |  |  | N | No
AG2-656 | Kanawha River - Carbondale 138 kV |  | WV | Kanawha | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AG2-657 - moved to TC2 | Kanawha River - Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 90 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-658 - moved to TC2 | Cowen 138 kV |  | WV | Webster | Active | APS | 210 | 210 | 135.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-659 - moved to TC2 | Kerr Dam – Hawtree 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/30/2025 |  |  | N | No
AG2-660 - moved to TC2 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 600 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-661 - moved to TC2 | Hopewell - Colonial Trail 230 kV |  | VA | Surry | Active | Dominion | 150 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-662 | Stephensburg - Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 90 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-663 | Pidgeon - Lisbon 69 kV |  | OH | Columbiana | Withdrawn | ATSI | 40 | 40 | 31.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 8/16/2022 |  | 7/31/2025 |  |  | N | No
AG2-664 | TodHunter – Trenton 138 kV |  | OH | Butler | Withdrawn | DEOK | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 8/19/2024 |  | 7/31/2025 |  |  | N | No
AG2-665 - moved to TC2 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 180 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-666 | Spurlock - Flemingsburg 138 kV |  | KY | Jackson | Withdrawn | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AG2-667 | Wakesfield - Poolesville 34.5 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 12.53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/18/2024 |  | 11/1/2023 |  |  | N | No
AG2-668 - moved to TC2 | Harvey Run 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 4/22/2025 |  | 11/1/2023 |  |  | N | No
AG2-669 | Loudoun - Meadow Brook 500 kV |  | VA | Rappahannock | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 6/4/2024 |  | 12/31/2025 |  |  | N | No
AG2-670 - moved to TC2 | Greensburg 69 kV |  | KY | Green | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-671 | Hope - Frenchburg 69 kV |  | KY | Montgomery | Withdrawn | EKPC | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 8/8/2024 |  | 12/31/2023 |  |  | N | No
AG2-672 | Conaway 138 kV |  | DE | Sussex | Withdrawn | DPL | 8 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 8/15/2022 |  | 9/4/2023 |  |  | N | No
AG2-673 | Fitzell 33 kV |  | MD | Baltimore County | Withdrawn | BGE | 9.92 | 9.92 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/30/2022 |  |  | N | No
AG2-674 | Quad Cities - Sterling Steel 345 kV |  | IL | Whiteside | Withdrawn | ComEd | 212.1 | 212.1 | 37.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 10/1/2023 |  |  | N | No
AG2-675 - moved to TC2 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 335 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-676 | Russell Co 161 kV |  | KY | Russell | Withdrawn | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-677 | Russell Co J - Jamestown T 161 kV |  | KY | Russell | Withdrawn | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-678 | Vicco - Beckham 138 kV |  | KY | Knott | Withdrawn | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-679 | Daisy - Collier 69 kV |  | KY | Letcher | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-680 | South Anna - Louisa 230 kV |  | VA | Madison | Withdrawn | Dominion | 202 | 202 | 121.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-681 | Soft Shell - Bonny Man 138 kV |  | KY | Perry | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-682 | Stinnett 161 kV |  | KY | Leslie | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-683 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-684 | Summer Shade 161 kV |  | KY | Metcalfe | Withdrawn | EKPC | 331 | 331 | 198.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-685 | Big Sandy-Inez 138 kV |  | KY | Martin | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-686 | Powell Mountain 138 kV |  | WV | Nicholas | Withdrawn | APS | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-687 | Garrard 345 kV |  | KY | Garrard | Withdrawn | EKPC | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-688 | Imperial-Joffre 138 kV |  | PA | Clearfield | Withdrawn | APS | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-689 | Tenmile 138 kV |  | WV | N/A | Withdrawn | AEP | 125 | 125 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2024 |  |  | N | No
AG2-690 - moved to TC2 | Sullivan - Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 1/29/2025 |  | 6/1/2024 |  |  | N | No
AG2-691 | New Lebanon - Ohio Hutchings 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 49.5 | 49.5 | 39.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 10/17/2024 |  | 7/31/2025 |  |  | N | No
AH1-001 | Bartonsville-Meadowbrook 138 kV |  | VA | Frederick | Withdrawn | APS | 220 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2021 | N/A | N/A |  | 12/18/2024 |  | 12/12/2023 |  |  | N | No
AH1-002 | Hector 115 kV |  | PA | Potter | Withdrawn | PENELEC | 50 | 50 | 7.35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-003 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 130 | 130 | 19.11 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-004 - moved to TC2 | Avon - Renaker 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/7/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-005 - moved to TC2 | East Towanda-South Troy 115 kV II |  | PA | Bradford | Active | PENELEC | 51 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/9/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-006 | Essex 26 kV |  | NJ | Essex | Withdrawn | PSEG | 3.7 | 3.7 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/9/2021 | N/A | N/A |  | 6/11/2021 |  | 12/1/2022 |  |  | N | No
AH1-007 | Plymouth 69 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/9/2021 | N/A | N/A |  | 7/12/2021 |  | 12/1/2022 |  |  | N | No
AH1-008 | Bergen 230 kV |  | OH | Union | Withdrawn | PSEG | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/12/2021 | N/A | N/A |  | 10/12/2021 |  | 12/1/2026 |  |  | S | No
AH1-009 |  |  | IL | DeKalb | Withdrawn | ComEd | 86 | 86 | 54.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2021 | N/A | N/A |  | 4/14/2021 |  | 12/2/2024 |  |  | N | No
AH1-010 | Stony River - Buffalo Coal 66 kV |  | WV | Grant | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-011 | Fulton - Tidd 69 kV |  | WV | Brooke | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-012 - moved to TC2 | Louisa - North Anna 230 kV |  | VA | Louisa | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH1-013 | Hanna - Tanners Creek 345 kV |  | IN | Shelby | Withdrawn | AEP | 500 | 0 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-014 | Sorenson 345 kV |  | IN | Huntington | Withdrawn | AEP | 111.8 | 111.8 | 67.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-015 | Academia 138 kV |  | OH | Knox | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2021 | N/A | N/A |  | 12/18/2024 |  | 12/2/2024 |  |  | N | No
AH1-016 | Central Hardin 138 kV |  | KY | Hardin | Withdrawn | EKPC | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2021 | N/A | N/A |  | 8/18/2021 |  | 12/2/2024 |  |  | N | No
AH1-017 | Copperstone-North Lebanon 230 kV III |  | PA | Lebanon | Withdrawn | ME | 100 | 30 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2023 |  |  | N | No
AH1-018 | Cunningham - Elmont 500 kV |  | VA | Fluvanna | Withdrawn | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-019 | Cunningham - Elmont 500 kV II |  | VA | Fluvanna | Withdrawn | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-020 | Kidds Store – Fork Union 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 38 | 38 | 22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-021 | North Temple 781-1 13.2 kV |  | PA | Berks | Withdrawn | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  | 8/9/2024 |  | 11/30/2022 |  |  | N | No
AH1-022 | Allen 13.2 kV |  | PA | Cumberland | Withdrawn | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  | 4/14/2023 |  | 11/30/2022 |  |  | N | No
AH1-023 | Corning Glass-Bush Town Junction 34.5 kV |  | PA | Franklin | Withdrawn | APS | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  | 8/9/2024 |  | 11/30/2022 |  |  | N | No
AH1-024 | Lickdale 626-2 13.2 kV |  | PA | Lebanon | Withdrawn | ME | 2 | 2 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  | 8/9/2024 |  | 11/30/2022 |  |  | N | No
AH1-025 | Myerstown 751-2 13.2 kV |  | PA | Lebanon | Withdrawn | ME | 4.5 | 4.5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  | 8/9/2024 |  | 11/30/2022 |  |  | N | No
AH1-026 | Newberry 576-4 13.2 kV |  | PA | York | Withdrawn | ME | 4.5 | 4.5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  | 8/9/2024 |  | 11/30/2022 |  |  | N | No
AH1-027 - moved to TC2 | Cartanza 230 kV |  | DE | Kent | Active | DPL | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/20/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-028 | Freeman1 12.47 kV |  | VA | Brunswick | Withdrawn | Dominion | 8.75 | 8.75 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2021 | N/A | N/A |  | 9/13/2021 |  | 12/20/2023 |  |  | N | No
AH1-029 | WV-PJM1 12 kV |  | IL | Cook | Withdrawn | AEP | 1 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/3/2021 | N/A | N/A |  | 8/3/2021 |  | 5/31/2021 |  |  | Y | No
AH1-030 | WV PJM2 12 kV |  | IL | Cook | Withdrawn | AEP | 1 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/3/2021 | N/A | N/A |  | 8/3/2021 |  | 6/30/2022 |  |  | Y | No
AH1-031 | National-Tangy 138 kV III |  | OH | Madison | Withdrawn | ATSI | 77 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2021 | N/A | N/A |  | 12/1/2023 |  | 12/31/2024 |  |  | N | No
AH1-032 | West Millersport 138 kV |  | OH | Fairfield | Withdrawn | AEP | 138 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-033 - moved to TC2 | Sligo 34.5 kV |  | NC | Currituck | Active | Dominion | 19.5 | 19.5 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 8/15/2024 |  |  | N | No
AH1-034 - moved to TC2 | Patton Road Junction - Summer Shade 69 kV |  | KY | Barren | Active | EKPC | 100 | 100 | 70 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 11/15/2025 |  |  | N | No
AH1-035 - moved to TC2 | Plymouth 34.5 kV |  | NC | Washington | Active | Dominion | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 9/15/2024 |  |  | N | No
AH1-036 | Centerburg 138 kV |  | OH | Licking | Withdrawn | AEP | 277.5 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-037 | Chippewa D557 8.320 kV |  | N/A | N/A | Withdrawn | ATSI | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2021 | N/A | N/A |  | 12/18/2024 |  | 11/1/2023 |  |  | Y | No
AH1-038 | Kramer |  | N/A | N/A | Withdrawn | PENELEC | 3.825 | 3.825 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2021 | N/A | N/A |  | 1/4/2022 |  | 11/1/2023 |  |  | Y | No
AH1-039 | Mt. Hermon 23 kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/19/2021 | N/A | N/A |  | 1/25/2022 |  | 10/1/2023 |  |  | N | No
AH1-040 - moved to TC2 | Mackeys - Creswell 115 kV |  | NC | Washington | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2021 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH1-041 - moved to TC2 | Pennville 138 kV |  | IN | Jay | Withdrawn | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2021 | N/A | N/A |  | 7/3/2025 |  | 7/1/2025 |  |  | N | No
AH1-042 - moved to TC2 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 154 | 99.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/25/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AH1-043 | Sand Hills - Brunswick 69 kV |  | NJ | Middlesex | Withdrawn | PSEG | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2021 | N/A | N/A |  | 12/19/2024 |  | 5/15/2024 |  |  | N | No
AH1-044 - moved to TC2 | Nelson - Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 800 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-045 - moved to TC2 | Zion Energy Center 345 kV |  | IL | Lake | Withdrawn | ComEd | 658 | 23 | 13.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/1/2021 | N/A | N/A |  | 2/27/2025 |  | 6/1/2023 |  |  | N | No
AH1-046 - moved to TC2 | Peach Bottom 500 kV |  | PA | York | Withdrawn | PECO | 905 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/1/2021 | N/A | N/A |  | 4/25/2025 |  | 6/1/2023 |  |  | N | No
AH1-047 - moved to TC2 | Marengo - Belvidere 138 kV |  | IL | Boone | Active | ComEd | 58.6 | 58.6 | 37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/6/2021 | N/A | N/A |  |  |  | 9/13/2022 |  |  | N | No
AH1-048 | Riverton 138 |  | VA | Warren | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2024 |  |  | N | No
AH1-049 | Erie East – Union City Ckt 00234-31 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2023 |  |  | N | No
AH1-050 - moved to TC2 | Eclipse-Piney 115 kV |  | PA | Venango | Active | PENELEC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-051 - moved to TC2 | Eclipse-Piney 115 kV II |  | PA | Venango | Active | PENELEC | 80 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-052 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 260 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AH1-053 | Luthersburg - Curwensville 12.47 kV |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/8/2021 | N/A | N/A |  | 6/5/2024 |  | 6/30/2023 |  |  | N | No
AH1-054 - moved to TC2 | Upton-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 8.25 | 8.25 | 3.465 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/9/2021 | N/A | N/A |  |  |  | 7/8/2022 |  |  | N | No
AH1-055 - moved to TC2 | Kyger Creek - Don Marquis 345 kV |  | OH | Jackson | Active | OVEC | 220 | 220 | 154 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2021 | N/A | N/A |  |  |  | 11/15/2026 |  |  | N | No
AH1-056 - moved to TC2 | Red House D.P. 115kV |  | VA | Campbell | Active | Dominion | 100 | 100 | 68.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2021 | N/A | N/A |  |  |  | 11/15/2026 |  |  | N | No
AH1-057 - moved to TC2 | Edgewood 12.47 kV |  | MD | Wicomico | Active | DPL | 7.2 | 7.2 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/15/2021 | N/A | N/A |  |  |  | 1/31/2023 |  |  | N | No
AH1-058 | Galion 138 kV IV |  | OH | Morrow | Withdrawn | ATSI | 204 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/16/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-059 - moved to TC2 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 120 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/16/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-060 - moved to TC2 | Cardington-Liberty 69 kV III |  | OH | Morrow | Active | ATSI | 94 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-061 | Bernville 13.2kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-062 | London-Tangy 69 kV II |  | OH | Madison | Withdrawn | ATSI | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/22/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-063 | Spring Creek – South Abingdon 138 kV |  | VA | Washington | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-064 | Hopewell 34.5kV |  | VA | City of Hopewell | Withdrawn | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2023 |  |  | N | No
AH1-065 - moved to TC2 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH1-066 - moved to TC2 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH1-067 | Minotola 12.47 kV |  | NJ | Gloucester | Withdrawn | AEC | 8.5 | 8.5 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  | 12/18/2024 |  | 12/10/2023 |  |  | N | No
AH1-068 | Williamstown 12.47 kV |  | NJ | Gloucester | Withdrawn | AEC | 12 | 12 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2021 | N/A | N/A |  | 12/18/2024 |  | 12/10/2023 |  |  | N | No
AH1-069 - moved to TC2 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AH1-070 - moved to TC2 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 34 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AH1-071 - moved to TC2 | Midlothian 34.5 kV |  | VA | Powhatan | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-072 - moved to TC2 | Red Onion - VC5 69 kV |  | VA | Dickenson | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AH1-073 - moved to TC2 | Red Onion - VC5 69 kV |  | VA | Dickenson | Active | AEP | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AH1-074 | Fitchville-New London 69 kV |  | OH | Huron | Withdrawn | ATSI | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-075 - moved to TC2 | North Waldo - Wild Creek 138 kV |  | OH | Marion | Active | AEP | 68 | 8 | 24.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-076 - moved to TC2 | Loyalhanna - Reed Junction 25 kV |  | PA | Westmoreland | Withdrawn | APS | 18 | 18 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  | 3/14/2025 |  | 12/31/2023 |  |  | N | No
AH1-077 | TBD 34.5 kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 3 | 1.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/18/2024 |  | 8/9/2021 |  |  | N | No
AH1-078 | Paulsboro 69 kV II |  | NJ | Gloucester | Withdrawn | AEC | 79 | 0 | 58 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2022 |  |  | N | No
AH1-079 | Harmony Village 34.5kV |  | VA | Middlesex | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/18/2024 |  | 12/20/2024 |  |  | N | No
AH1-080 | Virginia Beach - Pendleton 115 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/18/2024 |  | 1/1/2025 |  |  | N | No
AH1-081 - moved to TC2 | Knob Lick 69kV |  | KY | Metcalfe | Withdrawn | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 5/5/2025 |  | 12/20/2024 |  |  | N | No
AH1-082 - moved to TC2 | Knob Lick 69kV |  | KY | Metcalfe | Withdrawn | EKPC | 104 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 5/5/2025 |  | 12/20/2024 |  |  | N | No
AH1-083 - moved to TC2 | Summer Shade - Green County 161 kV |  | KY | Metcalfe | Withdrawn | EKPC | 250 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 5/5/2025 |  | 12/20/2024 |  |  | N | No
AH1-084 - moved to TC2 | Sullivan 345 kV |  | IN | Sullivan | Withdrawn | AEP | 2500 | 500 | 500 |  | Capacity | Merchant Transmission |  | DC | 500 FTIR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | S | No
AH1-085 | Sullivan 345kV |  | N/A | N/A | Withdrawn | AEP | 500 | 500 | 0 |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 11/23/2024 |  | 12/31/2025 |  |  | S | No
AH1-086 - moved to TC2 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-087 - moved to TC2 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 110 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-088 - moved to TC2 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 130 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-089 - moved to TC2 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 150 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-090 | Surry - Hopewell 230 kV |  | VA | Surry | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/18/2024 |  | 11/15/2024 |  |  | N | No
AH1-091 - moved to TC2 | Ahoskie 34.5kV |  | NC | Hertford | Active | Dominion | 17 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AH1-092 - moved to TC2 | SedgeHill - Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 5/7/2025 |  | 6/1/2025 |  |  | N | No
AH1-093 | SedgeHill - Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 160 | 60 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2025 |  |  | N | No
AH1-094 - moved to TC2 | Wells - Shinrock 69 kV I |  | OH | Huron | Withdrawn | ATSI | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 7/1/2025 |  | 6/1/2025 |  |  | N | No
AH1-095 | Wells - Shinrock 69 kV II |  | OH | Huron | Withdrawn | ATSI | 69.9 | 20 | 13 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2025 |  |  | N | No
AH1-096 | Wells - Shinrock 69 kv III |  | OH | Huron | Withdrawn | ATSI | 79.9 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2025 |  |  | N | No
AH1-097 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Withdrawn | AEP | 20 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-098 - moved to TC2 | Wolf Glade-West Carroll 138 kV |  | VA | Carroll | Active | AEP | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-099 | Glady Run–Xenia 69 kV |  | OH | Greene | Withdrawn | Dayton | 20 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 11/1/2024 |  | 6/1/2025 |  |  | N | No
AH1-100 | Effort Mountain-Gilbert 138 kV II |  | PA | Monroe | Withdrawn | PPL | 45.2 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 8/26/2024 |  | 6/1/2025 |  |  | N | No
AH1-101 | River EC 138 kV |  | IL | Cook | Withdrawn | ComEd | 57.78 | 57.78 | 23.12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  | 8/26/2021 |  | 5/31/2024 |  |  | N | No
AH1-102 - moved to TC2 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 100 | 100 | 63.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-103 | Pinewood - St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2021 | N/A | N/A |  | 1/10/2024 |  | 6/1/2025 |  |  | N | No
AH1-104 | Hepburna 12.47 kV Grampian ckt |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2021 | N/A | N/A |  | 6/5/2024 |  | 7/22/2023 |  |  | N | No
AH1-105 | TBD 23 kV |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/3/2021 | N/A | N/A |  | 11/8/2021 |  | 4/1/2022 |  |  | N | No
AH1-106 - moved to TC2 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AH1-107 - moved to TC2 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AH1-108 - moved to TC2 | Spruance NUG 230 kV |  | VA | City of Richmond | Active | Dominion | 66 | 0 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2021 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AH1-109 | Krendale - Unionville 12.47 kV |  | OH | Adams | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ah1109_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ah1109_wmpa.pdf | Not Required | N/A | N/A |  | 8/3/2021 | N/A | N/A |  | 12/13/2023 |  | 9/20/2024 | 9/20/2024 |  | Y | No
AH1-110 | Newville 12 kV II |  | PA | Cumberland | Withdrawn | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2021 | N/A | N/A |  | 8/7/2024 |  | 7/31/2023 |  |  | N | No
AH1-111 | Walker 12 kV |  | PA | Juniata | Withdrawn | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2021 | N/A | N/A |  | 8/7/2024 |  | 7/31/2023 |  |  | N | No
AH1-112 | New Meredith 23 kV |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2021 | N/A | N/A |  | 11/8/2021 |  | 4/1/2022 |  |  | N | No
AH1-113 | North Pole - Russelville 34.5 kV |  | OH | Brown | Withdrawn | DEOK | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2023 |  |  | N | No
AH1-114 | North Pole - Russelville 34.5 kV |  | OH | Brown | Withdrawn | DEOK | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2023 |  |  | N | No
AH1-115 |  |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2021 | N/A | N/A |  | 9/2/2021 |  | 4/1/2022 |  |  | N | No
AH1-116 5132083 | PJM-MECS |  | N/A | N/A | Withdrawn |  | 1200 | 1200 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/12/2021 | 6/1/2023 | 6/1/2024 |  | 6/15/2022 |  |  |  |  | PP | No
AH1-117 5136432 | PJM-CIN |  | N/A | N/A | Withdrawn |  |  | 260 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/12/2021 | 6/1/2023 | 6/1/2024 |  | 5/2/2023 |  |  |  |  | PP | No
AH1-118 | Windsor 25 kV |  | WV | Brooke | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-119 | Bismark-Doubs 500 kV |  | VA | Frederick | Withdrawn | Dominion | 100 | 100 | 66.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-120 | Felton 23kV |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/17/2021 | N/A | N/A |  | 11/8/2021 |  | 4/1/2022 |  |  | N | No
AH1-121 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2021 | N/A | N/A |  | 9/9/2021 |  | 8/12/2022 |  |  | Y | No
AH1-122 | Dowling 138 kV II |  | OH | Wood | Withdrawn | ATSI | 75 | 22 | 9.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/19/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-123 | Locust Grove D.P. 34.5kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2021 | N/A | N/A |  | 11/17/2021 |  | 2/28/2023 |  |  | N | No
AH1-124 - moved to TC2 | Vint Hill 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-125 - moved to TC2 | Sycoline 34.5kV |  | VA | Loudoun | Active | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-126 | Bowman 12.5kV |  | VA | Prince William | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  | 7/14/2022 |  | 12/23/2022 |  |  | N | No
AH1-127 - moved to TC2 | Railroad 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-128 - moved to TC2 | Railroad 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-129 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2021 | N/A | N/A |  | 12/18/2024 |  | 2/28/2023 |  |  | N | No
AH1-130 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2021 | N/A | N/A |  | 12/18/2024 |  | 2/28/2023 |  |  | N | No
AH1-131 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  | 12/18/2024 |  | 2/28/2023 |  |  | N | No
AH1-132 | Double Toll Gate - Strasburg 34.5 kV |  | VA | Frederick | Withdrawn | APS | 14.4 | 14.4 | 14.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  | 12/17/2024 |  | 1/1/2022 |  |  | N | No
AH1-133 - moved to TC2 | Saltville - Tazewell 138 kV |  | VA | Tazewell | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-134 | Northern Neck 230 kV |  | VA | Richmond | Withdrawn | Dominion | 20 | 0 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2021 | N/A | N/A |  | 10/5/2021 |  | 1/1/2023 |  |  | N | No
AH1-135 | Vienna - Vienna 8 138 kV |  | N/A | N/A | Withdrawn | DPL |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2021 | N/A | N/A |  | 12/14/2023 |  | 6/1/2023 |  |  | EE | No
AH1-136 - moved to TC2 | Falcon - Middle Creek 46 kV |  | KY | N/A | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-137 |  |  | PA | Adams | Withdrawn | PPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  | 8/26/2021 |  | 12/31/2022 |  |  | Y | No
AH1-138 - moved to TC2 | Penniman 34.5 kV |  | VA | City of Williamsburg | Active | Dominion | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/15/2022 |  |  | N | No
AH1-139 | Cooper 34.5kV |  | PA | York | Withdrawn | PECO | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | Y | No
AH1-140 - moved to TC2 | Vasco 138 kV |  | PA | Westmoreland | Active | APS | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-141 | Darbytown 230 kV |  | VA | Henrico | Withdrawn | Dominion | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-142 | Darbytown 230 kV II |  | VA | Henrico | Withdrawn | Dominion | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2024 |  |  | N | No
AH1-143 | Darbytown 230 kV III |  | VA | Henrico | Withdrawn | Dominion | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-144 - moved to TC2 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-145 - moved to TC2 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 200 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-146 - moved to TC2 | White Rock - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-147 - moved to TC2 | White Rock - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 400 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-148 - moved to TC2 | White Rock - Wayne 345 kV |  | IL | Ogle | Withdrawn | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-149 | Moselem-Saint Peters Tap 69 kV |  | PA | Berks | Withdrawn | ME | 8.375 | 8.375 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2021 | N/A | N/A |  | 12/18/2024 |  | 9/19/2022 |  |  | N | No
AH1-150 - moved to TC2 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1000 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-151 - moved to TC2 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-152 - moved to TC2 | Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 150 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 7/4/2025 |  | 12/31/2025 |  |  | N | No
AH1-153 - moved to TC2 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 300 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-154 - moved to TC2 | Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 300 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 7/4/2025 |  | 12/31/2025 |  |  | N | No
AH1-154A | Mount Rock12 kV II |  | PA | Snyder | Withdrawn | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 2/14/2022 |  | 12/31/2022 |  |  | N | No
AH1-154B | Hughesville 12 kV |  | PA | Lycoming | Withdrawn | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 2/14/2022 |  | 12/31/2022 |  |  | N | No
AH1-155 5139596 | NIPS-PJM |  | N/A | N/A | Confirmed |  |  | 3 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/ft-feas/ah1155_fea.pdf | Executed Agreement and/or Study |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 8/27/2021 | 12/1/2021 | 12/1/2026 | [6 empty] | PP | No
AH1-156 | Cane Ridge 69 kV |  | KY | Bourbon | Withdrawn | EKPC | 40 | 40 | 25.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-157 - moved to TC2 | Penniman - Waller 230 kV |  | VA | York | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 1/1/2025 |  |  | N | No
AH1-158 - moved to TC2 | Eclipse-Piney 115 kV III |  | PA | Venango | Active | PENELEC | 80 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-159 - moved to TC2 | Conneaut-Conneaut Tap 69 kV |  | PA | Crawford | Withdrawn | ATSI | 20 | 20 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2021 | N/A | N/A |  | 7/7/2025 |  | 11/1/2023 |  |  | N | No
AH1-160 - moved to TC2 | Tower Hill 34.5 kV |  | PA | Tioga | Withdrawn | PENELEC | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 3/28/2025 |  | 11/1/2023 |  |  | N | No
AH1-161 | Canal 69 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2021 | N/A | N/A |  | 12/18/2024 |  | 11/1/2023 |  |  | N | No
AH1-162 - moved to TC2 | Curryville-RKB-Yellow Creek 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 16 | 16 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 7/7/2025 |  | 11/1/2023 |  |  | N | No
AH1-163 - moved to TC2 | Millersburg 69 kV |  | KY | N/A | Withdrawn | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 1/28/2025 |  | 7/31/2025 |  |  | N | No
AH1-164 - moved to TC2 | Oak Level - Tank Hill 138 kV |  | VA | Franklin | Active | AEP | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-165 - moved to TC2 | Will County 138 kV |  | IL | Will | Active | ComEd | 72 | 72 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-166 | Carson – Suffolk 500 kV |  | VA | Sussex | Withdrawn | Dominion | 800 | 0 | 320 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 10/12/2021 |  | 12/1/2024 |  |  | N | No
AH1-167 | Pinewood - St Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 80 | 80 | 51.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2026 |  |  | N | No
AH1-168 | Pinewood - St Johns 115 kV II |  | VA | Caroline | Withdrawn | Dominion | 120 | 40 | 25.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2026 |  |  | N | No
AH1-169 | Greenbush 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 12/18/2024 |  | 12/20/2024 |  |  | N | No
AH1-170 - moved to TC2 | Columbia DP 115kV |  | VA | Goochland | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-171 | Columbia DP 115kV |  | VA | Goochland | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  | 12/18/2024 |  | 12/20/2024 |  |  | N | No
AH1-172 | Wolf Glade 34.5 kV |  | VA | Carroll | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-173 | Buckhorn 34.5 kV |  | VA | Tazewell | Withdrawn | AEP | 16.65 | 16.65 | 9.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 8/18/2023 |  | 12/31/2022 |  |  | N | No
AH1-174 | Westlake 34.5 kV |  | VA | Franklin | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-175 | Sheffield 34.5 kV |  | VA | Henry | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-176 | Ridgeway 34.5 kV |  | VA | Henry | Withdrawn | AEP | 18.8 | 18.8 | 11.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-177 | Willis Gap 34.5 kV |  | VA | Carroll | Withdrawn | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 3/2/2023 |  | 12/31/2022 |  |  | N | No
AH1-178 | Remington - Morrisville 34.5 kV |  | VA | Fauquier | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-179 - moved to TC2 | Edinburg - Woodstock DP 34.5 kV |  | VA | Shenandoah | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 4/9/2025 |  | 12/31/2022 |  |  | N | No
AH1-180 | Westlake 34.5 kV |  | VA | Franklin | Withdrawn | AEP | 9 | 9 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-181 | Stuart 34.5 |  | VA | Patrick | Withdrawn | AEP | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 9/5/2024 |  | 12/31/2022 |  |  | N | No
AH1-182 | Peak Creek 34.5 |  | VA | Pulaski | Withdrawn | AEP | 11.45 | 11.45 | 6.87 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-183 | Remington - Elm 34.5 kV |  | VA | Fauquier | Withdrawn | Dominion | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 8/15/2023 |  | 12/31/2022 |  |  | N | No
AH1-184 | Powhatan - Powhatan DP 24.94 kV |  | VA | Powhatan | Withdrawn | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2022 |  |  | N | No
AH1-185 - moved to TC2 | Benn's Church - Smithfield 34.5 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 2/25/2025 |  | 12/31/2022 |  |  | N | No
AH1-186 | Maysville-Sharon 69 kV II |  | PA | Mercer | Withdrawn | ATSI | 19.9 | 0 | 6.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 12/18/2024 |  | 10/18/2024 |  |  | N | No
AH1-187 | Andover (Maysville) 69 kV III |  | PA | Crawford | Withdrawn | ATSI | 17.9 | 0 | 5.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 10/8/2021 |  | 10/18/2024 |  |  | N | No
AH1-188 - moved to TC2 | Pigeon Creek 138 kV |  | WV | Mingo | Active | AEP | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-189 - moved to TC2 | Hopkins 138 kV |  | WV | N/A | Withdrawn | AEP | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  | 7/3/2025 |  | 6/1/2025 |  |  | N | No
AH1-190 | Waukegan 138 kV |  | IL | Lake | Withdrawn | ComEd | 80 | 80 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-191 | Powerton 138 kV |  | IL | Tazewell | Withdrawn | ComEd | 20.9 | 20.9 | 12.065 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-192 | Sunbury-Columbia 69kV |  | PA | Northumberland | Withdrawn | PPL | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 3/14/2022 |  | 9/1/2023 |  |  | N | No
AH1-193 | Sunbury-Danville 69 kV |  | PA | Northumberland | Withdrawn | PPL | 5 | 5 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 3/14/2022 |  | 9/1/2023 |  |  | N | No
AH1-194 | Warfordsburg – Hancock 34.5 kV |  | PA | Fulton | Withdrawn | APS | 5 | 5 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 3/14/2022 |  | 9/1/2023 |  |  | N | No
AH1-195 | Mechanicsburg - Darby 138 kV |  | OH | Champaign | Withdrawn | Dayton | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2021 | N/A | N/A |  | 8/8/2022 |  | 9/1/2024 |  |  | N | No
AH1-196 - moved to TC2 | Prairie 345 kV |  | IL | McHenry | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2021 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH1-197 - moved to TC2 | Occoquan 230kV |  | VA | Fairfax | Withdrawn | Dominion | 98 | 0 | 7.1 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 3/14/2025 |  | 8/20/2021 |  |  | N | No
AH1-198 | Marysville - Sorenson 765 kV |  | OH | Logan | Withdrawn | AEP | 1355 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-199 | Loretto 345 kV |  | IL | Livingston | Withdrawn | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-200 | Compressor 605 69kV |  | PA | Wyoming | Withdrawn | PPL | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2021 | N/A | N/A |  | 10/6/2023 |  | 12/31/2023 |  |  | N | No
AH1-201 - moved to TC2 | Allegheny-New Baltimore 115kV |  | PA | Somerset | Active | PENELEC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-202 | New Baltimore 115 kV II (Mountain Ridge Solar) |  | PA | Somerset | Withdrawn | PENELEC | 120 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2021 | N/A | N/A |  | 12/18/2024 |  | 8/31/2023 |  |  | N | No
AH1-203 - moved to TC2 | Allegheny-Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-204 | Allegheny-Somerset 115 kV II |  | PA | Somerset | Withdrawn | PENELEC | 90 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2021 | N/A | N/A |  | 12/18/2024 |  | 8/31/2023 |  |  | N | No
AH1-205 - moved to TC2 | Allegheny-New Baltimore 115kV |  | PA | Somerset | Active | PENELEC | 40 | 0 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-206 - moved to TC2 | Bethelboro 138 kV |  | PA | Fayette | Active | APS | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-207 | Bethelboro 25 kV-1 |  | PA | Fayette | Withdrawn | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-208 | Bethelboro 25 kV-2 |  | PA | Fayette | Withdrawn | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-209 | Bethelboro 25 kV-3 |  | PA | Fayette | Withdrawn | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-210 | Bethelboro 25 kV-4 |  | PA | Fayette | Withdrawn | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-211 | Bethelboro 25 kV-5 |  | PA | Fayette | Withdrawn | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-212 - moved to TC2 | Bethlehem - Lilly 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-213 | James River 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 52.5 | 52.5 | 31.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 4/1/2024 |  | 2/1/2025 |  |  | N | No
AH1-214 | Red House DP 115 kV |  | VA | Campbell | Withdrawn | Dominion | 44.1 | 44.1 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 6/21/2024 |  | 2/1/2025 |  |  | N | No
AH1-215 - moved to TC2 | Central VA-Twitty 115 kV |  | VA | Charlotte | Active | Dominion | 31.5 | 31.5 | 18.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-216 - moved to TC2 | Smithfield-Surry 230 kV |  | VA | Isle of Wight | Active | Dominion | 99 | 99 | 79.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-217 - moved to TC2 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Active | Dominion | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-218 | Garner DP 115 kV |  | VA | Northumberland | Withdrawn | Dominion | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 10/18/2023 |  | 2/1/2025 |  |  | N | No
AH1-219 | Blue Jacket 138 kV |  | OH | Logan | Withdrawn | Dayton | 39.9 | 39.9 | 23.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 4/8/2024 |  | 2/1/2025 |  |  | N | No
AH1-220 - moved to TC2 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-221 - moved to TC2 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 75 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-222 - moved to TC2 | Ladysmith CT 230 kV |  | VA | Caroline | Withdrawn | Dominion | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 4/29/2025 |  | 12/1/2023 |  |  | N | No
AH1-223 - moved to TC2 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 150 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-224 | Willard 69 kV |  | OH | Huron | Withdrawn | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 11/18/2022 |  | 8/31/2023 |  |  | N | No
AH1-225 | Wood Solar 69 kV |  | OH | Wayne | Withdrawn | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 8/31/2023 |  |  | N | No
AH1-226 - moved to TC2 | Clubhouse - Sapony 230 kV |  | VA | City of Emporia | Withdrawn | Dominion | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 4/11/2025 |  | 12/1/2025 |  |  | N | No
AH1-227 - moved to TC2 | Flemming - Fremont 69 kV |  | VA | Wise | Active | AEP | 51.3 | 51.3 | 30.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-228 | Marsh Run 230kV |  | VA | Fauquier | Withdrawn | Dominion | 615 | 18 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 10/1/2024 |  |  | N | No
AH1-229 | Louisa 230kV |  | VA | Louisa | Withdrawn | Dominion | 564 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AH1-230 | Sabinsville 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-231 | Lanexa 230kV |  | VA | New Kent | Withdrawn | Dominion | 28.8 | 28.8 | 28.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-232 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2025 |  |  | N | No
AH1-233 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 175 | 0 | 70 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2025 |  |  | N | No
AH1-234 - moved to TC2 | Wempletown - Paddock 345 kV |  | IL | Winnebago | Active | ComEd | 224 | 224 | 29.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/21/2025 |  |  | N | No
AH1-235 | Kilgore Compressor Facility 138 kV |  | OH | Harrison | Withdrawn | AEP | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/25/2023 |  |  | N | No
AH1-236 | Bane 69 kV |  | OH | Carroll | Withdrawn | AEP | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-237 | Ladysmith- Elmont 230kV |  | VA | Caroline | Withdrawn | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-238 | Ladysmith- Elmont 230kV |  | VA | Caroline | Withdrawn | Dominion | 180 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-239 - moved to TC2 | Upchurch - Zula 69 kV |  | KY | Boone | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-240 | Wayne County 161 kV |  | KY | Boone | Withdrawn | EKPC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-241 - moved to TC2 | Cobbs Creek - James River Industrial 115kV |  | VA | Cumberland | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-242 | New Bethlehem-Armstrong 138kV |  | PA | Clarion | Withdrawn | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-243 | New Bethlehem – Armstrong 138kV |  | PA | Clarion | Withdrawn | APS | 60 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-244 | Yukon-Bethelboro 138kV |  | PA | Fayette | Withdrawn | APS | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-245 | Yukon-Bethelboro 138kV |  | PA | Fayette | Withdrawn | APS | 160 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-246 | Osterberg 115kV |  | PA | Bedford | Withdrawn | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-247 - moved to TC2 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-248 - moved to TC2 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 65 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-249 - moved to TC2 | Lardin – Lake Lynn 138kV |  | PA | Fayette | Active | APS | 145 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-250 | Todds Tavern- Spotsylvania/Goldsdale 115kV |  | VA | Spotsylvania | Withdrawn | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 3/3/2023 |  | 12/31/2024 |  |  | N | No
AH1-251 - moved to TC2 | Todds Tavern- Spotsylvania/Goldsdale 115kV |  | VA | Spotsylvania | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-252 | Wharton - Sundial 138 kV |  | WV | Barbour | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-253 | Price 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 15.5 | 15.5 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 10/1/2024 |  |  | N | No
AH1-254 - moved to TC2 | Greenland Gap 500 kV II |  | WV | Barbour | Active | APS | 171.4 | 171.4 | 36.538 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-255 - moved to TC2 | Greenland Gap III |  | WV | Grant | Withdrawn | APS | 240 | 240 | 240 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 7/7/2025 |  | 7/31/2025 |  |  | N | No
AH1-256 | Greeland Gap 500 kV IV |  | WV | Grant | Withdrawn | APS | 951.6 | 240 | 240 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 7/31/2025 |  |  | N | No
AH1-257 - moved to TC2 | Broadway - Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-258 - moved to TC2 | Belford - Keansburg 34.5 kV |  | NJ | Monmouth | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-259 | Chesterfield- Centralia 115kV |  | VA | Chesterfield | Withdrawn | Dominion | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-260 - moved to TC2 | New Freedom - Monroe 230 kV |  | NJ | Camden | Active | AEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-261 - moved to TC2 | Northeast - Riverside 230 kV |  | MD | Baltimore County | Active | BGE | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-262 | Deep Creek 115 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 11/30/2023 |  |  | N | No
AH1-263 - moved to TC2 | Chancellor 115 kV |  | VA | Spotsylvania | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-264 | Suffolk- Sunbury 230kV |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-265 - moved to TC2 | Winslow - Monroe 69kV |  | NJ | Camden | Active | AEC | 29.4 | 29.4 | 12.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-266 | Clubhouse – Lakeview 230 kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-267 | Papermill IND – Harmony Village 230 kV |  | VA | King and Queen | Withdrawn | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-268 - moved to TC2 | Seward-Glory 115 kV II |  | PA | Indiana | Active | PENELEC | 100 | 0 | 36.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-269 - moved to TC2 | Claytor 138 kV |  | VA | Pulaski | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-270 | Hayden 345 kV |  | OH | Franklin | Withdrawn | AEP | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2023 |  |  | N | No
AH1-271 - moved to TC2 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 110 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 9/20/2024 |  |  | N | No
AH1-272 - moved to TC2 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 185 | 185 | 123.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-273 | Brown - Eastwood 138 kV |  | OH | Brown | Withdrawn | DEOK | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/26/2025 |  |  | N | No
AH1-274 - moved to TC2 | Butler 69 kV |  | NJ | Gloucester | Active | AEC | 16.7 | 16.7 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-275 | Chippewa D557 8.32 kV |  | N/A | N/A | Withdrawn | ATSI | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 11/1/2023 |  |  | Y | No
AH1-276 | Leasure 12.47kV |  | VA | Campbell | Withdrawn | PENELEC | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 6/15/2022 |  | 11/1/2023 |  |  | Y | No
AH1-277 | Indian River 230kV |  | DE | Sussex | Withdrawn | DPL | 1035 | 1035 | 279 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2027 |  |  | N | No
AH1-278 | Milford - Indian River/Cool Springs 230kV |  | DE | Sussex | Withdrawn | DPL | 1035 | 1035 | 279 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2027 |  |  | N | No
AH1-279 | Poolesville - Winchester 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 104 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/12/2023 |  |  | N | No
AH1-280 - moved to TC2 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 106 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AH1-281 - moved to TC2 | Bluegrass Parkway Tap - Woodlawn 69 kV |  | KY | Nelson | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/7/2024 |  |  | N | No
AH1-282 - moved to TC2 | Galion - Ohio Central 345 kV |  | OH | Morrow | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-283 - moved to TC2 | Mount Storm-Pruntytown 500kV |  | MD | Garrett | Active | APS | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AH1-284 | West Willow 12 kV |  | PA | Adams | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | Y | No
AH1-285 - moved to TC2 | Sandwich 138 kV |  | IL | DeKalb | Active | ComEd | 86 | 86 | 11.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-286 | Bradford North 34.5kV |  | WV | Preston | Withdrawn | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 11/1/2023 |  |  | Y | No
AH1-287 | Houseville – Cooperstown 25 kV |  | OH | Madison | Withdrawn | APS | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 11/1/2023 |  |  | Y | No
AH1-288 | Chickahominy 230kV |  | VA | Charles City | Withdrawn | Dominion | 43.2 | 43.2 | 43.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-289 | Eugene 345 kV |  | IN | Vermillion | Withdrawn | AEP | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2028 |  |  | N | No
AH1-290 - moved to TC2 | BASF - Washburn Solar 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 7/7/2025 |  | 9/9/2022 |  |  | N | No
AH1-291 - moved to TC2 | Rock Creek-Hummel Creek 138 kV |  | IN | Huntington | Withdrawn | AEP | 185 | 185 | 111 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-292 - moved to TC2 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-293 | Makahoy 138 kV |  | IN | Madison | Withdrawn | AEP | 120 | 0 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-294 - moved to TC2 | Mclean 345 kV |  | IL | McLean | Withdrawn | ComEd | 350 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-295 - moved to TC2 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Withdrawn | ComEd | 130 | 130 | 22.88 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-296 - moved to TC2 | Beason 345 kV |  | IL | Logan | Withdrawn | ComEd | 175 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-297 - moved to TC2 | Kewanee - E.D. Edwards 138 kV |  | IL | Stark | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-298 - moved to TC2 | Meridian 345 kV |  | IN | Whitley | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-299 | Coventry 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/7/2021 |  | 12/31/2025 |  |  | N | No
AH1-300 | Hacienda 138 kV |  | IN | Allen | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-301 | Milan 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-302 - moved to TC2 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-303 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Withdrawn | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-304 - moved to TC2 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 0 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-305 - moved to TC2 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 0 | 35.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-306 - moved to TC2 | Mississinewa-Gaston 138 kV |  | IN | Grant | Active | AEP | 200 | 0 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-307 - moved to TC2 | Delaware-Van Buren 138 kV |  | IN | Delaware | Withdrawn | AEP | 213 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-308 - moved to TC2 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 205 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-309 - moved to TC2 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 0 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-310 | Colby - Valley 138 kV |  | MI | Van Buren | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-311 - moved to TC2 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 0 | 2.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-312 | Shilo DP – Conetoe DP 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-313 - moved to TC2 | Moshannon-Milesburg 230 kV VII |  | PA | Centre | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-314 - moved to TC2 | East Danville 138 kV |  | VA | Pittsylvania | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-315 | Maroe 69 kV |  | OH | Henry | Withdrawn | ATSI | 96 | 96 | 57.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/14/2024 |  | 12/31/2025 |  |  | N | No
AH1-316 - moved to TC2 | Todd 25 kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 0 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/7/2025 |  | 12/31/2025 |  |  | N | No
AH1-317 | Greene - Beatty 345 kV |  | OH | Madison | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-318 - moved to TC2 | Cole 345 kV |  | OH | Franklin | Withdrawn | AEP | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-319 - moved to TC2 | East Springfield-London 138 kV II |  | OH | Clark | Withdrawn | ATSI | 54 | 54 | 54 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-320 - moved to TC2 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Withdrawn | Dayton | 275.55 | 69 | 69 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-321 - moved to TC2 | Eldean 138 kV |  | OH | Miami | Withdrawn | Dayton | 232 | 54 | 54 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-322 | Fostoria Central - Lemoyne 345 kV |  | OH | Miami | Withdrawn | AEP | 390 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-323 - moved to TC2 | Elmont 230 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-324 - moved to TC2 | Colonial Trail – Surry 230 kV |  | VA | Surry | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-325 - moved to TC2 | Kirk 138 kV |  | OH | Licking | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-326 | West Newton - Lynn 138 kV |  | OH | Hardin | Withdrawn | AEP | 110 | 0 | 19.07 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-327 - moved to TC2 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 250 | 0 | 8.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-328 - moved to TC2 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 206.55 | 0 | 21.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-329 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Withdrawn | AEP | 130 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-330 | Tyner - McKee 69 kV |  | KY | N/A | Withdrawn | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-331 - moved to TC2 | Edinboro South-Erie South 25kV |  | PA | Erie | Withdrawn | PENELEC | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 7/3/2025 |  | 6/1/2023 |  |  | N | No
AH1-332 | West Hills - Craigsville Junction 25 kV |  | PA | Armstrong | Withdrawn | APS | 19.9 | 19.9 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2023 |  |  | N | No
AH1-333 | Miller - Canal 69kV |  | OH | Butler | Withdrawn | DEOK | 48 | 48 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 4/26/2024 |  |  | N | No
AH1-334 - moved to TC2 | Lakehurst - Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/9/2022 |  |  | N | No
AH1-335 | Furnace Brook Tap - Warren County Resource Recovery 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/9/2022 |  |  | N | No
AH1-336 | Bremo Bluff - Buckingham 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 56 | 56 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-337 - moved to TC2 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 46 | 46 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-338 - moved to TC2 | McGirr Rd - Ritchie Road 138kV |  | IL | Lee | Active | ComEd | 180 | 180 | 23.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/21/2025 |  |  | N | No
AH1-339 - moved to TC2 | West Crawford 69 kV |  | OH | Wyandot | Active | AEP | 80 | 80 | 6.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/21/2025 |  |  | N | No
AH1-340 - moved to TC2 | Cheat Lake-Ruthbelle 138 kV |  | WV | Preston | Active | APS | 48.89 | 48.89 | 29.33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AH1-341 - moved to TC2 | Stillman ;RT - Dixon ;R 138KV 138kv |  | IL | Ogle | Active | ComEd | 150 | 150 | 96.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/7/2025 |  |  | N | No
AH1-342 | Carlos Junction 138 kV II |  | MD | Allegany | Withdrawn | APS | 75 | 75 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/1/2021 |  | 7/16/2025 |  |  | N | No
AH1-343 - moved to TC2 | Crystal Hill DP- Perth 115kV |  | VA | Halifax | Active | Dominion | 69 | 69 | 41.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-344 | Sparta Solar 34.5kV |  | NJ | Atlantic | Withdrawn | JCPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 1/4/2022 |  | 9/20/2023 |  |  | Y | No
AH1-345 - moved to TC2 | Remington 324 34.5 kV |  | VA | Fauquier | Active | Dominion | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AH1-346 | Harrisonburg 356 34.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/29/2024 |  | 12/31/2023 |  |  | N | No
AH1-347 | North Pole 492 34.5 kV |  | VA | Goochland | Withdrawn | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/5/2024 |  | 3/31/2023 |  |  | N | No
AH1-348 - moved to TC2 | Pound 34.5 kV |  | VA | Wise | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/21/2023 |  |  | N | No
AH1-349 | Powhatan 406 34.5 kV |  | VA | Powhatan | Withdrawn | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/5/2024 |  | 12/31/2023 |  |  | N | No
AH1-350 | Sunnyside – Carrolton 138 kV |  | OH | Stark | Withdrawn | AEP | 92.4 | 92.4 | 55.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 11/15/2024 |  | 6/1/2025 |  |  | N | No
AH1-351 | Hillsboro-Wye Mills 138kV |  | MD | Queen Anne's | Withdrawn | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2025 |  |  | N | No
AH1-352 - moved to TC2 | Red Eye 138 kV |  | VA | Campbell | Withdrawn | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/28/2025 |  | 9/30/2023 |  |  | N | No
AH1-353 - moved to TC2 | Lena 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 9/10/2024 |  |  | N | No
AH1-354 - moved to TC2 | Lena 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 60 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 9/10/2024 |  |  | N | No
AH1-355 - moved to TC2 | Owl Trap Switching Station 115kV |  | VA | Gloucester | Withdrawn | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/25/2025 |  | 9/10/2024 |  |  | N | No
AH1-356 - moved to TC2 | Kings Creek 138kV |  | MD | Somerset | Withdrawn | DPL | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/14/2025 |  | 9/30/2023 |  |  | N | No
AH1-357 - moved to TC2 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 180 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-358 - moved to TC2 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 200 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-359 - moved to TC2 | Pierce Brook - Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 220 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-360 - moved to TC2 | Pierce Brook - Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 240 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-361 - moved to TC2 | Minonk 345 kV |  | IL | Woodford | Withdrawn | ComEd | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/12/2025 |  | 9/10/2024 |  |  | N | No
AH1-362 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-363 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-364 | Harmony Village 230kV |  | VA | Middlesex | Withdrawn | Dominion | 68 | 68 | 68 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-365 | Iron Bridge 230kV |  | VA | Chesterfield | Withdrawn | Dominion | 50.4 | 50.4 | 50.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-366 | Whitely 138 kV |  | PA | Greene | Withdrawn | APS | 30 | 30 | 22 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/13/2024 |  | 9/10/2023 |  |  | N | No
AH1-367 | Franklin 138 kV |  | PA | Greene | Withdrawn | APS | 74 | 74 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/13/2024 |  | 9/10/2023 |  |  | N | No
AH1-367A - moved to TC2 | Franklin 138 kV II |  | PA | Greene | Active | APS | 72 | 72 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AH1-368 | Cloverdale - Joshua Falls 765 kV |  | VA | Bedford | Withdrawn | AEP | 125 | 125 | 83.3333 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-369 | Backbone Mountain 138 kV II |  | WV | Tucker | Withdrawn | APS | 40 | 20 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 1/23/2023 |  | 12/31/2023 |  |  | N | No
AH1-370 | Mather - Stoney Point Junction 25 kV |  | PA | Greene | Withdrawn | APS | 8 | 8 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/3/2024 |  |  | N | No
AH1-371 | Universal 12 kV |  | PA | Allegheny | Withdrawn | DL | 13 | 13 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/15/2021 |  | 6/3/2024 |  |  | N | No
AH1-372 | Piney - Timblin 115 kV |  | PA | Armstrong | Withdrawn | APS | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/3/2024 |  |  | N | No
AH1-373 | Buckeye No. 3 - Cowell Junction 25kV |  | PA | Greene | Withdrawn | APS | 12.8 | 12.8 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/3/2024 |  |  | N | No
AH1-374 | Bremo-Cartersville 230 kV II |  | VA | Cumberland | Withdrawn | Dominion | 115 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/9/2024 |  | 6/30/2026 |  |  | N | No
AH1-375 | Cobbs Creek- James River 115kV |  | VA | Fluvanna | Withdrawn | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 11/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-376 - moved to TC2 | Ronceverte - Clenden 46 kV |  | WV | Greenbrier | Withdrawn | APS | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 4/22/2025 |  | 6/1/2025 |  |  | N | No
AH1-377 - moved to TC2 | Clover- Farmville 230kV |  | VA | Prince Edward | Active | Dominion | 186 | 186 | 111.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-378 - moved to TC2 | Lunenburg- Butcher Creek 115kV |  | VA | Lunenburg | Withdrawn | Dominion | 51 | 51 | 30.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 4/16/2025 |  | 6/1/2025 |  |  | N | No
AH1-379 | Hickman 69 kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/20/2024 |  |  | N | No
AH1-380 - moved to TC2 | Mt Olive - Kenny 69kV |  | MD | Worcester | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-381 | Lone Gum - Rockcastle 138 kV |  | VA | Bedford | Withdrawn | AEP | 99.5 | 99.5 | 59.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2025 |  |  | N | No
AH1-382 | Van Arsdell 69 kV |  | KY | Mercer | Withdrawn | EKPC | 20 | 20 | 17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/10/2025 |  |  | N | No
AH1-383 | Celanese 138 kV |  | VA | Giles | Withdrawn | AEP | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-384 | Indian River 230kV |  | DE | Sussex | Withdrawn | DPL | 1410 | 1410 | 380.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2027 |  |  | N | No
AH1-385 | Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 109 | 109 | 65.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-386 | Kerr Dam - Chase City 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-387 - moved to TC2 | Meadowbrook-Greenland Gap 500kV |  | WV | Hampshire | Active | APS | 150 | 150 | 22.05 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 1/9/2025 |  |  | N | No
AH1-388 | Chase City-Herbert 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 115 | 115 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/20/2024 |  |  | N | No
AH1-389 | Utica East Ohio Midstream 138 kV |  | OH | Warren | Withdrawn | ATSI | 19.95 | 19.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-390 - moved to TC2 | TBD 69 kV |  | PA | Northumberland | Withdrawn | PPL | 19.9 | 19.9 | 14.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/12/2025 |  | 7/31/2023 |  |  | N | No
AH1-391 - moved to TC2 | Olive 138 kV |  | IN | St. Joseph | Active | AEP | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/16/2025 |  |  | N | No
AH1-392 - moved to TC2 | Gravel Pit-Kankakee 138 kV |  | IN | St. Joseph | Active | AEP | 90 | 90 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/16/2025 |  |  | N | No
AH1-393 | Markus Solar 115 kV |  | PA | Indiana | Withdrawn | PENELEC | 3.75 | 3.75 | 1.425 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/4/2021 |  | 12/31/2023 |  |  | N | No
AH1-394 | Mainesburg 115 kV |  | PA | Tioga | Withdrawn | PENELEC | 10.5 | 10.5 | 3.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 2/2/2022 |  | 12/31/2023 |  |  | N | No
AH1-395 | Mainesburg 115 kV II |  | PA | Tioga | Withdrawn | PENELEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2023 |  |  | N | No
AH1-396 - moved to TC2 | Gary 24.94 kV |  | VA | Lunenburg | Active | Dominion | 12 | 12 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-397 - moved to TC2 | Shacklesfords 34.5 kV |  | VA | King and Queen | Active | Dominion | 19.818 | 19.818 | 2.97 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-398 | Oak Grove 22.9 kV |  | VA | Westmoreland | Withdrawn | Dominion | 18 | 18 | 11.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2021 | N/A | N/A |  | 12/18/2024 |  | 10/2/2023 |  |  | N | No
AH1-399 - moved to TC2 | North Doswell 12.5 kV |  | VA | Hanover | Active | Dominion | 9.87 | 9.87 | 1.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-400 | Jones Creek - Aladdin 138 kV |  | IN | Madison | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2025 |  |  | N | No
AH1-401 | Jones Creek - Aliddin 138 kV |  | IN | Madison | Withdrawn | AEP | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/17/2024 |  | 6/1/2025 |  |  | N | No
AH1-402 | Shelocta 115kV |  | PA | Indiana | Withdrawn | PENELEC | 85 | 85 | 55.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/21/2024 |  | 12/31/2024 |  |  | N | No
AH1-403 | Shelocta 115kV |  | PA | Indiana | Withdrawn | PENELEC | 85 | 0 | 29.1 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/21/2024 |  | 12/31/2024 |  |  | N | No
AH1-404 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Withdrawn | OVEC | 210 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/13/2024 |  | 12/31/2024 |  |  | N | No
AH1-405 | Exchange Tap I 69 kV |  | PA | Northumberland | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/13/2024 |  | 10/18/2024 |  |  | N | No
AH1-406 | Exchange Tap 69 kV II |  | PA | Northumberland | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/13/2024 |  | 10/18/2024 |  |  | N | No
AH1-407 | Exchange Tap 69 kV III |  | PA | Northumberland | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/13/2024 |  | 10/18/2024 |  |  | N | No
AH1-408 - moved to TC2 | Freeman DP – Lawrenceville 115 kV |  | VA | Brunswick | Active | Dominion | 120 | 120 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-409 | Brodhead - Maretburg 69 kV |  | KY | N/A | Withdrawn | EKPC | 58 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2024 |  |  | N | No
AH1-410 | Union City Tap – JK Smith 138 kV |  | KY | Madison | Withdrawn | EKPC | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2024 |  |  | N | No
AH1-411 | Phillipsburg - Ingersol Rand 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 5.75 | 5.75 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/8/2024 |  | 9/8/2022 |  |  | N | No
AH1-412 | Franklintown 34.5 kV |  | WV | Jefferson | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/19/2024 |  | 10/1/2025 |  |  | N | No
AH1-413 | Wayne Trace 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 8/7/2024 |  | 10/1/2025 |  |  | N | No
AH1-414 | Leslie - Pineville 161 kV |  | KY | Leslie | Withdrawn | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 2/29/2024 |  | 10/1/2025 |  |  | N | No
AH1-415 | Bremo Bluff 34.5kV |  | VA | Fluvanna | Withdrawn | Dominion | 15.975 | 15.975 | 8.6265 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/10/2024 |  | 10/11/2023 |  |  | N | No
AH1-416 | Bellefontaine 69 kV |  | OH | Logan | Withdrawn | Dayton | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/16/2024 |  | 10/1/2025 |  |  | N | No
AH1-417 | Castalia 69 kV |  | OH | Erie | Withdrawn | ATSI | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/24/2024 |  | 10/1/2025 |  |  | N | No
AH1-418 | Elkhorn City - Second Fork 69 kV |  | KY | Pike | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/13/2024 |  | 10/1/2025 |  |  | N | No
AH1-419 | Thompson 34.5 kV II |  | PA | Susquehanna | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/1/2025 |  |  | N | No
AH1-420 | Fentress 34.5kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/26/2023 |  |  | N | No
AH1-421 | West Mingo 69 kV |  | OH | Champaign | Withdrawn | Dayton | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-422 | West Mingo 69 kV |  | OH | Champaign | Withdrawn | Dayton | 60 | 20 | 18.85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-423 | West Mingo 69 kV |  | OH | Champaign | Withdrawn | Dayton | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-424 | Sandborn 34.5 kV |  | OH | Ashtabula | Withdrawn | ATSI | 19.2 | 19.2 | 11.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-425 | Lemoyne 138kV |  | OH | Ottawa | Withdrawn | ATSI | 32 | 32 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2024 |  |  | N | No
AH1-426 - moved to TC2 | Gilboa-Jones Branch 138 kV IV |  | WV | Kanawha | Active | APS | 64.6 | 64.6 | 64.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-426A - moved to TC2 | Gilboa-Jones Branch 138 kV V |  | WV | Nicholas | Active | APS | 96.9 | 32.3 | 32.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-427 - moved to TC2 | Tommy Gooch - Garrard County 69 kV |  | KY | N/A | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-428 - moved to TC2 | Tommy Gooch - Garrard County 69 kV |  | KY | Boone | Withdrawn | EKPC | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 9/1/2026 |  |  | N | No
AH1-429 - moved to TC2 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Withdrawn | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 9/1/2026 |  |  | N | No
AH1-430 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Withdrawn | EKPC | 90 | 0 | 36 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2026 |  |  | N | No
AH1-431 | Pennville 138 kV |  | IN | Jay | Withdrawn | AEP | 125 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2025 |  |  | N | No
AH1-432 - moved to TC2 | Randolph - Hodgin 138 kV |  | IN | Randolph | Withdrawn | AEP | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 4/1/2025 |  |  | N | No
AH1-433 | Kingsland 69 kV |  | IN | Wells | Withdrawn | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 4/1/2025 |  |  | N | No
AH1-434 - moved to TC2 | Carolina- Earleys 115kV |  | NC | Northhampton | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 9/1/2026 |  |  | N | No
AH1-435 | Carolina- Earleys 115kV |  | NC | Northhampton | Withdrawn | Dominion | 75 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2026 |  |  | N | No
AH1-436 | Mackeys- Creswell 115kV |  | NC | Washington | Withdrawn | Dominion | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2025 |  |  | N | No
AH1-437 | Remington- Gordonsville 230kV |  | VA | Culpeper | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2026 |  |  | N | No
AH1-438 | Remington- Gordonsville 230kV |  | VA | Culpeper | Withdrawn | Dominion | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/1/2026 |  |  | N | No
AH1-439 - moved to TC2 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-440 - moved to TC2 | Buckingham- Farmville 230kV |  | VA | Cumberland | Withdrawn | Dominion | 85 | 0 | 34 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 9/1/2026 |  |  | N | No
AH1-441 | Cunningham - Elmont 500 kV III |  | VA | Fluvanna | Withdrawn | Dominion | 149 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-442 | Cunningham - Elmont 500 kV IV |  | VA | Fluvanna | Withdrawn | Dominion | 149 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-443 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Withdrawn | Dominion | 0 | 0 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/30/2026 |  |  | N | No
AH1-444 | Fentress – Sligo 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 200 | 200 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/18/2021 |  | 9/1/2025 |  |  | N | No
AH1-445 | Belleville 46 kV |  | PA | Mifflin | Withdrawn | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 8/7/2024 |  | 9/30/2023 |  |  | N | No
AH1-446 - moved to TC2 | Sanders DP - Westmoreland 230 kV |  | VA | Westmoreland | Withdrawn | Dominion | 65 | 65 | 19.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/20/2025 |  | 12/2/2024 |  |  | N | No
AH1-447 - moved to TC2 | Axton – Danville #2 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/20/2025 |  | 12/2/2024 |  |  | N | No
AH1-448 | East Palmerton-Harwood 230 kV |  | PA | Carbon | Withdrawn | PPL | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 12/1/2024 |  |  | N | No
AH1-449 | Muskingum River - Sporn 345 kV |  | OH | Washington | Withdrawn | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AH1-450 | Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2025 |  |  | N | No
AH1-451 | Hopkins 138 kV |  | WV | N/A | Withdrawn | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2025 |  |  | N | No
AH1-452 - moved to TC2 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 8.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-453 | Eugene 345 kV |  | IN | Vermillion | Withdrawn | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2028 |  |  | N | No
AH1-454 | Pinewood- St Johns 115kV |  | VA | Caroline | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-455 | Middle Creek 69 kV |  | KY | Magoffin | Withdrawn | EKPC | 60 | 60 | 39.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 11/2/2023 |  | 9/1/2025 |  |  | N | No
AH1-456 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-457 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 130 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-458 | Hampshire - Ridgeley 138 kV 1 |  | WV | Hampshire | Withdrawn | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-459 | Hampshire - Ridgeley 138 kV 2 |  | WV | Hampshire | Withdrawn | APS | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/30/2024 |  |  | N | No
AH1-460 - moved to TC2 | Hooversville - Scalp Level 115 kV |  | PA | Somerset | Active | PENELEC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-461 - moved to TC2 | Buckhorn 138 kV |  | VA | Tazewell | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-462 - moved to TC2 | Rachel Hill 115 kV |  | PA | Cambria | Withdrawn | PENELEC | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 2/12/2025 |  | 12/31/2024 |  |  | N | No
AH1-463 - moved to TC2 | Owingsville - Preston 69 kV |  | KY | Bath | Withdrawn | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 4/22/2025 |  | 12/31/2024 |  |  | N | No
AH1-464 | Hinkston 24.9 kV |  | KY | Montgomery | Withdrawn | EKPC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 3/2/2023 |  | 12/31/2022 |  |  | N | No
AH1-465 | Carson – Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 350 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-466 - moved to TC2 | Baker - Broadford 765 kV |  | KY | Boone | Withdrawn | AEP | 600 | 600 | 360 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 2/25/2025 |  | 12/31/2024 |  |  | N | No
AH1-467 - moved to TC2 | Baker - Broadford 765 kV |  | KY | Boone | Withdrawn | AEP | 900 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 2/25/2025 |  | 12/31/2024 |  |  | N | No
AH1-468 | Hokes-Jackson 69 kV V |  | PA | York | Withdrawn | ME | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/11/2021 |  | 9/25/2023 |  |  | N | No
AH1-469 | Derry Tap-Derry Bus 69 kV III |  | PA | Montour | Withdrawn | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-470 | Derry Tap- Derry Bus 69 kV IV |  | PA | Northumberland | Withdrawn | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-471 | Derry Tap- Derry Bus 69 kV VI |  | PA | Snyder | Withdrawn | PPL | 27.5 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-472 | Derry Tap- Derry Bus 69 kV VII |  | PA | Columbia | Withdrawn | PPL | 91 | 56 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-473 | Hokes-Jackson 69 kV VI |  | PA | York | Withdrawn | ME | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/11/2021 |  | 9/25/2023 |  |  | N | No
AH1-474 | Edinboro South-Venango Junction 115 kV III |  | PA | Crawford | Withdrawn | PENELEC | 203.5 | 87 | 87 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-475 | Edinboro-Cambridge Springs 34.5 kV II |  | PA | Crawford | Withdrawn | PENELEC | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-476 | Hunterstown-Texas Eastern Tap 115 kV II |  | PA | Adams | Withdrawn | ME | 170.5 | 73 | 73 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/23/2024 |  |  | N | No
AH1-477 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 112 | 112 | 112 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-478 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Withdrawn | PPL | 60 | 40 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-479 | New Carlisle 138 kV |  | IN | St. Joseph | Withdrawn | AEP | 192 | 82 | 82 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-480 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Withdrawn | AEP | 132 | 57 | 57 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-481 | Reynolds - Meadow Lake #1 345 kV |  | IN | White | Withdrawn | AEP | 196 | 84 | 84 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2024 |  |  | N | No
AH1-482 - moved to TC2 | Olive - Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 338 | 78 | 78 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-483 | Honda Marysville Tap 69 kV |  | OH | Union | Withdrawn | Dayton | 142 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/23/2024 |  |  | N | No
AH1-484 | Madison - Tanners Creek 138 kV |  | IN | Henry | Withdrawn | AEP | 267.5 | 115 | 115 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/24/2023 |  |  | N | No
AH1-485 | Brookside-Cloverdale 138 kV II |  | OH | Wayne | Withdrawn | ATSI | 228 | 98 | 98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/11/2021 |  | 9/25/2023 |  |  | N | No
AH1-486 | Maysville 69 kV 1 |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 7/30/2024 |  |  | N | No
AH1-487 - moved to TC2 | Camp Reynolds 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-488 | Maysville 34.5 kV 3 |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/30/2024 |  |  | N | No
AH1-489 | Maysville 34.5 kV 4 |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/30/2024 |  |  | N | No
AH1-490 - moved to TC2 | Venango Junction - Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-491 - moved to TC2 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-492 - moved to TC2 | Bernville 13 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 6/9/2025 |  | 7/30/2024 |  |  | N | No
AH1-493 | Bernville 34.5 kV 2 |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 7/30/2024 |  |  | N | No
AH1-494 | Wakefield 12 kV |  | PA | Lancaster | Withdrawn | PPL | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/5/2023 |  | 6/30/2024 |  |  | N | No
AH1-495 | Middleburg 12 kV |  | PA | Snyder | Withdrawn | PPL | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/5/2023 |  | 6/30/2024 |  |  | N | No
AH1-496 | West Berwick 12 kV |  | PA | Columbia | Withdrawn | PPL | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/5/2023 |  | 6/30/2024 |  |  | N | No
AH1-497 | Hadley 12.47kV |  | PA | Mercer | Withdrawn | ATSI | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-498 | Jamestown 12.47kV |  | PA | Crawford | Withdrawn | ATSI | 5 | 5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-499 | Stoneboro 12.47kV |  | PA | Mercer | Withdrawn | ATSI | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-500 | Conesville Junction – Parkview Road Junction 46 kV |  | PA | Potter | Withdrawn | APS | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-501 | Tionesta Junction – Crown 34.5 kV |  | PA | Forest | Withdrawn | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-502 | Dequine - Eugene 345 kV |  | IN | Warren | Withdrawn | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2028 |  |  | N | No
AH1-503 | Kings Fork – Chuckatuck 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 150 | 150 | 127.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/30/2025 |  |  | N | No
AH1-504 | Lickdale 13.2kV |  | PA | Lebanon | Withdrawn | ME | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-505 | Wheatland 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-506 | Oceanview Wind 3 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 2056 | 730 | 300 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/30/2028 |  |  | N | No
AH1-507 | Oceanview Wind 4 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 2786 | 730 | 300 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/30/2028 |  |  | N | No
AH1-508 | Bremo-Fork Union Military Academy 34.5 kV |  | VA | Fluvanna | Withdrawn | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/18/2023 |  | 2/1/2025 |  |  | N | No
AH1-509 | TBD 12 kV |  | PA | Northumberland | Withdrawn | PPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/14/2022 |  | 12/31/2023 |  |  | Y | No
AH1-510 | Clarence Solar 12 kV |  | N/A | N/A | Withdrawn | PENELEC | 4.95 | 4.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/1/2021 |  | 12/31/2023 |  |  | Y | No
AH1-511 | Blacklick Solar 12 kV |  | N/A | N/A | Withdrawn | PENELEC | 4.95 | 4.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/1/2021 |  | 12/31/2023 |  |  | Y | No
AH1-512 | Brush Creek Solar 12 kV |  | N/A | N/A | Withdrawn | PENELEC | 4.95 | 4.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/1/2021 |  | 12/31/2023 |  |  | Y | No
AH1-513 | Summit Community Solar 12 kV |  | N/A | N/A | Withdrawn | APS | 4.95 | 4.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/1/2021 |  | 12/31/2023 |  |  | Y | No
AH1-514 | Philipsburg - Emeigh 12.47 kV-1 |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/29/2023 |  |  | N | No
AH1-515 | Philipsburg - Emeigh 12.47 kV-2 |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/29/2023 |  |  | N | No
AH1-515A | Springdale - Wycoff 12.8 kV |  | PA | Allegheny | Withdrawn | APS | 5 | 5 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/14/2022 |  | 12/29/2023 |  |  | N | No
AH1-516 | Springfield Road - Springfield Road 69 kV |  | OH | Butler | Withdrawn | DEOK | 70 | 70 | 44.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/1/2025 |  |  | N | No
AH1-517 |  |  | IL | Adams | Withdrawn | ComEd |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 6/1/2022 |  |  | Y | No
AH1-518 | Pulaski Sub-New Wilmington 69kV |  | PA | Lawrence | Withdrawn | ATSI | 19 | 19 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2023 |  |  | N | No
AH1-519 |  |  | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 134.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 10/15/2024 |  |  | N | No
AH1-520 | Blue Jacket-Kirby 138 kV V |  | OH | Union | Withdrawn | ATSI | 120 | 120 | 79.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/15/2024 |  |  | N | No
AH1-521 | Blue Jacket-Kirby 138 kV VI |  | OH | Union | Withdrawn | ATSI | 100 | 100 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/15/2024 |  |  | N | No
AH1-522 | Timber Switch 138 kV |  | OH | Paulding | Withdrawn | AEP | 47 | 47 | 28.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-523 | Heidelberg 69 kV |  | PA | Lebanon | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 7/30/2024 |  |  | N | No
AH1-524 | University Park - Olive 345 kV |  | IN | LaPorte | Withdrawn | AEP | 117 | 117 | 70.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/18/2023 |  | 12/31/2025 |  |  | N | No
AH1-525 | University Park - Olive 345 kV |  | IN | LaPorte | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 7/18/2023 |  | 12/31/2025 |  |  | N | No
AH1-526 - moved to TC2 | Knox - Washington CEC 138 kV |  | OH | Carroll | Withdrawn | ATSI | 80 | 80 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 6/5/2025 |  | 10/31/2025 |  |  | N | No
AH1-527 | Chase City- Herbert Plant Substation 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/30/2025 |  |  | N | No
AH1-528 - moved to TC2 | Rawlings - Unity 500 kV |  | VA | Brunswick | Active | Dominion | 300.8 | 300.8 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/30/2025 |  |  | N | No
AH1-529 | Renaker - Avon 138 kV |  | KY | Bourbon | Withdrawn | EKPC | 89 | 24 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2025 |  |  | N | No
AH1-530 - moved to TC2 | Fairfield – Reily 69 kV |  | OH | Butler | Withdrawn | DEOK | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 2/4/2025 |  | 3/1/2025 |  |  | N | No
AH1-531 | Salyers Rd 34.5 kV |  | OH | Pike | Withdrawn | AEP | 21 | 21 | 12.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2025 |  |  | N | No
AH1-532 | Marion County - Marion Co. Industrial 161 kV |  | KY | Marion | Withdrawn | EKPC | 37.8 | 37.8 | 22.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2025 |  |  | N | No
AH1-533 - moved to TC2 | Sunbury-Juniata II |  | PA | Perry | Withdrawn | PPL | 185.2 | 96.2 | 38.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 3/1/2025 |  |  | N | No
AH1-534 | Sullivan Gardens - Walters 138 kV |  | TN | Greene | Withdrawn | AEP | 22.7 | 22.7 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2025 |  |  | N | No
AH1-535 - moved to TC2 | Nagel - Cane River 230 kV |  | TN | Hawkins | Active | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-536 - moved to TC2 | Church-Oil City 138kV |  | MD | Queen Anne's | Active | DPL | 41.8 | 41.8 | 8.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-537 - moved to TC2 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 178.5 | 178.5 | 17.85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-538 - moved to TC2 | East Lima - Haviland 138 kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 3/1/2025 |  |  | N | No
AH1-539 - moved to TC2 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 129.4 | 129.4 | 25.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-540 - moved to TC2 | Byron to Wayne 345 kV |  | IL | Ogle | Withdrawn | ComEd | 165 | 165 | 33 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 3/1/2025 |  |  | N | No
AH1-541 - moved to TC2 | Chestnut 345 kV |  | IL | DeWitt | Active | ComEd | 92.4 | 92.4 | 27.72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-542 - moved to TC2 | Crissinger-Delaware Business Park 138kV |  | OH | Marion | Active | ATSI | 110 | 110 | 22 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-543 - moved to TC2 | Mulberry – Tazewell 345 kV |  | IL | Livingston | Active | ComEd | 157.4 | 157.4 | 31.48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-544 | La Salle 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 67.7 | 67.7 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/1/2025 |  |  | N | No
AH1-545 - moved to TC2 | Wylie Ridge-Tidd 345kV |  | PA | Washington | Active | APS | 200 | 200 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-546 - moved to TC2 | Bremo - Buckingham 230 kV |  | VA | Buckingham | Active | Dominion | 79.8 | 79.8 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-547 | Reynolds - Olive #1 345 kV |  | IN | White | Withdrawn | AEP | 180 | 0 | 74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2022 |  |  | N | No
AH1-548 | Sorenson 345 kV |  | IN | Huntington | Withdrawn | AEP | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-549 - moved to TC2 | Allen - RP Mone 345 kV |  | IN | Allen | Withdrawn | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/31/2025 |  |  | N | No
AH1-550 | Hazelton - Kirk 138 kV |  | OH | Licking | Withdrawn | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/17/2024 |  | 12/31/2025 |  |  | N | No
AH1-551 |  |  | OH | Carroll | Withdrawn | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 10/31/2025 |  |  | N | No
AH1-552 - moved to TC2 | Chalk Point 230 kV |  | MD | Prince George's | Active | PEPCO | 670.2 | 670.2 | 670.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-553 | Broadview -Tangy 138 kV II |  | OH | Madison | Withdrawn | ATSI | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/17/2024 |  | 10/1/2025 |  |  | N | No
AH1-554 | Lick 138 kV |  | OH | Jackson | Withdrawn | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/1/2025 |  |  | N | No
AH1-555 | Maxwell 138 kV |  | OH | Cuyahoga | Withdrawn | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/18/2021 |  | 10/1/2025 |  |  | N | No
AH1-556 | Larrabee 230 kV III |  | NJ | Monmouth | Withdrawn | JCPL | 805.2 | 360 | 63.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2029 |  |  | N | No
AH1-557 - moved to TC2 | Larrabee Collector Station 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1300 | 1300 | 228.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 2/14/2025 |  | 10/31/2029 |  |  | N | No
AH1-558 - moved to TC2 | Four Rivers 230kV |  | VA | Hanover | Withdrawn | Dominion | 996 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 6/26/2025 |  | 6/1/2025 |  |  | N | No
AH1-559 |  |  | IL | Will | Withdrawn | ComEd | 896 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 11/1/2021 |  | 6/1/2025 |  |  | N | No
AH1-560 - moved to TC2 | University Park 138 kV |  | IL | Will | Withdrawn | ComEd | 473 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 6/30/2025 |  | 6/1/2025 |  |  | N | No
AH1-561 - moved to TC2 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 1075 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 6/27/2025 |  | 6/1/2025 |  |  | N | No
AH1-562 - moved to TC2 | Springdale 138kV |  | PA | Allegheny | Withdrawn | APS | 356 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 6/30/2025 |  | 6/1/2025 |  |  | N | No
AH1-563 - moved to TC2 | Aurora E.C. 138kV |  | IL | N/A | Active | ComEd | 1206 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-564 - moved to TC2 | Rockford II 138 kV |  | IL | Winnebago | Active | ComEd | 330 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-565 - moved to TC2 | Lemoyne 345kV |  | OH | Wood | Withdrawn | ATSI | 950 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 5/7/2025 |  | 6/1/2025 |  |  | N | No
AH1-566 - moved to TC2 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 1038.1 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 6/30/2025 |  | 6/1/2025 |  |  | N | No
AH1-567 - moved to TC2 | University Park 138 kV |  | IL | Will | Active | ComEd | 328 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-568 | Keen Mountain 138 kV |  | VA | Buchanan | Withdrawn | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 6/1/2025 |  |  | N | No
AH1-569 - moved to TC2 | Tangy - National 138 kV |  | OH | Union | Withdrawn | ATSI | 42 | 42 | 31.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/7/2025 |  | 12/1/2024 |  |  | N | No
AH1-570 - moved to TC2 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 25 | 25 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-571 - moved to TC2 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 45 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-572 - moved to TC2 | South Morral-Uncapher Switch 69 kV |  | OH | Marion | Withdrawn | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/1/2024 |  |  | N | No
AH1-573 - moved to TC2 | South Morral-Uncapher Switch 69 kV |  | OH | Marion | Withdrawn | AEP | 49.99 | 19.99 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/3/2025 |  | 12/1/2024 |  |  | N | No
AH1-574 | Harrington 69kV |  | DE | Kent | Withdrawn | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/25/2024 |  |  | N | No
AH1-575 | Harrington 69kV |  | DE | Kent | Withdrawn | DPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/25/2024 |  |  | N | No
AH1-576 | South Harrington 69kV |  | DE | Kent | Withdrawn | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/25/2024 |  |  | N | No
AH1-577 - moved to TC2 | Clutch 69 kV |  | OH | Wayne | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2028 |  |  | N | No
AH1-578 - moved to TC2 | Clutch 69 kV |  | OH | Wayne | Active | AEP | 98 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2028 |  |  | N | No
AH1-579 | Marysville – Hyatt 345 kV |  | OH | Union | Withdrawn | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2028 |  |  | N | No
AH1-580 - moved to TC2 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 400 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-581 |  |  | OH | Pickaway | Withdrawn | Dayton | 200 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 5/1/2025 |  |  | N | No
AH1-582 | Marysville - Flatlick 765 kV |  | OH | Madison | Withdrawn | AEP | 800 | 0 | 146.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2026 |  |  | N | No
AH1-583 | Marysville - Flatlick 765 kV |  | OH | Madison | Withdrawn | AEP | 800 | 0 | 146.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 5/1/2026 |  |  | N | No
AH1-584 - moved to TC2 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-585 - moved to TC2 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-586 - moved to TC2 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 145 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-587 - moved to TC2 | Farmers Valley – Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-588 - moved to TC2 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 240 | 240 | 144 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-589 - moved to TC2 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 410 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-590 - moved to TC2 | Cherry Ridge 66 kV |  | WV | Grant | Withdrawn | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/8/2025 |  | 12/16/2024 |  |  | N | No
AH1-591 - moved to TC2 | Cherry Ridge 66kV |  | WV | Grant | Withdrawn | APS | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/8/2025 |  | 12/16/2024 |  |  | N | No
AH1-592 - moved to TC2 | Cherry Ridge 66kV |  | WV | Grant | Withdrawn | APS | 145 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 7/8/2025 |  | 12/16/2024 |  |  | N | No
AH1-593 | Hazelton 138 |  | WV | Preston | Withdrawn | APS | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/16/2024 |  |  | N | No
AH1-594 | Hazelton 138kV |  | WV | Preston | Withdrawn | APS | 97 | 32 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/16/2024 |  |  | N | No
AH1-595 | Fowler Ridge 345 kV |  | IN | Benton | Withdrawn | AEP | 150 | 150 | 96.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/3/2025 |  |  | N | No
AH1-596 | Fowler Ridge 345 kV |  | IN | Benton | Withdrawn | AEP | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/3/2025 |  |  | N | No
AH1-597 | LM Troy 138 kV |  | OH | Ashland | Withdrawn | ATSI | 110 | 110 | 70.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/3/2025 |  |  | N | No
AH1-598 | LM Troy 138 kV |  | OH | Ashland | Withdrawn | ATSI | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 3/3/2025 |  |  | N | No
AH1-599 |  |  | IL | Lee | Withdrawn | ComEd | 150 | 150 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 3/3/2025 |  |  | N | No
AH1-600 |  |  | IL | Lee | Withdrawn | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 3/3/2025 |  |  | N | No
AH1-601 |  |  | IL | Lee | Withdrawn | ComEd | 300 | 300 | 192.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 3/3/2025 |  |  | N | No
AH1-602 |  |  | IL | Lee | Withdrawn | ComEd | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/13/2021 |  | 3/3/2025 |  |  | N | No
AH1-603 |  |  | OH | Crawford | Withdrawn | AEP | 200 | 200 | 129.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/14/2021 |  | 3/3/2025 |  |  | N | No
AH1-604 |  |  | OH | Crawford | Withdrawn | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/14/2021 |  | 3/3/2025 |  |  | N | No
AH1-605 |  |  | IN | Union | Withdrawn | AEP | 120 | 120 | 77 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/14/2021 |  | 3/3/2025 |  |  | N | No
AH1-606 |  |  | IN | Union | Withdrawn | AEP | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/14/2021 |  | 3/3/2025 |  |  | N | No
AH1-607 |  |  | IN | Delaware | Withdrawn | AEP | 119.04 | 119.04 | 71.424 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/19/2021 |  | 4/30/2025 |  |  | N | No
AH1-608 | Milliron-Brookside 138kV |  | OH | Richland | Withdrawn | ATSI | 49.26 | 49.26 | 29.556 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 10/12/2021 |  | 4/30/2025 |  |  | N | No
AH1-609 | Milliron-Brookside 138kV |  | OH | Richland | Withdrawn | ATSI | 168.31 | 168.31 | 100.986 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 4/30/2025 |  |  | N | No
AH1-610 | Altavista - Stonemill 69 kV |  | VA | Accomack | Withdrawn | Dominion |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 10/23/2023 |  | 12/31/2024 |  |  | EE | No
AH1-611 | Perkiomenville 34.5kV |  | PA | Montgomery | Withdrawn | PECO | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/5/2023 |  | 6/30/2024 |  |  | N | No
AH1-612 | North Orwell - East Sayre 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/7/2023 |  | 6/30/2024 |  |  | N | No
AH1-613 | Earleys- Suffolk 230kV |  | VA | City of Suffolk | Withdrawn | Dominion | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 3/22/2024 |  | 10/1/2025 |  |  | N | No
AH1-614 | Burns 69 kV |  | OH | Clermont | Withdrawn | DEOK | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/23/2024 |  | 10/1/2025 |  |  | N | No
AH1-615 | Pine Creek 138 kV |  | PA | Allegheny | Withdrawn | DL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 10/1/2025 |  |  | N | No
AH1-616 | Chicago Heights 138 kV |  | IL | Cook | Withdrawn | ComEd | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 9/19/2024 |  | 10/1/2025 |  |  | N | No
AH1-617 - moved to TC2 | Harbert Metering 138 kV |  | KY | N/A | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AH1-618 | Beaver Creek 138 kV |  | KY | N/A | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/30/2024 |  |  | N | No
AH1-619 | Beaver Creek 138 kV |  | KY | N/A | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/30/2024 |  |  | N | No
AH1-620 | Carville 138kV |  | MD | Queen Anne's | Withdrawn | DPL | 76 | 76 | 45.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-621 | Steele-Milford 230kV |  | MD | Allegany | Withdrawn | DPL | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-622 | Five Fork 115kV |  | PA | York | Withdrawn | PECO | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-623 | South Anna - Desper 230 kV |  | VA | Louisa | Withdrawn | Dominion | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-624 | Mainesburg-Homer City 345kV |  | PA | Clearfield | Withdrawn | PENELEC | 230 | 230 | 138 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-625 | Cowen 138kV |  | WV | Webster | Withdrawn | APS | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 12/1/2025 |  |  | N | No
AH1-626 - moved to TC2 | Ladysmith 230 kV |  | VA | Caroline | Withdrawn | Dominion | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 1/14/2025 |  | 3/21/2025 |  |  | N | No
AH1-627 - moved to TC2 | Ladysmith 230 kV II |  | VA | Caroline | Withdrawn | Dominion | 125 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 1/14/2025 |  | 3/21/2025 |  |  | N | No
AH1-628 5141135 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 670 | 670 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 9/7/2021 | 6/1/2025 | 6/1/2027 |  | 6/19/2024 |  |  |  |  | PP | No
AH1-629 | Hokes-Grantley 69 kV III |  | PA | York | Withdrawn | ME | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 10/18/2021 |  | 9/25/2023 |  |  | N | No
AH1-630 | Penns Tap-Richfield Tie 69 kV V |  | PA | Snyder | Withdrawn | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-631 | Edinboro South 34.5 kV III |  | PA | Crawford | Withdrawn | PENELEC | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-632 | Mercersburg-Milnor 34.5 kV III |  | PA | Franklin | Withdrawn | APS | 27 | 12 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  | 12/18/2024 |  | 9/25/2023 |  |  | N | No
AH1-633 | Powerton to Katydid 345 kV |  | IL | Livingston | Withdrawn | ComEd | 288 | 288 | 172.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  | 12/18/2024 |  | 9/26/2024 |  |  | N | No
AH1-634 - moved to TC2 | Indian River 230kV I |  | DE | Sussex | Active | DPL | 323.1 | 68 | 17.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-635 |  |  | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 134.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  | 10/19/2021 |  | 10/15/2024 |  |  | N | No
AH1-636 |  |  | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 134.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  | 10/19/2021 |  | 10/15/2024 |  |  | N | No
AH1-637 - moved to TC2 | Oak Grove 34.5 kV |  | VA | Westmoreland | Active | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AH1-638 | Pleasantville 12.47kV |  | NJ | Atlantic | Withdrawn | AEC | 1.625 | 1.625 | 0.6825 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  | 8/15/2022 |  | 11/1/2022 |  |  | N | No
AH1-639 | Lordstown - Mansfield 345 kV |  | OH | Mahoning | Withdrawn | ATSI | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  | 12/18/2024 |  | 10/31/2025 |  |  | N | No
AH1-640 | Gladys DP - Stonemill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  | 12/18/2024 |  | 12/3/2025 |  |  | N | No
AH1-641 - moved to TC2 | Churchtown - Upper Pittsgrove 138kV |  | NJ | Salem | Active | AEC | 65 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-642 | Morgantown - Tompkinsville 69kV |  | MD | Charles | Withdrawn | SMECO | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  | 10/13/2021 |  | 10/31/2023 |  |  | N | No
AH1-643 | Hewitt Road - Oakville 69kV |  | MD | St. Mary's | Withdrawn | SMECO | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  | 10/14/2021 |  | 10/31/2023 |  |  | N | No
AH1-644 - moved to TC2 | Spicewood Metering 138 kV |  | KY | N/A | Active | AEP | 100 | 100 | 65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2021 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH1-645 | Surry - Yadkin 500 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2021 | N/A | N/A |  | 3/25/2024 |  | 10/1/2025 |  |  | N | No
AH1-646 | Lake Lynn – Gerards Fort 25 kV |  | PA | Fayette | Withdrawn | APS | 19.9 | 19.9 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2021 | N/A | N/A |  | 8/12/2024 |  | 12/31/2023 |  |  | N | No
AH1-647 | Greensboro 25 kV |  | PA | Greene | Withdrawn | APS | 19.9 | 19.9 | 12.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2021 | N/A | N/A |  | 8/12/2024 |  | 12/31/2023 |  |  | N | No
AH1-648 | Grays Ferry 230kV |  | PA | Philadelphia | Withdrawn | PECO | 168 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2021 | N/A | N/A |  | 8/27/2024 |  | 6/1/2022 |  |  | N | No
AH1-649 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 9/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-650 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 11/21/2024 |  | 12/31/2024 |  |  | N | No
AH1-651 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2021 | N/A | N/A |  | 9/6/2024 |  | 12/31/2024 |  |  | N | No
AH1-652 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 9/6/2024 |  | 12/31/2024 |  |  | N | No
AH1-653 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 11/23/2024 |  | 12/31/2025 |  |  | N | No
AH1-654 | Kincaid 345 kV |  | IL | Christian | Withdrawn | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-655 | SE Canton 138 kV |  | OH | Stark | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2021 | N/A | N/A |  | 11/23/2024 |  | 12/31/2025 |  |  | N | No
AH1-656 | Gary 115kV |  | VA | Lunenburg | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 6/28/2023 |  | 12/31/2024 |  |  | N | No
AH1-657 | Nelson 345 kV |  | IL | DeKalb | Withdrawn | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-658 | R. P. Mone 345 kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 11/23/2024 |  | 12/31/2025 |  |  | N | No
AH1-659 | Cordova 345 kV |  | IL | Lee | Withdrawn | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  | 12/18/2024 |  | 12/31/2024 |  |  | N | No
AH1-660 | Taylor 69kV |  | DE | Sussex | Withdrawn | DPL | 6.66 | 6.66 | 4.19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2021 | N/A | N/A |  | 2/16/2023 |  | 11/30/2023 |  |  | N | No
AH1-661 - moved to TC2 | Cannelville 12.47 kV |  | OH | Muskingum | Active | AEP | 10.07 | 10.07 | 9.06 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-662 | Wells 69kV |  | DE | Kent | Withdrawn | DPL | 7.66 | 7.66 | 5.3844 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2021 | N/A | N/A |  | 2/15/2022 |  | 9/30/2023 |  |  | N | No
AH1-663 | River EC 138 kV |  | IL | Cook | Withdrawn | ComEd | 57.78 | 57.78 | 57.78 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2021 | N/A | N/A |  | 12/18/2024 |  | 5/31/2024 |  |  | N | No
AH1-664 - formerly AE1-144 - moved to TC2 | Goddard-Plumville 138 kV |  | KY | Fleming | Active | EKPC | 100 | 100 | 66.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | [5 empty] | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AH1-665 - formerly AE2-038 - moved to TC2 | Goddard-Plumsville 138 kV II |  | KY | Fleming | Active | EKPC | 180 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | [5 empty] | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AH1-666 - formerly AF1-256 - moved to TC2 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | [5 empty] | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-667 - formerly AF2-121 - moved to TC2 | Philipsburg-Shawville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 18 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | [5 empty] | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AH1-668 - formerly AG1-257 - moved to TC2 | Madisonburg Jct-Millheim 46 kV |  | PA | Centre | Withdrawn | APS | 19.9 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | [5 empty] | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  | 3/7/2025 |  | 8/1/2022 |  |  | N | No
AH1-669 - formerly AG1-326 - moved to TC2 | Circleville-Biers Run 138 kV |  | OH | Ross | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-670 - formerly AG1-401 - moved to TC2 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Active | ComEd | 250 | 250 | 49.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AH1-672 - formerly AG1-529 - moved to TC2 | Farmview 138 kV |  | DE | Sussex | Active | DPL | 75 | 75 | 48.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | [5 empty] | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-673 - formerly AG1-535 - moved to TC2 | State Line - River Energy Center 138 kV |  | IL | Cook | Active | ComEd | 85 | 85 | 85 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | [5 empty] | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-676 - moved to TC2 | Gordonsville 230 kV |  | VA | Orange | Active | Dominion | 1294.6 | 1294.6 | 1275.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2031 |  |  | N | No
AH1-677 - moved to TC2 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 1756 | 0 | 67 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-678 - moved to TC2 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 1525.5 | 0 | 34 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-679 - moved to TC2 | Four Rivers 230 kV |  | VA | Hanover | Active | Dominion | 766 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2028 |  |  | N | No
AH1-680 - moved to TC2 | Sammis - South Canton 345 kV |  | OH | Carroll | Active | AEP | 1300 | 1300 | 1300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/1/2030 |  |  | N | No
AH1-681 - moved to TC2 | Cunningham 500 kV |  | VA | Fluvanna | Active | Dominion | 1000 | 0 | 27.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AH1-682 - moved to TC2 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 21 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 11/30/2027 |  |  | N | No
AH1-683 - moved to TC2 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 10/15/2027 |  |  | N | No
AH1-684 - moved to TC2 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 23 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 4/15/2028 |  |  | N | No
AH1-685 - moved to TC2 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 26 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2028 |  |  | N | No
AH1-686 - moved to TC2 | Hanging Rock 765 kV |  | OH | Lawrence | Active | AEP | 1364 | 24 | 21 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH1-687 - moved to TC2 | Bear Garden 230kV |  | VA | Buckingham | Active | Dominion | 682 | 0 | 51 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/1/2029 |  |  | N | No
AH1-690 - moved to TC2 | Bay Shore - Lallendorf 345 kV |  | OH | Lucas | Active | ATSI | 1475 | 1475 | 1440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 3/1/2031 |  |  | N | No
AH1-691 - moved to TC2 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 26 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2029 |  |  | N | No
AH1-692 - moved to TC2 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 26 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 11/30/2028 |  |  | N | No
AH1-693 - moved to TC2 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 4/15/2029 |  |  | N | No
AH1-694 - moved to TC2 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 10/15/2028 |  |  | N | No
AH1-695 - moved to TC2 | Three Mile Island 230 kV |  | PA | Dauphin | Active | ME | 859 | 859 | 803 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 10/1/2027 |  |  | N | No
AH1-696 - moved to TC2 | Possum Point 230kV |  | VA | Prince William | Active | Dominion | 668 | 0 | 94 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/1/2030 |  |  | N | No
AH1-697 - moved to TC2 | Lackawanna 230kV |  | PA | Lackawanna | Withdrawn | PPL | 1522 | 39 | 78.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  | 7/3/2025 |  | 5/19/2028 |  |  | N | No
AH1-698 - moved to TC2 | Braidwood 345 kV |  | IL | Will | Active | ComEd | 2584 | 130 | 57.6 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/6/2027 |  |  | N | No
AH1-699 - moved to TC2 | Wellsville 345 kV |  | OH | Columbiana | Active | ATSI | 1210 | 58 | 69 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 3/3/2025 |  |  | N | No
AH1-701 - moved to TC2 | Valero 69 kV |  | NJ | Gloucester | Active | AEC | 61 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AH1-702 - moved to TC2 | Byron 345 kV |  | IL | Ogle | Active | ComEd | 2530 | 88 | 43 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 4/2/2026 |  |  | N | No
AH1-703 - moved to TC2 | Bergen 230kV |  | NJ | Bergen | Active | PSEG | 670.61 | 35.61 | 51.254 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/21/2027 |  |  | N | No
AH1-704 - moved to TC2 | Hannibal 138 kV |  | OH | Monroe | Active | AEP | 509 | 24 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-705 - moved to TC2 | Sunbury #1 500kV |  | PA | Snyder | Active | PPL | 1153.4 | 32.4 | 32.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2027 |  |  | N | No
AH1-706 - moved to TC2 | Lordstown 345 kV |  | OH | Trumbull | Active | ATSI | 970.453 | 30.453 | 23.823 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 11/22/2027 |  |  | N | No
AH1-707 - moved to TC2 | Saegers 230 kV |  | PA | Lycoming | Active | PPL | 907 | 0 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH1-710 - moved to TC2 | Salem 500kV |  | NJ | Salem | Active | PSEG | 2650.8 | 256.8 | 228.2 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AH1-711 - moved to TC2 | Lemoyne 345 kV |  | OH | Wood | Active | ATSI | 1108.2 | 408.2 | 292.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2030 |  |  | N | No
AH1-712 - moved to TC2 | Cunningham 500 kV |  | VA | Fluvanna | Active | Dominion | 776 | 776 | 611 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/30/2031 |  |  | N | No
AH1-713 - moved to TC2 | Mt. Storm 500kV |  | WV | Grant | Active | Dominion | 538 | 0 | 14 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/1/2030 |  |  | N | No
AH1-714 - moved to TC2 | Lasalle 345 kV |  | IL | Lasalle | Active | ComEd | 1360 | 169 | 174.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 3/24/2029 |  |  | N | No
AH1-715 - moved to TC2 | Linden 230kV |  | NJ | Union | Active | PSEG | 803.17 | 127.17 | 149.369 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2029 |  |  | N | No
AH1-716 - moved to TC2 | Surry-Skiffes Creek 500kV |  | VA | James City | Active | Dominion | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/11/2029 |  |  | N | No
AH1-717 - moved to TC2 | Gravel Neck 230 kV |  | VA | Surry | Active | Dominion | 453 | 85 | 92.7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/31/2031 |  |  | N | No
AH1-718 - moved to TC2 | Nelson 345 kV |  | IL | Lee | Active | ComEd | 391 | 11 | 38 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/29/2028 |  |  | N | No
AH1-719 - moved to TC2 | Beverly 345 kV |  | OH | Washington | Active | AEP | 694 | 24 | 21 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH1-720 - moved to TC2 | East Towanda 230 kV |  | PA | Bradford | Active | PENELEC | 907.5 | 0 | 60 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH1-721 - moved to TC2 | Laurel-Cooper 161 kV |  | KY | N/A | Active | EKPC | 786 | 786 | 758.9507 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 12/31/2030 |  |  | N | No
AH1-722 - moved to TC2 | Linden 230kV |  | NJ | Union | Active | PSEG | 806.4 | 130.4 | 158.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2030 |  |  | N | No
AH1-723 - moved to TC2 | Cunningham 500 kV |  | VA | Fluvanna | Active | Dominion | 776 | 776 | 712 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/30/2031 |  |  | N | No
AH1-725 - moved to TC2 | Conastone 500 kV |  | MD | Harford | Active | BGE | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/11/2029 |  |  | N | No
AH1-726 - moved to TC2 | Surry-Skiffes Creek 500kV |  | VA | James City | Withdrawn | Dominion | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  | 7/3/2025 |  | 6/11/2029 |  |  | N | No
AH1-727 - moved to TC2 | Brambleton-Goose Creek 500kV |  | VA | Loudoun | Active | Dominion | 425 | 425 | 425 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 6/11/2029 |  |  | N | No
AH1-729 - moved to TC2 | Ocean Court 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AH1-734 - moved to TC2 | South Bend 500 kV |  | PA | Indiana | Active | APS | 1058.4 | 270.3 | 268.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/31/2030 |  |  | N | No
AH1-735 - moved to TC2 | Richland 138 kV |  | OH | Defiance | Active | ATSI | 447 | 19 | 55 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AH1-744 - moved to TC2 | Cheltenham 500 kV |  | MD | Prince George's | Active | PEPCO | 853.5 | 53.5 | 48.285 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 11/22/2027 |  |  | N | No
AH1-746 - moved to TC2 | Madera - Westover South 115 kV |  | PA | Clearfield | Active | PENELEC | 109.9 | 0 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  |  | N/A | N/A |  |  |  | 4/29/2026 |  |  | N | No
AH2-001 | Rattlesnake Hill Waste Heat Recovery |  | PA | Susquehanna | Active | PENELEC | 3.6 | 3.6 | 2.9 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-002 | Temple Hill - Roseville 69 kV |  | KY | Barren | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-003 | Hickory Grove 115 kV |  | VA | Halifax | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2021 | N/A | N/A |  | 3/26/2024 |  | 5/1/2024 |  |  | N | No
AH2-004 | Perth – Crystal Hill 115 kV |  | VA | Halifax | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2021 | N/A | N/A |  | 12/1/2023 |  | 5/1/2024 |  |  | N | No
AH2-005 | Pamplin – Willis Tap 115 kV |  | VA | Prince Edward | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2021 | N/A | N/A |  | 2/9/2024 |  | 5/1/2024 |  |  | N | No
AH2-006 | Harrison - Good Hope 138 kV |  | OH | Pickaway | Active | AEP | 14.234 | 14.234 | 14.234 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-007 | Texas Eastern - Jeffersonville 69 kV |  | OH | Fayette | Active | Dayton | 10.12 | 10.12 | 10.12 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-008 | Bear Peak East Providence II |  | PA | Bedford | Withdrawn | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/6/2021 | N/A | N/A |  | 9/18/2023 |  | 9/15/2023 |  |  | N | No
AH2-009 | Galion 138 kV V |  | OH | Morrow | Active | ATSI | 244 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-010 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 1455 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/7/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-011 | National-Tangy 138kV IV |  | OH | Madison | Withdrawn | ATSI | 177 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/9/2021 | N/A | N/A |  | 12/1/2023 |  | 12/31/2024 |  |  | N | No
AH2-012 | Sinai 12.47 kV |  | VA | Halifax | Withdrawn | Dominion | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/2021 | N/A | N/A |  | 11/12/2021 |  | 12/31/2022 |  |  | N | No
AH2-013 | Cartersville 34.5 kV |  | VA | Cumberland | Active | Dominion | 15.996 | 15.996 | 15.996 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH2-014 | Crane Solar 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH2-015 | Nelson 138 kV |  | IL | Lee | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2021 | N/A | N/A |  |  |  | 3/24/2025 |  |  | N | No
AH2-016 | Stonycreek 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2021 | N/A | N/A |  | 9/18/2023 |  | 5/10/2023 |  |  | N | No
AH2-017 | Brothersvalley 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/22/2021 | N/A | N/A |  | 9/18/2023 |  | 5/15/2023 |  |  | N | No
AH2-018 | Lawrence 12.47 kV |  | PA | Clearfield | Withdrawn | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/22/2021 | N/A | N/A |  | 9/18/2023 |  | 5/15/2023 |  |  | N | No
AH2-019 |  |  | MD | Allegany | Withdrawn | DPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2021 | N/A | N/A |  | 12/7/2021 |  | 2/15/2022 |  |  | Y | No
AH2-020 |  |  | PA | Columbia | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2021 | N/A | N/A |  | 11/29/2021 |  | 12/29/2023 |  |  | Y | No
AH2-021 | Summer Shade - Barren County 161 kV |  | KY | Barren | Active | EKPC | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2021 | N/A | N/A |  |  |  | 11/13/2026 |  |  | N | No
AH2-022 | Bear Peak West Providence LLC |  | PA | Bedford | Withdrawn | PENELEC | 8.25 | 8.25 | 4.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2021 | N/A | N/A |  | 9/18/2023 |  | 5/15/2023 |  |  | N | No
AH2-023 | McDowell 12.47 kV |  | PA | Mercer | Active | ATSI | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-024 | Kodiak Solar 13.2 kV |  | PA | Jefferson | Active | PENELEC | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AH2-025 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2021 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-026 |  |  | VA | City of Richmond | Withdrawn | Dominion | 72 | 72 | 72 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2021 | N/A | N/A |  | 12/1/2021 |  | 9/15/2024 |  |  | N | No
AH2-028 | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 44 | 44 | 44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2021 | N/A | N/A |  |  |  | 10/28/2025 |  |  | N | No
AH2-028A | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2021 | N/A | N/A |  |  |  | 10/28/2025 |  |  | N | No
AH2-029 | Cedarville 12 kV |  | OH | Greene | Withdrawn | Dayton | 18 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2021 | N/A | N/A |  | 10/3/2023 |  | 10/30/2025 |  |  | N | No
AH2-030 | Feagan's Mill 138 kV |  | WV | Jefferson | Active | APS | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-031 | Feagan's Mill 138 kV II |  | WV | Jefferson | Active | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-032 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-033 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-034 | Possum Point 230kV |  | VA | Prince William | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-035 | Possum Point 500kV |  | VA | Prince William | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-036 | Young 12.47 |  | PA | Bradford | Active | PENELEC | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH2-037 | Booth 12.47 |  | PA | Fulton | Active | APS | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH2-038 | Weirton - Arroyo 25 kV |  | WV | Hancock | Active | APS | 10.75 | 10.75 | 5.4395 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-039 | Chesapeake - Paw Paw 23 kV |  | WV | Marion | Active | APS | 5.5 | 5.5 | 2.728 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-040 | William - Blackwater 69 kV |  | WV | Tucker | Active | APS | 11.5 | 11.5 | 5.7615 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-041 | Osage - Collins Ferry 23 kV |  | WV | Monongalia | Active | APS | 18.89 | 18.89 | 9.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-042 | Marlowe - North Martinsburg 34.5 kV |  | WV | Berkeley | Active | APS | 5.75 | 5.75 | 3.6858 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-043 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/19/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-044 | Clearfield 12.5 kV |  | PA | Clearfield | Active | APS | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH2-045 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AH2-046 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AH2-047 5157311 | PJM-TVA |  | N/A | N/A | Active |  | 495 | 495 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress |  |  |  |  | https://www.pjm.com/pjmfiles/N/A | N/A | N/A | [5 empty] | 12/15/2021 | 3/1/2022 | 3/1/2027 | [6 empty] | PP | No
AH2-048 | Bayview 69kV |  | VA | Northampton | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-049 | Crisfield 69kV |  | MD | Somerset | Active | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-050 | Tasley 69kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-051 | Edge Moore 230kV |  | DE | New Castle | Active | DPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-052 | New Hope 12.47 kV |  | MD | Allegany | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2021 | N/A | N/A |  |  |  | 12/2/2022 |  |  | Y | No
AH2-053 | Mardela Springs 12.47 kV |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2021 | N/A | N/A |  |  |  | 12/2/2022 |  |  | Y | No
AH2-054 | Edgewood 12.47 kV I |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2021 | N/A | N/A |  |  |  | 12/2/2022 |  |  | Y | No
AH2-055 | TBD 69kV |  | MD | Unknown | Active | DPL | 0.99 | 0.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2021 | N/A | N/A |  |  |  | 2/15/2022 |  |  | Y | No
AH2-056 | Chesterfield 230 kV II |  | VA | Chesterfield | Active | Dominion | 60 | 0 | 36 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH2-057 | Scottsville - CVEC Delivery Point 46 kV |  | VA | Buckingham | Active | AEP | 74.9 | 29.9 | 17.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH2-058 | Possum Point 115 kV |  | VA | Prince William | Active | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-059 | Possum Point 115 kV II |  | VA | Prince William | Active | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AH2-060 | Possum Point 230 kV |  | VA | Prince William | Active | Dominion | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AH2-061 | Possum Point 230 kV II |  | VA | Prince William | Active | Dominion | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2021 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-062 | TBD 34kV |  | PA | Chester | Active | PECO | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH2-063 | North Ramsey 23 kV |  | PA | Beaver | Active | DL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-064 | South Ramsey 23 kV |  | PA | Beaver | Active | DL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-065 | TBD 69kV |  | MD | Prince George's | Active | DPL | 1.992 | 1.992 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2021 | N/A | N/A |  |  |  | 12/1/2022 |  |  | Y | No
AH2-066 | Jefferson 12.5 kV |  | PA | Jefferson | Active | PENELEC | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/4/2022 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AH2-067 | Mount Rose 13 kV |  | IL | Cook | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/12/2022 | N/A | N/A |  | 3/8/2022 |  | 12/29/2023 |  |  | Y | No
AH2-068 | Pemberville - West End Fostoria 69 kV |  | OH | Wood | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/13/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-069 | JAckson Ferry - Progress Park 138 kV |  | VA | Wythe | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/13/2022 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AH2-070 | Edgewood 12.47 kV II |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2022 | N/A | N/A |  |  |  | 1/27/2023 |  |  | Y | No
AH2-071 | Edgewood 12.47 kV III |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2022 | N/A | N/A |  |  |  | 1/27/2023 |  |  | Y | No
AH2-072 | Damascus 69 kV |  | VA | Washington | Active | AEP | 62.1 | 62.1 | 62.1 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2022 | N/A | N/A |  |  |  | 1/1/2025 |  |  | N | No
AH2-073 | Ashtabula County PV Project 2 |  | OH | Ashtabula | Withdrawn | ATSI | 10 | 10 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2022 | N/A | N/A |  | 8/4/2025 |  | 9/14/2024 |  |  | N | No
AH2-074 | Ashtabula County PV Project 1 |  | OH | Ashtabula | Withdrawn | ATSI | 10 | 10 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2022 | N/A | N/A |  | 8/4/2025 |  | 9/14/2024 |  |  | N | No
AH2-075 | Hampton VA 2 |  | VA | City of Hampton | Active | Dominion | 29.12 | 29.12 | 29.12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2022 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH2-076 | Bonneyman - Softshell 138 kV |  | KY | Perry | Active | AEP | 52.5 | 52.5 | 48.17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2022 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-077 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-078 | Dryburg - Chase City 230 kV |  | VA | Charlotte | Active | Dominion | 99.67 | 99.67 | 59.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 1/3/2025 |  |  | N | No
AH2-079 |  |  | VA | Charlotte | Withdrawn | Dominion | 69 | 69 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  | 2/28/2022 |  | 1/3/2025 |  |  | N | No
AH2-080 | Brunswick - Gasburg 69 kV |  | VA | Brunswick | Active | Dominion | 52.65 | 52.65 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  |  |  | 1/3/2025 |  |  | N | No
AH2-081 | Bentley Farms 69 kV |  | OH | Fayette | Active | Dayton | 35.5 | 35.5 | 21.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 9/19/2025 |  |  | N | No
AH2-082 | New Holland - Washington Courthouse 69 kV |  | OH | Fayette | Active | Dayton | 33.25 | 33.25 | 19.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 1/3/2025 |  |  | N | No
AH2-083 | Correctional |  | VA | Caroline | Active | Dominion | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-084 | Sowego |  | VA | Fauquier | Active | Dominion | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-085 | Byron-Wayne 345 kV |  | IL | DeKalb | Active | ComEd | 145.335 | 145.335 | 87.201 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  |  |  | 11/11/2026 |  |  | N | No
AH2-086 | Byron – Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-087 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-088 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-089 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-090 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-091 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-092 | Kidds Store-Sherwood 115 kV |  | VA | Albemarle | Withdrawn | Dominion | 138 | 0 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  | 3/9/2022 |  | 12/31/2026 |  |  | N | No
AH2-093 | Jasper 69 kV |  | OH | Greene | Active | Dayton | 32 | 32 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-094 | Lakeville 12 kV II |  | PA | Wayne | Active | PPL | 4.95 | 4.95 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 5/5/2023 |  |  | N | No
AH2-095 | Crawford 13.8 kV |  | PA | Crawford | Active | PENELEC | 3.3 | 3.3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 7/13/2022 |  |  | N | No
AH2-096 | West Cambridge - Airey 69 kV |  | MD | Dorchester | Active | DPL | 19.5 | 19.5 | 8.19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH2-100 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-101 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-102 | Blaine - Roanoke 138 kV |  | VA | Franklin | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 5/4/2026 |  |  | N | No
AH2-103 | Gans - South Union 138 kV |  | PA | Fayette | Active | APS | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 5/4/2026 |  |  | N | No
AH2-104 | Willis Mts- Farmville 115kV |  | VA | Cumberland | Active | Dominion | 72 | 72 | 39.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2022 | N/A | N/A |  |  |  | 11/1/2024 |  |  | N | No
AH2-105 | Merck 34.5 kV |  | VA | Rockingham | Active | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2022 | N/A | N/A |  |  |  | 1/1/2024 |  |  | N | No
AH2-106 | Wellsville 345 kV |  | OH | Columbiana | Active | ATSI | 1210 | 58 | 69 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2022 | N/A | N/A |  |  |  | 2/28/2022 |  |  | N | No
AH2-107 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 69 | 69 | 69 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-108 | Potter-Harlan 69 kV |  | PA | Lawrence | Withdrawn | ATSI | 95 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2022 | N/A | N/A |  | 3/18/2022 |  | 6/1/2026 |  |  | N | No
AH2-109 | TBD 12.47kV |  | NJ | Unknown | Active | AEC | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2022 | N/A | N/A |  |  |  | 12/1/2022 |  |  | Y | No
AH2-110 | Wells - Harrington 69 kV |  | PA | Fulton | Withdrawn | DPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2022 | N/A | N/A |  | 3/14/2022 |  | 12/31/2023 |  |  | Y | No
AH2-111 | Hannibal 138 kV |  | OH | Monroe | Active | AEP | 505 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2022 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AH2-112 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 250 | 250 | 170 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2022 | N/A | N/A |  |  |  | 2/27/2026 |  |  | N | No
AH2-113 | Dresden – Pontiac Midpoint 345kV |  | IL | Livingston | Active | ComEd | 250 | 250 | 170 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2022 | N/A | N/A |  |  |  | 2/27/2026 |  |  | N | No
AH2-115 | Mansfield - Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-116 | Garman - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-117 | Dorton - Henry Clay 46 kV |  | KY | Pike | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-118 | Ripley Switch – Grayton 69kV |  | MD | Charles | Withdrawn | PEPCO | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  | 1/9/2024 |  | 12/1/2024 |  |  | N | No
AH2-119 | Morgan Street - Titusville 34.5 kV |  | PA | Crawford | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2022 | N/A | N/A |  |  |  | 12/30/2025 |  |  | N | No
AH2-120 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-121 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 500 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-122 | Nelson-Lee County 345 kV |  | IL | Lee | Active | ComEd | 220 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-123 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 420 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-124 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-125 | Kensington 138 kV |  | KY | N/A | Active | ComEd | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-126 | Tidd 138 kV |  | OH | Jefferson | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2022 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AH2-127 | Burlington 26 kV |  | NJ | Burlington | Active | PSEG | 20 | 15 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2022 | N/A | N/A |  |  |  | 9/19/2023 |  |  | N | No
AH2-128 | Stone Solar 34.5 kV |  | PA | Clarion | Active | APS | 8 | 8 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AH2-129 | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 52 | 36 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AH2-130 | Clark Co - Spencer Road 138 kV |  | KY | N/A | Active | EKPC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-131 | Bridgeport 230kV |  | NJ | Gloucester | Active | AEC | 225 | 0 | 103.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH2-132 | Chambers 230kV |  | NJ | Salem | Active | AEC | 240 | 0 | 117 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-133 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AH2-134 | TBD 34.5 kV |  | WV | Kanawha | Withdrawn | DPL | 4.95 | 4.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  | 3/21/2022 |  | 12/31/2023 |  |  | Y | No
AH2-135 | Harwood- McAdoo 69 kV |  | PA | Luzerne | Active | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/19/2025 |  |  | N | No
AH2-136 | Dunnsville 345 kV |  | VA | Essex | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 3/26/2025 |  | 12/1/2024 |  |  | N | No
AH2-137 | Monroe - Coolwell 12.47 kV |  | VA | Amherst | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-138 | Arrington Circuit 12.47 kV |  | VA | Nelson | Withdrawn | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 4/6/2025 |  | 12/1/2026 |  |  | N | No
AH2-139 |  |  | VA | Prince George | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 4/14/2022 |  | 12/31/2024 |  |  | N | No
AH2-140 |  |  | VA | Greensville | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 4/14/2022 |  | 12/31/2024 |  |  | N | No
AH2-141 |  |  | VA | Prince George | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 4/14/2022 |  | 12/31/2024 |  |  | N | No
AH2-142 |  |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 4/14/2022 |  | 12/31/2024 |  |  | N | No
AH2-143 |  |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  | 4/14/2022 |  | 12/31/2024 |  |  | N | No
AH2-144 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-145 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 52.3 | 52.3 | 52.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-146 | Adams - Seaman 69 kV |  | OH | Adams | Active | AEP | 87.2 | 87.2 | 52.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/30/2027 |  |  | N | No
AH2-147 | Marysville - Sorenson 765 kV |  | OH | Logan | Withdrawn | AEP | 119 | 119 | 108.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  | 7/7/2023 |  | 2/25/2027 |  |  | N | No
AH2-148 | East Lima - Marysville 345 kV |  | OH | Union | Active | AEP | 152 | 152 | 143.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 2/25/2027 |  |  | N | No
AH2-149 | Stinger - Valley 138 kV |  | MI | Van Buren | Active | AEP | 150 | 150 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/29/2026 |  |  | N | No
AH2-150 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 0 | 320 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-151 | SedgeHill - Person 230kV |  | VA | Halifax | Active | Dominion | 195 | 35 | 21 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-152 | Effort Mountain-Gilbert 138 kV IV |  | PA | Monroe | Withdrawn | PPL | 90 | 44.8 | 26.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  | 8/26/2024 |  | 6/1/2025 |  |  | N | No
AH2-153 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 180 | 180 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-154 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 118 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-155 | Lyons-Allen Jct 138 kV |  | OH | Fulton | Active | ATSI | 95 | 95 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-156 | Buckeye P-Wakeman 69 kV |  | OH | Huron | Active | ATSI | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-157 | Hooversville-Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-158 | Somerset-Hooversville 115 kV |  | PA | Somerset | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-159 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-160 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 69 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-161 | Prospect 25 kV |  | PA | Butler | Withdrawn | APS | 18.8 | 18.8 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  | 8/13/2024 |  | 12/31/2024 |  |  | N | No
AH2-162 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Withdrawn | BGE | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  | 8/6/2025 |  | 3/1/2026 |  |  | N | No
AH2-163 | Kittanning - Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 49.8 | 19.8 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-164 | Chatfield 69 kV |  | OH | Crawford | Active | AEP | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-165 | Fayette - Lyons 138 kV |  | OH | Fulton | Active | ATSI | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-166 | Lyons 138 kV |  | OH | Fulton | Active | ATSI | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-167 | Campbell Tap-McDowell 69 kV |  | PA | Mercer | Withdrawn | ATSI | 6.6 | 6.6 | 0 |  | Energy | Generation Interconnection | Diesel |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2022 | N/A | N/A |  | 5/6/2022 |  | 7/1/2022 |  |  | N | No
AH2-168 | Beatty - MT Hope 345 kV |  | OH | Madison | Active | ATSI | 185 | 185 | 111 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-169 | Thornville - Pleasantville 69 kV |  | OH | Perry | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-170 | Byron 345 |  | IL | Will | Withdrawn | ComEd | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2026 |  |  | N | No
AH2-171 | Davis Creek 345 kV |  | IL | Kankakee | Withdrawn | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2026 |  |  | N | No
AH2-172 | Wilton 345 kV |  | IL | Will | Withdrawn | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2026 |  |  | N | No
AH2-173 | Maryland 138 kV |  | IL | Ogle | Withdrawn | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 1/15/2025 |  | 12/31/2026 |  |  | N | No
AH2-174 | PA- Fort Hill 12.47 kV |  | OH | Perry | Withdrawn | APS | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/3/2024 |  | 6/21/2024 |  |  | Y | No
AH2-175 | Montgomery 12 kV |  | N/A | N/A | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  | 1/5/2024 |  | 6/21/2024 |  |  | Y | No
AH2-176 | Hughesville 12 kV |  | N/A | N/A | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 1/5/2024 |  | 6/21/2024 |  |  | Y | No
AH2-177 | Hamlin 12 kV |  | N/A | N/A | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 1/5/2024 |  | 6/21/2024 |  |  | Y | No
AH2-178 | Trexlertown 12 kV |  | N/A | N/A | Withdrawn | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 2/20/2024 |  | 6/21/2024 |  |  | Y | No
AH2-179 | Millville 12 kV |  | N/A | N/A | Withdrawn | PPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 1/5/2024 |  | 6/21/2024 |  |  | Y | No
AH2-180 | Rohrsburg 12 kV |  | N/A | N/A | Withdrawn | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 1/5/2024 |  | 6/21/2024 |  |  | Y | No
AH2-181 | PA-Schwoyer 13.2 kV |  | PA | Mercer | Active | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 6/21/2024 |  |  | Y | No
AH2-182 | PA-Oknefski 12.47 kV |  | VA | Rockingham | Withdrawn | APS | 3 | 3 |  |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  | 1/3/2024 |  | 6/21/2024 |  |  | Y | No
AH2-183 | PA-Montmorenci 12.47 kV |  | IL | Ogle | Withdrawn | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  | 1/3/2024 |  | 6/21/2024 |  |  | Y | No