## Table 1
Item | Queue Date | Facility Name | Service | Proposed POI | Facility Location | Sum Net MW | Fuel Type | In-Service | Customer Sync | Customer COD | Study Phase | GIA Phase
GI-214 | 2025-07-09 | SR Norwood III | Interconnection | Sinquefield Road 115 kV Substation | Warren County, GA | 150 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Received | Application under Review
GI-212 | 2025-04-15 | 6505 US Hwy 221 | Interconnection | Wadley 115 kV Substation | Jefferson County, GA | 110 | Solar PV | 3/30/20285 | 2028-04-30 | 2028-06-30 | SIS Unerway | System Impact Study
GI-211 | 2025-03-29 | Dougherty County BESS | Interconnection | Pecan City 115 kV Sub/ Pecan City 115 kV tap T/L | Dougherty County, GA | 120 | BESS | Not included | Not included | Not included | Received | Application under Review
GI-210 | 2025-03-29 | Flint River 2 780 MW Unit | Interconnection | Raccoon Creek Substation | Mitchell County, GA | 780 | Gas | 2028-06-01 | 2028-12-01 | 2029-06-01 | Received | Application under Review
GI-209 | 2025-03-18 | Sawmill Junction | Interconnection | New Gresston sub - Eastman Primary 115 kV line | Dodge County, GA | 120 | Solar PV | 2029-08-01 | 2029-08-02 | 2029-11-15 | SISA Issued | Application under Review
GI-208 | 2025-01-09 | SR Dry Branch | Interconnection | Bonaire Primary - South Macon 230 kV Line | Twiggs County, GA | 172 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Final SIS Issued | System Impact Study
GI-207 | 2025-01-08 | SR Millen | Interconnection | Millen Primary - Waynesboro 115 kV line | Jenkins County, GA | 65 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Final SIS Issued | System Impact Study
GI-206 | 2024-12-19 | SR Norwood II | Interconnection | Sinquefield Road 115 kV Substation | Warren County, GA | 143 | Solar PV | 2028-06-01 | 2028-07-01 | 2028-12-31 | Final SIS Issued | System Impact Study
GI-205 | 2024-12-19 | SR Wrens | Interconnection | Branch - Springhill Church 230 kV Line | Jefferson County, GA | 194 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Final SIS Issued | System Impact Study
GI-204 | 2024-12-18 | SR Bartown frmly Jefferson | Interconnection | Sandersville #1 - Wadley 115 kV via Pervis Road - Louisville Junction 115 kV tap | Jefferson County, GA | 200 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Final SIS Issued | System Impact Study
GI-203 | 2024-12-18 | SR Doerun | Interconnection | Mitchell - Moultrie 115 kV Line | Colquitt County, GA | 130 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Final SIS Issued | System Impact Study
GI-202 | 2024-12-17 | SR Warthen | Interconnection | Branch - Wrens 230 kV Line | Washington County, GA | 135 | Solar PV | 2029-05-01 | 2029-09-01 | 2029-12-31 | Draft SIS Issued | System Impact Study
GI-200 | 2024-12-17 | Scarboro Solar | Interconnection | Grove Church 115 kV Substation | Miller County, GA | 75 | Solar PV + ESS | 2030-10-28 | 2030-11-28 | 2031-02-28 | SIS Unerway | System Impact Study
GI-199 | 2024-12-11 | Rebecca Solar | Interconnection | North Tifton - Pitts 230 kV line | Turner County, GA | 120 | Solar PV | 2028-09-01 | 2028-10-01 | 2028-12-01 | Final SIS Issued | System Impact Study
GI-198 | 2024-10-09 | Flint River 780 MW Unit | Interconnection | Raccoon Creek Substation | Mitchell County, GA | 780 | natural gas | 2028-08-01 | 2029-02-01 | 2029-08-01 | Final SIS Issued | System Impact Study
GI-197 | 2024-10-01 | Washington County Solar | Interconnection | Tiger Creek 230 kV Substation | Washington County, GA | 203 | Solar PV + ESS | 2026-07-30 | 2026-12-15 | 2027-04-01 | Final SIS Issued | System Impact Study
GI-196 | 2024-08-31 | SR Grady_SR Whigham | Interconnection | South Bainbridge – Thomasville 230 kV TL | Grady County, GA | 150 | Solar PV | 2028-05-01 | 2028-09-01 | 2028-12-15 | IA Executed | Full NTP
GI-195 | 2024-08-20 | Altamaha Green Energy | Interconnection | Jessup – Ludowici Primary 115 kV TL | Wayne County, GA | 70 | Synchronous | 2027-04-01 | 2027-12-01 | 2028-03-01 | Final FS Issued | Facilities Study
GI-194 | 2024-08-05 | Talbot U7 | Interconnection | Talbot County 1 or 2 substation (TBD) | Talbot County, GA | 250 | natural gas | 2029-03-31 | 2029-03-31 | 2029-03-31 | Project Scoping | Facilities Study
GI-193 | 2024-08-05 | Smarr CC | Interconnection | Big Smarr 500 kV substation (TBD) | Monroe County, GA | 2000 | natural gas | 2028-03-31 | 2028-03-31 | 2028-03-31 | Project Scoping | Facilities Study
GI-190 | 2024-01-09 | Spain Energy Center | Interconnection | Spain 230 kV Substation | Brooks County, GA | 141 | Solar PV + ESS | 2028-09-01 | 2028-11-01 | 2028-12-13 | Draft FS Issued | Facilities Study
GI-189 | 2024-01-08 | TOCE GA Solar 4 | Interconnection | Wadley – Waynesboro TL line tap | Jefferson County, GA | 325 | Solar PV + ESS | 2027-02-28 | 2027-03-28 | 2027-06-01 | Draft FS Issued | Facilities Study
GI-187 | 2023-10-20 | Pecan Energy Storage | Interconnection | Raccoon Creek 230 kV SS | Mitchell County, GA | 207.6 | Solar PV + ESS | 2029-01-15 | 2029-01-30 | 2029-04-30 | Draft FS Issued | Facilities Study
GI-186 | 2023-09-28 | SR Bacon III Solar | Interconnection | Offerman - Douglas 230 kV TL | Bacon County, GA | 100 | Solar PV | 2028-05-01 | 2028-08-01 | 2028-11-30 | Data Review | Application Review in Progress
GI-185 | 2023-09-28 | SR Bacon II Solar | Interconnection | Offerman - Douglas 230 kV TL | Bacon County, GA | 115 | Solar PV | 2027-05-01 | 2027-08-01 | 2027-11-30 | Data Review | Application Review in Progress
GI-184 | 2023-09-20 | Beaver Creek Solar | Interconnection | Gordon - Milledgeville (White) 115 kV TL | Baldwin County, GA | 183 | Solar PV + ESS | 2026-10-01 | 2026-10-15 | 2027-04-01 | Project Scoping | Facilities Study
GI-183 | 2023-09-20 | SR Rochelle II Solar | Interconnection | Fitzgerald - Pitts 115 kV TL | Wilcox County, GA | 90 | Solar PV | 2026-04-01 | 2026-06-01 | 2026-11-01 | IA Executed | Full NTP
GI-182 | 2023-09-20 | Pelham Solar | Interconnection | Folkston - St. George 115 kV TL | Charlton County, GA | 120 | Solar PV | 2025-07-01 | 2025-07-15 | 2025-11-30 | Draft SIS Issued | System Impact Study
GI-181 | 2023-09-19 | Hammond Solar | Interconnection | Hammond - Anniston 230 kV TL | Floyd County, Ga | 225 | Solar PV | 2025-07-01 | 2025-07-15 | 2025-11-30 | Draft SIS Issued | System Impact Study
GI-180 | 2023-08-04 | Pepper Hammock 200 MW | Interconnection | Thalmann - Offerman 230 kV TL | Glynn County, GA | 200 | Solar PV | 2026-06-30 | 2026-07-30 | 2026-08-30 | Draft FS Issued | Facilities Study
GI-177 | 2023-08-03 | TOCE GA 1 Solar | Interconnection | Greens Cut - Greens Cut Junction 115 kV Tap | Burke County, GA | 125 | Solar PV | 2026-04-01 | 2026-05-01 | 2026-09-01 | Final SIS Issued | System Impact Study
GI-176 | 2023-07-14 | SR Mendes | Interconnection | Claxton-Ludowici Primary 115 kV | Tattnall County, GA | 60 | Solar PV | 2026-04-01 | 2026-09-01 | 2026-12-31 | IA Executed | Full NTP
GI-175 | 2023-05-20 | Live Oak Solar | Interconnection | 230 kV Bus at North Dublin 230 kV SS | Laurens County, GA | 200 | Solar PV + ESS | 2026-04-10 | 2026-05-29 | 2026-10-05 | Final FS Issued | Facilities Study
GI-173 | 2023-05-02 | SR Norwood Solar | Interconnection | Ray Place Road-Warrenton Primary 115 kV TL | Warren County, GA | 107 | Solar PV | 2026-04-01 | 2026-04-15 | 2026-06-30 | IA Executed | Full NTP
GI-172 | 2023-04-06 | Red Dirt Solar | Interconnection | Patsiliga Creek - Talbot County #1 230 kV | Talbot County, GA | 153 | Solar PV + ESS | 2026-07-27 | 2026-08-31 | 2026-09-30 | Final FS Issued | Facilities Study
GI-170 | 2022-11-30 | Ocilla Solar | Interconnection | Lake Beatrice - Stump Lake 115 kV TL | Irwin County, GA | 150 | Solar PV | 2025-09-01 | 2025-10-15 | 2025-11-30 | Draft FS Issued | Facilities Study
GI-169 | 2022-11-29 | Brenneman Solar | Interconnection | North Americus – Perry 115 kV TL | Macon County, GA | 150 | Solar PV | 2024-07-01 | 2024-08-01 | 2024-11-30 | Final FS Issued | Facilities Study
GI-168 | 2022-07-06 | Pepper Hammock 500 Solar | Interconnection | Hatch - Thalmann 500 kV TL | Glynn County, GA | 500 | Solar PV | 2024-06-30 | 2024-07-30 | 2024-08-30 | Final FS Issued | Facilities Study
GI-166 | 2022-06-21 | Pepper Hammock Solar | Interconnection | Offerman 230 kV -Thalmann 230 kV TL | Glynn County, GA | 200 | Solar PV | 2024-06-30 | 2024-07-30 | 2024-08-30 | Final FS Issued | Facilities Study
GI-164 | 2022-06-07 | Crawford Solar | Interconnection | Dorsett(GTC)-Thomaston 230 kV TL | Crawford County, GA | 160 | Solar PV + ESS | 2025-10-30 | 2025-11-15 | 2025-12-31 | Final SIS Issued | System Impact Study
GI-162 | 2022-03-16 | Two Rivers Solar | Interconnection | Homeland - Kingsland 115 kV line | Camden County, GA | 102 | Solar PV + ESS | 2027-06-15 | 2027-06-29 | 2027-09-21 | Final FS Issued | Facilities Study
GI-161 | 2022-01-28 | Meriwether Panther Solar | Interconnection | GTC 115 kV substation on Rocky Mount Rd | Meriwether County, GA | 125 | Solar PV + ESS | 2026-10-31 | 2026-11-30 | 2026-12-31 | Final SIS Issued | Facilities Study
GI-160 | 2022-01-12 | Rock House Solar | Interconnection | Thomson 230 kV Substation | McDuffie County, GA | 250 | Solar PV + ESS | 2024-11-01 | 2024-11-15 | 2025-03-01 | Final FS Issued | Facilities Study
GI-159 | 2021-12-16 | Cherry Tree Solar | Interconnection | Sandersville-Wadley 230 kV | Washington County, GA | 150 | Solar PV + ESS | 2025-10-01 | 2025-10-15 | 2025-12-01 | Draft FS Issued | Facilities Study
GI-158 | 2021-12-09 | SR Rochelle Solar | Interconnection | Fitzgerald - Pitts 115 kV TL | Wilcox County, GA | 120 | Solar PV | 2026-06-01 | 2026-08-01 | 2026-12-31 | IA Executed | Full NTP
GI-157 | 2021-12-01 | Talbot Solar | Interconnection | Talbot County Energy – Butler Sub | Talbot County, GA | 150 | Solar PV | 2023-08-01 | 2023-10-30 | 2023-12-30 | Draft FS Issued | Facilities Study
GI-155 | 2021-12-01 | Fairboro Solar | Interconnection | Wilsonville – Kettle Creek | Ware County, GA | 200 | Solar PV | 2023-08-01 | 2023-10-30 | 2023-12-30 | Draft FS Issued | Facilities Study
GI-153 | 2021-07-19 | Long Cane Solar | Interconnection | Glassbridge - Glassbridge Tap 115 kV TL | Troup County, GA | 80 | Solar PV + ESS | 2024-09-15 | 2024-09-22 | 2024-11-30 | Final SIS Issued | System Impact Study
GI-152 | 2021-06-23 | Crossroads Solar | Interconnection | Ludowici - Riceboro 115 kV TL | Liberty County, GA | 150 | Solar PV + ESS | 2024-03-01 | 2024-03-20 | 2024-05-30 | Final FS Issued | Facilities Study
GI-149 | 2021-05-04 | Dellwood Solar | Interconnection | Vidalia-Wadley Primary (white) 230 kV line | Emanuel County, GA | 150 | Solar PV+ESS | 2023-09-30 | 2024-01-31 | 2024-02-28 | Final FS issued | Facilities Study
GI-145 | 2020-11-16 | Moxley Solar | Interconnection | Tiger Creek- Wadley Primary 230kV line | Jefferson County, GA | 120 | Solar Pv | 2024-10-01 | 2024-10-30 | 2024-12-31 | Final FS Issued | Facilities Study
GI-143 | 2020-08-26 | SR Bacon | Interconnection | Offerman-Douglas 230 kV TL | Bacon County, GA | 85 | Solar PV | 2026-07-01 | 2026-08-01 | 2026-11-01 | IA Executed | Full NTP
GI-142 | 2020-08-13 | Cherry Blossom Solar | Interconnection | Danville 115 kV Substation | Twiggs County, GA | 150 | Solar PV+ESS | 2023-04-15 | 2023-05-15 | 2023-06-15 | Final SIS Issued | FSA Issued
GI-139 | 2020-04-17 | SR Toombs | Interconnection | Wadley Primary - Vidalia 230 kV | Toombs County, GA | 250 | Solar PV | 2024-03-15 | 2024-04-03 | 2024-11-30 | IA Executed | Full NTP
GI-136 | 2020-02-23 | RV Solar | Interconnection | Claxton-Ludowici Primary 115 kV | Tattnall County, GA | 100 | Solar PV | 2022-09-01 | 2022-10-15 | 2022-11-30 | Final FS issued | Facilities Study
GI-133 | 2019-12-11 | Union City Storage II | Interconnection | Union City substation | Fulton County, GA | 100 | Battery | 2022-09-01 | 2022-09-15 | 2022-11-30 | Final FS issued | Facilities Study
GI-132 | 2019-12-11 | Union City Storage I | Interconnection | Union City substation | Fulton County, GA | 200 | Battery | 2022-09-01 | 2022-09-15 | 2022-11-30 | Final FS issued | Facilities Study
GI-130 | 2019-11-26 | Thundering Springs | Interconnection | No Dublin-Wadley Prim 230 kV TL | Laurens County, GA | 240 | Solar PV+ESS | 2023-06-01 | 2023-09-01 | 2023-12-01 | Final FS issued | Facilities Study
GI-128 | 2019-10-10 | SR Metter | Interconnection | Statesboro - Vidalia 230 kV TL | Candler County, GA | 80 | Solar PV | 2025-10-15 | 2025-11-15 | 2025-11-30 | IA Executed | Full NTP
GI-125 | 2019-10-04 | Bear Bin Solar | Interconnection | Walk Ikey Creek 115 kV SS | Terrell County, GA | 150 | Solar PV | 2023-10-01 | 2023-10-30 | 2023-12-31 | Final FS issued | Facilities Study
GI-124 | 2019-10-04 | All Star Solar | Interconnection | Pine Grove 115 kV Substation | Appling County, GA | 95 | Solar PV | 2023-10-01 | 2023-10-30 | 2023-12-31 | Final FS issued | Facilities Study
GI-122 | 2019-09-02 | Dawson Solar | Interconnection | Dawson - Greenhouse Rd 115 KV | Terrell County, GA | 150 | Solar PV | 2022-09-15 | 2022-09-01 | 2022-12-01 | Final FS issued | Facilities Study
GI-118 | 2019-05-30 | Limestone Solar | Interconnection | North Americus – Perry 115 kV TL | Macon County, GA | 150 | Solar PV+BESS | 2021-09-30 | 2021-10-31 | 2021-12-31 | Final FS Issued | Facilities Study
GI-112 | 2018-07-02 | Shellman Solar | Interconnection | Cuthbert Pr – Dawson Pr 115 kV | Randolph County, GA | 100 | Solar PV | 2022-09-15 | 2022-10-01 | 2022-11-15 | Final FS issued | Withdrawn
GI-100 | 2017-04-19 | Oakhurst Solar Farm | Interconnection | Raccoon Creek 230kV Sub | Mitchell County, GA | 200 | Solar PV+BESS | 2021-05-01 | 2021-06-01 | 2021-12-01 | Final FS issued | Facilities Study
As of 8/19/2025