## Table 1
Santee Cooper Generator Interconnection Queue
Queue Position | Queue Date | Date of Completed Application | Customer Name | Location County/State | SCPSA Substation | SCPSA Line | Sum Capacity (MW) | Win Capacity (MW) | Unit Type | Fuel | BESS Capacity | Projected In- Service Date | Type of Service Requested | Studies Available | Phase I DISIS | Phase II DISIS | Phase III DISIS (Restudy) | Facilities Studay | Project Status
1 | 2001-04-02 | N/A | SCPSA | Berkeley, SC | Jefferies 115 kV | N/A | 128 | 128 | Hydro Turbine | Water |  | 2005-04-25 |  | N/A | N/A | N/A |  | N/A | Operational
2 | 2001-04-01 | N/A | SCPSA | Berkeley, SC | Jefferies 115 kV | N/A | 92 | 92 | Steam Turbine | Oil |  | 2005-05-07 |  | N/A | N/A | N/A |  | N/A | Decommissioned
3 | 2001-04-01 | N/A | SCPSA | Horry, SC | Myrtle Beach 115 kV | N/A | 20 | 22 | CT | Oil/Gas |  | 2005-05-15 |  | N/A | N/A | N/A |  | N/A | Operational
4 | 2001-04-01 | N/A | SCPSA | Horry, SC | Grainger 115 kV | N/A | 170 | 170 | Steam Turbine | Coal |  | 2005-05-19 |  | N/A | N/A | N/A |  | N/A | Decommissioned
5 | 2001-04-01 | N/A | SCPSA | Berkeley, SC | Jefferies 115 kV | N/A | 306 | 306 | Steam Turbine | Coal |  | 2005-05-23 |  | N/A | N/A | N/A |  | N/A | Decommissioned
6 | 2001-04-01 | N/A | SCPSA | Horry, SC | Myrtle Beach 115 kV | N/A | 40 | 50 | CT | Oil |  | 2005-05-25 |  | N/A | N/A | N/A |  | N/A | Operational
7 | 2001-04-01 | N/A | SCPSA | Beaufort, SC | Hilton Head 115 kV | N/A | 20 | 25 | CT | Oil |  | 2005-05-26 |  | N/A | N/A | N/A |  | N/A | Operational
8 | 2001-04-01 | N/A | SCPSA | Beaufort, SC | Hilton Head 115 kV | N/A | 20 | 25 | CT | Oil |  | 2005-05-27 |  | N/A | N/A | N/A |  | N/A | Operational
9 | 2001-04-01 | N/A | SCPSA | Georgetown, SC | Winyah 115 kV | N/A | 295 | 295 | Steam Turbine | Coal |  | 2005-05-28 |  | N/A | N/A | N/A |  | N/A | Operational
10 | 2001-04-01 | N/A | SCPSA | Horry, SC | Myrtle Beach 115 kV | N/A | 30 | 35 | CT | Oil |  | 2005-05-29 |  | N/A | N/A | N/A |  | N/A | Operational
11 | 2001-04-01 | N/A | SCPSA | Georgetown, SC | Winyah 230 kV | N/A | 295 | 295 | Steam Turbine | Coal |  | 2005-05-30 |  | N/A | N/A | N/A |  | N/A | Operational
12 | 2001-04-01 | N/A | SCPSA | Beaufort, SC | Hilton Head 115 kV | N/A | 57 | 70 | CT | Oil |  | 2005-06-01 |  | N/A | N/A | N/A |  | N/A | Operational
13 | 2001-04-01 | N/A | SCPSA | Georgetown, SC | Winyah 230 kV | N/A | 295 | 295 | Steam Turbine | Coal |  | 2005-06-02 |  | N/A | N/A | N/A |  | N/A | Operational
14 | 2001-04-01 | N/A | SCPSA | Georgetown, SC | Winyah 230 kV | N/A | 270 | 270 | Steam Turbine | Coal |  | 2005-06-03 |  | N/A | N/A | N/A |  | N/A | Operational
15 | 2001-04-01 | N/A | SCPSA/SCEG | Fairfield, SC | VC Summer 230 kV | N/A | 318 | 318 | Steam Turbine | Nuclear |  | 2005-06-05 |  | N/A | N/A | N/A |  | N/A | Operational
16 | 2001-04-01 | N/A | SCPSA | Berkeley, SC | Cross 230 kV | N/A | 540 | 540 | Steam Turbine | Coal |  | 2005-06-05 |  | N/A | N/A | N/A |  | N/A | Operational
17 | 2001-04-01 | N/A | SCPSA | Berkeley, SC | Cross 230 kV | N/A | 620 | 620 | Steam Turbine | Coal |  | 2005-06-17 |  | N/A | N/A | N/A |  | N/A | Operational
18 | 2001-04-01 | N/A | SCPSA | Abbeville, SC | Rainey 230 kV | N/A | 882 | 739 | CC | Gas |  | 2002-03-01 |  | N/A | N/A | N/A |  | N/A | Operational
19 | 2001-04-01 | N/A | SCPSA | Abbeville, SC | Rainey 230 kV | N/A | 273 | 222 | CT | Gas |  | 2004-01-01 |  | N/A | N/A | N/A |  | N/A | Operational
20 | 2001-04-06 | 2001-05-14 | Masked | Jasper, SC | N/A | Masked | 620 |  | CC | Gas |  | 2004-05-01 |  | N/A | N/A | N/A |  | N/A | Withdrawn
21 | 2001-04-06 | 2001-05-14 | Masked | Jasper, SC | N/A | Masked | 620 |  | CC | Gas |  | 2004-05-01 |  | N/A | N/A | N/A |  | N/A | Withdrawn
22 | 2003-10-30 | 2003-10-28 | Masked | Calhoun, SC | Masked | Masked | 400 | 450 | CT | Gas |  | TBD | NR | Yes | N/A | Complete |  | Complete | Withdrawn
23 | 2005-01-13 | 2005-01-13 | SCPSA | Berkeley, SC | Cross 230 kV | N/A | 600 | 600 | Steam Turbine | Coal |  | 2006-06-01 | NR | No | N/A | N/A |  | N/A | Operational
24 | 2005-01-13 | 2005-01-13 | SCPSA | Berkeley, SC | Cross 230 kV | N/A | 600 | 600 | Steam Turbine | Coal |  | 2009-06-01 | NR | No | N/A | N/A |  | N/A | Operational
25 | 2007-05-09 | 2007-05-03 | SCPSA | Florence, SC | Pee Dee 230 kV | N/A | 609 | 609 | Steam Turbine | Coal |  | 2012-01-01 | NR | N/A | Withdrawn | Withdrawn |  | Withdrawn | Withdrawn
26 | 2007-11-02 | 2008-01-02 | SCPSA | Florence, SC | Pee Dee 230 kV | N/A | 609 | 609 | Steam Turbine | Coal |  | 2013-01-01 | NR | Yes | N/A | Complete |  | Complete | Withdrawn
27 | 2008-01-24 | 2008-01-15 | Masked | Abbeville, SC | Rainey 230 kV | N/A | 237 | 252 | CT | Gas |  | 2011-01-01 | NR | No | Withdrawn | Withdrawn |  | Withdrawn | Withdrawn
28 | 2009-05-26 | 2009-05-22 | Domtar | Bennettsville, SC | Bennettsville 69 kV | N/A | 51 | 51 | Steam Turbine | Byproduct |  | 2010-11-01 | NR | Yes | Complete | Complete |  | Complete | Operational
29 | 2009-05-29 | 2009-05-28 | Masked | Newberry, SC | Masked | Masked | 55.9 | 55.9 | Steam Turbine | Biomass |  | 2012-05-31 | NR | N/A | Complete | Complete |  | Withdrawn | Withdrawn
30 | 2011-02-17 | 2011-02-15 | Masked | Kershaw, SC | Masked | Masked | 19.9 | 19.9 | Steam Turbine | Biomass |  | 2012-12-31 | NR | Yes | Complete | Complete |  | Complete | Operational
31 | 2011-02-17 | 2011-02-15 | SRE | Dorchester, SC | Harleyville 115 kV | Masked | 19.9 | 19.9 | Steam Turbine | Biomass |  | 2012-12-31 | NR | Yes | Complete | Complete |  | Complete | Operational
32 | 2011-02-17 | 2011-02-15 | SRE | Allendale, SC | Allendale 69 kV | Masked | 19.9 | 19.9 | Steam Turbine | Biomass |  | 2012-12-31 | NR | Yes | Complete | Complete |  | Complete | Operational
33 | 2011-10-21 | 2011-10-21 | IPCO | Georgetown, SC | Georgetown 34 kV | Masked | 65 | 62 | Steam Turbine | Biomass |  | 2012-03-31 | NR | Yes | Complete | Complete |  | Complete | Operational
34 | 2012-01-24 | 2012-01-13 | Masked | Newberry, SC | Masked | N/A | 15 | 15 | Hydro Turbine | Water |  | 2017-01-01 | NR | Yes | Complete | Complete |  | Complete | Withdrawn
35 | 2014-06-30 | 2014-05-29 | Masked | Cainhoy, SC | Masked | N/A | 27.5 | 28.5 | Steam Turbine | Byproduct |  | 2016-07-01 | NR | No | Complete | Complete |  | Complete | Operational
37 | 2015-03-13 | 2015-02-16 | Masked | Bamberg, SC | Masked | Masked | 20 | 20 | Solar | Sun |  | 2016-04-01 | NR | No | Complete | Complete |  | Complete | Withdrawn
38 | 2015-03-23 | 2015-03-20 | Masked | Jasper, SC | Masked | Masked | 74.9 | 74.9 | Solar | Sun |  | TBD | NR | No | Complete | Complete |  | Complete | Withdrawn
39 | 2015-06-23 | 2015-06-16 | Masked | Orangeburg, SC | Shamrock 115 kV Sub | N/A | 42 | 42 | Solar | Sun |  | 2016-12-15 | NR | No | Complete | Complete |  | Complete | Construction
40 | 2015-08-21 | 2015-08-07 | Masked | Allendale, SC | N/A | Allendale - Sycamore 69 kV | 20 | 20 | Solar | Sun |  | 2016-11-15 | NR | No | Complete | Complete |  | Complete | Withdrawn
42 | 2015-10-09 | 2015-09-30 | Masked | Clarendon, SC | Masked | Masked | 75 | 75 | Solar | Sun |  | 2017-10-01 | NR | No | Complete | Complete |  | Complete | Withdrawn
43 | 2017-04-01 | 2017-03-23 | Masked | Orangeburg, SC | N/A | Orangeburg-St George 115 kV | 75 | 75 | Solar | Sun |  | 2019-06-01 | NR | No | Complete | Complete |  | Complete | Withdrawn
44 | 2017-08-25 | 2017-08-09 | Masked | Jasper, SC | N/A | Bluffton-Varnville 115kV | 75 | 75 | Solar | Sun |  | 2019-09-01 | NR/ER | No | Complete | Complete |  | Complete | Complete
45 | 2017-09-13 | 2017-09-01 | Masked | Aiken, SC | Masked | Shamrock-Aiken 115 kV | 75 | 75 | Solar | Sun |  | 2019-09-01 | NR/ER | No | Complete | Complete |  | Complete | Complete
46 | 2017-09-18 | 2017-09-15 | Masked | Georgetown , SC | Campfield 230-115 kV | N/A | 75 | 75 | Solar | Sun |  | 2019-09-01 | NR/ER | No | Complete | Complete |  | Complete | Complete
47 | 2017-09-18 | 2017-09-15 | Masked | Georgetown , SC | Campfield 230-115 kV | N/A | 75 | 75 | Solar | Sun |  | 2019-09-01 | NR/ER | No | Complete | Complete |  | Complete | Complete
48 | 2017-09-18 | 2017-09-15 | Masked | Horry, SC | Bucksville 230-115 kV | N/A | 75 | 75 | Solar | Sun |  | 2019-09-01 | NR/ER | No | Complete | Complete |  | Complete | Complete
49 | 2017-11-02 | 2017-08-28 | Masked | Lexington, SC | N/A | Batesburg-Aiken 115 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
50 | 2017-11-02 | 2017-08-28 | Masked | Georgetown, SC | N/A | Winyah-Campfield 230 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | Complete |  | In Progress | Withdrawn
51 | 2017-11-02 | 2017-08-28 | Masked | Beaufort/Hampton, SC | Yemassee 230 kV | N/A | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | Complete |  | Complete | Withdrawn
52 | 2017-11-03 | 2017-09-05 | Masked | Colleton, SC | N/A | Mateeba-Yemassee 230 kV | 75 | 75 | Solar | Sun |  | 2019-09-01 | NR/ER | No | N/A | Complete |  | Complete | Withdrawn
53 | 2017-11-14 | 2017-09-22 | Masked | Newberry, SC | N/A | Newberry-GwdCty 230 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | Complete |  | In Progress | Withdrawn
54 | 2017-11-14 | 2017-09-22 | Gunsight | Lexington, SC | N/A | Sandy Run-Orangeburg 115 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | Complete |  | Complete | Operational
55 | 2017-11-16 | 2017-09-27 | Masked | Allendale, SC | N/A | Allendale-Fairfax 69 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
56 | 2017-11-16 | 2017-09-27 | Masked | Berkeley, SC | N/A | Cross-Orangeburg 230 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | Complete |  | Complete | Withdrawn
57 | 2017-11-16 | 2017-09-27 | Masked | Williamsburg, SC | N/A | Winyah-Hemingway115 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | N/A | Complete |  | Complete | Withdrawn
58 | 2017-11-16 | 2017-09-27 | Masked | Barnwell, SC | N/A | Shamrock-Barnwell 69 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
59 | 2017-11-16 | 2017-09-27 | Masked | Aiken, SC | N/A | Aiken-Batesburg 115 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
60 | 2017-11-16 | 2017-09-27 | Masked | Clarendon, SC | N/A | Orangeburg-St. George 115 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
61 | 2017-11-16 | 2017-09-27 | Masked | Dillon, SC | N/A | Marion-Bennettsville 230 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
62 | 2017-11-16 | 2017-09-27 | Allora | Lexington, SC | N/A | Batesburg-Columbia 115 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | N/A | Complete |  | Complete | Operational
63 | 2017-11-21 | 2017-09-27 | Centerfield | Chesterfield, SC | N/A | Indian Creek-Grantham 69 kV | 75 | 75 | Solar | Sun |  | 2019-12-31 | NR/ER | No | N/A | Complete |  | Complete | Operational
64 | 2017-12-14 | 2017-08-28 | Masked | Richland, SC | N/A | Columbia-Blythewood 69 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
65 | 2017-12-15 | 2017-08-08 | Masked | Richland, SC | N/A | Pinewood-Sandy Run 115 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
66 | 2017-12-15 | 2017-08-08 | Masked | Fairfield, SC | N/A | VCS-Blythewood 230 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
67 | 2017-12-15 | 2017-08-08 | Masked | Newberry, SC | N/A | VCS-Pomaria 230 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
68 | 2017-12-15 | 2017-08-08 | Masked | Marion, SC | N/A | Hemingway-Marion 230 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | Complete |  | Complete | Withdrawn
69 | 2018-01-04 | 2017-10-10 | Masked | Newberry, SC | Newberry 230-115-69 kV | N/A | 1212 | 1207 | CT | Gas |  | 2021-06-01 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
70 | 2018-01-04 | 2017-10-13 | Masked | Orangeburg, SC | N/A | Cross-Orangeburg 230 kV | 72 | 75 | Solar | Sun |  | 2019-12-01 | NR/ER | No | N/A | Complete |  | Complete | Withdrawn
71 | 2018-01-04 | 2017-10-20 | Masked | Anderson, SC | Rainey 230-115 kV | N/A | 1265 | 1261 | CT | Gas |  | 2021-06-01 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
72 | 2018-01-04 | 2017-11-07 | Masked | Richland, SC | N/A | Pinewood-Sandy Run 115 kV | 75 | 75 | Solar | Sun |  | 2020-09-01 | NR/ER | No | N/A | Complete |  | In Progress | Complete
73 | 2018-01-04 | 2017-11-15 | Masked | Lexington, SC | N/A | Batesburg-Shamrock 115 kV | 72 | 75 | Solar | Sun |  | 2025-12-31 |  | No | N/A | Complete |  | In Progress | Withdrawn
74 | 2018-01-04 | 2017-11-21 | Landrace | Horry, SC | Bucksville 230-115 kV | N/A | 55 | 55 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | Complete |  | In Progress | Operational
75 | 2018-01-04 | 2017-11-30 | Masked | Colleton, SC | N/A | Mateeba-Yemassee 230 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No |  |  |  |  | Withdrawn
76 | 2018-01-04 | 2017-11-30 | Masked | Charleston, SC | N/A | Mateeba-Yemassee 230 kV | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No |  |  |  |  | Withdrawn
77 | 2018-01-04 | 2017-11-30 | Masked | Dorchester, SC | MATEEBA SUB | N/A | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No |  |  |  |  | Withdrawn
Queue Position | Queue Date | Date of Completed Application | Customer Name | Location County/State | SCPSA Substation | SCPSA Line | Sum Capacity (MW) | Win Capacity (MW) | Unit Type | Fuel | BESS Capacity | Projected In- Service Date | Type of Service Requested | Studies Available | Phase I DISIS | Phase II DISIS | Phase III DISIS (Restudy) | Facilities Studay | Project Status
78 | 2018-01-04 | 2017-11-30 | Masked | Colleton, SC | N/A | Bells - St. George 115kV #2 | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | Complete |  | In Progress | Withdrawn
79 | 2018-01-04 | 2017-11-30 | Masked | Horry, SC | Red Bluff 115kV Bus #2 | N/A | 100 | 100 | Solar | Sun |  | 2019-12-01 | NR/ER | No | Complete | Complete |  | In Progress | Withdrawn
80 | 2018-01-04 | 2017-12-27 | Masked | Berkeley, SC | N/A | Jefferies-Pinewood 115 kV | 60 | 65 | Solar | Sun |  | 2019-11-30 | NR/ER | No | N/A | Complete |  | In Progress | Withdrawn
81 | 2018-01-26 | 2018-01-15 | Masked | Marlboro, SC | TBD | Bennettsville - Indian Creek #1 69 kV | 75 | 75 | Solar | Sun |  | 2018-12-01 | NR/ER | No | N/A | Complete |  | Complete | Complete
82 | 2018-01-26 | 2018-01-23 | Masked | Aiken, SC | TBD | TBD | 75 | 75 | Solar | Sun |  | 2018-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
83 | 2018-02-09 | 2018-02-08 | Masked | Williamsburg, SC | Hemingway 230 kV Bus | N/A | 75 | 75 | Solar | Sun |  | 2019-12-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
84 | 2018-02-09 | 2018-02-08 | Masked | Williamsburg, SC | N/A | Cross - Kingstree #1 & #2 230 kV | 75 | 75 | Solar | Sun |  | 2019-12-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
85 | 2018-02-09 | 2018-02-08 | Masked | Georgetown, SC | N/A | Winyah-Campfield 230 kV | 75 | 75 | Solar | Sun |  | 2019-12-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
86 | 2018-02-09 | 2018-02-08 | Masked | Georgetown, SC | N/A | Jefferies - Winyah 230 kV Line | 75 | 75 | Solar | Sun |  | 2019-12-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
87 | 2018-02-09 | 2018-02-08 | Masked | Georgetown, SC | N/A | Jefferies - Winyah 230 kV Line | 75 | 75 | Solar | Sun |  | 2019-12-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
88 | 2018-02-13 | 2018-02-13 | Masked | Georgetown, SC | N/A | Georgetown-Kingstree 115kV | 75 | 75 | Solar | Sun |  | 2019-12-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
89 | 2018-03-21 | 2018-02-22 | Masked | Marlboro, SC | N/A | Bennettsville-Latta 69 kV | 19.9 | 19.9 | Solar | Sun |  |  | NR/ER | No | N/A | Complete |  |  | Withdrawn
90 | 2018-03-21 | 2018-03-15 | Masked | Edgefield, SC | N/A | Aiken 1-Batesburg 115 kV | 75 | 75 | Solar | Sun |  | 2020-06-30 | NR/ER | No | N/A | Complete |  |  | Withdrawn
91 | 2018-04-11 | 2018-03-20 | Masked | Abbeville, SC | N/A | Greenwood Co - RB Russell 230 kV | 75 | 75 | Solar | Sun |  | 2020-11-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
92 | 2018-04-11 | 2018-03-20 | Masked | Dorchester, SC | Mateeba Sw. Station | N/A | 75 | 75 | Solar | Sun |  | 2020-11-30 | NR/ER | No | N/A | Complete |  |  | Withdrawn
93 | 2018-04-11 | 2018-03-21 | Masked | Georgetown, SC | N/A | Saint Stephen Hydro-Kingstree 115 | 75 | 75 | Solar | Sun |  | 2020-06-30 | NR/ER | No | Complete | Complete |  | In Progress | Withdrawn
94 | 2018-04-11 | 2018-03-21 | Masked | Horry, SC | TBD | Batesburg-Hemingway 230 kV | 75 | 75 | Solar | Sun |  | 2018-06-30 | NR/ER | No | In Progress |  |  |  | Withdrawn
95 | 2018-04-26 | 2018-03-26 | Masked | Fairfield, SC | N/A | Winnsboro-Blythewood 69 kV | 50 | 50 | Solar | Sun |  | 2020-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
96 | 2018-04-26 | 2018-03-26 | Masked | Kershaw, SC | N/A | Camden-Dalzell 230 kV | 100 | 100 | Solar | Sun |  | 2020-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
97 | 2018-04-26 | 2018-03-26 | Masked | Orangeburg, SC | N/A | Orangeburg - Shamrock 115 kV | 100 | 100 | Solar | Sun |  | 2020-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
98 | 2018-04-26 | 2018-03-26 | Masked | Kershaw, SC | N/A | Orangeburg - Shamrock 230 kV | 100 | 100 | Solar | Sun |  | 2020-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
99 | 2018-04-26 | 2018-03-26 | Masked | Kershaw, SC | N/A | Camden-South Behune 230 kV | 100 | 100 | Solar | Sun |  | 2020-12-01 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
100 | 2018-04-26 | 2018-04-16 | Masked | Aiken, SC | N/A | Aiken 1 - Batesburg 115 kV Line | 20 | 20 | Solar | Sun |  | 2020-11-30 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
101 | 2018-05-11 | 2018-04-16 | Masked | Edgefield, SC | N/A | Aiken #1 - Batesburg 115 kV on Mayson Tap | 75 | 75 | Solar | Sun |  | 2020-11-30 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
102 | 2018-05-11 | 2018-04-30 | Masked | Darlington, SC | N/A | S. Bethune - Grantham 69 kV | 20 | 20 | Solar | Sun |  | 2019-07-01 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
103 | 2018-05-11 | 2018-04-30 | Masked | Sumter, SC | TBD | TBD | 7.4 | 7.4 | Solar | Sun |  | 2019-03-31 | NR/ER | No | In Progress |  |  |  | Withdrawn
104 | 2018-05-11 | 2018-05-11 | Masked | Abbeville, SC | N/A | Greenwood Co - RB Russell 230 kV | 75 | 75 | Solar | Sun |  | 2020-09-30 | NR/ER | No | Complete | In Progress |  |  | Withdrawn
105 | 2018-05-15 | 2018-05-15 | Masked | Dillon, SC | N/A | Latta - Bennettsville 69 kV Line | 200 | 200 | Solar | Sun |  | 2020-12-31 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
106 | 2018-07-06 | 2018-05-31 | Masked | Horry, SC | TBD | TBD | 22 | 22 | Solar | Sun |  | 2020-06-01 | NR/ER | No |  |  |  |  | Withdrawn
107 | 2018-07-06 | 2018-06-04 | Masked | Orangeburg, SC | TBD | Orangeburg - St. George #2 115 kV Line | 40 | 40 | Solar | Sun |  | 2020-06-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
108 | 2018-07-06 | 2018-07-03 | Masked | Orangeburg, SC | TBD | TBD | 75 | 75 | Solar | Sun |  | 2020-07-01 | NR/ER | No |  |  |  |  | Withdrawn
109 | 2018-07-06 | 2018-07-03 | Masked | Horry, SC | N/A | Marion - Conway 115 kV Line | 64 | 64 | Solar | Sun |  | 2020-06-01 | NR/ER | No | In Progress |  |  |  | In Progress
110 | 2018-07-27 | 2018-07-06 | Masked | Orangeburg, SC | N/A | Cross - Orangeburg 230kV | 75 | 75 | Solar | Sun |  | 2020-12-01 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
111 | 2018-07-27 | 2018-07-26 | Masked | Lexington, SC | TBD | Sandy Run 115 kV Bus or Sandy Run - Columbia 115 kV Lines | 50 | 50 | Solar | Sun |  | 2020-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
112 | 2018-07-27 | 2018-07-26 | Masked | Florence , SC | TBD | Marion - Lake City 69 kV Line | 50 | 50 | Solar | Sun |  | 2020-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
113 | 2018-07-27 | 2018-07-26 | Masked | Orangeburg, SC | TBD | Orangeburg - St. George #1 115 kV Line | 100 | 100 | Solar | Sun |  | 2020-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
114 | 2018-07-27 | 2018-07-26 | Masked | Williamsburg, SC | TBD | Hemingway - Kingstree 230 kV Line | 100 | 100 | Solar | Sun |  | 2020-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
115 | 2018-10-10 | 2018-09-10 | Masked | Marlboro, SC | N/A | Bennettsville - Indian Creek #1 69 kV | 19.9 | 19.9 | Solar | Sun |  | 9/31/19 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
116 | 2018-10-10 | 2018-09-10 | Masked | Chesterfield, SC | N/A | Grantham - Indian Creek #1 69 kV Line | 19.9 | 19.9 | Solar | Sun |  | 2019-10-31 | NR/ER | No | N/A | In Progress |  |  | Withdrawn
117 | 2018-10-10 | 2018-09-19 | Masked | Lexington, SC | TBD | Columbia - Sandy Run #2 115kV | 32.5 | 32.5 | Solar | Sun |  | 2019-12-31 | NR/ER | No | In Progress |  |  |  | Withdrawn
118 | 2018-12-14 | 2018-10-12 | Masked | Marlboro, SC | TBD | Bennettsville - Indian Creek #1 69 kV | 19.9 | 19.9 | Solar | Sun |  | 2020-07-30 | NR/ER | No | In Progress |  |  |  | Withdrawn
119 | 2018-12-14 | 2018-11-29 | Masked | Dorchester, SC | TBD | TBD | 350 | 350 | Solar | Sun |  | 2021-12-01 | NR/ER | No | In Progress |  |  |  | Withdrawn
120 | 2018-12-14 | 2018-12-03 | Masked | Greenwood, SC | Greenwood 230 kV Sw Sta | TBD | 75 | 75 | Solar | Sun |  | 2021-12-01 | ER | No |  | In Progress |  |  | Withdrawn
121 | 2019-02-12 | 2018-12-13 | Masked | Marlboro, SC | TBD | TBD | 19.9 | 19.9 | Solar | Sun |  |  | NR/ER | No |  | In Progress |  |  | Withdrawn
122 | 2019-02-12 | 2019-01-18 | Masked | Aiken, SC | N/A | Aiken - Shamrock 115 kV Line | 102.6 |  | Solar | Sun |  | 2025-06-01 | NR | No |  |  |  |  | Withdrawn
123 | 2019-02-12 | 2019-01-22 | Masked | Aiken, SC | TBD | TBD | 81.6 |  | Solar | Sun |  | 2021-06-01 | ER | No |  |  |  |  | Withdrawn
124 | 2019-02-12 | 2019-01-22 | Masked | Aiken, SC | N/A | Batesburg - Shamrock 115 kV Line | 74 | 74 | Solar | Sun | 35 | 2025-06-01 | NR | Yes | Complete | Complete | N/A | Complete | Construction
125 | 2019-03-15 | 2018-01-24 | Masked | Berkeley, SC | TBD | TBD | 100 |  | Solar | Sun |  | 2020-12-01 | NR/ER | No |  |  |  |  | Withdrawn
126 | 2019-07-17 | 2018-01-24 | Masked | Berkeley, SC | TBD | Jefferies - Winyah 230 kV Line | 100 |  | Solar | Sun |  | 2020-12-01 | NR/ER | No |  |  |  |  | Withdrawn
127 | 2019-07-17 | 2019-01-28 | Masked | Clarendon, SC | TBD | Cross-Dalzell 230 kV | 75 |  | Solar | Sun |  | 2021-06-01 | NR/ER | No |  |  |  |  | Withdrawn
128 | 2019-07-17 | 2019-01-28 | Masked | Sumter, SC | N/A | Scottsville - Dalzell 69 kV Line | 74.9 |  | Solar | Sun |  | 2025-12-31 | NR | No |  |  |  |  | Withdrawn
129 | 2019-07-17 | 2018-01-28 | Masked | Aiken, SC | TBD | TBD | 60 |  | Solar | Sun |  | 2021-06-01 | ER | No |  |  |  |  | Withdrawn
130 | 2019-07-17 | 2019-05-28 | Masked | Georgetown, SC | TBD | Winyah-Jefferies 230 kV line | 100 | 100 | Solar | Sun |  | 2021-12-31 | NR | No |  |  |  |  | Construction
131 | 2019-07-17 | 2019-06-17 | Masked | Laurens, SC | TBD | TBD | 160 |  | Solar | Sun |  | 2022-12-31 | NR/ER | No |  |  |  |  | Withdrawn
132 | 2019-12-20 | 2019-07-30 | Masked | Hampton, SC | Varnville 230 kV Bus | N/A | 75 |  | Solar | Sun |  | 2024-05-01 | NR | Yes | Complete | Complete | N/A | Complete | 2022 Trans Cluster
133 | 2019-12-20 | 2019-09-03 | Masked | Dorchester, SC | TBD | TBD | 74.99 | 74.99 | Solar | Sun |  | 2022-03-01 | NR/ER | No |  |  |  |  | Withdrawn
134 | 2019-12-20 | 2019-09-09 | Masked | Orangeburg, SC | N/A | Orangeburg - St. George #1 115 kV Line | 75 | 75 | Solar | Sun |  | 2026-03-01 | NR | No |  |  |  |  | Withdrawn
135 | 2019-12-20 | 2019-10-14 | Masked | Georgetown, SC | TBD | TBD | 100 | 100 | Solar | Sun |  | 2021-11-15 | NR | No |  |  |  |  | Construction
136 | 2019-12-20 | 2019-10-29 | Masked | Georgetown, SC | TBD | TBD | 75 | 75 | Solar | Sun |  | 2022-03-01 | NR/ER | No |  |  |  |  | Withdrawn
137 | 2020-05-08 | 2019-11-15 | Masked | Orangeburg, SC | Orangeburg 115 kV Bus | N/A | 100 | 100 | Solar/BESS | Sun/Battery | 100 | 2024-12-31 | NR | Yes | Complete | Complete | N/A | Complete | Construction
138 | 2020-05-08 | 2019-11-15 | Masked | Horry, SC | TBD | TBD | 74.9 | 74.9 | Solar | Sun |  | 2022-12-30 | NR/ER | No |  |  |  |  | Withdrawn
139 | 2020-05-08 | 2019-12-12 | Masked | Orangeburg, SC | Shamrock 115 kV Bus | N/A | 74.9 | 74.9 | Solar | Sun |  | 2027-12-31 | NR | No |  |  |  |  | Withdrawn
140 | 2020-05-08 | 2019-12-18 | Masked | Horry, SC | TBD | TBD | 100 | 100 | Solar | Battery |  | 2022-12-01 | NR/ER | No |  |  |  |  | Withdrawn
141 | 2020-05-08 | 2019-12-18 | Masked | Richland, SC | TBD | TBD | 125 | 125 | Solar | Sun |  | 2023-06-30 | NR/ER | No |  |  |  |  | Withdrawn
142 | 2020-05-08 | 2019-12-27 | Masked | Saluda, SC | TBD | TBD | 125 | 125 | Solar | Sun |  | 2023-06-30 | NR/ER | No |  |  |  |  | Withdrawn
143 | 2020-05-08 | 2020-01-01 | Masked | Fairfield, SC | N/A | Blythewood - Lugoff 69 kV Line | 20 | 20 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
144 | 2020-05-08 | 2020-01-24 | Masked | Kershaw, SC | N/A | Flat Creek - South Bethune 230 kV Line | 75 |  | Solar | Sun |  | 2025-12-15 | NR | Yes | Complete | Complete | N/A | Complete | Withdrawn
145 | 2020-05-08 | 2020-01-24 | Masked | Williamsburg, SC | TBD | TBD | 400 | 400 | Solar | Sun |  | 2023-06-30 | NR/ER | No |  |  |  |  | Withdrawn
146 | 2020-05-08 | 2020-02-10 | Masked | Marion, SC | TBD | TBD | 400 | 400 | Solar | Sun |  | 2023-06-30 | NR/ER | No |  |  |  |  | Withdrawn
147 | 2020-05-08 | 2020-02-11 | Masked | Clarendon, SC | N/A | Pinewood-Wilson 69 kV line | 35 | 35 | Solar | Sun |  | 2025-12-31 | NR | No |  |  |  |  | Withdrawn
148 | 2020-05-08 | 2020-02-11 | Masked | Anderson, SC | TBD | TBD | 140 | 170 | CT | Gas |  | 2021-06-01 | NR/ER | No |  |  |  |  | Withdrawn
149 | 2020-05-08 | 2020-02-27 | Masked | Georgetown, SC | TBD | TBD | 360 | 360 | CT | Gas |  | 2024-06-01 | NR/ER | No |  |  |  |  | Withdrawn
150 | 2020-05-08 | 2020-02-27 | Masked | Georgetown, SC | TBD | TBD | 360 | 360 | CT | Gas |  | 2024-06-01 | NR/ER | No |  |  |  |  | Withdrawn
151 | 2020-05-08 | 2020-02-27 | Masked | Georgetown, SC | TBD | TBD | 870 | 870 | CCGT | Gas |  | 2024-06-01 | NR/ER | No |  |  |  |  | Withdrawn
152 | 2020-05-08 | 2020-02-27 | Masked | Georgetown, SC | TBD | TBD | 870 | 870 | CCGT | Gas |  | 2024-06-01 | NR/ER | No |  |  |  |  | Withdrawn
153 | 2021-01-20 |  | Masked | Horry, SC | TBD | TBD | 103.5 | 113.3 | CT | Gas |  | TBD | NR/ER | No |  |  |  |  | Withdrawn
154 | 2021-01-20 | 2020-07-16 | Masked | Colleton, SC | TBD | TBD | 20 | 20 | Solar | Gas |  | TBD | NR/ER | No |  |  |  |  | Withdrawn
155 |  | 2020-07-27 | Masked | Allendale, SC | TBD | TBD | 86 | 86 | Solar | Sun |  | 2023-12-15 | ER | No |  |  |  |  | Withdrawn
156 | 2021-01-20 | 2020-07-29 | Masked | Newberry, SC | N/A | Newberry - Bush River 69 kV Line | 30 | 30 | Solar | Sun |  | 2025-12-31 | NR | No |  |  |  |  | Withdrawn
Queue Position | Queue Date | Date of Completed Application | Customer Name | Location County/State | SCPSA Substation | SCPSA Line | Sum Capacity (MW) | Win Capacity (MW) | Unit Type | Fuel | BESS Capacity | Projected In- Service Date | Type of Service Requested | Studies Available | Phase I DISIS | Phase II DISIS | Phase III DISIS (Restudy) | Facilities Studay | Project Status
157 | 2021-01-20 | 2020-08-01 | Masked | Aiken, SC | TBD | TBD | 60 | 60 | Solar | Sun |  | 2022-06-30 | NR/ER | No |  |  |  |  | Withdrawn
158 | 2021-01-20 | 2020-08-01 | Masked | Lexington, SC | TBD | TBD | 50 | 50 | Solar | Sun |  | 2022-06-30 | NR/ER | No |  |  |  |  | Withdrawn
159 | 2021-01-20 | 2020-08-01 | Masked | Berkeley, SC | TBD | TBD | 50 | 50 | Solar | Sun |  | 2022-06-30 | NR/ER | No |  |  |  |  | Withdrawn
160 | 2021-06-02 | 9/9/2020 (8:29am) | Masked |  | TBD | TBD | 75 | 75 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
161 | 2021-06-02 | 9/9/20 (1:15pm) | Masked |  | TBD | TBD | 200 | 200 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
162 | 2021-06-02 | 2020-09-11 | Masked |  | TBD | TBD | 125 | 125 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
163 | 2021-06-02 | 2020-10-13 | Masked | Sumter | Dalzell 230 kV Bus | N/A | 50 | 50 | Solar/BESS | Sun/Battery | 50 | 2024-08-01 | NR | No |  |  |  |  | Withdrawn
164 | 2021-06-02 | 2020-11-16 | Masked | Marlboro | TBD | TBD | 125 | 125 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
165 | 2021-10-26 | 2021-01-12 | Masked | Georgetown | N/A | Winyah - Jefferies 230 kV Line | 50 |  | Solar | Sun |  | 2024-12-31 | NR | Yes | Complete | Complete | N/A | Complete | Construction
166 | 2021-10-26 | 2021-01-12 | Masked | Georgetown | TBD | TBD | 79.9 | 79.9 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
166B | 2021-10-26 | 2021-02-12 | Masked | Georgetown | N/A | Jefferies - Georgetown 115 kV Line | 140 | 140 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
167 | 2021-10-26 | 2021-03-19 | Masked | Darlington | Darlington 69 kV Bus | N/A | 74.99 |  | Solar | Sun |  | 2025-09-01 | NR | Yes | Complete | Complete | N/A | Complete | Suspension
167B | 2021-10-26 | 2021-03-22 | Masked | Richland | TBD | Pinewood - Silver Lake #2 115 kV Line | 55 | 55 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
167C | 2021-10-26 | 2021-03-24 | Masked | Orangeburg | TBD | TBD |  |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
168 | 2021-10-26 | 2021-04-08 | Masked | Marlboro | Bennettsville 230 kV | TBD | 125 | 125 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
169 | 2021-10-26 | 2021-04-23 | Masked | Newberry | TBD | TBD | 100 | 50 | Solar | Sun/Battery |  |  |  | No |  |  |  |  | Withdrawn
170 | 2021-10-26 | 2021-06-08 | Masked | Williamsburg | TBD | TBD | 120 | 120 | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
171 | 2021-10-26 | 2021-06-08 | Masked | Williamsburg | N/A | Winyah - Hemingway 230 kV Line | 249 |  | Solar | Sun |  | 2028-10-15 |  | Yes | Complete | Complete | N/A | Complete | Construction
172 | 2021-10-26 | 2021-06-08 | Masked | Williamsburg | N/A | Kingstree - Wilson 69 kV Line | 50 |  | Solar | Sun |  | 2025-10-15 |  | Yes | Complete | Complete | N/A | Complete | Withdrawn
173 | 2022-02-11 | 2021-10-07 | Masked | Darlington | TBD | TBD | 50 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
173B | 2022-02-11 | 2021-10-11 | Masked | Lexington | TBD | TBD | 152.3 |  | Solar | Sun/Battery |  |  |  | No |  |  |  |  | Withdrawn
174 | 2022-02-11 | 2021-11-15 | Masked | Chesterfield | TBD | TBD | 74 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
175 | 2022-02-11 | 2021-11-22 | Masked | Lancaster | TBD | TBD | 75 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
176 | 2022-02-11 | 2021-11-30 | Masked | Georgetown | TBD | TBD | 100 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
177 | 2022-02-11 | 2021-11-30 | Masked | Georgetown | TBD | TBD | 100 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
178 | 2022-02-11 | 2021-12-21 | Masked | Williamsburg | N/A | Jefferies - Kingstree 230 kV Line | 75 |  | Solar | Sun |  | 2027-03-09 | ER | No |  |  |  |  | Withdrawn
179 | 2022-04-05 | 2022-02-10 | Masked | Williamsburg | TBD | TBD | 74.9 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
180 | 2022-04-05 | 2022-02-10 | Masked | Williamsburg | TBD | TBD | 74.9 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
181 | 2022-04-05 | 2022-02-10 | Masked | Williamsburg | TBD | TBD | 74.9 |  | Solar | Sun |  |  |  | No |  |  |  |  | Withdrawn
182 | 2022-04-05 | 2022-02-10 | Masked | Williamsburg/Clarendon | N/A | Wilson - Lake City 69 kV Line | 50 |  | Solar | Sun |  | 2024-12-31 | NR | No |  |  |  |  | Withdrawn
183 | 2022-04-05 | 2022-02-11 | Masked | Kershaw | N/A | Flat Creek - South Bethune 230 kV Line | 150.03 |  | Solar | Sun |  | 2024-12-31 | NR | No |  |  |  |  | Withdrawn
184 | 2023-06-01 | 2023-01-02 | Masked | Orangeburg | N/A | Sandy Run - Orangeburg #2 115 kV Line | 50 | 50 | Solar | Sun |  | 2025-09-27 | NR | Yes | Complete | Complete |  |  | Withdrawn
185 | 2023-06-01 | 2023-01-02 | Masked | Colleton | N/A | Smoaks Tap 115 kV Line (CEPCI Owned) | 22.575 | 22.575 | Solar | Sun |  | 2026-03-27 | NR | No | Complete |  |  |  | Withdrawn
186 | 2023-06-01 | 2023-01-10 | Masked | Marion | N/A | Lake City - Marion 230 kV Line | 100 | 100 | Solar | Sun |  | 2024-04-08 | ER | Yes | Complete | Complete |  |  | Withdrawn
187 | 2023-06-01 | 2023-01-16 | Masked | Hampton | N/A | Varnville - Bells Crossroads 115 kV Line | 100 | 100 | Solar | Sun |  | 2024-04-08 | ER | Yes | Complete | Complete |  |  | Withdrawn
188 | 2023-06-01 | 2023-01-17 | Masked | Marion | N/A | Pringle Ferry Tap 115kV Line (CEPCI Owned) | 200 | 200 | Solar | Sun |  | 2024-04-08 | ER | Yes | Complete | Complete |  |  | Withdrawn
189 | 2023-06-01 | 2023-03-10 | Masked | Williamsburg | N/A | Hemingway - Kingstree 230 kV Line | 75 | 75 | Solar | Sun |  | 2027-12-31 | NR | No | Complete |  |  |  | Withdrawn
190 | 2023-06-01 | 2023-03-10 | Masked | Williamsburg | N/A | Hemingway - Kingstree 230 kV Line | 175 | 175 | Solar/BESS | Sun/Battery |  | 2027-12-31 | NR | No | Complete |  |  |  | Withdrawn
191 | 2023-06-01 | 2023-05-04 | Masked | Sumter | N/A | Dalzell - Camden 230 kV Line | 200 | 200 | Solar | Sun |  | 2027-01-31 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
192 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 7 |  | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
193 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 7 |  | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
194 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 7 |  | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
195 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 18 | 18 | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
196 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 18 | 18 | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
197 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 18 | 18 | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
198 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 18 | 18 | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
199 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 20 | 20 | Mat. Mod. NG | NG |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
200 | 2023-06-01 | 2023-05-05 | Masked | Anderson | Rainey 230 kV Sw. Station | N/A | 189 | 209 | HRSG | Heat Recovery |  | TBD | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
201 | 2023-06-01 | 2023-05-10 | Masked | Kershaw | South Bethune 230 & 69 kV Sw. Stat. | N/A | 190 |  | Solar/BESS | Sun/Battery |  | 2027-02-19 | NR | No | Complete |  |  |  | Withdrawn
202 | 2023-06-01 | 2023-05-15 | Masked | Chesterfield | N/A | SOUTH BETHUNE - DARLINGTON COUNTY (DEP) 230kV LINE | 75 | 75 | Solar | Sun |  | 2027-06-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
203 | 2023-06-01 | 2023-05-17 | Masked | Kershaw | N/A | Camden - South Bethune 230 kV Line | 75 | 75 | Solar | Sun |  | 2027-10-12 | NR | Yes | Complete | Complete |  |  | Withdrawn
204 | 2023-06-01 | 2023-05-23 | Masked | Sumter | N/A | PINEWOOD - SCOTTSVILLE 69kV LINE | 75 | 75 | Solar/BESS | Sun/Battery | 75 | 2026-05-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
205 | 2023-06-01 | 2023-05-24 | Masked | Berkeley | N/A | CROSS - CARNES CROSSROADS 230kV LINE | 198 | 198 | Solar/BESS | Sun/Battery | 50 | 2027-01-30 | NR | Yes | Complete | Complete |  |  | Withdrawn
206 | 2023-06-01 | 2023-05-24 | Masked | Berkeley | N/A |  | 198 | 198 | Solar/BESS | Sun/Battery | 50 | 2027-01-30 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
207 | 2023-06-01 | 2023-05-24 | Masked | Marlboro | N/A | MARION - BENNETTSVILLE 230kV LINE | 88.2 | 88.2 | Solar | Sun |  | 46357 | NR | Yes | Complete | Complete |  |  | Withdrawn
208 | 2023-06-01 | 2023-05-25 | Masked | Aiken | N/A | SHAMROCK - AIKEN 115kV LINE | 74.9 | 74.9 | Solar | Sun |  | 2026-06-01 | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
209 | 2023-06-01 | 2023-05-25 | Masked | Kershaw | CASSATT 69 KV STATION(BLACK RIVER CO-OP DELIVERY POINT) | N/A | 19.95 | 19.95 | Solar | Sun |  | 2026-12-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
210 | 2023-06-01 | 2023-05-25 | Masked | Clarendon | N/A | JEFFERIES - PINEWOOD 115kV LINE | 74.9 | 74.9 | Solar | Sun |  | 2026-05-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
211 | 2023-06-01 | 2023-05-26 | Masked | Horry | N/A | ALLEN - PINE LEVEL 115 KV | 74.8 | 74.8 | Solar | Sun |  | 2026-12-31 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
212 | 2023-06-01 | 2023-05-26 | Masked | Calhoun | N/A | ORANGEBURG - ST. GEORGE 115 KV LINE NO.2 | 74.8 | 74.8 | Solar | Sun |  | 2026-12-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
213 | 2023-06-01 | 2023-05-26 | Masked | Aiken | N/A | POOLE'S MILL - PELION 115 KV LINE (CEPCI OWNED) | 74.9 |  | Solar | Sun |  | 2025-12-01 | NR | No |  |  |  |  | Withdrawn
214 | 2023-06-01 | 2023-05-26 | Masked | Chesterfield | N/A | G W TEAL 69kV LINE (CEPCI OWNED RADIAL) | 49.9 | 49.9 | Solar | Sun |  | 2025-12-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
215 | 2023-06-01 | 2023-05-26 | Masked | Newberry | N/A | BUSH RIVER LONG LANE 69kV LINE (CEPCI OWNED) | 30 |  | Solar | Sun |  | 2025-12-01 | NR | No |  |  |  |  | Withdrawn
216 | 2023-06-01 | 2023-05-26 | Masked | Kershaw | N/A | BOONETOWN TAP 69kV LINE (CEPCI OWNED) | 49.9 | 49.9 | Solar | Sun |  | 2025-12-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
217 | 2023-06-01 | 2023-05-26 | Masked | Georgetown | N/A | JEFFERIES - GEORGETOWN #3 115 KV LINE | 100 | 100 | BESS | Battery | 100 | 2026-11-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
218 | 2023-06-01 | 2023-05-26 | Masked | Saluda | N/A | AIKEN NO 1 - BATESBURG 115kV LINE | 150 |  | Solar/BESS | Sun/Battery |  | 2026-06-01 | NR | No | Complete |  |  |  | Withdrawn
219 | 2023-06-01 | 2023-05-30 | Masked | Georgetown | N/A | CAMPFIELD - BUCKSVILLE 230kV LINE | 212.5 | 212.5 | Solar | Sun |  | 46874 | NR | Yes | Complete | Complete |  |  | Withdrawn
220 | 2023-06-01 | 2023-05-30 | Masked | Georgetown | N/A | WINYAH - BUCKSVILLE 230kV LINE | 250 | 250 | Solar/BESS | Sun/Battery | 250 | 2028-05-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
221 | 2023-06-01 | 2023-05-30 | Masked | Sumter | N/A | DALZELL - CAMDEN 230 kV LINE | 50 | 50 | BESS | Battery | 50 | 2027-01-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
222 | 2023-06-01 | 2023-05-30 | Masked | Colleton | COLLETON CO. COMMERCE PK (COASTAL CO-OP DELIVERY POINT) | N/A | 74.5 | 74.5 | BESS | Battery | 74.5 | 2028-06-30 | NR | Yes | Complete | Complete | Complete | Complete | 2023 Cluster
223 | 2023-06-01 | 2023-05-30 | Masked | Williamsburg | WILLIAMSBURG IND. PARK (SANTEE CO-OP DELIVERY POINT) | N/A | 74.5 | 74.5 | BESS | Battery | 74.5 | 2028-06-30 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
224 | 2023-06-01 | 2023-05-30 | Masked | Orangeburg | N/A | ORANGEBURG - ST GEORGE LINE NO. 2 115 KV LINE | 74.5 | 74.5 | BESS | Battery | 74.5 | 2028-06-30 | NR | Yes | Complete | Complete |  |  | Withdrawn
225 | 2023-06-01 | 2023-05-30 | Masked | Dillon/Marion | N/A | MARION - BENNETTSVILLE 230 kV LINE | 150 | 150 | Solar | Sun |  | 2027-01-31 | NR | No | Complete |  |  |  | Withdrawn
226 | 2023-06-01 | 2023-05-30 | Masked | Kershaw | N/A | SOUTH BETHUNE - FLAT CREEK 230 kV LINE | 80 | 80 | Solar/BESS | Sun/Battery | 80 | 2026-12-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
227 | 2023-06-01 | 2023-05-30 | Masked | Colleton | N/A | BELLS CROSSROADS - ST. GEORGE 115kV LINE | 80 | 80 | Solar/BESS | Sun/Battery | 80 | 2026-12-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
228 | 2023-06-01 | 2023-05-30 | Masked | Berkeley | JAMESTOWN STATION(BERKELEY CO-OP DELIVERY POINT) | N/A | 74.9 | 74.9 | BESS | Battery | 74.9 | 2028-06-30 | NR | Yes | Complete | Complete |  |  | Withdrawn
Queue Position | Queue Date | Date of Completed Application | Customer Name | Location County/State | SCPSA Substation | SCPSA Line | Sum Capacity (MW) | Win Capacity (MW) | Unit Type | Fuel | BESS Capacity | Projected In- Service Date | Type of Service Requested | Studies Available | Phase I DISIS | Phase II DISIS | Phase III DISIS (Restudy) | Facilities Studay | Project Status
229 | 2023-06-01 | 2023-05-30 | Masked | Berkeley | JAMESTOWN STATION (BERKELEY CO-OP DELIVERY POINT) | N/A | 150 |  | BESS | Battery |  | 2028-06-30 | NR | No |  |  |  |  | Withdrawn
230 | 2023-06-01 | 2023-05-30 | Masked | Williamsburg | HEMINGWAY 230 -115 kV STATION | N/A | 74.9 | 74.9 | BESS | Battery | 74.9 | 2028-06-30 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
231 | 2023-06-01 | 2023-05-30 | Masked | Williamsburg | HEMINGWAY 230 -115 kV STATION | N/A | 150 |  | BESS | Battery |  | 2028-06-30 | NR | No |  |  |  |  | Withdrawn
232 | 2023-06-01 | 2023-05-30 | Masked | Dillon/Marion | N/A | MARION - BENNETTSVILLE 230kV LINE | 250 | 250 | BESS | Battery | 100 | 2027-01-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
233 | 2023-06-01 | 2023-05-30 | Masked | Orangeburg | N/A | BAMBERG SW STA - ORANGBURG 69kV LINE | 120 |  | Solar/BESS | Sun/Battery |  | 2027-09-30 | NR | No |  |  |  |  | Withdrawn
234 | 2023-06-01 | 2023-05-30 | Masked | Hampton | Varnville 230 kV Bus | N/A | 75 | 75 | BESS | Battery | 75 | 2027-10-31 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
235 | 2023-06-01 | 2023-05-31 | Masked | Aiken | N/A | SILVER BLUFF - NORTH AUGUSTA 115kV LINE (CEPCI OWNED) | 73 | 73 | Solar | Sun | 0 | 2026-12-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
236 | 2023-06-01 | 2023-05-31 | Masked | Chesterfield | N/A | FLAT CREEK - INDIAN CREEK NO.1 69kV LINE | 74.9 |  | Solar/BESS | Sun/Battery |  | 2026-12-31 | NR | No | Complete |  |  |  | Withdrawn
237 | 2023-06-01 | 2023-05-31 | Masked | Aiken | N/A | POOLE'S MILL - PELION 115kV LINE (CEPCI OWNED) | 65 | 65 | Solar | Sun | 0 | 2026-12-31 | NR | Yes | Complete | Complete |  |  | Withdrawn
238 | 2023-06-01 | 2023-05-31 | Masked | Marion | N/A | LAKE CITY - MARION 230 kV LINE | 75 | 75 | Solar | Sun |  | 2027-12-31 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
239 | 2023-06-01 | 2023-05-31 | Masked | Marion | N/A | LAKE CITY - MARION 230 kV LINE | 55 | 55 | Solar | Sun |  | 2027-12-31 | NR | Yes | Complete | Complete | Complete |  | 2023 Cluster
240 | 2023-06-01 | 2023-05-31 | Masked | Aiken | CROSSROADS STATION (AIKEN CO-OP DELIVERY POINT) | N/A | 55 | 55 | BESS | Battery |  | 2027-06-30 | NR | No | Complete |  |  |  | Withdrawn
241 | 2023-06-01 | 2023-05-31 | Masked | Lancaster | N/A | RICHBURG - FLAT CREEK 230kV LINE | 75 | 75 | Solar | Sun |  | 2027-06-01 | NR | No |  |  |  |  | Withdrawn
242 | 2023-06-01 | 2023-05-31 | Masked | Colleton | N/A | BELLS CROSSROADS - ST. GEORGE 115kV LINE | 75 | 75 | BESS | Battery | 75 | 2027-04-01 | NR | Yes | Complete | Complete |  |  | Withdrawn
243 | 2024-02-01 | 2024-01-01 | Masked | Florence | N/A | HEMINGWAY - LAKE CITY 230kV LINE | 75 | 75 | Solar | Sun |  | 2028-12-31 | NR | No | Complete |  |  |  | Withdrawn
244 | 2024-02-01 | 2024-01-01 | Masked | Williamsburg | N/A | JEFFERIES - KINGSTREE 230kV LINE | 175 | 175 | Solar | Sun |  | 2028-12-31 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
245 | 2024-02-01 | 2024-01-01 | Masked | Williamsburg | N/A | CROSS - KINGSTREE #1 230kV LINE | 175 | 175 | Solar | Sun |  | 2028-12-31 | NR | No |  |  |  |  | Withdrawn
246 | 2024-02-01 | 2024-01-01 | Masked | Williamsburg | N/A | JEFFERIES - KINGSTREE 230kV LINE | 75 | 75 | Solar | Sun |  | 2028-12-31 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
247 | 2024-02-01 | 2024-01-01 | Masked | Kershaw | N/A | BLYTHEWOOD - LUGOFF 230kV LINE | 125 | 125 | Solar | Sun |  | 2028-12-31 | NR | Yes | Complete |  |  |  | Withdrawn
248 | 2024-02-01 | 2024-01-01 | Masked | Williamsburg | N/A | CROSS - KINGSTREE #1 230kV LINE | 75 | 75 | Solar | Sun |  | 2028-12-31 | NR | No |  |  |  |  | Withdrawn
249 | 2024-02-01 | 2024-01-01 | Masked | Clarendon | N/A | CROSS - PINEWOOD 230kV LINE | 75 | 75 | Solar | Sun |  | 2028-12-31 | NR | No |  |  |  |  | Withdrawn
250 | 2024-02-01 | 2024-01-01 | Masked | Kershaw | N/A | BLYTHEWOOD - LUGOFF 230kV LINE | 75 | 75 | BESS | Battery |  | 2028-12-31 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
251 | 2024-02-01 | 2024-01-01 | Masked | Williamsburg | N/A | JEFFERIES - KINGSTREE 230kV LINE | 75 | 75 | BESS | Battery |  | 2028-12-31 | NR | Yes | Complete |  |  |  | Withdrawn
252 | 2024-02-01 | 2024-01-01 | Masked | Florence | N/A | HEMINGWAY - LAKE CITY 230kV LINE | 75 | 75 | BESS | Battery |  | 2028-12-31 | NR | No | Complete |  |  |  | Withdrawn
253 | 2024-02-01 | 2024-01-01 | Masked | Clarendon | N/A | CROSS - PINEWOOD 230kV LINE | 75 | 75 | BESS | Battery |  | 2028-12-31 | NR | No |  |  |  |  | Withdrawn
254 | 2024-02-01 | 2024-01-01 | Masked | Williamsburg | N/A | CROSS - KINGSTREE #1 230kV LINE | 75 | 75 | BESS | Battery |  | 2028-12-31 | NR | No |  |  |  |  | Withdrawn
255 | 2024-05-15 | 2024-01-02 | Masked | Saluda | N/A | AIKEN NO 1 - BATESBURG 115kV LINE | 74.99 | 74.99 | Solar | Sun |  | 2026-08-01 | NR | No |  |  |  |  | Withdrawn
256 | 2024-05-15 | 2024-01-02 | Masked | Orangeburg | N/A | ST GEORGE - ORANGEBURG 115kV LINE | 74.99 | 74.99 | Solar | Sun |  | 2026-08-01 | NR | No |  |  |  |  | Withdrawn
257 | 2024-05-15 | 2024-01-18 | Masked | Aiken | N/A | AIKEN 230 SUB - AIKEN 115 SUB 115kV LINE | 74.9 | 74.9 | Solar | Sun |  | 46266 | NR | No |  |  |  |  | Withdrawn
258 | 2024-05-15 | 2024-01-18 | Masked | Aiken | N/A | AIKEN 230 SUB - AIKEN 115 SUB 115kV LINE | 74.9 | 74.9 | BESS | Battery |  | 46266 | NR | No |  |  |  |  | Withdrawn
259 | 2024-05-15 | 2024-02-27 | Masked | Allendale | N/A | FAIRFAX - ALLENDALE SWITCHING STATION 69kV LINE | 48 | 48 | Solar | Sun |  | 2026-07-01 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
260 | 2024-05-15 | 2024-05-15 | Masked | Marion | MARION SUB (@230KV) | N/A | 249.9 | 249.9 | Solar | Sun |  | 2028-10-01 | NR | No | Complete |  |  |  | Withdrawn
261 | 2024-05-15 | 2024-05-15 | Masked | Dillon | LATTA 69kV SWITCHING STATION | N/A | 49.9 | 49.9 | Solar | Sun |  | 2025-05-15 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
262 | 2024-06-05 | 2024-05-17 | Masked | Berkeley |  | JEFFERIES - GEORGETOWN #2 115kV LINE | 75 | 75 | Solar | Sun |  | 2028-10-01 | NR | No |  |  |  |  | Withdrawn
263 | 2024-06-05 |  | Masked | Williamsburg |  | WINYAH - HEMINGWAY 230kV LINE | (Mat Mod to #171) |  | Solar | Sun |  | 2028-11-01 | NR | No | Complete |  |  |  | Withdrawn
264 | 2024-06-05 | 2024-05-24 | Masked | Clarendon |  | CROSS - PINEWOOD 230kV LINE | 75 | 75 | Solar | Sun |  | 2028-08-05 | ER | No |  |  |  |  | Withdrawn
265 | 2024-06-05 | 2024-05-28 | Masked | Saluda |  | MAYSON TAP 115kV LINE (CEPCI OWNED) | 75 | 75 | Solar | Sun |  | 2028-08-05 | NR | No |  |  |  |  | Withdrawn
266 | 2024-06-05 | 2024-05-29 | Masked | Hampton | VARNVILLE 230 kV BUS |  | 100 | 100 | Solar | Sun |  | 2028-06-01 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
267 | 2024-06-05 | 2024-05-30 | Masked | Saluda |  | NEWBERRY - BATESBURG 230kV LINE | 185.5 | 185.5 | Solar | Sun |  | 2028-06-30 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
268 | 2024-06-05 | 2024-05-30 | Masked | Richland |  | PINEWOOD - SANDY RUN 115kV LINE | 51 | 51 | Solar | Sun |  | 2027-12-31 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
269 | 2024-06-05 | 2024-05-30 | Masked | Orangeburg |  | CROSS - ORANGEBURG 230kV LINE | 150 | 150 | BESS | Battery |  | 2028-06-06 | ER | No |  |  |  |  | Withdrawn
270 | 2024-06-05 | 2024-05-30 | Masked | Williamsburg |  | JEFFERIES - KINGSTREE 230kV LINE | 150 | 150 | Solar | Sun |  | 2029-12-31 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
271 | 2024-06-05 | 2024-05-30 | Masked | Chesterfield |  | FLAT CREEK - INDIAN CREEK NO. 1 69kV LINE | 50 | 50 | Solar | Sun |  | 2028-06-01 | NR | No | Complete |  |  |  | Withdrawn
272 | 2024-06-05 | 2024-05-30 | Masked | Orangeburg |  | ORANGEBURG - ST. GEORGE NO. 2 LINE | 74.9 | 74.9 | Solar | Sun |  | 2028-06-01 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
273 | 2024-06-05 | 2024-05-30 | Masked | Fairfield |  | V.C. SUMMER - WINNSBORO 230kV LINE | 74.9 | 74.9 | Solar | Sun |  | 2028-06-01 | NR | No |  |  |  |  | Withdrawn
274 | 2024-06-05 | 2024-05-30 | Masked | Darlington |  | SOUTH BETHUNE - GRANTHAM 69kV LINE | 74.5 | 74.5 | Solar | Sun |  | 2027-12-31 | NR | No | Complete |  |  |  | Withdrawn
275 | 2024-06-05 | 2024-05-30 | Masked | Chesterfield |  | A. O. SMITH TAP 69kV LINE | 46 | 46 | Solar | Sun |  | 46752 | NR | Yes |  |  |  |  | Withdrawn
276 | 2024-06-05 | 2024-05-30 | Masked | Sumter |  | SCOTTSVILLE 69kV SWITCHING STATION | 49.9 | 49.9 | Solar | Sun |  | 2028-03-31 | NR | No |  |  |  |  | Withdrawn
277 | 2024-06-05 | 2024-05-30 | Masked | Darlington |  | ANTIOCH TAP 115kV (OPER @ 69kV) LINE (CEPCI OWNED) | 49.9 | 49.9 | Solar | Sun |  | 2028-03-31 | NR | No |  |  |  |  | Withdrawn
278 | 2024-06-05 | 2024-05-30 | Masked | Williamsburg | HEMINGWAY 230 - 115 SUBSTATION (230 kV Bus) |  | 149.5 | 149.5 | Solar | Sun |  | 2028-06-30 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
279 | 2024-06-05 | 2024-05-31 | Masked | Allendale | ALLENDALE 69 kV SWITCHING STATION |  | 65 | 65 | Solar/BESS | Sun/Battery |  | 2028-08-01 | ER | No | Complete |  |  |  | Withdrawn
280 | 2024-06-05 | 2024-05-31 | Masked | Fairfield | WINNSBORO COOP 69kV STATION (CEPCI OWNED) |  | 29.26 | 29.26 | Solar | Sun |  | 2025-12-31 | NR | No | Complete |  |  |  | Withdrawn
281 | 2024-06-05 | 2024-05-31 | Masked | Aiken |  | WINDSOR TAP 115kV LINE (CEPCI OWNED) | 74.9 | 74.9 | Solar | Sun |  | 2028-06-30 | NR | Yes | Complete | Complete |  |  | 2024 Cluster
282 | 2025-01-03 | 2025-01-01 | Masked | Marion |  | LAKE CITY - MARION 230 kV LINE | 120 | 120 | Solar | Sun |  | 1930-09-01 | NRIS | No |  |  |  |  | 2025 Cluster
283 | 2025-02-10 | 2025-02-07 | Masked | Colleton |  | VARNVILLE - INDIAN FIELD 230 KV LINE (FUTURE) | 819.4 | 819.4 | CCGT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
284 | 2025-02-10 | 2025-02-07 | Masked | Colleton |  | VARNVILLE - INDIAN FIELD 230 KV LINE (FUTURE) | 819.4 | 819.4 | CCGT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
285 | 2025-02-10 | 2025-02-07 | Masked | Colleton |  | VARNVILLE - INDIAN FIELD 230 KV LINE (FUTURE) | 819.4 | 819.4 | CCGT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
286 | 2025-05-19 | 2025-03-11 | Masked | Orangeburg |  | NORTH - SWANSEA 115kV LINE | 60 | 60 | Solar | Sun |  | 2027-11-30 | NRIS | No |  |  |  |  | 2025 Cluster
287 | 2025-05-19 | 2025-04-04 | Masked | Fairfield |  | WINNSBORO - GREAT FALLS 69kV LINE | 29.7 | 29.7 | Solar | Sun |  | 2027-03-01 | ERIS | No |  |  |  |  | 2025 Cluster
288 | 2025-05-19 | 2025-05-13 | Masked | Chester | RICHBURG 230-69KV SUBSTATION |  | 55.6 | 55.6 | CT | NG | 100 | 1930-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
289 | 2025-05-19 | 2025-05-13 | Masked | Chester | RICHBURG 230-69KV SUBSTATION |  | 55.6 | 55.6 | CT | NG |  | 1930-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
290 | 2025-05-19 | 2025-05-13 | Masked | Chester | RICHBURG 230-69KV SUBSTATION |  | 55.6 | 55.6 | CT | NG |  | 1930-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
291 | 2025-05-19 | 2025-05-13 | Masked | Chester | RICHBURG 230-69KV SUBSTATION |  | 55.6 | 55.6 | CT | NG |  | 1930-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
292 | 2025-05-19 | 2025-05-14 | Masked | Georgetown |  | JEFFERIES - GEORGETOWN #3 115kV LINE | 100 | 100 | CT | NG |  | 1930-03-01 | NRIS | No |  |  |  |  | 2025 Cluster
293 | 2025-05-19 | 2025-05-15 | Masked | Georgetown |  | WINYAH - CHARITY 230kV LINE | 55.6 | 55.6 | CT | NG |  | 2028-01-31 | NRIS | No |  |  |  |  | 2025 Cluster
294 | 2025-05-19 | 2025-05-15 | Masked | Georgetown |  | WINYAH - CHARITY 230kV LINE | 55.6 | 55.6 | CT | NG |  | 2028-01-31 | NRIS | No |  |  |  |  | 2025 Cluster
295 | 2025-05-19 | 2025-05-16 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 55.6 | 55.6 | CT | NG |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
296 | 2025-05-19 | 2025-05-16 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 55.6 | 55.6 | CT | NG |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
297 | 2025-05-19 | 2025-05-16 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 55.6 | 55.6 | CT | NG |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
298 | 2025-05-19 | 2025-05-16 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 55.6 | 55.6 | CT | NG |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
299 | 2025-05-29 | 2025-05-21 | Masked | Georgetown |  | WINYAH - CHARITY 230kV LINE | 100 | 100 | BESS | Battery | 100 | 2027-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
300 | 2025-05-29 | 2025-05-26 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 457.6 | 457.6 | CT | NG |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
301 | 2025-05-29 | 2025-05-26 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 457.6 | 457.6 | HRSG | Heat Recovery |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
302 | 2025-05-29 | 2025-05-26 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 207.5 | 207.5 | CT | NG |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
303 | 2025-05-29 | 2025-05-26 | Masked | Colleton |  | VARNVILLE - YEMASSEE 230kV LINE | 207.5 | 207.5 | HRSG | Heat Recovery |  | 1932-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
304 | 2025-05-29 | 2025-05-27 | Masked | Aiken | AIKEN 230-115 (AIKEN NO.3) |  | 55.6 | 55.6 | CT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
Queue Position | Queue Date | Date of Completed Application | Customer Name | Location County/State | SCPSA Substation | SCPSA Line | Sum Capacity (MW) | Win Capacity (MW) | Unit Type | Fuel | BESS Capacity | Projected In- Service Date | Type of Service Requested | Studies Available | Phase I DISIS | Phase II DISIS | Phase III DISIS (Restudy) | Facilities Studay | Project Status
305 | 2025-05-29 | 2025-05-27 | Masked | Aiken | AIKEN 230-115 (AIKEN NO.3) |  | 55.6 | 55.6 | CT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
306 | 2025-05-29 | 2025-05-27 | Masked | Aiken | AIKEN 230-115 (AIKEN NO.3) |  | 55.6 | 55.6 | CT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
307 | 2025-05-29 | 2025-05-27 | Masked | Aiken | AIKEN 230-115 (AIKEN NO.3) |  | 55.6 | 55.6 | CT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
308 | 2025-05-29 | 2025-05-28 | Masked | Berkeley |  | CROSS - JEFFERIES 230kV LINE | 250 | 250 | BESS | Battery | 250 | 2028-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
309 | 2025-05-29 | 2025-05-28 | Masked | Dorchester |  | CROSS - CARNES CROSSROADS 230kV LINE | 199 | 199 | BESS | Battery | 199 | 2028-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
310 | 2025-05-29 | 2025-05-28 | Masked | Dorchester |  | CROSS - CARNES CROSSROADS 230kV LINE | 199 | 199 | BESS | Battery | 199 | 2028-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
311 | 2025-05-29 | 2025-05-29 | Masked | Lexington |  | LAKE MURRAY 69kV LINE | 60 | 60 | Solar/BESS | Sun/Battery | 60 | 1930-03-01 | NRIS | No |  |  |  |  | 2025 Cluster
312 | 2025-06-02 | 2025-05-29 | Masked | Williamsburg | PINEWOOD 69 - 115KV SUBSTATION |  | 74.9 | 74.9 | BESS | Battery | 74.9 | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
313 | 2025-06-02 | 2025-05-29 | Masked | Williamsburg | PINEWOOD 69 - 115KV SUBSTATION |  | 55 | 55 | BESS | Battery | 55 | 2029-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
314 | 2025-06-02 | 2025-05-30 | Masked | Barnwell | AIKEN 230-115 (AIKEN NO.3) |  | 635 | 635 | CCGT | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | Withdrawn
315 | 2025-06-02 | 2025-05-30 | Masked | Florence |  | DARLINGTON - FLORENCE 69kV LINE | 148.8 | 148.8 | RICE | NG |  | 2029-12-31 | NRIS | No |  |  |  |  | Withdrawn
316 | 2025-06-02 | 2025-05-30 | Masked | Hampton | VARNVILLE 115 kV BUS |  | 150 | 150 | Solar | Sun |  | 2028-12-31 | NRIS | No |  |  |  |  | 2025 Cluster
Notes:
Rainey was planned prior to FERC requiring Generation Interconnection Requests. This plan included the Powerblock, 2A, 2B, and units 3, 4, and 5. Therefore, no generator interconnection
request was provided for these units, they were grandfathered.
A generation interconnection request was required of units 6, 7, and 8 because they were not included in the initial planning of Rainey.
Rainey Capacity is calculated as:
| Summer | Winter
Powerblock | 447 MW | 530 MW
2A | 146 Mw | 176 MW
2B | 146 Mw | 176 MW
3 | 74 MW | 91 MW
4 | 74 MW | 91 MW
5 | 74 MW | 91 MW