## Table 1
Louisville Gas and Electric and Kentucky Utilities (LG&E and KU) Generation Interconnection Queue Updated as of 08/28/2025 (Sorted by Queue Date)
| Interconnection Request Information |  | Location of Interconnect |  |  |  | Status |  |  |  | In Service Date 4 |  | Generator Information |  | Capacity (MW) |  | Studies
Cluster Study | Queue Number | Queue Date (Application Date) | County | State | Control Area (CA) | Point of Interconnect (POI) | Request Status (In Service, GIA Signed, Active, Interim GIA, Withdrawn) | Interim or Provisional Interconnection Service Requested? | Available Reports (FBS, ISIS, SIS, FS) | Affiliate (YES/NO) | Initial Application Commercial Operation Date | Updated Commercial Operation Date | Type of Service (NRIS, ERIS) | Type of Generating Facility and Fuel Type | Max Summer Output | Max Winter Output | Study Status/Deviations from Study Timeline | Why Interconnection was not Completed?
| LGE-GIS-2007-001 | 2007-02-28 | Muhlenberg County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No | SIS, FS | Yes | 2015-01-12 | N/A | NRIS | Steam Turbine | 750 | 750 | N/A* | Customer withdrew after completion of the Facility Study.
| LGE-GIS-2007-002 | 2007-02-28 | Muhlenberg County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No | SIS, FS | Yes | 2016-01-12 | N/A | NRIS | Combined Cycle | 610 | 610 | N/A* | Customer withdrew after completion of the Facility Study.
| LGE-GIS-2007-003 | 2007-03-02 | Henderson County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No | None | Yes | 2011-03-31 | N/A | ERIS | Combined Cycle | 640 | 640 | N/A* | Withdrawn by customer.
| LGE-GIS-2007-004 | 2007-04-24 | Henderson County | KY | LGEE | Daviess 345 kV substation bus | Withdrawn | No | FBS, SIS, SIS reposted, FS | No | 2011-03-31 | N/A | NRIS | Coal/gasification | 563 | 642 | N/A* | Customer withdrew after completion of the Facility Study.
| LGE-GIS-2008-001 | 2008-03-14 | Wise County | VA | LGEE | LKE’s Old Dominion (ODP) system tapping the existing Arnold to Dorchester 161 kV line | Withdrawn | Yes | ISIS, FS | No | 2011-12-01 | 2014-12-31 | NRIS | Wind Turbine/Wind | 129 | 129 | N/A* | Customer withdrew after completion of the Facility Study.
| LGE-GIS-2008-002 | 2008-11-05 | Ohio County | KY | LGEE |  | Withdrawn | No |  | Yes | 2010-08-01 | N/A | NRIS | Small Gen Synchronous | 5 | 5 | N/A* | Withdrawn by customer.
| LGE-GIS-2008-003 | 2008-11-05 | Henry County | KY | LGEE | Skylight Substation on the 69 kV side | Withdrawn | No |  | Yes | 2010-08-01 | N/A | NRIS | Small Gen Synchronous | 9 | 9 | N/A* | Withdrawn by customer.
| LGE-GIS-2008-004 | 2008-11-05 | Lincoln County | KY | LGEE |  | Withdrawn | No |  | Yes | 2010-08-01 | N/A | NRIS | Small Gen Synchronous | 6 | 6 | N/A* | Withdrawn by customer.
| LGE-GIS-2009-001 | 2009-02-23 | McCraken County | KY | LGEE | Grahamville – South Paducah 161 kV line | LGIA signed, In Service | Yes | ISIS, FS | Yes | 2010-05-01 | N/A | ERIS | Combined Cycle/Gas | 106 | 123 | N/A*
| LGE-GIS-2009-002 |  | Muhlenberg County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No |  | Yes | 2017-04-01 | N/A | NRIS | Combined Cycle/Gas | 640 | 690 | N/A* | Withdrawn by customer.
| LGE-GIS-2009-003 | 2009-11-16 | Muhlenberg County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No |  | Yes | 2017-04-01 | N/A | NRIS | Combustion Turbine/Steam | 535 | 560 | N/A* | Withdrawn by customer.
| LGE-GIS-2009-004 | 2009-12-29 | Trimble County | KY | LGEE | Trimble County 345 kV | Interim GIA signed, In-Service, LGIA signed | Yes | ISIS | Yes | 2010-05-01 | 2010-10-01 | ERIS1 | Steam Turbine | Addition 35 (Total 785) | Addition 35 (Total 785) | N/A*
| LGE-GIS-2010-001 | 2010-04-07 | Jefferson County | KY | LGEE | Cane Run Switching Station 138 kV | LGIA signed | No | FBS, SIS, FS | Yes | 2016-01-01 | 2015-03-01 | NRIS | 2x1 Combustion Turbine/Steam | 640 | 690 | LGIA Signed
| LGE-GIS-2010-002 | 2010-11-08 | Jefferson County | KY | LGEE | New substation that will tap and tie into the Mill Creek – Middletown 345 kV and the Mill Creek – Blue Lick 345 kV line; requested feasibility restudy for Alternative POI - Mill Creek to Hardin 345 kV line | Withdrawn | No | FBS | No | 2016-06-01 | N/A | NRIS/ERIS | 2x1 Combustion Turbine/Steam | 610 | 704 | N/A* | Withdrawn by customer.
| LGE-GIS-2010-003 | 2010-11-30 | Muhlenberg County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No | SIS | Yes | 2016-01-01 | 2018-01-01 | NRIS | Combustion Turbine/Steam | 640 | 690 | Customer withdrew the request while the FS was in progress | Withdrawn by customer.
| LGE-GIS-2011-001 | 2011-01-21 | Oldham County | KY | LGEE | Buckner Substation on the 345 kV | Withdrawn | No | FBS | No | 2015-01-01 | N/A | NRIS | Combustion Turbine | 450 | 450 | Feasibility Study completed | Withdrawn by customer.
| LGE-GIS-2011-002 | 2011-02-22 | Jefferson County | KY | LGEE | Cane Run Switching Station 138 kV uprate | Withdrawn | No | None | Yes | 2016-01-01 | 2015-03-01 | NRIS | Combustion Turbine/Steam | 20 (Revised from 50) | 30 (Revised from 75) | Customer withdrew the request while the SIS was in progress | Withdrawn by customer.
| LGE-GIS-2011-003 | 2011-02-22 | Jefferson County | KY | LGEE | Ohio Falls Uprate | LGIA signed | Yes | ISIS, SIS, FS | Yes | 2014-12-01 | 2013-01-01 | NRIS | Hydro Turbine/Hydro | 21 | 21 | Completed ISIS, SIS, and Facilities Study; LGIA signed
| LGE-GIS-2011-004 | 2011-05-16 | Mercer County | KY | LGEE | Brown Substation on 345 kV side | Withdrawn | No | None | Yes | 2018-01-01 | N/A | NRIS | Combustion Turbine/Steam | 790 (Revised from 825) | 880 (Revised from 915) | Customer withdrew the request while the SIS was in progress | Withdrawn by customer.
| LGE-GIS-2011-005 | 2011-11-18 | Mercer County | KY | LGEE | Dix Dam Uprate | Interim LGIA signed; LGIA signed | Yes | ISIS, SIS | Yes | 2012-03-30 | 2013-03-15 | NRIS | Hydro Turbine/Hydro | 6 | 6 | Completed Interim SIS, Interim LGIA signed; SIS completed and report posted. LGIA signed
| LGE-GIS-2013-001 | 2013-08-23 | Jefferson County | KY | LGEE | Cane Run Switching Station 138 kV uprate | LGIA signed | No | SIS | Yes | 2015-03-01 | N/A | NRIS | Combustion Turbine/Steam | Addition 51 (Total 691) | Addition 1 (Total 691) | SIS completed and report posted. LGIA signed
| LGE-GIS-2013-002 | 2013-10-16 | Muhlenberg County | KY | LGEE | Green River substation on the 161 kV side | Withdrawn | No | SIS | Yes | 2018-03-01 | N/A | NRIS | Combustion Turbine/Steam | 807 | 898 | SIS completed and report posted. Customer withdrew the request after completion of the SIS | Withdrawn by customer.
| LGE-GIS-2014-001 | 2014-08-22 | Mercer County | KY | LGEE | Brown Plant on the 138 kV side | SGIA signed | No | SIS, FS | Yes | 2016-01-01 | N/A | ERIS | Solar | 10 | 10 | SIS, FS completed and report posted. SGIA signed
| LGE-GIS-2016-001 | 2016-03-21 | Clark County | KY | LGEE | HQ Office 69 kV | SGIA signed | No | SIS | No | 2017-04-01 | N/A | ERIS | Solar | 9 | 9 | SIS completed and report posted. SGIA signed
| LGE-GIS-2017-001 | 2017-02-08 | Hickman County | KY | LGEE | Clinton-South Paducah 69 kV | withdrawn | No | FBS | No | 2019-05-01 | N/A | NRIS | Solar | 35 | 35 | Feasibility Study completed | Withdrawn by customer.
| LGE-GIS-2017-002 | 2017-03-01 | Lyon County | KY | LGEE | North Princeton - Livingston Co 161 kV | LGIA signed | No | SIS, FS | No | 2019-05-01 | 2024-05-01 | NRIS | Solar | 86 | 86 | LGIA signed
| LGE-GIS-2017-003 | 2017-04-27 | Harrison County | KY | LGEE | Cynthiana EK Tap - Millersburg 69 kV | LGIA terminated | No | FBS, SIS, FS | No | 2019-06-01 | 2021-06-01 | NRIS/ERIS | Solar | 35 | 35 | LGIA terminated
| LGE-GIS-2017-004 | 2017-06-28 | Harrison County | KY | LGEE | Cynthiana EK Tap - Oxford 69 kV | Withdrawn | No | FBS | No | 2019-06-01 | N/A | NRIS/ERIS | Solar | 25 | 25 | Feasibility Study completed. Customer withdrew the request after completion of the FBS | Withdrawn by customer.
| LGE-GIS-2017-005 | 2017-08-04 | Harrison County | KY | LGEE | Cynthiana EK Tap - Renaker 69 kV | Withdrawn | No | FBS | No | 2018-10-01 | N/A | ERIS | Solar | 10 | 10 | Feasibility Study completed. Customer withdrew the request after completion of the FBS | Withdrawn by customer.
| LGE-GIS-2017-006 | 2017-08-18 | Muhlenberg County | KY | LGEE | 138 kV Green River substation (Alternate POI: Green River - Green River Tap 138 kV) | LGIA terminated | No | FBS, SIS, FS | No | 2019-12-31 | 2019-08-31 | NRIS/ERIS | Solar | 100 | 100 | LGIA terminated
| LGE-GIS-2018-001 | 2018-08-17 | Estill County | KY | LGEE | Rice Substation | withdrawn | No | None | No | 2018-12-01 | N/A | ERIS | Hydro Turbine/Hydro | 3 | 3 | Deemed withdrawn before study | Withdrawn by customer.
| LGE-GIS-2018-002 | 2018-10-01 | Daviess County | KY | LGEE | Green River Steel - Cloverport 138 kV line | Withdrawn | No | None | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 120 | 120 | Customer withdrew the request while the Feasibility Study was in progress | Withdrawn by customer.
| LGE-GIS-2018-003 | 2018-10-01 | Hart County | KY | LGEE | Bonneville - West Lebanon 138 kV line | Withdrawn | No | None | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 120 | 120 | Customer withdrew the request while the Feasibility Study was in progress | Withdrawn by customer.
| LGE-GIS-2018-004 | 2018-10-01 | Union County | KY | LGEE | Morganfield - Corydon Tap 161 kV line | Withdrawn | No | FBS | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 120 | 120 | Feasibility Study completed. Customer withdrew the request after completion of the FBS | Withdrawn by customer.
| LGE-GIS-2018-005 | 2018-10-01 | McLean County | KY | LGEE | Rumsey - Pettit 69 kV line | Withdrawn | No | None | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 60 | 60 | Withdrawn before study | Withdrawn by customer.
| LGE-GIS-2018-006 | 2018-10-01 | Hopkins County | KY | LGEE | North Earlington - River Quenn Tap 161 kV line | Withdrawn | No | None | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 120 | 120 | Withdrawn before study | Withdrawn by customer.
| LGE-GIS-2018-007 | 2018-10-01 | Fleming County | KY | LGEE | Goddard - Flemingsburg tap 138 kV line | Withdrawn | No | None | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 120 | 120 | Customer withdrew the request while the Feasibility Study was in progress | Withdrawn by customer.
| LGE-GIS-2018-008 | 2018-10-16 | Estill County | KY | LGEE | Rice Substation | Withdrawn | No | None | No | 2018-12-01 | N/A | ERIS | Hydro Turbine/Hydro | 2.64 reduced to 1.5 MW | 2.64 reduced to 1.5 MW | Customer withdrew the application after SGIA was issued | Withdrawn by customer.
| LGE-GIS-2018-009 | 2018-11-13 | LaRue County | KY | LGEE | Lebanon Junction - Summer Shade 161 kV line | Withdrawn | No | None | No | 2022-06-01 | N/A | NRIS/ERIS | Solar | 120 | 120 | Withdrawn before study | Withdrawn by customer.
| LGE-GIS-2019-001 | 2019-01-15 | Washington County and Marion County | KY | LGEE | Lebanon – Danville Tap 138 kV line | LGIA terminated | No | FBS.SIS,FS | No | 2019-12-31 | 2023-12-01 | NRIS | Solar | 120 reduced to 110 MW | 120 reduced to 110 MW | LGIA terminated
| LGE-GIS-2019-002 | 2019-02-06 | Ballard County | KY | LGEE | Grahamville – Wickliffe 161 kV Line | LGIA terminated | No | FBS.SIS,FS | No | 2022-06-01 | 2026-09-30 | NRIS | Solar | 110 reduced to 104 MW | 110 reduced to 104 MW | LGIA terminated
| LGE-GIS-2019-003 | 2019-02-07 | Meade County | KY | LGEE | Cloverport – Tiptop 138 kV line | LGIA Terminated | No | FBS.SIS,FS | No | 2022-12-01 | N/A | NRIS | Solar/Battery changed to Solar | 200 reduced to 121 MW | 200 reduced to 121 MW | LGIA Terminated
| LGE-GIS-2019-004 | 2019-02-07 | Breckinridge County | KY | LGEE | Hardinsburg 138 kV Substation | LGIA terminated | No | FBS.SIS,FS | No | 2022-12-01 | 2026-09-08 | NRIS | Solar | 200 reduced to 100MW | 200 reduced to 100MW | LGIA terminated
| LGE-GIS-2019-005 | 2019-03-13 | Webster County | KY | LGEE | Green River – Corydon Tap 161 kV line | Withdrawn | No | FBS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 80 | 80 | Withdrawn by customer on 06/24/2020 during SIS | Withdrawn by customer
| LGE-GIS-2019-006 | 2019-03-18 | Union County | KY | LGEE | Morganfield – Nebo 69 kV double circuit line | Withdrawn | No | None | No | 2023-11-01 | 2021-11-01 | NRIS/ERIS | Solar | 200 | 200 | Withdrawn by customer on 05/23/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-007 | 2019-03-18 | Scott County | KY | LGEE | Primary: Scott 138 kV substation; Alternate: POI the Scott – Adams 138 kV line | Withdrawn | No | None | No | 2021-10-01 | N/A | NRIS/ERIS | Solar | 101 | 101 | Withdrawn by customer on 09/26/2019 while under study; started study 9/26; send deemed withdrawal notice for data deficiency but ITO retracted deemed withdrawal notice on 9/25 | Withdrawn by customer.
Louisville Gas and Electric and Kentucky Utilities (LG&E and KU) Generation Interconnection Queue Updated as of 07/31/2025 (Sorted by Queue Date)
| Interconnection Request Information |  | Location of Interconnect |  |  |  | Status |  |  |  | In Service Date 4 |  | Generator Information |  | Capacity (MW) |  | Studies
Cluster Study | Queue Number | Queue Date (Application Date) | County | State | Control Area (CA) | Point of Interconnect (POI) | Request Status (In Service, GIA Signed, Active, Interim GIA, Withdrawn) | Interim or Provisional Interconnection Service Requested? | Available Reports (FBS, ISIS, SIS, FS, PRSIS,PRFS,TCS) | Affiliate (YES/NO) | Initial Application Commercial Operation Date | Updated Commercial Operation Date | Type of Service (NRIS, ERIS) | Type of Generating Facility and Fuel Type | Max Summer Output | Max Winter Output | Study Status/Deviations from Study Timeline | Why Interconnection was not Completed?
| LGE-GIS-2019-008 | 2019-03-22 | Caldwell County | KY | LGEE | North Princeton 161 kV Substation | LGIA terminated | No | FBS,SIS,FS | No | 2021-12-31 | N/A | NRIS | Solar | 100 | 100 | LGIA terminated
| LGE-GIS-2019-009 | 2019-03-22 | Henderson County | KY | LGEE | Tap to Corydon 161 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 05/07/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-010 | 2019-03-22 | Lyon County | KY | LGEE | North Princeton to South Paducah 161 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 05/07/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-011 | 2019-03-22 | Mercer County | KY | LGEE | Danville Tap- Brown Plant 138 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 06/17/2019 did not execute FBS study agreement | Withdrawn by customer.
| LGE-GIS-2019-012 | 2019-03-22 | Muhlenberg County | KY | LGEE | Green River Substation or Green River to Tap 161 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 05/07/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-013 | 2019-03-22 | Union County | KY | LGEE | Crittenden to Morganfield 161 kV | Withdrawn | No | FBS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 01/28/2020 after scoping meeting prior to executing SIS agreement | Withdrawn by customer.
| LGE-GIS-2019-014 | 2019-03-22 | Ballard County | KY | LGEE | Grahamville to Wickliffe 161 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 06/17/2019 did not execute FBS study agreement | Withdrawn by customer.
| LGE-GIS-2019-015 | 2019-03-22 | Grayson County | KY | LGEE | Ohio County to Shrewsbury 138 kV | Withdrawn | No | FBS,SIS,FS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 08/04/2021 during the LGIA negotiations | Withdrawn by customer.
| LGE-GIS-2019-016 | 2019-03-22 | Henderson County | KY | LGEE | Corydon Tap to Green River 161 kV | Withdrawn | No | FBS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 04/15/2020 after feasibility study; did not execute SIS agreement | Withdrawn by customer.
| LGE-GIS-2019-017 | 2019-03-22 | Hart County | KY | LGEE | Bonnieville to Lebanon West 138 kV | Withdrawn | No | FBS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 04/29/2020 after feasibility study; did not execute SIS agreement | Withdrawn by customer.
| LGE-GIS-2019-018 | 2019-03-22 | McLean County | KY | LGEE | Tap to Green River 161 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 05/07/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-019 | 2019-03-22 | Union County | KY | LGEE | Crittenden to Morganfield 161 kV | Withdrawn | No | None | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 05/07/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-020 | 2019-03-22 | Hopkins County | KY | LGEE | Corydon Tap to Green River 161 kV | Withdrawn | No | FBS,SIS,FS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 reduced to 85 | 100 reduced to 85 | Withdrawn by customer on 05/21/2021 after facilities study | Withdrawn by customer.
| LGE-GIS-2019-021 | 2019-03-27 | Ballard County | KY | LGEE | Barlow - Forrestdale 69 kV line | Withdrawn | No | None | No | 2022-01-12 | N/A | NRIS/ERIS | Solar | 80 | 80 | Withdrawn by customer on 06/07/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-022 | 2019-03-29 | Fayette County | KY | LGEE | Adams – Innovation Tap 138 kV line | Withdrawn | No | FBS | No | 2021-12-15 | N/A | NRIS/ERIS | Solar | 75 | 75 | Withdrawn by customer on 06/18/2020 after scoping meeting prior to the SIS | Withdrawn by customer.
| LGE-GIS-2019-023 | 2019-03-29 | Lyon County, Caldwell County | KY | LGEE | Livingston Co. - North Princeton 161 kV line | Withdrawn | No | FBS,SIS | No | 2021-12-15 | N/A | NRIS/ERIS | Solar | 150 | 150 | Withdrawn by customer on 05/04/2021 prior to execution of facilities stud | Withdrawn by customer.
| LGE-GIS-2019-024 | 2019-03-29 | Woodford County | KY | LGEE | Ghent - Lexington 345 kV Line | Withdrawn | No | None | No | 2022-12-31 | N/A | NRIS/ERIS | Solar | 200 | 200 | Withdrawn by customer on 12/09/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-025 | 2019-05-02 | Mercer County | KY | LGEE | Bardstown - Brown CT 138 kV Line | LGIA signed | No | FBS,SIS,FS | No | 2022-12-01 | 2026-10-01 | NRIS | Solar | 99 | 99 | LGIA Signed
| LGE-GIS-2019-026 | 2019-05-07 | Mason County | KY | LGEE | Kenton - Wedonia 138 kV | Withdrawn | No | None | No | 2021-07-31 | N/A | NRIS/ERIS | Solar | 60 | 60 | Withdrawn by customer on 07/08/2019 after scoping meeting prior to the feasibility | Withdrawn by customer.
| LGE-GIS-2019-027 | 2019-08-30 | Scott County | KY | LGEE | Adams - Scott County 138kV | Withdrawn | No | FBS | No | 2022-12-31 | N/A | NRIS/ERIS | Solar | 200 | 200 | Withdrawn by customer on 09/10/2020 without executing SIS agreemen | Withdrawn by customer.
| LGE-GIS-2019-028 | 2019-08-30 | Caldwell County | KY | LGEE | North Princeton 161 kV Substation; Feasibility study proposed North Princeton – Earlington North 161 kV line | Withdrawn | No | FBS | No | 2022-12-31 | N/A | NRIS/ERIS | Solar | 150 | 150 | Withdrawn by customer on 11/02/2020 without executing SIS agreemen | Withdrawn by customer.
| LGE-GIS-2019-029 3 | 2019-11-08 | Hardin County | KY | LGEE | Black Branch- Hardinsburg 138 kV | LGIA terminated | Yes | PRSIS,FBS,PRFS,SIS,FS | No | 2021-12-31 | 2024-12-31 | NRIS | Solar | 100 | 100 | LGIA terminated
| LGE-GIS-2019-030 3 | 2019-11-08 | Hardin County | KY | LGEE | Hardin County 69 kV Substation | Withdrawn | Yes | PRSIS | No | 2021-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 08/20/2020 after the provisional SIS | Withdrawn by customer.
| LGE-GIS-2020-001 | 2020-10-02 | Madison County | KY | LGEE | Lake Reba - West Irvine Line Tap 161 kV | LGIA terminated | No | FBS,SIS,FS | No | 2024-12-31 | 2024-12-31 | NRIS | Solar | 50 | 50 | LGIA terminated
| LGE-GIS-2020-002 | 2020-11-03 | Mercer County | KY | LGEE | Harrodsburg - West Cliff 69kV | Withdrawn | No | FBS,SIS | No | 2024-12-31 | N/A | NRIS/ERIS | Solar | 105 | 105 | SIS Completed | Withdrawn by customer.
| LGE-GIS-2021-001 | 2021-01-06 | Caldwell County | KY | LGEE | North Princeton 161 kV Substation | Withdrawn | No | FBS,FBS Restudy | No | 2023-12-31 | N/A | NRIS/ERIS | Solar | 100 | 100 | Withdrawn by customer on 10/08/2021 before executing SIS agreement | Withdrawn by customer.
| LGE-GIS-2021-002 | 2021-01-08 | Union County | KY | LGEE | Morganfield 161kV Substation | Withdrawn | No | FBS | No | 2023-12-31 | N/A | NRIS/ERIS | Solar | 150 | 150 | Withdrawn by customer on 07/21/2021 without executing SIS agreemen | Withdrawn by customer.
| LGE-GIS-2021-003 | 2021-01-08 | Ohio County | KY | LGEE | Matanzas 138 kV Substation or Matanzas-Ohio County 138 kV line | Withdrawn | No | FBS | No | 2023-12-31 | N/A | NRIS/ERIS | Solar | 150 | 150 | Withdrawn by customer on 08/26/2021 without executing SIS agreemen | Withdrawn by customer.
| LGE-GIS-2021-004 | 2021-01-08 | Muhlenberg County | KY | LGEE | Green River-River Queen Tap 161 kV | Withdrawn | No | FBS | No | 2023-12-31 | N/A | NRIS/ERIS | Solar | 150 | 150 | Withdrawn by customer on 08/26/2021 without executing SIS agreemen | Withdrawn by customer.
| LGE-GIS-2021-005 | 2021-01-21 | Jefferson County | KY | LGEE | Mill Creek 345 kV Station | Withdrawn | No | None | Yes | 2025-12-31 | N/A | NRIS | Natural Gas Combined Cycle | 620 | 635 | Withdrawn by customer on 10/22/2021 during SIS study; | Withdrawn by customer.
| LGE-GIS-2021-006 | 2021-01-21 | Mercer County | KY | LGEE | South 138 kV bus of the Brown North Substation | Withdrawn | No | None | Yes | 2025-12-31 | N/A | NRIS | Natural Gas Combined Cycle | 620 | 635 | Withdrawn by customer on 10/22/2021 before SIS study start | Withdrawn by customer.
| LGE-GIS-2021-007 | 2021-03-22 | McCracken County | KY | LGEE | Primary: Grahamville 161 kV bus ; Alternate: Grahamville – Wickliffe 161 kV line, SIS Primary changed to : Grahamville 161 kV bus | LGIA signed, currently suspended | No | FBS,SIS,FS | No | 2023-06-15 | 2026-06-15 | NRIS | Solar | 120 | 120 | LGIA signed, currently suspended9
| LGE-GIS-2021-008 | 2021-03-22 | Clark | IN | LGEE | Primary: Trimble County 345 kV bus; Alternate: Trimble to Speed 345 kV line, SIS Primary changed to: Trimble to Speed 345 kV line | LGIA signed, currently suspended | No | FBS,SIS,FS | No | 2023-06-15 | 2026-06-15 | NRIS | Solar/Battery | 1200 reduced to 500 | 1200 reduced to 500 | LGIA signed, currently suspended
| LGE-GIS-2021-009 | 2021-03-22 | Hardin | KY | LGEE | Primary: Hardin County 345 kV bus; Alternate: Hardin County – Daviess County 345 kV line, SIS Primary changed to: Hardin County – Daviess County 345 kV line | LGIA signed, currently suspended | No | FBS,FBS Restudy,SIS,FS | No | 2023-06-15 | 2026-06-15 | NRIS | Solar/Battery | 200 | 200 | LGIA signed, currently suspended
| LGE-GIS-2021-010 | 2021-03-22 | Marion | KY | LGEE | Lebanon 138 kV bus | LGIA signed | No | FBS,SIS,FS | No | 2023-06-15 | 2026-06-15 | NRIS | Solar | 120 | 120 | LGIA Signed
| LGE-GIS-2021-011 | 2021-03-25 | Jefferson County | KY | LGEE | Mill Creek 138 KV substation | LGIA signed, currently suspended | No | FBS,SIS,FS | No | 2024-12-01 | 2026-12-31 | NRIS | Battery | 300 | 300 | LGIA signed, currently suspended
| LGE-GIS-2021-012 | 2021-03-26 | Mercer County | KY | LGEE | Bardstown - Brown CT 138 kV line | Withdrawn | No | SIS | No | 2024-12-01 | 2027-12-01 | NRIS | Battery | 100 | 100 | Customer withdrew the request on 06/27/2023 while the FS was in progress | Withdrawn by customer.
| LGE-GIS-2021-013 | 2021-03-29 | Hardin | KY | LGEE | Hardin County 69 kV Substation | LGIA signed | No | SIS,FS | No | 2025-05-31 | 2028-05-31 | NRIS | Battery | 120 | 120 | LGIA signed
| LGE-GIS-2021-014 | 2021-03-30 | Bullitt | KY | LGEE | Blue Lick 345 kV | Withdrawn | No | FBS,SIS | No | 2025-12-15 | N/A | NRIS/ERIS | Battery | 300 | 300 | Withdrawn by customer on 09/05/2023 before the FS started | Withdrawn by customer.
| LGE-GIS-2021-015 | 2021-03-30 | Bullitt | KY | LGEE | Blue Lick 345 kV | Withdrawn | No | FBS | No | 2028-12-15 | N/A | NRIS/ERIS | Battery | 300 | 300 | Withdrawn by customer on 09/05/2023 during SIS | Withdrawn by customer.
| LGE-GIS-2021-016 | 2021-03-31 | Jefferson County | KY | LGEE | Primary: Mill Creek - Ashby 138 kV line; alternate: Mill Creek 138 kV bus | Withdrawn | No | None | No | 2024-06-01 | N/A | NRIS/ERIS | Battery | 250 | 250 | Withdrawn by customer on 09/13/2023 during SIS | Withdrawn by customer.
| LGE-GIS-2021-017 | 2021-04-27 | Mason County | KY | LGEE | Wedonia - Kenton 138 kV line | LGIA signed, currently suspended | No | SIS,FS | No | 2023-12-31 | 2026-12-31 | NRIS | Solar/Battery | 100 | 100 | LGIA signed, currently suspended
| LGE-GIS-2021-018 | 2021-05-01 | Bath County | KY | LGEE | Spencer Road to Farmers Tap 138 kV line | LGIA signed, currently suspended | No | FBS, SIS, FS | No | 2024-11-30 | 2027-11-30 | NRIS | Solar/Battery | 250 reduced to 110 | 250 reduced to 110 | LGIA signed, currently suspended
| LGE-GIS-2021-019 | 2021-05-10 | Boyle County | KY | LGEE | Primary: KY ST Hospital Substation 69 kV Bus; Alternate: KY ST Hospital Tap - Danville E 69 kV line | LGIA signed, currently suspended | No | FBS, SIS, FS | No | 2025-03-31 | 2027-06-01 | NRIS | Solar | 100 | 100 | LGIA signed, currently suspended
| LGE-GIS-2021-020 | 2021-06-24 | McCracken | KY | LGEE | Primary: Grahamville 161 kV bus; Alternate: Grahamville – Wickliffe 161 kV line | LGIA signed | No | FBS, SIS, FS | No | 2023-12-31 | 2026-12-31 | NRIS | Solar/Battery | Addition of 120 MW PV/BESS (total 240 MW PV & 120 BESS ) | 120 | Capacity Increase to LGE-GIS-2021-007, LGIA signed (see related row)
| LGE-GIS-2021-021 | 2021-09-17 | Wise County | VA | LGEE | Dorchester - Bond 69 kV line | Withdrawn | No | None | No | Q4 2023 | N/A | ERIS | Solar | 10 | 10 | Withdrawn by customer on 10/27/2021 after scoping meeting | Withdrawn by customer.
| LGE-GIS-2021-022 | 2021-09-17 | Wise County | VA | LGEE | Dorchester - St Paul 69 kV line | Withdrawn | No | None | No | Q4 2023 | N/A | ERIS | Solar | 20 | 20 | Withdrawn by customer on 10/27/2021 after scoping meeting | Withdrawn by customer.
| LGE-GIS-2021-023 | 2021-10-05 | Fayette County | KY | LGEE | Primary: West Lexington 345 kV; Alternate: West Lexington-Brown North 345 kV | Withdrawn | No | FBS | No | 2024-09-30 | N/A | NRIS/ERIS | Battery | 200 | 200 | Withdrawn by customer on 01/17/2023 before SIS study start; | Withdrawn by customer.
| LGE-GIS-2021-024 | 2021-10-05 | Floyd County | IN | LGEE | Primary: Paddys West 345 kV ; Alternate: Paddys West-Cane Run Tap 345 kV | Withdrawn | No | FBS | No | 2024-09-30 | N/A | NRIS/ERIS | Battery | 200 | 200 | Deemed withdrawn on 02/25/2023 before SIS study start; | Withdrawn.
| LGE-GIS-2021-026 | 2021-10-25 | Wise County | VA | LGEE | Dorchester - St Paul 69 kV line | Withdrawn | No | FBS | No | 2023-10-01 | N/A | NRIS/ERIS | Solar | 20 | 20 | Withdrawn by customer on 09/30/2024 before TCS
| LGE-GIS-2021-027 | 2021-10-25 | Wise County | VA | LGEE | Dorchester - Bond 69 kV line | Withdrawn | No | FBS | No | 2023-10-01 | N/A | NRIS/ERIS | Solar | 20 reduced to 10 | 20 reduced to 10 | Withdrawn by customer on 09/30/2024 before TCS
| LGE-GIS-2022-001 | 2022-02-17 | Ballard County | KY | LGEE | Grahamville – Wickliffe 161 kV line | Withdrawn | No | FBS | No | 2026-09-30 | N/A | NRIS/ERIS | Solar | 125 | 125 | Deemed Withdrawn on 10/23/2024
| LGE-GIS-2022-002 | 2022-05-02 | Wise County | VA | LGEE | Dorchester to Blackwood 69 kV line | Withdrawn | No | None | No | 2025-06-01 | N/A | NRIS/ERIS | Solar | 40 | 40 | Withdrawn by customer on 10/04/2024 before TCS
Part of TCS 2024 | LGE-GIS-2022-0035 | 2022-06-21 | Jefferson County | KY | LGEE | Mill Creek Substation 345 kV bus | Active | Yes | PRSIS, PRFS,TCS | Yes | 2027-04-01 | N/A | NRIS | Natural Gas Combined Cycle | 645 | 660 | TCS completed on July 18,2025
| LGE-GIS-2022-004 | 2022-06-21 | Mercer County | KY | LGEE | Brown North Substation 345 kV bus | Withdrawn | No | None | Yes | 2027-04-01 | N/A | NRIS | Natural Gas Combined Cycle | 645 | 660 | Withdrawn by customer on 11/07/2022 after scoping meeting prior to | Withdrawn by customer.
| LGE-GIS-2022-005 | 2022-07-26 | Clarke and Jefferson Counties, Indiana | IN | LGEE | Trimble Co to Ghent line 345 kV as primary POI and Trimble Co substation 345 kV bus as alternate POI | Withdrawn | No | FBS | No | 2029-01-09 | N/A | ERIS | Solar/Battery | 1400 | 1400 | Withdrawn by customer on 06/30/2023 prior to SIS study; | Withdrawn by customer.
| LGE-GIS-2022-006 | 2022-08-22 | Clarke and Jefferson Counties, Indiana | IN | LGEE | Trimble Co to Ghent line 345 kV as primary POI and Trimble Co substation 345 kV bus as alternate POI | Withdrawn | No | FBS, FBS Restudy | No | 2029-01-09 | N/A | NRIS/ERIS | Solar/Battery | 1400 reduced to 1000 | 1400 reduced to 1000 | Withdrawn by customer on 03/08/2024 prior to SIS study; | Withdrawn by customer.
| LGE-GIS-2022-007 | 2022-09-06 | Lincoln County | KY | LGEE | West Garrard – Pineville 345 kV line | Withdrawn | No | None | No | 2026-10-01 | N/A | NRIS/ERIS | Solar/Battery | 150 | 150 | Withdrawn by customer on 09/09/2024 before TCS
| LGE-GIS-2022-008 | 2022-09-07 | Lee County | VA | LGEE | Pocket North Substation 161 kV bus | Withdrawn | No | FBS | No | 2024-09-10 | N/A | NRIS/ERIS | Solar/Battery | 45 | 45 | Deemed withdrawn on 09/14/2023 before SIS Study started | Withdrawn.
| LGE-GIS-2022-009 | 2022-09-21 | Lincoln County | KY | LGEE | West Garrard – Pineville 345 kV line | Withdrawn | No | None | No | 2026-10-01 | N/A | NRIS/ERIS | Solar/Battery | 100 | 100 | Withdrawn by customer on 03/11/2024 before SIS Study started | Withdrawn by customer.
| LGE-GIS-2022-010 | 2022-09-30 | Bell County | KY | LGEE | Pineville - Harlan #1 161 kV line | Withdrawn | No | FBS | No | 2030-12-31 | N/A | NRIS/ERIS | Hydro Pumped Storage | 216 | 216 | Withdrawn by customer on 09/26/2024 before TCS
| LGE-GIS-2022-011 | 2022-10-28 | Mercer County | KY | LGEE | Brown North Substation 138 kV bus | Withdrawn | No | None | Yes | 2028-03-01 | N/A | NRIS | Natural Gas Combined Cycle | 645 | 660 | Withdrawn by customer on 09/19/2023 before SIS Study started | Withdrawn by customer.
| LGE-GIS-2023-001 | 2023-03-22 | Mercer County | KY | LGEE | Brown North Substation 345 kV bus. | Withdrawn | No | None | Yes | 2026-12-31 | N/A | NRIS | Battery | 125 | 125 | Withdrawn by customer on 05/17/2023 before SIS Study started | Withdrawn by customer.
Part of TCS 2024 | LGE-GIS-2023-0026 | 2023-04-14 | Mercer County | KY | LGEE | Brown North Substation 345 kV bus. | Active | Yes | TCS | Yes | 2028-04-01 | 2030-04-01 | NRIS | Natural Gas Combined Cycle | 645 | 660 | TCS completed on July 18,2025
Part of TCS 2024 | LGE-GIS-2023-0037 | 2023-04-20 | Mercer County | KY | LGEE | Brown North Substation 345 kV bus. | Active | No | PRSIS, PRFS,TCS | Yes | 2026-12-31 | 2026-02-01 | NRIS | Battery | 125 | 125 | TCS completed on July 18,2025
| LGE-GIS-2023-004 | 2023-05-02 | Mercer County | KY | LGEE | Harrodsburg – West Cliff 69 kV line | Withdrawn | No | FBS | No | 2027-09-01 | N/A | NRIS/ERIS | Solar/Battery | 99 reduced to 89 | 99 reduced to 89 | Withdrawn by customer on 09/30/2024 before TCS
| LGE-GIS-2023-005 | 2023-06-14 | Caldwell County | KY | LGEE | North Princeton 161kV Substation | Withdrawn | No | FBS | No | 2026-03-31 | N/A | NRIS/ERIS | Solar | 200 reduced to 100 | 200 reduced to 100 | Withdrawn by customer on 10/04/2024 before TCS
| LGE-GIS-2023-006 | 2023-07-24 | Daviess County | KY | LGEE | Zion to Green River Steel 69kV line | Withdrawn | No | FBS | No | 2027-09-01 | N/A | NRIS/ERIS | Solar/Battery | 125 | 125 | Withdrawn by customer on 09/30/2024 before TCS
Part of TCS 2024 | LGE-GIS-2023-007 | 2023-08-21 | Hopkins County | KY | LGEE | 161kV Earlington North Substation | Active | No | FBS,TCS | No | 2026-12-12 | 2027-12-31 | NRIS | Solar | 138 | 138 | TCS completed on July 18,2025
| LGE-GIS-2024-001 | 2024-01-23 | Grayson County | KY | LGEE | Ohio Co–Leitchfield 69 kV Line | Withdrawn | No | FBS | No | 2027-12-31 | N/A | NRIS/ERIS | Solar/Battery | 75 | 75 | Withdrawn by customer on 08/013/2024
Part of TCS 2024 | LGE-GIS-2024-0028 | 2024-02-14 | Hopkins County | KY | LGEE | 2MADSNV LP W to 2 EARLINGTN N 69 kV line | Active | No | PRSIS, PRFS,TCS | No | 2027-04-01 | N/A | NRIS | Natural Gas Engines | 75 | 75 | TCS completed on July 18,2025
| LGE-GIS-2024-003 | 2024-03-21 | Croydon County | KY | LGEE | Tunnel Hill | Withdrawn | No | None | No | 2027-06-15 | N/A | NRIS | Solar | 50 | 50 | Deemed withdrawn on 05/04/2024 due to deficient request | Withdrawn.
Part of TCS 2024 | LGE-GIS-2024-004 | 2024-04-09 | Mercer County | KY | LGEE | Bardstown - Brown CT 138 kV Line | Active | No | TCS | Yes | 2026-10-01 | 10/1/2026 (reversed per customer's request) | NRIS | Solar | 22 | 22 | TCS completed on July 18,2025
| LGE-GIS-2024-005 | 2024-05-02 | Breckinridge County | KY | LGEE | Hardin County to Davies County 345 kV Line | Withdrawn | No | None | No | 2027-12-01 | N/A | NRIS | Solar/Battery | 200 | 200 | Withdrawn by customer on 09/26/2024 before TCS
Part of TCS 2024 | LGE-GIS-2024-006 | 2024-05-03 | Jefferson County | KY | LGEE | Cane Run CT Substation 138kV | Active | No | TCS | Yes | 2026-05-04 | N/A | NRIS | Combustion Gas Turbine /Steam | 94 | 94 | TCS completed on July 18,2025
| LGE-GIS-2024-007 | 06/052024 | Harlan County | KY | LGEE | Arnold Substation 161 kV | Withdrawn | No | None | No | 2028-09-30 | N/A | NRIS/ERIS | Wind Turbine/Wind | 250 | 250 | Withdrawn by customer on 09/24/2024 before TCS
| LGE-GIS-2024-008 | 2024-06-12 | Crittenden County | KY | LGEE | Crittenden Substation 161 kV | Withdrawn | No | None | No | 2027-03-01 | N/A | NRIS/ERIS | Solar | 150 | 150 | Withdrawn by customer on 09/06/2024 before TCS
Please also see Generation Interconnection Study Status Document posted under Generation Interconnection Information Folder
Legend:
| N/A |  | Not Applicable
| N/A* |  | Information not available since studies are complete prior to TranServ International, Inc. (TranServ) Independent Transmission Organization (ITO) transition
| FBS |  | Feasibility Study
| SIS |  | System Impact Study
| ISIS |  | Interim System Impact Study
| FS |  | Facility Study
| PRSIS |  | Provisional System Impact Study
| PRFS |  | Provisional Facility Study
| Fuel Type |  | Coal, Gas, Biomass, Steam, Hydro, Wind, Diesel, Co-Gen, Combined Cycle, Solar, Nuclear
| Type of Generating Facility |  | Combined Cycle, Base Load, or Combustion Turbine
| TCS |  | Transitional Cluster Study
| Footnotes: |  | 1 Originally requested as NRIS
2 for the suspended LGIA's, the actual in-service date will depend on the required interconnection and network upgrade construction lead time after the customer notification to start construction.
3 LGE-GIS-2019-029 and LGE-GIS-2019-030 provisional GI request received on 3/11/2020
4 LG&E/KU requests only the Commercial Operation Date in place of In Service Date.
· Commercial Operation Date of a unit is the date on which the Generating Facility commences Commercial Operation as agreed to by the Parties.
5 LGE-GIS-2022-003 provisional GI request received on 5/16/2023, PRSIS is posted on 9/25/2023, PRFS is posted on 01/16/2024, PLGIA signed.
6 LGE-GIS-2023-002 provisional GI request received on 5/16/2023. PRSIS 2023-002 was withdrawn by customer on 11-08-2023
7 LGE-GIS-2023-003 provisional GI request received on 12/19/2023. PRSIS posted on 06/14/2024. PRFS is posted on 10/18/2024. PLGIA is signed.
8 LGE-GIS-2024-002 provisional GI request received on 8/12/2024. PRSIS started on 09/16/2024.PRSIS posted on 12/06/2024.PRFS posted on 04/29/2025.PLGIA signed on 07/28/2025
9 LGE-GIS-2021-007 Amended LGIA also includes 120 MW PV/BESS of LGE-GIS-2021-020 totaling to 240 MW PV & 120 MW BESS.